## AOP Summary
Zone | ZH | AOP 2026-27 OVERALL STATUS |  |  |  | APR 25 |  |  | OCT 25 | [5 empty] | NOV 25 | [6 empty] | DEC 25 | [7 empty] | JAN 26 | [6 empty] | FEB 26 | [6 empty] | MAR 26 |  |  |  |  | APRIL 26 |  |  |  |  | MAY 26 |  |  |  |  | JUNE 26 |  |  |  |  | JULY 26 |  |  |  |  | AUGUST 26
|  | Planned | Actual | WIP | YTS | March 25 Carry Forward | APR 25 Planned | APR 25 Actual | AUG 25 Carry Forward | SEP 25 Carry Forward | Oct 25 Planned | Oct 25 Actual | TOTAL Oct 25 Actual | WIP | AUG 25 Carry Forward | SEP 25 Carry Forward | OCT 25 Carry Forward | NOV 25 Planned | NOV 25 Actual | TOTAL NOV 25 Actual | WIP | AUG 25 Carry Forward | SEP 25 Carry Forward | OCT 25 Carry Forward | NOV 25 Carry Forward | DEC 25 Planned | DEC 25 Actual | TOTAL DEC 25 Actual | WIP | OCT 25 Carry Forward | NOV 25 Carry Forward | DEC 25 Carry Forward | JAN 26 Planned | JAN 26 Actual | TOTAL JAN 26 Actual | WIP | NOV 25 Carry Forward | DEC 25 Carry Forward | JAN 26 Carry Forward | FEB 26 Planned | FEB 26 Actual | TOTAL FEB 26 Actual | WIP | MAR 26 Planned | TOTAL MAR 26 Actual | WIP | YTS | TOTAL MAR 26 Actual | APRIL 26 Planned | APR 26 Actual | WIP | YTS | TOTAL APR 26 Actual | MAY 26 Planned | MAY 26 Actual | WIP | YTS | TOTAL MAY 26 Actual | JUNE 26 Planned | JUNE 26 Actual | WIP | YTS | TOTAL JUNE 26 Actual | JULY 26 Planned | JULY 26 Actual | WIP | YTS | TOTAL JULY 26 Actual | AUGUST 26 Planned | AUGUST 26 Actual | WIP | YTS | TOTAL JULY 26 Actual
[6 empty] | Actual |  |  | Actual | Actual |  |  |  |  | Actual | Actual | Actual |  |  |  |  | Actual | Actual | Actual | Actual |  |  |  |  | Actual | Actual | Actual |  |  |  |  | Actual | Actual | Actual
NORTH WEST | RT | 77 | 70 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 33 | 0 | 1 | 0 | 0 | 8 | 33 | 2 | 0 | 33 | 34 | 35 | 4 | 0 | 35 | 19 | 2 | 19 | 0 | 2 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 48 | 37 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 16 | 1 | 0 | 16 | 24 | 20 | 10 | 0 | 20 | 13 | 1 | 13 | 0 | 1 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 54 | 39 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | 13 | 17 | 6 | 0 | 17 | 23 | 19 | 7 | 0 | 19 | 6 | 3 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 179 | 146 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 60 | 0 | 1 | 0 | 0 | 33 | 66 | 9 | 0 | 66 | 81 | 74 | 21 | 0 | 74 | 38 | 6 | 38 | 0 | 6 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH EAST | SZ FO | 253 | 157 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 5 | 30 | 0 | 6 | 0 | 0 | 154 | 41 | 66 | 0 | 41 | 56 | 102 | 26 | 0 | 102 | 49 | 14 | 42 | 0 | 14 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 391 | 352 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 137 | 0 | 7 | 0 | 0 | 103 | 157 | 10 | 0 | 157 | 138 | 187 | 23 | 0 | 187 | 61 | 8 | 60 | 0 | 8 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 99 | 58 | 52 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 23 | 0 | 10 | 0 | 0 | 47 | 11 | 23 | 0 | 11 | 19 | 45 | 5 | 0 | 45 | 8 | 2 | 7 | 1 | 2 | 4 | 0 | 3 | 1 | 0 | 1 | 0 | 1 | 0 | 0
| TOTAL | 743 | 567 | 304 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 32 | 0 | 0 | 6 | 190 | 0 | 23 | 0 | 0 | 304 | 209 | 99 | 0 | 209 | 213 | 334 | 54 | 0 | 334 | 118 | 24 | 109 | 1 | 24 | 11 | 0 | 10 | 1 | 0 | 1 | 0 | 1 | 0 | 0
Grand Total |  | 922 | 713 | 382 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 35 | 0 | 0 | 7 | 250 | 0 | 24 | 0 | 0 | 337 | 275 | 108 | 0 | 275 | 294 | 408 | 75 | 0 | 408 | 156 | 30 | 147 | 1 | 30 | 18 | 0 | 17 | 1 | 0 | 1 | 0 | 1 | 0 | 0

## PAN INDIA Summary
EPC (PAN INDIA) ROLLOUT STATUS AT A GLANCE - FY 2026-27
Sl. No. | Business Format / Sub Format | Site Type | PM Head | AOP FY 2025-26 | Carry Forward |  |  | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  |  |  | EPC READY | LAUNCHED | YTL | YTL - Dropped by Business | TOTAL EPC READY | TOTAL LAUNCHED | TOTAL YTL | TOTAL YTL - Dropped by Business | WIP | MARCH 25 BACKLOG BTG | APRIL 25 BACKLOG BTG | MAY 25 BACKLOG BTG | JUNE 25 BACKLOG BTG | JULY 25 BACKLOG BTG | AUGUST 25 BACKLOG BTG | SEPTEMBER 25 BACKLOG BTG | OCTOBER 25 BACKLOG BTG | NOVEMBER 25 BACKLOG BTG | MARCH 25 PLANNED | APRIL 25 PLANNED | MAY 25 PLANNED | JUNE 25 PLANNED | JULY 25 PLANNED | AUGUST 25 PLANNED | SEPTEMBER 25 PLANNED | OCTOBER 25 PLANNED | NOVEMBER 25 PLANNED | DECEMBER 25 PLANNED | JANUARY 26 PLANNED | FEBRUARY 26 PLANNED | MARCH 26 PLANNED | APRIL 26 PLANNED | MAY 26 PLANNED | JUNE 26 PLANNED | JULY 26 PLANNED | AUGUST 26 PLANNED | On Hold | Partial WIP | YTS | Dropped | NRFC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[5 empty] | EPC Ready Previous FY | LAUNCHED | YTL | 2026-04-01 | 2026-05-01 | 2026-06-01 | Q1 TOTAL | 2026-07-01 | 2026-08-01 | 2026-09-01 | Q2 TOTAL | 2026-10-01 | 2026-11-01 | 2026-12-01 | Q3 TOTAL | 2027-01-01 | 2027-02-01 | 2027-03-01 | Q4 TOTAL | [41 empty] | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Design WIP | ML Received - Business Issue | SDR Done - ML Pending | SDR - In Progress | Pre SDR Site | Pre Budget Dehire Site
|  |  |  | 2265 | 34 | 25 | 9 | 275 | 408 | 30 | 713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713 | 408 | 305 | 0 | 747 | 433 | 314 | 0 | 382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 24 | 108 | 75 | 147 | 17 | 1 | 76 | 4 | 3 | 29 | 578 | 156 | 211 | 67 | 9 | 126 | 0 | 4 | 5
A | A. Consumer Electronics & Jewels |  |  | 1078 | 6 | 3 | 3 | 15 | 6 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 8 | 13 | 0 | 27 | 11 | 16 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 25 | 0 | 0 | 1 | 14 | 0 | 0 | 0
1 | Digital Stores | NSO | Amit C | 85 | 4 | 2 | 2 | 5 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 4 | 0 | 11 | 5 | 6 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12 | 0 | 0 | 1 | 11 | 0 | 0 | 0
2 | My Jio Store | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Compact Digital | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0
4 | DMS |  |  | 150 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 3 | 0 | 4 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Digital Bismi |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Digital 3K | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
7 | Maintenance & Service Location (MSL) | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | RESQ |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Digital - Refit | Refit | Amit C | 89 | 2 | 1 | 1 | 5 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 4 | 0 | 8 | 3 | 5 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | MJS to DMS Refit | Refit | Amit C | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Consumer Electronics - Dehire | Dehire | Amit C | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Jewels SAS | NSO | Amit C | 22 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Jewels - Refit | Refit | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Jewels - Dehire | Dehire | Amit C | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | B. Fashion & Lifestyle |  |  | 1270 | 2 | 2 | 0 | 234 | 353 | 23 | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 354 | 256 | 0 | 612 | 356 | 256 | 0 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 23 | 98 | 42 | 86 | 9 | 0 | 35 | 1 | 0 | 9 | 258 | 28 | 137 | 49 | 2 | 40 | 0 | 2 | 0
1 | Trends (Trends + Trends 3.0) | NSO | Srinivas P | 50 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 2 | 0 | 3 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4 | 2 | 0 | 0 | 14 | 0 | 0 | 0
1.1 | Trends | NSO | Srinivas P | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2 | 1 | 0 | 0 | 13 | 0 | 0 | 0
1.2 | Trends 3.0 | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 2 | 0 | 3 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0
1.3 | Trends 4.0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Trends Small Town (TST + TST 3.0) | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0
2.1 | Trends Small Town | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0
2.2 | Trends Small Town 3.0 | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
3 | Trends Woman (Woman + Woman 3.0) | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
3.1 | Trends Woman | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
3.2 | Trends WIW 3.0 | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Yousta (Yousta + Yousta Conversion) | NSO | Srinivas P | 5 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 26 | 10 | 7 | 2 | 0 | 6 | 0 | 1 | 0
4.1 | Yousta | NSO | Srinivas P | 5 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 8 | 6 | 2 | 0 | 6 | 0 | 1 | 0
4.2 | Yousta Conversion | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
5 | Azorte (Azorte + Azorte Conversion) | NSO | Srinivas P | 12 | 0 | 0 | 0 | 1 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 2 | 1 | 0 | 3 | 0 | 0 | 0
5.1 | Azorte | NSO | Srinivas P | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2 | 1 | 0 | 3 | 0 | 0 | 0
5.2 | Azorte Conversion | NSO | Srinivas P | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Trends Man | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0
7 | Trends Junior | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Avantra | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
9 | Trends Footwear | NSO | Srinivas P | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 3 | 9 | 0 | 1 | 1 | 0 | 0 | 0
10 | Performax | NSO | Srinivas P | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
11 | Kalanikethan / VRK Heritage | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | GAP EBO | NSO | Srinivas P | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 4 | 8 | 0 | 0 | 7 | 0 | 0 | 0
13 | Portico EBO | NSO | Srinivas P | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Catwalk | NSO | Srinivas P | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
15 | Centro NSO | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Fashion Factory | NSO | Srinivas P | 18 | 1 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 4 | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0
17 | Swadesh | NSO | Srinivas P | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Johnplayer EBO | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
19 | Lee Cooper EBO | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
20 | Amante | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
21 | Zivame EBO | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0
22 | Ancestry | NSO | Srinivas P | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Clovia | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
24 | Cover Story | NSO | Srinivas P | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | POS Migration | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0
26 | Ajio | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Ecko SIS | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
28 | Performax SIS | NSO | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0
29 | Clovia - POS Migration | Refit | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0
30 | Trends - Refit | Refit | Srinivas P | - | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 6 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0
31 | Trends - Renovation | Refit | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 18 | 46 | 0 | 0 | 0 | 0 | 0
32 | Footwear - Refit | Refit | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
33 | F&L - Dehire | Dehire | Srinivas P | 115 | 0 | 0 | 0 | 1 | 9 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 11 | 0 | 0 | 0 | 0
34 | Trends Transformation (Full) |  |  | 46 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 7 | 0 | 5 | 0 | 0 | 0 | 0
35 | Trends Transformation (Partial) |  |  | 1004 | 0 | 0 | 0 | 232 | 333 | 21 | 586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586 | 338 | 248 | 0 | 586 | 338 | 248 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 23 | 97 | 39 | 57 | 0 | 0 | 16 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | C. Grocery |  |  | 2627 | 6 | 6 | 0 | 9 | 22 | 3 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 14 | 20 | 0 | 40 | 20 | 20 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 15 | 45 | 6 | 0 | 8 | 0 | 1 | 5 | 85 | 31 | 16 | 8 | 6 | 24 | 0 | 0 | 0
1 | Smart | NSO | Ketan Shah | 200 | 6 | 6 | 0 | 4 | 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 2 | 0 | 14 | 12 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 1 | 0 | 49 | 17 | 8 | 2 | 6 | 16 | 0 | 0 | 0
2 | FreshPik | NSO | Ketan Shah | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
3 | Smart Point | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
4 | Women's World @ SBZ | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Grocery Bismi | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
7 | Grocery - Refit | Refit | Ketan Shah | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 18 | 5 | 5 | 4 | 0 | 4 | 0 | 0 | 0
8 | Grocery - Refit (Partial) | Refit | Ketan Shah | 1933 | 0 | 0 | 0 | 0 | 7 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 34 | 0 | 0 | 3 | 0 | 0 | 1 | 0
9 | Grocery - SLP Works |  |  | - | 0 | 0 | 0 | 2 | 7 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 7 | 0 | 9 | 2 | 7 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 2 | 0
10 | Smart Bazar - Refit | Refit | Ketan Shah | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Dark Store to Smart point Conversion |  |  | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | BWS in Smart Bazar | NSO | Ketan Shah | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Grocery - Dehire | Dehire | Ketan Shah | - | 0 | 0 | 0 | 2 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
14 | Signature (Signature + Sig. Fresh Plus) | NSO | Ketan Shah | 94 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
14.1 | Signature | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
14.2 | Signature to Go Fresh Conversion |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14.3 | Go Fresh | NSO | Ketan Shah | 10 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Blushlace SIS (SIS in Smart + SIS in Smart Bazar) | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
15.1 | Blushlace in Smart | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
15.2 | Blushlace in Smart Bazar | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Centro Footwear (V Retail) | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 4 | 1 | 1 | 0 | 1 | 0 | 0 | 0
17 | Centro Footwear (V Retail) - The Shoe Store | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Centro Footwear (V Retail) in Smart Bazar | NSO | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Centro Footwear (V Retail) - Refit | Refit | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Centro Footwear (V Retail) - Dehire | Dehire | Ketan Shah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | D. Pharma Format |  |  | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1 | Pharma COCO Store (SP Fix Setup) | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Netmed |  |  | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | E. Other Business |  |  | 109 | 0 | 0 | 0 | 3 | 3 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 6 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 23 | 0 | 0 | 2 | 46 | 13 | 4 | 2 | 0 | 27 | 0 | 0 | 0
1 | 7-Eleven | NSO | Amit C | 100 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 23 | 0 | 0 | 2 | 38 | 13 | 2 | 0 | 0 | 23 | 0 | 0 | 0
2 | 7-Eleven - Dehire | Dehire | Amit C | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Furniture - Mid Premium Store (UL) | NSO | Amit C | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0
4 | Urban Ladder SIS | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
5 | Misc - Dehire | Dehire | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
6 | Misc - Refit |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | R&D FMCG Lab | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Beauty (TIRA) | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | F. SCM |  |  | 100 | 4 | 0 | 4 | 3 | 3 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 6 | 0 | 11 | 1 | 10 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 62 | 8 | 33 | 5 | 0 | 11 | 0 | 0 | 5
1 | Milk Basket | SCM | Srinivas P | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
2 | Smart Hub - DC | SCM | Srinivas P | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Smart Net - DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Metro | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | PCS | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0
6 | SCM - Dehire | Dehire | Srinivas P | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 5
7 | SCM BF |  |  | 85 | 4 | 0 | 4 | 1 | 3 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 9 | 0 | 9 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 47 | 6 | 28 | 4 | 0 | 9 | 0 | 0 | 0
7.1 | CPC | SCM | Srinivas P | 0 | 3 | 0 | 3 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 7 | 2 | 0 | 0 | 0 | 0 | 0
7.2 | Value DC | SCM | Srinivas P | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 4 | 0 | 4 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 1 | 6 | 2 | 0 | 3 | 0 | 0 | 0
7.3 | Beauty DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.4 | Digital DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11 | 1 | 6 | 0 | 0 | 4 | 0 | 0 | 0
7.5 | WH | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
7.6 | B2C | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.7 | F&L DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0
7.8 | FC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.9 | Jewels DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.10 | Pharma-DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.11 | Smart Bazar DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.12 | Urban Ladder DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
7.13 | Jio DC | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
7.14 | Record Room | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.15 | Market Place | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0
G | G. GreenField and Other Large Scale Projects |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
1 | Mall Revamp | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
2 | Greenfield | SCM | Srinivas P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | I. Petro |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 46 | 44 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1 | Terminal Aug | Petro | Anand P | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
2 | Mini Depo - Aug | Petro | Anand P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Consumer Pump | Petro | Anand P | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | J. Jio Business |  |  | 193 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 7 | 7 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0
1 | Jio Mart Digital | NSO | Anand P | 185 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 7 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Jio Centre | NSO | Srinivas P/Amit C | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0
K | K. Other Office Infrastructure |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1 | Admin Office (Corporate Services) | NSO | Amit C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
L | L. Dark Store |  |  | 450 | 16 | 14 | 2 | 7 | 8 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 8 | 10 | 0 | 34 | 22 | 12 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 1 | 13 | 29 | 6 | 14 | 2 | 0 | 5 | 0 | 2 | 0
1 | Dark Store | NSO | Srinivas P/Amit C | 450 | 16 | 14 | 2 | 7 | 8 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 8 | 10 | 0 | 34 | 22 | 12 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 1 | 13 | 29 | 6 | 14 | 2 | 0 | 5 | 0 | 2 | 0
M | M. Brands |  |  | - | 0 | 0 | 0 | 4 | 1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0
1 | Ed-A-Mamma EBO | NSO | Srinivas P | - | 0 | 0 | 0 | 4 | 1 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 5 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0
| Grand Total |  |  | 5902 | 34 | 25 | 9 | 275 | 408 | 30 | 713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 713 | 408 | 305 | 0 | 747 | 433 | 314 | 0 | 382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 24 | 108 | 75 | 147 | 17 | 1 | 76 | 4 | 3 | 29 | 578 | 156 | 211 | 67 | 9 | 126 | 0 | 4 | 5

## Main Backup
APEX ID | Sl. No. | Land ID | 9008 Store Code | NP01 Site Code | PD | Business Format | Format | Sub Format | PM Head | PM | PM Planner | Site Type (Dehire/NSO/Refit) | Zone | ZH | State | Cluster | EIC | Site Name | City | Area (Sqft) | RFC Date | Actual Start Date | Standard Duration | Change Note / Site Specific Duration | Planned Finish Date | Forecasted Finish Date | Actual Finish Date | EPC Status (Current Week) | % Completion (Current Week) | Remarks (Current Week) | HOTO Date | Launch Date | LAUNCHED / YTL | FY | AOP / NON AOP | Planned (Month) Bucket | Actual (Month) Bucket | Target Date | Target | P vs A | Dehire Target | Need Push / Sure | Remarks | RFP | Rent Start Date | Dead Rent Days | Dead Rent Bucket | Dead Rent Status | ML Date | LOA Date | EPC Status (Last Week) | % Completion (Last Week) | Remarks (Last Week) | AOP / NON Phase | Phase Wise Sites
GRDSKC14784 | 1 | DS-MH-00125 | TBMN | QHNQ | DARKMQHNQ00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  | Biplab Hota | Yelwande Property, Hinjewadi | Pune | 2782 | 2026-04-29 | 2026-04-30 | 15 |  | 2026-05-15 | 2026-06-01 | 2026-06-02 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MAY 26 PLANNED | JUNE 26
MBSKAK14858 | 2 |  |  |  |  | F. SCM | SCM BF | Milk Basket | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka |  |  | Whitefield Bangalore -Milkbasket Additional Area - Survey No: 86, 90/3 & 91/3 , Koralur Village, Kasaba Hobli, Hoskote Taluk,Bangalore-560067 |  | 44420 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | MAY 25
SMRTBK14902 | 3 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | Wankhede property, Malkhapur | Buldhana |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
CATWRT13832 | 4 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Catwalk | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | VR MALL MOHALI | Mohali |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
AMANRT4572 | 5 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Amante | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | VR Mall |  | 344 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRTRSD15194 | 6 |  | TPM2 | Q0NI | TFITAQ0NI03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  | Ramana Babu PMC | Vizag Waltair Rd Siripuram | Vizag | 13877 | 2026-02-05 | 2026-02-05 | 0 | 15 | 2026-02-20 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-1 EPC | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRSD15188 | 7 |  | TN49 | NC50 | TRNDANC5006 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  | Ramana Babu PMC | Vizag Daba Garden | Vizag | 13107 | 2026-02-05 | 2026-02-05 | 0 | 15 | 2026-02-20 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-1 EPC | 2026-04-12 | 2026-04-12 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRSD15142 | 8 |  | TQE7 | Q0XN | TFITAQ0XN02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  | Surya Teja Duddu | Vishakhapatnam Madhuravada | Visakhapatnam | 15440 | 2026-01-29 | 2026-01-29 | 0 | 15 | 2026-02-13 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-1 EPC | 2026-04-14 | 2026-04-14 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
GRDSKC15268 | 9 | DS-MH-00126 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  |  | Vinayak Arcade - Akurdi, Pune | Pune |  |  |  | 15 |  |  |  |  | Dropped | [5 empty] | FY 26-27 | AOP |  |  | OCTOBER 25
GRDSRT14773 | 10 | DS-DL-00328 | TBFP | QHHX | DARKDQHHX00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Arun Bhati | Vikaspuri | Delhi | 2379 | 2026-02-25 | 2026-03-11 | 15 |  | 2026-03-26 | 2026-04-06 | 2026-04-07 | EPC Ready | 100% |  | PENDING | 2026-04-30 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
SCPCAK14857 | 11 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Andhra Pradesh |  |  | Vijayawada FFDC - Vijayawada |  | 37376 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
VADCKC14912 | 12 |  | SAQN | QHIL | DCDCCQHIL00 | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Chattisgarh |  | Abhay Shrivastava | VFDC - Dumartarai, Raipur | Raipur | 91898 | 2026-02-13 | 2026-02-20 | 60 | 0 | 2026-04-21 | 2026-06-15 |  | WIP | 90% |  |  |  |  | FY 26-27 | AOP | APRIL 26 PLANNED
POSMRT11376 | 13 |  | T5ZH | QM0O | RZIVDQM0O00 | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi | Prakhar Pratap Singh | Vegas Mall | Delhi & Ncr | 520 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRDSBK232 | 14 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat | Surat |  | Ved Road,Surat | Surat |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
TRDSBK11231 | 15 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | Marathwada |  | Vazirabad,Nanded | Nanded |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SCPCAK13877 | 16 |  | S0GI | Q4KF | CPC1VQ4KF00 | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Kerala | Ernakulam | Dijeesh P D | Vazhakulam, Aluva-FFDC additional Scope | Ernakulam | 61093 | 2025-12-30 | 2025-12-30 | 0 | 30 | 2026-01-29 | 2026-02-25 | 2026-02-23 | EPC Ready Previous FY | 100% | YTL | 2026-05-25 |  | YTL | FY 25-26 | AOP
GRDSRT14738 | 17 | DS-DL-00209 | T9U0 | Q8A0 | DARKDQ8A000 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | RT | Delhi & NCR |  | Manoj Gupta | Vasant Kunj | Delhi NCR |  |  |  | 15 |  |  | 2025-12-13 |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
SNDCKC13716 | 18 |  | 9693 | NFZ8 | SMRTGNFZ801 | F. SCM | SCM | Smart Net - DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Gujarat |  | Haresh Patil | Vantara Jamnagar | Jamnagar | 19087 | 2025-11-15 | 2025-11-18 | 90 | 0 | 2026-02-16 | 2026-04-16 | 2026-04-15 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
POSMRT11378 | 19 |  | T5ZG | QM0N | RZIVDQM0N00 | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi | Saket Sharma | V3S Mall | Delhi & Ncr | 550 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  | 2024-10-15 |  |  | FY 26-27 | NON AOP
ZIVART10522 | 20 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Zivame EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi |  | Uttam Nagar, Delhi | Delhi | 767 |  |  | 15 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13245 | 21 |  | T9XE | QXOE |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Rajasthan | Udaipur |  | Urban Square Mall | Udaipur | 556 |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
GRDHRT5045 | 22 |  | FROI | QFBQ | DH-SMPT-451-UP-U2FW | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | North | KC | Uttar Pradesh | Kanpur | Sanjoy Das | UP Kanpur KIDWAI NAGAR | Kanpur | 2300 | 2026-03-09 | 2026-03-09 | 0 | 15 | 2026-03-24 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% |  | PENDING | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
YOTHBK14883 | 23 |  | TBET | QHHB | TYOUMQHHB00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Maharashtra | West Maharashtra | Shivkumar Goswami | Unit - F1a to F1f at First Floor, Seasons Mall, Pune | Pune | 6070 | 2026-01-19 | 2026-01-27 | 35 | 20 | 2026-03-23 | 2026-03-25 | 2026-03-25 | EPC Ready Previous FY | 100% | Exp Launch by 15/Apr | 2026-05-13 | 2026-05-15 | Launched | FY 25-26 | AOP |  |  | OCTOBER 25
FLDHKC12701 | 24 |  | TDP8 | NL53 | DH-TEXP-419-PB-TDP8 | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Punjab |  |  | TST Zirakpur | Zirakpur |  |  |  | 0 | 25 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDHBK13261 | 25 |  | TUO3 | Q2OL |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Maharashtra | West Maharashtra |  | TS Kolhapur Circle, Civil Hospital Rd | Kolhapur |  |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
TRDSBK10916 | 26 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | Vidarbha |  | TRENDSMHGadchiroliBus Stand > Vision Mall | Gadchiroli |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
YOCOBK13313 | 27 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta Conversion | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Chattisgarh | Raipur |  | TRENDS TO Yousta - Pandri, Raipur | Raipur | 13815 |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
AZORBK11465 | 28 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | GMU | Mumbai |  | Trends to Azorte - Alpha One | Mumbai |  |  |  | 60 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRD3RT13839 | 29 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh |  |  | Trends Renovation 2.0 to 3.0 - Z square Mall Kanpur | Kanpur |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3RT13840 | 30 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh |  |  | Trends Renovation 2.0 to 3.0 - SP marg Allahabad | Allahabad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3BK13374 | 31 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | Trends Renovation - Viviana Mall thane- Phase 1 | Thane |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3BK13373 | 32 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | Trends Renovation - Seawoods Grand central- Phase 1 | Navi Mumbai |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3BK13791 | 33 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | Trends Renovation - Malad Inorbit Mall- Phase1 | Malad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3BK13376 | 34 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | Trends Renovation - Malad Infinity Mall- Phase 1 | Malad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3BK13375 | 35 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Maharashtra | West Maharashtra |  | Trends Renovation - Amanora Mall Pune- Phase 1 | Pune |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRDSBK14959 | 36 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU |  |  | Trends Growells Kandivali | Mumbai | 5878 | [7 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
TRD3RT13833 | 37 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi |  | Trends 3.0 Renovation - Rajouri Garden | Delhi |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3BK13792 | 38 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Maharashtra | North Maharashtra |  | Trends 3.0 Renovation - Nasik CityCentre Mal- Phase 1 | Nashik |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
TRD3BK13793 | 39 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Maharashtra | West Maharashtra |  | Trends 3.0 Renovation - Amanora Mall, Pune | Pune |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
MIAGKC14820 | 40 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  | Atul3 Garg | Tilbegumpur- Exhaust Stack to be provided for DG 82.5 KVA | Tilbegumpur |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGKC14819 | 41 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  | Atul3 Garg | Tilbegumpur - Provision of Hazardous waste Shed. | Tilbegumpur |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
MIAGKC14821 | 42 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  | Atul3 Garg | Tilbegumpur - Louvers on FW Ph shed. Phase I (6 Depot’s) | Tilbegumpur |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGKC12175 | 43 |  | Not Applicable | Not Applicable | PETRO-MDUPTI4 | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  | Neeraj Kumar | Tilbegampur-Transformer replacement at (7 Mini Depots ) with statutory approvals | Tilbegampur | 8000 | 2024-11-04 | 2024-11-04 | 0 | 157 |  | 2025-04-30 |  | Partial WIP | 87% | WIP - On Hold |  |  |  | FY 26-27 | AOP |  |  | MAY 25
MIAGAK14807 | 44 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Andhra Pradesh |  |  | Tada- Exhaust Stack to be provided for DG 82.5 KVA | Tada |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP |  |  | MAY 25
MIAGAK14806 | 45 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Andhra Pradesh |  |  | Tada - Provision of Hazardous waste Shed. | Tada |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14808 | 46 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Andhra Pradesh |  |  | Tada - Louvers on FW Ph shed. Phase I (6 Depot’s) | Tada |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
ZIVART10565 | 47 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Zivame EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | Sushma Capitol Zirakpur | Zirakpur | 514 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GAPERT10689 | 48 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | Sushma Capital, Peer Muchalla, Zirakpur. PB | Zirakpur |  |  |  | 45 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC10942 | 49 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | GMU | Mumbai |  | Sunteck West World,Naigaon | Mumbai |  |  |  | 0 | 25 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTKC14533 | 50 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | KC | Gujarat |  |  | Strip Mall | Jamnagar |  |  |  | 35 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14910 | 51 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Spectrum Metro | Noida |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | NOVEMBER 25
GRDHKC12634 | 52 |  | U11F | Q8WS | DH-SMPT-451-UP-U11F | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | North | KC | Uttar Pradesh | Lucknow |  | SP UP Lck Janki Ext Bithauli CR | Lucknow | 3073 |  |  | 0 | 15 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHKC14186 | 53 |  | U3WI |  | DH-SMPT-451-RJ-U3WI | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | North | KC | Rajasthan |  |  | SP RJ Balotra Hotel City Square | Barmer | 8000 |  |  | 0 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHKC14209 | 54 |  | U25T |  | DH-SMPT-451-MH-U25T | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | West | KC | Maharashtra |  |  | SP Railway Station Main Rd B | Bhadravati | 3202 | 2025-10-15 | 2025-11-04 | 0 | 15 |  | 2025-12-04 |  | On Hold | 2% |  |  |  |  | FY 26-27 | NON AOP
GAPEBK11225 | 55 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | Solitaire World Plaza, Bibwewadi, Pune | Pune |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT10380 | 56 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Smart Ghana Shopping Mall Elite Chowk | Jhansi |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT10359 | 57 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Smart GC Tower | Bijnor |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
SMRTRT14899 | 58 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Delhi & NCR |  |  | Smart at The Core, Opp Crossing Republic, Ghaziabad | Ghaziabad | 23000 |  |  | 35 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14898 | 59 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Delhi & NCR |  |  | Smart at Oxy Street, Koyal Enclave, Loni Road, Ghaziabad | Ghaziabad | 20000 |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14906 | 60 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Smart : - Sun Twilight Metro Street, Sector-27, Greater Noida | Noida |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14897 | 61 |  | TBGU | QHJC | SMRTUQHJC00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Smart - Mini Bypass Road, Karmchari Nagar, Bareilly (Semi Constructed) | Bareilly | 21790 | 2026-06-01 | 2026-06-01 | 35 |  | 2026-07-06 | 2026-07-06 |  | WIP | 8% |  |  |  |  | FY 26-27 | AOP | JULY 26 PLANNED
SMRTBK14904 | 62 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Chattisgarh |  |  | Smart - BTS Property option at Kohka, Bhilai (CG) | Durg Bhilai |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSBK14751 | 63 | DS-GMU-00097 | TL6V | QZ0J | DARKMQZ0J00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU |  | Hareshprasad Mishra | Siddarth Nagar, Goregoan West | Mumbai | 1860 | 2026-02-11 | 2026-02-17 | 15 |  | 2026-03-04 | 2026-03-25 | 2026-03-25 | EPC Ready Previous FY | 100% | YTL | OTHER ISSUES | 2026-05-16 | Launched | FY 25-26 | AOP
GRDSKC14757 | 64 | DS-MH-00090 |  | QHCJ | DARKMQHCJ00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  | Sushanta Kumar Behera | Shridhar Kalash, Besa square, Nagpur | Nagpur |  |  |  | 15 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSBK14772 | 65 | DS-MH-00119 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | Maharashtra |  |  | Shri Sadguru Siddharudha Adhyatma Samit, Ramnagar | Nagpur |  |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRFTRT14957 | 66 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | Shop No 429L Brand Road Model Town Ludhiana Punjab | Ludhiana | 2263 | [7 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
YOTHBK14879 | 67 |  | TBG5 | QHJI | TYOUMQHJI00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Maharashtra | West Maharashtra | Rahul Atal | Shop No 1,2 &3, Aakar Prime -Gangapur Road -Nashik | Nashik | 6166 | 2026-04-10 | 2026-04-13 | 35 | 10 | 2026-05-28 | 2026-06-15 |  | WIP | 75% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED |  | AUGUST 25
SMRTBK10365 | 68 |  | T7IH | QP2K | SMRTMQP2K00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra | Marathwada | Rohit Patil | Shivaji Putala, Vazirabad, Nanded- | Nanded | 25602 | 2026-01-12 | 2026-01-16 | 35 | 7 | 2026-02-27 | 2026-02-28 | 2026-03-02 | EPC Ready Previous FY | 100% |  | 2026-04-28 | 2026-04-30 | Launched | FY 25-26 | AOP |  |  | SEPTEMBER 25
GRDSKC15267 | 69 | DS-GMU-00178 | TBI3 | QHLG | DARKMQHLG00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU |  |  | Shiravane, Sector-1, Nerul - Nikhil Hydraulics | Mumbai | 2706 | 2026-03-09 | 2026-03-12 | 15 |  | 2026-03-27 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% |  | PENDING | 2026-05-15 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
SMRTBK14535 | 70 |  | TBH1 | QHKJ | SMRTMQHKJ00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | Shinde Complex, Shirur | Pune | 18714 | 2026-05-25 | 2026-05-28 | 35 |  | 2026-07-02 | 2026-07-02 |  | WIP | 10% |  |  |  |  | FY 26-27 | AOP | JULY 26 PLANNED
TEAGAK14565 | 71 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu |  | Vasant A | Shifting of ROSOV LCS (24 No’s) at Chennai from Dyke area to area near Tank Farm approach Road along with FLP Distribution Box |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
SIGNBK14568 | 72 |  |  |  |  | C. Grocery | Grocery | Signature | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Chattisgarh |  |  | Shankar Nagar | Raipur | 4027 |  |  | 35 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | NON AOP
POSMRT11389 | 73 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh | Lucknow |  | Shalimar Lucknow | Lucknow | 236 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
SMRTBK10388 | 74 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | SFC Annexe |  |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
COPUKC13442 | 75 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | West Bengal | Kharagpur |  | Setup a petrol pump at RIL (Shyam Sel Group), Kharagpur site | Kharagpur |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
GAPERT11220 | 76 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi - NCR |  | Sector 13 Dwarka | Delhi & NCR |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
TRFTRT10692 | 77 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi |  | Sarojini Market | Delhi |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSKC14749 | 78 | DS-DL-00038 | TM2E | QZ4M | DARKDQZ4M00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Akhilesh Kumar Singh | Sarita Vihar | Delhi NCR | 3489 | 2026-01-29 | 2026-02-16 | 15 |  | 2026-03-03 | 2026-03-28 | 2026-03-31 | EPC Ready Previous FY | 100% | YTL | 2026-04-20 | 2026-04-17 | Launched | FY 25-26 | AOP
GAPERT13418 | 79 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Rajasthan | Jodhpur |  | Sardarpura Road, Jodhpur | Jodhpur |  |  |  | 45 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14893 | 80 |  | TH5A | QZGO | SMRT9QZGO00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Punjab |  |  | Saran Complex, Abohar ,Punjab | Abohar | 20000 | 2026-04-15 | 2026-04-27 | 35 |  | 2026-06-01 | 2026-06-25 |  | WIP | 45% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
TRFTRT11644 | 81 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttarakhand | Dehradun |  | Sanwal Plaza, haldwani-Haldwani | Haldwani |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SCDHAK12650 | 82 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | East | AK | West Bengal |  |  | Sankrail DC | Sankrail | 45000 |  |  | 0 |  |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
GAPERT11229 | 83 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh | Lucknow |  | Saharaganj Mall, Shahnajaf Road, Lucknow | Lucknow | 3146 |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | MAY 25
MAREKC13731 | 84 |  |  |  |  | G. GreenField and Other Large Scale Projects | GreenField | Mall Revamp | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Delhi & NCR | Delhi |  | RM VIKASPURI | Delhi |  |  |  | 0 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
TEAGKC13803 | 85 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Delhi & NCR | Delhi - NCR | Anand Singh | Rewari - Implementing Rainwater Harvesting | Rewari | 5500 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% | Budget Submitted - Approval Awaited |  |  |  | FY 26-27 | AOP |  |  | JULY 25
TEAGKC13465 | 86 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Delhi & NCR | Delhi - NCR | Anand Singh/Ram Kumar Yadav | Rewari - Cement Concrete paving under pipeline manifold area at all 5 OTs. | Rewari | 26910 | 2026-03-18 | 2026-03-18 | 0 | 90 | 2026-06-16 | 2026-06-16 |  | WIP | 46% | WIP |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
PERFBK10913 | 87 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat |  |  | Reliance Mall, F-10, First Floor, Survey No 44, Moti Khavdi, Jamnagar Gujarat - 361142 | Jamnagar |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FFNSBK14887 | 88 |  | TBCI | QHEV | TRFFMQHEV00 | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | GMU | Mumbai | Vaibhav Jadhav | Reliance Mall D Victoria Borivali | Borivali | 13078 | 2026-01-16 | 2026-01-19 | 45 |  | 2026-03-05 | 2026-03-25 | 2026-03-24 | EPC Ready Previous FY | 100% |  | 2026-04-01 | 2026-04-15 | Launched | FY 25-26 | AOP
VADCAK14852 | 89 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Jharkhand |  |  | Ranchi VFDC - SITE AT TAIMARA, RANCHI, JARIA |  | 155119 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
GRDSRT14745 | 90 | DS-DL-00314 | TBEE | QHGS | DARKDQHGS00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Arun Bhati | Rampura Road | Delhi | 1737 | 2026-01-27 | 2026-01-29 | 15 |  | 2026-02-13 | 2026-03-07 | 2026-03-11 | EPC Ready Previous FY | 100% |  | 2026-03-31 | 2026-04-02 | Launched | FY 25-26 | AOP
FLDCKC14916 | 91 |  | SL3L | Q3K3 | CPC19Q3K302 | F. SCM | SCM BF | CPC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Uttar Pradesh |  | Surender Kumar Dhaka | Rajpura - Cold Room | Rajpura | 184397 | 2026-01-23 | 2026-03-31 | 45 |  | 2026-05-15 | 2026-06-10 |  | WIP | 80% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED
POSMRT11371 | 92 |  | T5TY | QL5E | RZIVDQL5E00 | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi | Prakhar Pratap Singh | Rajouri Garden | Delhi & Ncr | 769 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FLDHKC13154 | 93 | GJ-SM-RAJ-105 | TPH8 | Q0LI |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Gujarat | Rajkot |  | Rajkot Vandana Heritage Gondal Road | Rajkot | 13406 |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
TRWNBK11215 | 94 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Woman | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | Rajarampuri Kolhapur Sykes Extension | Kolhapur |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | NON AOP
VADCAK15252 | 95 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka |  |  | Rajamundry DC |  | 30000 |  |  | 0 |  |  |  |  | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | JUNE 25
SPCSKC13721 | 96 |  |  |  |  | F. SCM | SCM | PCS | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Haryana |  |  | Rai | Rai |  |  |  | 0 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
POSMBK11388 | 97 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | R Mall Thane | Thane | 583 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
POSMBK11381 | 98 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | R City Mall | Mumbai | 577 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
TRFTRT11645 | 99 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Rajasthan | Jaipur |  | Queens Road, Jaipur-jaipur | Jaipur |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRTRBK15151 | 100 |  | T9LI | QXCN | TFITMQXCN02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Pune Mall Of Millenia Wakad | Pune | 12422 | 2026-02-24 | 2026-02-24 | 0 | 15 | 2026-03-11 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-04 | 2026-04-04 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JULY 25
FLDHKC12741 | 101 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Maharashtra | West Maharashtra |  | Pune ascent Mall | Pune |  |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP |  |  | OCTOBER 25
SPCSAK11396 | 102 |  |  |  |  | F. SCM | SCM | PCS | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Telangana | Hyderabad |  | Pudur PCS- Additional Work | Hyderabad | 83076 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | DECEMBER 25
YOTHRT13534 | 103 |  | TK1R | QY0Q | TYOUUQY0Q00 | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Uttar Pradesh | Lucknow | PMC Karan Vashith | Prominent mall, Lucknow | Lucknow | 9273 | 2026-04-14 | 2026-04-17 | 35 |  | 2026-05-22 | 2026-06-05 | 2026-06-01 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MAY 26 PLANNED | JUNE 26
FFNSBK11214 | 104 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | Premier Plaza Mall, Chinchwad Pune | Pune |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
TRDSBK13422 | 105 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat | Surat |  | Prasang Party Plot, Opp. Mac Donald, Sama savli Road, Vadodara | Surat |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSBK14753 | 106 | DS-GMU-00082 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | GMU |  | Sunil Grandhe | Prarthane Ville Parle | Mumbai |  |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
MIAGAK14803 | 107 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu |  |  | Pollachi - Provision of Hazardous waste Shed. | Pollachi |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14804 | 108 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu |  |  | Pollachi - Louvers on FW Ph shed. Phase II (4 Depot’s) | Pollachi |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14805 | 109 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu |  |  | Pollachi - Borewell Head Protection | Pollachi |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  | s |  | FY 26-27 | AOP
POSMBK11375 | 110 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | PMC Kurla | Kurla | 427 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3RT11240 | 111 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends 3.0 | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi - NCR |  | PKS Town Central | Noida |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | NON AOP
CATWRT13417 | 112 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Catwalk | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh | Lucknow |  | Phoenix United Mall, Alambagh, Lucknow | Lucknow |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GAPERT13831 | 113 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh |  |  | Phoenix United Mall, Alambagh, Lucknow | Lucknow |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
AMANRT4573 | 114 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Amante | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh | Lucknow |  | Phoenix United Mall, Lucknow | Lucknow | 363 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FORFBK13795 | 115 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Footwear - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Maharashtra | West Maharashtra |  | Phoenix Market City (PMC), Pune | Pune |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
SGFPBK14579 | 116 |  | TBN3 | QHOL | FPIKMQHOL00 | C. Grocery | Grocery | FreshPik | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  | Rafique Khan | Pheonix Marketcity, Viman Nagar | Pune | 6560 | 2026-02-16 | 2026-03-24 | 75 |  | 2026-06-07 | 2026-06-10 |  | WIP | 78% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
TRWNBK10704 | 117 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Woman | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | Pebbles Plaza (Aero Mall) | Pune |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRMNBK10705 | 118 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Man | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | Pebbles Plaza (Aero Mall) | Pune |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
DIDCKC14869 | 119 |  |  | QW4M | DCDCRQW4M01 | F. SCM | SCM BF | Digital DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Rajasthan |  |  | PBG Jaipur | Jaipur | 62194 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
LEECBK13377 | 120 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Lee Cooper EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Madhya Pradesh | Bhopal |  | Payless to Lee Cooper 2.0 - DB Mall , Bhopal | Bhopal |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
MIAGKC14809 | 121 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Punjab |  |  | Patran - Provision of Hazardous waste Shed. | Patran |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGKC14810 | 122 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Punjab |  |  | Patran - Louvers on FW Ph shed. Phase II (4 Depot’s) | Patran |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGKC14811 | 123 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Punjab |  |  | Patran - Borewell Head Protection | Patran |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
VADCAK15250 | 124 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Bihar |  |  | Patna VFDC (BTS) with PTL |  | 177,955 |  |  | 0 |  |  |  |  | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP
FLDHKC12721 | 125 |  | TKN8 | QCA0 |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Uttar Pradesh |  |  | Partially De Hire Lower Ground Floor TKN8 Betiahata, Hanuman Mandir Road, Gorakhpur | Gorakhpur |  |  |  | 0 | 25 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSBK14755 | 126 | DS-GOA-00009 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | Goa |  | Imran Pasha | Panaji, Goa | Goa |  |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT11385 | 127 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh | Lucknow |  | PALLASIO-LUCKNOW | Lucknow | 566 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDSRT14789 | 128 | DS-DL-00322 | TBED | QHGR | DARKDQHGR00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | RT | Delhi & NCR |  |  | Paharganj | Delhi |  |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
TRSTBK10709 | 129 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Small Town | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Madhya Pradesh |  |  | Pachore |  |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
ZIVART10568 | 130 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Zivame EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh | Varanasi |  | ORDERLY BAZAAR, VARANASI | Varanasi | 441 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
FFNSBK13423 | 131 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Chattisgarh | Raipur |  | Opp Anupam Garden, Near RKC, G.E. Road, Raipur (adjacent to upcoming Digital Store) | Raipur |  |  |  | 45 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SGFPRT15073 | 132 |  | TBPD | QHPJ | GOFRHQHPJ00 | C. Grocery | Grocery | Go Fresh | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Haryana |  | Deepak Gothwal | OP Jindal | Sonipat | 2804 | 2026-02-25 | 2026-03-09 | 60 |  | 2026-05-08 | 2026-05-15 | 2026-05-12 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MAY 26 PLANNED | MAY 26
FLDHKC12720 | 133 | PB-SM-KHR-903 |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Punjab | Mohali |  | Omni Pacific Colonizers Private Limited | Mohali |  |  |  | 0 | 25 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
SMRTBK14903 | 134 |  | TL4Z | QY8T | SMRTGQY8T00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Gujarat |  | Nirmal Kumar | Om Orbit Mundhra, GJ | Mundhra | 15792 | 2026-02-24 | 2026-02-26 | 35 |  | 2026-04-02 | 2026-04-24 | 2026-04-22 | EPC Ready | 100% |  | PENDING | 2026-05-29 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | APRIL 26
SMRTBK14901 | 135 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | NSO SMART_KHADSE COMPLEX _ AKOLA_NAGPUR | NAGPUR | 14408 |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
EDAMRT14084 | 136 |  | TBDK | TBDK | EDMMDTBDK00 | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Delhi & NCR |  | Manish Kumar Rai | NPS Unity Elegante, Delhi | Delhi | 544 | 2026-01-29 | 2026-02-06 | 35 |  | 2026-03-13 | 2026-04-18 | 2026-04-21 | EPC Ready | 100% |  | 2026-05-20 | 2026-05-06 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
TRDSBK11233 | 137 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | GMU | Mumbai |  | Nisarg Green Commercial Building | Mumbai |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SmartW24 | 138 |  | TAEP | QFNL | SMRTMQFNL00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | GMU | Mumbai | Nirmal Kumar | NIRMAL LIFESTYLE, MULUND | Mumbai | 30300 | 2022-04-30 | 2022-04-30 | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
GRDSKC13968 | 139 | DS-GMU-00014 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU | Mumbai | Dindayal Maurya | Niraj Riveria, Kalyan | Mumbai | 2112 |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
TRFTRT11646 | 140 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh |  |  | Night Plaza, Aligarh-Aligarh | Aligarh |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
VADCAK13440 | 141 |  | S0KK | Q5JR | DCDCKQ5JR03 | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka | Bangalore | Sreekanth B | Nidagatta Bangalore VFDC - PTL Setup | Bangalore | 16455 | 2026-01-08 | 2026-04-11 | 30 |  | 2026-05-11 | 2026-06-06 |  | WIP | 80% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED
ZIVART10564 | 142 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Zivame EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | Nexus Mall, Amritsar | Amritsar | 321 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
YOTHRT13342 | 143 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Punjab |  |  | Nexus Mall, Amritsar | Amritsar |  |  |  | 35 |  |  |  |  | Pre SDR Site | 0% |  |  |  |  | FY 26-27 | AOP
GRDSKC15266 | 144 | DS-RJ-00037 | TBKJ | QHMD | DARKRQHMD00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Rajasthan |  | Vikas Sharma | New_Ajmer_1 Shastri Nagar | Ajmer | 2597 | 2026-02-09 | 2026-02-16 | 15 |  | 2026-03-03 | 2026-03-03 | 2026-03-04 | EPC Ready Previous FY | 100% |  | 2026-03-31 | 2026-04-02 | Launched | FY 25-26 | AOP
TRMNBK200 | 145 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Man | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | GMU | Mumbai |  | Neelsiddhi Amarante, Kalamboli, Panvel,Raigad | Panvel |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | NON AOP
TRWNBK11218 | 146 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Woman | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | GMU | Mumbai |  | Neelsiddhi Amarante, Kalamboli, Panvel,Raigad | Panvel |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDSKC15269 | 147 | DS-GJ-00018 | TBKH | QHMB | DARKGQHMB00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Gujarat |  |  | Neelkanth Square, Naroda | Ahmedabad | 2494 | 2026-02-17 | 2026-02-23 | 15 |  | 2026-03-10 | 2026-03-25 | 2026-03-23 | EPC Ready Previous FY | 100% | YTL | PENDING | 2026-04-16 | Launched | FY 25-26 | AOP
ULDCAK14923 | 148 |  | SH1U | Q6P0 | DCDCKQ6P000 | F. SCM | SCM BF | Urban Ladder DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka | Bangalore | Vinay H V | Neelamangala Urban Ladder- Manufacturing unit | Bangalore | 50290 | 2025-12-16 | 2026-01-14 | 45 | 0 | 2026-02-28 | 2026-05-11 | 2026-05-12 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
ULDCAK14924 | 149 |  | SH1U | Q6P0 | DCDCKQ6P000 | F. SCM | SCM BF | Urban Ladder DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka | Bangalore |  | Neelamangala Urban Ladder DC- Warehouse area | Bangalore | 169951 | 2026-03-24 | 2026-03-25 | 45 |  | 2026-05-09 | 2026-06-20 |  | WIP | 75% |  |  |  |  | FY 26-27 | NON AOP | MAY 26 PLANNED
TRDSRT193 | 150 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi |  | NDRAVG business park, Sarita Vihar, Delhi | Delhi |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
FFNSBK14922 | 151 |  | TBJW | QHLS | TRFFGQHLS00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat |  | Mayurdhwajsinh Solanki | Navsari Carolina Mall | Navsari | 7026 | 2026-02-24 | 2026-03-02 | 45 |  | 2026-04-16 | 2026-05-15 | 2026-05-25 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
TRSTBK11236 | 152 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Small Town | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Goa | Goa |  | Navelim | Goa |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | NON AOP
FFNSBK224 | 153 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | North Maharashtra |  | Nasik-Pinnacle Mall | Nashik |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SCDHAK12645 | 154 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | East | AK | Telangana | Hyderabad |  | Nalgonda SmartHub | Nalgonda | 25878 |  |  | 0 | 15 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
GRDSKC14785 | 155 | DS-MH-00029 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  | Sushant3 Behra | Nagpur, Dighori, Narsala Bhutekar Complex | Nagpur |  |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
SMRTBK14907 | 156 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | Nagpur London OCM5, Orange City street | NAGPUR |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
TRTRAK15201 | 157 |  | T729 | NGK7 | TRNDKNGK701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Mysore Nazarabad | Mysore | 9215 | 2026-02-16 | 2026-02-16 | 0 | 15 | 2026-03-03 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-21 | 2026-05-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
YOCOBK14872 | 158 |  |  | QHFU | TYOUMQHFU00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta Conversion | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | GMU |  |  | Mumbai Shagun Insignia Ulwe | Mumbai | 12830 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FLDHKC13148 | 159 | MU-SM-GMU-255 | 1925 | NF71 |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | GMU | Mumbai |  | Mumbai LittleWKhargh | Mumbai | 10255 |  |  | 0 | 25 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSBK14786 | 160 | DS-MH-00110 | TBCH | QHEU | DARKMQHEU00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | Maharashtra |  |  | MR Hall, Mohammadwadi, Pune | Pune | 3530.16 | 2025-11-25 | 2025-12-02 | 15 |  | 2025-12-17 | 2025-12-22 | 2026-01-06 | EPC Ready Previous FY | 100% |  | OTHER ISSUES | 2026-04-03 | Launched | FY 25-26 | AOP
GAPEBK11219 | 161 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | Motwani Chambers (NRB House), JB Road Pune | Pune |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
GRDSRT14759 | 162 | DS-DL-00308 | TA2Y | QAFP | DARKDQAFP00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Arun Bhati | Mongolpuri | Delhi NCR | 2935 | 2026-02-07 | 2026-02-15 | 15 |  | 2026-03-02 | 2026-03-25 | 2026-03-26 | EPC Ready Previous FY | 100% | YTL | 2026-04-20 | 2026-04-08 | Launched | FY 25-26 | AOP
MBSKKC14913 | 163 |  |  |  |  | F. SCM | SCM BF | Milk Basket | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  | Sangram Shinde | Monginis - Andheri | Mumbai | 13626 |  |  | 0 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTBK10348 | 164 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | Mohan Bhabad Heights Property | Malakpet |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14891 | 165 |  | T9QL | QXHR | SMRTIQXHR00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Himachal Pradesh |  |  | Mohalla Adarsh Nagar, Chamba, HP | Chamba | 21000 | 2026-04-24 | 2026-04-27 | 35 |  | 2026-06-01 | 2026-06-20 |  | WIP | 52% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
TRTRSD15210 | 166 |  | 5798 | NP29 | TRNDNNP2901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  | Maruthi Rao Patibandla | Miryalguda Sagar Rd | Hyderabad | 6329 | 2026-02-06 | 2026-02-06 | 0 | 15 | 2026-02-21 | 2026-04-30 | 2026-05-06 | EPC Ready | 100% | Cycle-1 EPC | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRD3BK14884 | 167 |  |  | QZ9G | TRNDMQZ9G00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends 3.0 | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra |  |  | MH-Pune-Baner-La Commercia | Pune | 12703 |  |  | 45 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
YOCOBK14880 | 168 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta Conversion | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | GMU |  |  | MH _ Kharghar _ Little World Mall | Kharghar | 9897 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
POSMRT11372 | 169 |  | T5YO | QL9V | RZIVHQL9V00 | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Haryana | Delhi - NCR | Prakhar Pratap Singh | MGF Metropolitan Mall | Gurugram | 507 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FORFRT13798 | 170 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Footwear - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Madhya Pradesh | Indore |  | Mega Mall Indore | Indore |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FORFBK13796 | 171 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Footwear - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | Maxus Mall Bhayander | Mumbai |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRDSBK11227 | 172 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat | Rajkot |  | Marvell Plus Mall, Rajkot, GJ | Rajkot |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
MARKKC14867 | 173 |  | S4AN | QX2J | MPFCHQX2J00 | F. SCM | SCM BF | Market Place | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Haryana |  | Balram Soni | Marketplace Koka Kulana | Jhajjar | 89548 | 2025-12-09 | 2026-03-10 | 45 | 0 | 2026-04-24 | 2026-06-10 |  | WIP | 90% | GRAP HOLD |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
MARKAK13878 | 174 |  |  |  |  | F. SCM | SCM BF | Market Place | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka | Bengaluru |  | Marketplace at Bangalore Neelamangala Metro DC | Bengaluru | 26550 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
MARKAK13752 | 175 |  |  |  |  | F. SCM | SCM BF | Market Place | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Chennai |  | Market Place Co-Located with Chennai B100 Digital DC | Chennai | 16493 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRTRAS15112 | 176 |  | T523 | NUU7 | TRNDTNUU701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Marina Mall - Trends | Chennai | 10709 | 2026-03-28 | 2026-03-28 | 0 | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
SMRTRT14892 | 177 |  | TC9N | QV7F | SMRTHQV7F00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Delhi & NCR |  |  | Mansha Vega, Sector-82, Faridabad | Faridabad | 25000 | 2026-04-27 | 2026-05-12 | 35 |  | 2026-06-04 | 2026-06-16 |  | WIP | 40% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
FLDCAK14854 | 178 |  |  |  |  | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka |  |  | Mangalore FFDC - Nandikoor, Padubidri, Mangalore -Udupi |  | 32044 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
MIAGKC14812 | 179 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Rajasthan |  |  | Mandar - Provision of Hazardous waste Shed. | Mandar |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGKC14814 | 180 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Rajasthan |  |  | Mandar - Louvers on FW Ph shed. Phase I (6 Depot’s) | Mandar |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGKC14813 | 181 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Rajasthan |  |  | Mandar - Exhaust Stack to be provided for DG 82.5 KVA | Mandar |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
TRMNRT11237 | 182 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Man | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh | Lucknow |  | Lulu Mall, Lucknow | Lucknow |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDSKC13971 | 183 | DS-GMU-00026 |  | QX8I | DARKMQX8I00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU | Mumbai | Dindayal Maurya | LOYALKA HOUSE - BABULNATH - GIRGAON- MUMBAI | Mumbai | 2112 |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
TRFTBK11223 | 184 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | Vidarbha |  | Land Mark Mall , > UGF- Ethnicity Store Wardha Road, Ramdaspeth , Nagpur. | Nagpur |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13244 | 185 |  | T32G | QZ1T |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Rajasthan | Udaipur |  | Lake city Mall | Udaipur | 897 |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
TRD3BK14885 | 186 |  | T0S1 | Q4HF | TRNDMQ4HF00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends 3.0 | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra | Imran Pasha | La Sky Lark | Pune | 12209 | 2026-02-02 | 2026-02-06 | 45 | 10 | 2026-04-02 | 2026-06-05 |  | WIP | 95% |  |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
GAPEBK10699 | 187 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | La Commercia Baner | Pune |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRD3BK13799 | 188 |  | TM7P | QZ9G | TRNDMQZ9G00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends 3.0 | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra | Imran Pasha | La Commercia Baner | Pune | 12703 | 2026-02-02 | 2026-02-06 | 45 |  | 2026-03-23 | 2026-05-08 | 2026-05-11 | EPC Ready | 100% |  | PENDING | 2026-05-16 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRAS15113 | 189 |  | TE94 | NVR3 | TRNDTNVR301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  | Vijayakumar M | Kovilambaka RadialRd | Chennai | 9866 | 2026-01-31 | 2026-01-31 | 0 | 15 | 2026-02-15 | 2026-05-31 |  | WIP |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED
GRDSBK14766 | 190 | DS-GMU-00165 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | GMU |  |  | Kotkar Industrial Estate,Goregson Eas | Mumbai |  |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14890 | 191 |  | T9RD | QXIM | SMRT9QXIM00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Punjab | Bhatinda | Harpreet Singh | KOTKAPURA,BATHINDA ROAD,FARIDKOT,PUNJAB | Faridkot | 19643 | 2026-01-20 | 2026-01-22 | 35 |  | 2026-02-26 | 2026-03-10 | 2026-03-07 | EPC Ready Previous FY | 100% |  | PENDING | 2026-04-11 | Launched | FY 25-26 | AOP
TRTRSD15105 | 192 |  | 1899 | NF57 | TRNDWNF5700 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  | Debraj Chakraborty | Kolkata Banik Towers | Kolkata | 8207 | 2026-01-30 | 2026-01-30 | 0 | 15 | 2026-02-14 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-1 EPC | 2026-04-14 | 2026-04-14 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
SCPCAK13726 | 193 |  | S4ND | QY6B | DCDCWQY6B00 | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | West Bengal | Kolkata | Balaram Sahu | Kolkata (Meri Chai) FFDC | Kolkata | 40197 | 2025-11-03 | 2025-11-14 | 0 | 60 | 2026-01-14 | 2026-02-18 | 2026-02-16 | EPC Ready Previous FY | 100% | YTL | 2026-02-02 |  | YTL | FY 25-26 | AOP
SCWHKC10992 | 194 |  | QX8X | QX8X | DCDCHQX8X00 | F. SCM | SCM BF | WH | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Haryana | Delhi - NCR | Shadab Alam | Koka - Kulana - Hamleys - RBL | Jhajjar | 250646 | 2025-11-10 | 2025-11-29 | 90 | 90 | 2026-02-27 | 2026-06-10 |  | WIP | 90% |  |  |  |  | FY 26-27 | AOP | FEBRUARY 26 PLANNED
SCDHAK12646 | 195 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | South | AK | Kerala | Cochin |  | Kochi- SmartHub | Kochi | 61099 |  |  | 0 |  |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
GRDSBK14787 | 196 | DS-MH-00120 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | Maharashtra |  |  | Khan Complex, Gulshan colony | Nashik |  |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
GRDSKC15270 | 197 | DS-MH-00108 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  |  | Karanjawane imperial, Pune | Pune |  |  |  | 15 |  |  |  |  | Dropped | [5 empty] | FY 26-27 | AOP
TEAGKC13462 | 198 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh | Kanpur | Manmohan Nautiyal | Kanpur- Earthing grid additional 50mm strip provision at all 5 OTs in line with Earthing adequacy study recommendations. | Kanpur |  |  |  | 0 | 90 |  |  |  | Budget Submitted - Approval Awaited | 0% | Budget Submitted - Approval Awaited |  |  |  | FY 26-27 | AOP
TEAGKC13668 | 199 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh | Kanpur | Manmohan Nautiyal | Kanpur - New MOC- Paving below Manifold Kanpur | Kanpur | 20000 |  |  | 0 | 120 |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
TEAGKC13816 | 200 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh | Kanpur | Manmohan Nautiyal | Kanpur - Implementing Rainwater Harvesting | Kanpur | 20000 |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
TEAGKC14846 | 201 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  | Manmohan Nautiyal | Kanpur - Emergency Exit (Staircase) for Control Room | Kanpur | 172 | 2026-03-09 | 2026-03-09 | 0 | 45 | 2026-04-23 | 2026-05-30 | 2026-05-28 | EPC Ready | 100% | EPC Ready | PENDING | 2026-05-28 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
ZIVART10567 | 202 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Zivame EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi |  | Kalkaji Delhi | Delhi & Ncr | 747 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SCDHAK15258 | 203 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | East | AK | Andhra Pradesh | Kadapa |  | Kadapa Smartub- Shed 4A | Kadapa | 19360 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
FLDHKC13248 | 204 |  | TCG7 | NAN0 |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Haryana |  |  | Jind Safidon Gate | Jind | 6772 |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP |  |  | OCTOBER 25
YOTHRT14875 | 205 |  |  | QABR | TYOUDQABR00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Delhi & NCR |  |  | Jasola Vihar Shaheen Bagh Metro Station, Delhi | Delhi | 8604 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRTRBK15183 | 206 |  | 8033 | NCT3 | TRNDGNCT303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | KC | Gujarat |  |  | Jamnagar Crystal Mall | Jamnagar | 16333 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 |  | WIP |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
FLDHKC13226 | 207 | UP-SM-JER-003 | TFR4 | QYU5 |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Uttar Pradesh |  |  | Jalesar TST | Jalesar | 4000 |  |  | 0 | 25 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
EDAMRT14921 | 208 |  | TK8X | TK8X | EDMMUTK8X00 | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Uttar Pradesh |  | Avinesh Pandey | IP Sigra Mall, Varanasi Shop No. 9,10 & 11, Vidyapeeth Road, Shastri Nagar, Varanasi UP 221002 | Varanasi | 1011 | 2026-02-10 | 2026-02-11 | 35 |  | 2026-03-18 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% |  | 2026-05-05 | 2026-05-04 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
FLDHKC12742 | 209 |  | 1954 | 1954 | DH-FOOT-419-MP-1954 | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Madhya Pradesh | Indore |  | 1954 Footprint Treasure Island Indore, # T-12 THIRD FLOOR TREASURE ISLAND, TOKOGANJ MAIN RD (MG RD) MP Footprint | Indore | 2526 | 2026-05-12 | 2026-05-12 | 0 | 25 | 2026-05-31 | 2026-06-06 | 2026-05-27 | EPC Ready | 100% |  | PENDING | 2026-05-27 | Launched | FY 26-27 | AOP | MAY 26 PLANNED | MAY 26
FORFBK13797 | 210 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Footwear - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | Infinity Mall Malad | Malad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
POSMBK11370 | 211 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | Infiniti Mall Malad | Malad | 635 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FLDCKC14915 | 212 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Madhya Pradesh |  |  | Indore (FFDC in VFDC) | Indore | 11118 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
VADCKC10987 | 213 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Madhya Pradesh | Indore |  | Indore | Indore |  |  |  | 0 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
TRTRSD15150 | 214 |  | TQ13 | ND87 | TRNDNND8704 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  | Maruthi Rao Patibandla | Hyderabad RK Puram | Hyderabad | 14106 | 2026-02-05 | 2026-02-05 | 0 | 15 | 2026-02-20 | 2026-05-31 | 2026-06-02 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | JUNE 26 | DECEMBER 25
TRTRSD15157 | 215 |  | TWQD | Q6H4 | TFITNQ6H401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  | Sai Kumar PMC | Hyderabad Nacharam near Digital & SMART | Hyderabad | 12724 | 2026-02-05 | 2026-02-05 | 0 | 15 | 2026-02-20 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-1 EPC | 2026-06-01 |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
VADCAK15253 | 216 |  | FREI | QA7O | DCDCNQA7O00 | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Telangana |  |  | Hyderabad Medchal VFDC-PTL Setup | Hyderabad | 18180 | 2026-02-27 | 2026-03-10 | 30 |  | 2026-04-09 | 2026-05-08 | 2026-05-08 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRTRSD15245 | 217 |  | T9QO | QXHU | TFITNQXHU01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  | Shankar T | Hyderabad Dammaiguda Secunderabad | Hyderabad | 9748 | 2026-02-05 | 2026-02-05 | 0 | 15 | 2026-02-20 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-1 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
MIAGAK14566 | 218 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Ranjit Sinha | Huzurnagar Mini Depo - Admin Building |  |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
MIAGAK14815 | 219 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Ranjit Sinha | Huzurnagar - Provision of Hazardous waste Shed. | Huzurnagar |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14817 | 220 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Ranjit Sinha | Huzurnagar - Louvers on FW Ph shed. Phase II (4 Depot’s) | Huzurnagar |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14816 | 221 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Ranjit Sinha | Huzurnagar - Exhaust Stack to be provided for DG 82.5 KVA | Huzurnagar |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14818 | 222 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Ranjit Sinha | Huzurnagar - Borewell Head Protection | Huzurnagar |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK13851 | 223 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana | Hyderabad | Rohin Chand | Huzurnagagr Mini Depo - Phase I works | Huzurnagar | 20000 | 2025-09-22 | 2025-09-23 | 0 | 120 | 2026-01-20 | 2026-06-16 |  | WIP | 89% | WIP |  |  |  | FY 26-27 | AOP | JANUARY 26 PLANNED
DIDCAK14853 | 224 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka |  |  | Hubli Digital DC - S M Enterprises S.No 69, Murarhalli village, Pune - Bangalore Road, Hubli |  | 111364 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DIDCAK15251 | 225 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka |  |  | Hubli Digital DC |  | 123000 |  |  | 0 |  |  |  |  | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
POSMBK11391 | 226 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | GMU | Mumbai |  | HSP Mall | Mumbai | 725 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
GAPERT13838 | 227 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | HLP Galleria |  |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSKC13969 | 228 | DS-GMU-00023 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU | Mumbai | Dindayal Maurya | Hindustan Mineral Products, Sion East | Mumbai | 2355 |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
TEAGAK13568 | 229 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | West Bengal | Kharagpur | Arshad Ali Shaukat | Haldia - Wind Girder & MVWSS Replacement - Haldia - Tk 1A, 1B , 7A & 7B | Haldia | 5000 | 2025-06-12 | 2025-06-12 | 0 | 152 | 2025-11-11 | 2026-04-30 | 2026-05-18 | EPC Ready | 100% | EPC Ready | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 | AOP | NOVEMBER 25 PLANNED | MAY 26
TEAGAK13456 | 230 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | West Bengal | Kharagpur | Arif Rahaman | Haldia - Paving below DP Vessel area | Haldia | 4250 | 2025-09-22 | 2025-09-22 | 0 | 120 | 2026-01-20 | 2026-06-06 |  | WIP | 91% | WIP |  |  |  | FY 26-27 | AOP | JANUARY 26 PLANNED
TEAGAK14567 | 231 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | West Bengal |  | Arifur Rehman | Haldia - Implementing Rainwater Harvesting |  |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
TEAGAK13458 | 232 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | West Bengal | Kharagpur | Arifur Rehman | Haldia - Cement Concrete paving under pipeline manifold area at all 5 OTs. | Haldia |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
SCPCAK12994 | 233 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | SD | Assam & NE | Guwahati |  | Guwahati Madanpur FFDC | Guwahati | 35892 |  |  | 0 | 45 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSBK13983 | 234 | DS-MH-00020 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | Maharashtra | North Maharashtra | Mithlesh8.Kumar@ril.com | Gulshan Colony, Nashik - Metro C&C Nashik | Nashik | 2578 |  |  | 15 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC10937 | 235 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | GMU | Mumbai |  | Gulmohar Plaza Virar | Mumbai |  |  |  | 0 | 25 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | OCTOBER 25
YOTHBK14877 | 236 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | GMU |  |  | Ground Floor, Bhumi Pinnacale, Roadpali, Kalamboli, Panvel 400706 Bhoomi Pinnacle | Kakamboli | 5451 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
AZORBK10915 | 237 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat |  |  | Green Township | Jamnagar |  |  |  | 60 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SIGNRT14569 | 238 |  |  |  |  | C. Grocery | Grocery | Go Fresh | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Gomti Nagar | Lucknow | 5490 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRSTRT11054 | 239 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Small Town 3.0 | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh |  |  | GOLA LAKHIMPUR KHERI | Lakhimpur Kheri |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDSKC14769 | 240 | DS-GMU-00163 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU |  | Dindayal1 Maurya | Gokhale Road, Naupada, Thane West | Mumbai |  |  |  | 15 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT11374 | 241 |  | T5TZ | QL5F | RZIVDQL5F00 | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi | Hanish Gupta | GK M Block | Delhi & Ncr | 900 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
MIAGAK14792 | 242 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Orissa |  |  | Girisola - Provision of Hazardous waste Shed. | Girisola |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14794 | 243 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Orissa |  |  | Girisola - Louvers on FW Ph shed. Phase I (6 Depot’s) | Girisola |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14793 | 244 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Orissa |  |  | Girisola- - Exhaust Stack to be provided for DG 82.5 KVA | Girisola |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
TRTRRT15089 | 245 |  | 8123 | NDB9 | TRNDUNDB900 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  | Sujit Brahma | Ghaziabad Mahagun | Ghaziabad | 15156 | 2026-01-29 | 2026-01-29 | 0 | 15 | 2026-02-13 | 2026-02-20 | 2026-04-27 | EPC Ready | 100% | Cycle-1 EPC | 2026-04-25 | 2026-04-25 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
GRDSRT14765 | 246 | DS-DL-00325 | TBII | QHKO | DARKHQHKO00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Sushil Kumar Sahu | GGN-Sector 79 | Gurugram | 1685 | 2026-02-25 | 2026-03-11 | 15 |  | 2026-03-26 | 2026-04-30 | 2026-04-28 | EPC Ready | 100% |  | PENDING | 2026-05-22 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
GAPERT13835 | 247 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi - NCR |  | GAP Kids - Felix Plaza Mall, NH 48, Gurgaon | Gurugram |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GAPERT13834 | 248 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi - NCR |  | GAP Adult - Felix Plaza Mall, NH 48, Gurgaon | Gurugram |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GAPERT14955 | 249 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | GAP - Sushma Capital, Peer Muchalla, Zirakpur. PB | Zirakpur | 4064 | [7 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
GAPERT14956 | 250 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | GAP - Downtown, Block A, BRS Nagar, Ludhiana, Punjab | Ludhiana | 4848 | [7 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
GRDSKC14779 | 251 | DS-MH-00113 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  | Biplab Hota | Friendship Residency, Baner - Pune | Pune |  |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRFTBK11463 | 252 |  | 1900 | NF58 | FOOTMNF5801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Maharashtra | West Maharashtra |  | Footwear Renovation - Seasons Mall_Pune | Pune | 2404 | 2026-04-27 | 2026-04-27 |  | 53 | 2026-06-19 | 2026-06-19 |  | WIP | 35% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
FORFBK13842 | 253 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Footwear - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Madhya Pradesh | Bhopal |  | Footwear Renovation - DB Mall , Bhopal | Bhopal |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FLDHKC12740 | 254 |  | F1IE | QEWD |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Goa | Goa |  | FF-GOA -MARGAON | Margaon |  |  |  | 0 | 25 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FFNSBK11459 | 255 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat | Ahmedabad |  | FF Renovation - Ahemadabad City gold Mall | Ahmedabad |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FFNSBK11462 | 256 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | FF Handewadi Pune | Pune |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRTRRT15038 | 257 |  | 8396 |  | TRNDHNDW900 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  | Shyam Sunder Sorout | Faridabd TIMS Crown | Faridabad | 7854 | 2026-01-30 | 2026-01-30 | 0 | 15 | 2026-02-14 | 2026-02-20 |  | On Hold |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP
SCDHAK12649 | 258 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | South | AK | Kerala | Ernakulam |  | Ernakulam-VFDC | Ernakulam | 34852 |  |  | 0 | 15 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
VADCAK13439 | 259 |  | S0XE | QI3S | DCDCVQI3S02 | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Kerala | Ernakulam |  | Ernakulam Aimury VFDC - PTL Setup | Ernakulam | 12592 | 2026-02-22 | 2026-03-03 | 30 | 0 | 2026-04-02 | 2026-06-20 |  | WIP | 94% |  |  |  |  | FY 26-27 | AOP | APRIL 26 PLANNED
GRDSKC14756 | 260 | DS-MH-00066 | TM4P | QZ6U | DARKMQZ6U00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  | Sushanta Kumar Behera | Empress Mall ,Cotton Market, Nagpur | Nagpur | 4699 | 2026-05-08 | 2026-05-14 | 15 |  | 2026-05-29 | 2026-06-13 |  | WIP | 38% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED
GAPEBK10698 | 261 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat |  |  | Emporis |  |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FFNSBK14886 | 262 |  | TL4B | QY7Y | TRFFMQY7Y00 | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra | Dnyaneshwar Patil | Elpro City Square Mall,Pune | Pune | 20393 | 2026-01-22 | 2026-01-25 | 45 | 15 | 2026-03-26 | 2026-04-30 | 2026-05-04 | EPC Ready | 100% |  | 2026-05-09 |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | MAY 26
SBRERT14517 | 263 |  | FRBD | Q4VT | RSBZ2Q4VT03 | C. Grocery | Grocery | Smart Bazar - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Punjab | Chandigarh | Sanjay Singh | Elante Mall | Chandigarh | 35554 | 2025-11-18 | 2025-11-18 | 0 | 60 | 2026-01-17 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | JANUARY 26 PLANNED | APRIL 26
GRDSRT14771 | 264 | DS-DL-00286 | T9I5 | Q6R0 | DARKDQ6R000 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | RT | Delhi & NCR | Delhi | Suresh Kumar | East Patel Nagar | Delhi NCR | 1444 | 2026-01-14 | 2026-01-24 | 15 |  | 2026-02-08 | 2026-03-10 | 2026-03-11 | EPC Ready Previous FY | 100% |  | 2026-04-02 | 2026-04-02 | Launched | FY 25-26 | AOP
FLDCAK14862 | 265 |  |  |  |  | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu |  |  | DWS Installation at Madurai( Nilakottai) F&L DC - |  | 31000 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDCAK14859 | 266 |  |  |  |  | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Telangana |  |  | DWS Installation at Kompally Hyderabad F&L DC - |  | 110000 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDCAK14861 | 267 |  | SA3T | QIMQ | DCDCKQIMQ00 | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka |  |  | Hoskote F & L DC - Setting up of Shein operation | Hoskote | 200000 |  |  | 75 |  | 1900-03-18 |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDCAK14860 | 268 |  |  |  |  | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu |  |  | DWS Installation at Chennai F&L DC - SURVEY NO.10/1B,GNT ROAD SEMBULIVARM VILLAGE PONNERI TALUK, TIRUVALLUR DISCTRICT CHENNAI |  | 106000 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
MAREKC14835 | 269 |  | DE01 | DE01 | 9015DDE0102 | G. GreenField and Other Large Scale Projects | GreenField | Mall Revamp | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Delhi & NCR |  | Sujeet Kumar | Dwarka Mall - Rewamp Phase 3 - Jio centre | Dwarka | 325000 | 2025-07-21 | 2025-07-23 | 0 | 40 | 2026-01-13 | 2026-06-30 |  | WIP | 93% | GRAP HOLD - Removed on 03/Feb |  |  |  | FY 26-27 | AOP | JANUARY 26 PLANNED
MAREKC14836 | 270 |  | DE01 | DE01 | 9015DDE0102 | G. GreenField and Other Large Scale Projects | GreenField | Mall Revamp | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Delhi & NCR |  | Sujeet Kumar | Dwarka Mall Revamp - Smart Area Work | Dwarka | 325000 | 2025-04-21 | 2025-12-10 | 0 | 120 | 2026-04-09 | 2026-06-30 |  | WIP | 40% |  |  |  |  | FY 26-27 | AOP | APRIL 26 PLANNED
FLDCKC14868 | 271 |  | SAQZ | QHIU | DCDCCQHIU00 | F. SCM | SCM BF | CPC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Chattisgarh |  | Abhay Shrivastava | FFDC Dumartarai, Raipur | Raipur | 11158 | 2026-02-13 | 2026-02-20 | 60 | 0 | 2026-04-21 | 2026-06-15 |  | WIP | 90% |  |  |  |  | FY 26-27 | AOP | APRIL 26 PLANNED
GRDSBK14938 | 272 | DS-MH-00098 | T9H7 | Q6K0 | DARKMQ6K000 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  |  | DS-MH-00098 - New DarkStore - Pune - Maharashtra - Shree Ram Industrial Estate, Survey No 143, Tathawade, Pune 411035 | Pune | 2439 | 2026-05-20 | 2026-05-23 | 15 |  | 2026-06-07 | 2026-06-07 |  | WIP | 35% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
GRDSBK14937 | 273 | DS-MH-00057 | TN1Q | QM2H | DARKMQM2H00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | Maharashtra | North Maharashtra | Rahul Atal | DS-MH-00057 - Dnyeshwar Nagar - Nashik - Maharashtra - Krishnai Mandai, Chetana Nagar , Near Dnyaneshwar Nagar : Nashik | Nashik | 3293 | 2026-02-02 | 2026-02-05 | 15 |  | 2026-02-20 | 2026-02-25 | 2026-02-25 | EPC Ready Previous FY | 100% |  | 2026-04-05 | 2026-04-02 | Launched | FY 25-26 | AOP
GRDSBK14842 | 274 | DS-GMU-0016 | T9U5 | Q8G0 | DARKMQ8G000 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | BK | GMU | Mumbai | Abhishek Mishra | DS-GMU-00166 - Sahkari Bhandar, Fun Fiesta Mall, Nalasopara West- DC -8-9-2025 - Mumbai - GMU - Sahkari Bhandar, Ground Floor, Fun Fiesta Mall, Sriprastha, Nalasopara West, Maharashtra 401203 | Mumbai | 2794 | 2026-01-12 | 2026-01-15 | 15 | 14 | 2026-02-13 | 2026-03-07 | 2026-03-11 | EPC Ready Previous FY | 100% | YTL | 2026-05-09 | 2026-04-30 | Launched | FY 25-26 | AOP
GRDSRT14939 | 275 | DS-DL-00324 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | RT | Delhi & NCR |  |  | DS-DL-00324 - Rohini Sec7 - Delhi - Delhi NCR - Village Naharpur, Rohini, Sector 7, Delhi 110085 :: [ID-9194] | Delhi |  |  |  |  | 0 |  |  |  | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
GRDSRT14941 | 276 | DS-DL-00274 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | RT | Delhi & NCR |  |  | DS-DL-00274 - Ghitorni - Delhi - Delhi NCR - Khasra No. 304, 2, 100 Feet Road, Ghitorni, New Delhi (Option 1) ID-8859 | Delhi |  |  |  |  | 0 |  |  |  | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
GRDSRT14654 | 277 | DS-DL-00242 | TM8V | QHAH | DARKDQHAH00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | RT | Delhi & NCR |  | Shyam Sunder Sorout | DS-DL-00242-DS Del33-D-56, Uday Chand Marg, South Extension, Part 1, New Delhi :: [ID-8009] | Delhi NCR | 2755 | 2025-10-10 | 2025-10-13 | 15 |  | 2025-10-28 | 2026-01-20 |  | Dropped | 88% |  |  |  |  | FY 26-27 | AOP
AZORRT11222 | 278 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab | Ludhiana |  | Downtown, Block A, BRS Nagar, Ludhiana, Punjab | Ludhiana | 19400 |  |  | 60 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT10390 | 279 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Docket - Smart - The Regency, Delhi Road | Qgcu |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
MIAGAK14795 | 280 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Bihar |  |  | Dobhi- Provision of Hazardous waste Shed. | Dobhi |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14796 | 281 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Bihar |  |  | Dobhi- Exhaust Stack to be provided for DG 82.5 KVA | Dobhi |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14797 | 282 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Bihar |  |  | Dobhi - Louvers on FW Ph shed. Phase I (6 Depot’s) | Dobhi |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14798 | 283 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Bihar |  |  | Dobhi - Borewell Head Protection | Dobhi |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
SGFPRT15072 | 284 |  | TBKX | QHMJ | GOFRDQHMJ00 | C. Grocery | Grocery | Go Fresh | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Delhi & NCR |  | Prakhar Singh | DLF Midtown, Motinagar | Delhi | 6796 | 2026-02-12 | 2026-02-20 | 60 |  | 2026-04-16 | 2026-06-15 |  | WIP | 80% |  |  |  |  | FY 26-27 | AOP | APRIL 26 PLANNED
TRDSBK11245 | 285 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | Dharashiv, Osmanabad, Patil complex | Pune |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
TRDSRT4507 | 286 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh |  |  | Deokali Road, Faizabad | Ayodhya |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
AZORRT238 | 287 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Haryana |  |  | Dehradun Raj Heights, Jakhan, Rajpur Road (BTS) | Jakhan |  |  |  | 60 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13253 | 288 | DE-SM-DEL-904/FG |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Uttar Pradesh | Delhi - NCR |  | CT-NOIDA-GREAT INDIA PLACE | Noida | 91195 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13255 | 289 | DE-SM-DEL-381/FG | F1MH | Q3QH | DH-CENT-419-DL-F1MH | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Delhi & NCR | Delhi |  | CT-NEW DELHI-ROHINI | Delhi | 72232 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13254 | 290 | PB-SM-MOH-075/FG |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Punjab | Mohali |  | CT-MOHALI-NORTH COUNTRY MALL | Mohali | 74500 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13256 | 291 | UP-SM-LUK-093 |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Uttar Pradesh | Lucknow |  | CT-LUCKNOW-SAHARA GANJ | Lucknow | 73774 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
COPUKC13444 | 292 |  | Not Applicable | Not Applicable | PETRO-CP-UPCTR08 | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh | Kanpur | Manmohan Nautiyal | CP-SIDDHARTHNAGAR,UP | Kanpur |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
COPUKC13443 | 293 |  | Not Applicable | Not Applicable | PETRO-CP-UPCTR04 | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh | Kanpur | Manmohan Nautiyal | CP-SAHIBABAD,UP | Kanpur |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
COPUKC13445 | 294 |  | Not Applicable | Not Applicable | PETRO-CP-UPCTR01 | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh | Kanpur | Manmohan Nautiyal | CP-ORAI,UP | Kanpur |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
COPUKC13447 | 295 |  | Not Applicable | Not Applicable | PETRO-CP-UPCTR02 | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh | Kanpur | Manmohan Nautiyal | CP-BANDA,UP | Kanpur |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
COPUKC15009 | 296 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  |  | CP –UPSRTC depot, Loni, UP | Loni |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | NOA - In Process |  |  |  | FY 26-27 | AOP
COPUAK14847 | 297 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Andhra Pradesh |  | Rohin Chand | CP –M/s Rashtriya Ispat Nigam Ltd, Vizag Steel, AP | Vishakhapatnam |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | NOA - In Process |  |  |  | FY 26-27 | AOP
COPUAK14706 | 298 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Orissa |  | Rohin Chand | CP - M/s Shivam Condev Pvt Ltd, Korput, OD | Bhubaneswar |  | 2025-11-16 |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | NOA - In Process |  |  |  | FY 26-27 | AOP
COPUKC13576 | 299 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | West | KC | Chattisgarh |  |  | CP - JSPL Gare IV/6(Mines) _ CG | Raigarh |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
COPUKC13923 | 300 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | West | KC | GMU | Mumbai | Biplab Hota | CP - BPSP - Hindustan Construction Company Ltd, Karjat, Raigad | Karjat | 6250 |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
COPUKC12917 | 301 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | West | KC | Maharashtra | Vidarbha |  | CP - 2 x 30 KL Consumer Pump,M/s LLYODS METAL & ENERGY LIMTED,Gadchiroli, MH | Gadchiroli |  |  |  | 0 |  |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
DIDCAK14856 | 302 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu |  |  | Consolidation of CDIT operation at Chennai B100 Digital DC - Building no B-100,Unnati Logistic Park Private Ltd, Indospace Industrial Park Meva, Mevalurkuppam Village, Sriperumbudur Taluk, Kancheepuram District, Tamil Nadu 602105 |  | 209270 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SCPCAK13885 | 303 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka | Bengaluru |  | Cold Room at FFDC Neelmangala | Bengaluru | 132185 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SCPCAK13853 | 304 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Chennai |  | Cold Room at FFDC Chennai | Chennai | 6530 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SCPCAK13826 | 305 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Orissa | Bhubaneshwar |  | Cold Room at FFDC Bhubaneshwar | Bhubaneshwar | 40565 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
VADCAK13303 | 306 |  | SAHO | QXNO | DCDCTQXNO02 | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Coimbatore |  | Coimbatore VFDC - PTL Setup | Coimbatore | 18523 | 2026-03-21 | 2026-03-23 | 30 |  | 2026-04-22 | 2026-05-09 | 2026-05-11 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
TRTRAS15204 | 307 |  | 9531 | NFP4 | TRNDTNFP400 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbatore Prozone Mall | Coimbatore | 11773 | 2026-03-19 | 2026-03-19 |  | 15 | 2026-04-03 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-13 | 2026-05-13 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26
SPCSAK11395 | 308 |  |  |  |  | F. SCM | SCM | PCS | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Coimbatore |  | Coimbatore PCS - Additional Work | Coimbatore | 36580 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DIDCAK13827 | 309 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Coimbatore |  | Coimbatore Digital-Modular to Civil Toilet Work | Coimbatore | 692 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRTRAS15180 | 310 |  | 8114 |  | TRNDTNDB102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbator Brokefield | Coimbatore | 15874 | [7 empty] | NRFC |  | Full Renovation |  |  |  | FY 26-27 | NON AOP
POSMRT10604 | 311 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA ZIRAKPUR | Zirakpur |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10594 | 312 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Haryana |  |  | CLOVIA YAMUNANAGAR | Yamunanagar |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10590 | 313 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi |  | CLOVIA VIKASPURI | Vikaspuri |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMBK10580 | 314 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Gujarat | Vadodara |  | CLOVIA VADODARA | Vadodara |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10583 | 315 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Rajasthan | Udaipur |  | CLOVIA UDAIPUR | Udaipur |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10602 | 316 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Haryana |  |  | CLOVIA SIRSA | Sirsa |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10595 | 317 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi |  | CLOVIA ROHINI | Rohini |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10600 | 318 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh |  |  | CLOVIA RAMPUR | Rampur |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10587 | 319 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi |  | CLOVIA PITAMPURA-Kohat | Pitampura-Kohat |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10584 | 320 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA PHAGWARA | Phagwara |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10592 | 321 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA PATHANKOT | Pathankot |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
POSMRT10581 | 322 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Haryana | Panipat |  | CLOVIA PANIPAT | Panipat |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10589 | 323 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh | Delhi - NCR |  | CLOVIA NOIDA SEC-18 | Noida |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10598 | 324 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA NAWANSHAHR | Nawanshahr |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10601 | 325 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi |  | CLOVIA MALVIYA NAGAR | Malviya Nagar |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10576 | 326 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh | Lucknow |  | CLOVIA LUCKNOW PLASSIO | Lucknow |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10579 | 327 |  |  | T5YC | CLOVDT5YC00 | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi | Hanish Gupta | CLOVIA LAJPAT NAGAR | Lajpat Nagar |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10591 | 328 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttarakhand | Dehradun |  | CLOVIA KASHIPUR | Kashipur |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10593 | 329 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh |  |  | CLOVIA JHANSI | Jhansi |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10578 | 330 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Jammu & Kashmir | Srinagar |  | CLOVIA JAMMU GN | Jammu |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10575 | 331 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA JALANDHAR | Jalandhar |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10574 | 332 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh |  |  | CLOVIA INDRA PURAM | Indra Puram |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10582 | 333 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA HOSHIARPUR | Hoshiarpur |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10577 | 334 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh |  |  | CLOVIA GAUR CITY MALL | Gaur |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10586 | 335 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA ELANTE MALL |  |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10599 | 336 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Uttar Pradesh |  |  | CLOVIA BAREILLY | Bareilly |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMRT10603 | 337 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Punjab |  |  | CLOVIA AMRITSAR NEXUS | Amritsar |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTBK14908 | 338 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | City Centre Mall | Dharashiv |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
CLOVBK10562 | 339 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat |  |  | City Centre Bharuch | Bharuch | 465 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FORFBK13794 | 340 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Footwear - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Chattisgarh | Raipur |  | City center Mega city Raipur | Raipur |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
LEECBK13843 | 341 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Lee Cooper EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Chattisgarh | Raipur |  | City center Mega city Raipur | Raipur |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
DIDCAK13829 | 342 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Chennai |  | Chennai-Mevalurkuppam B200 -Modular to Civil Toilet Work | Chennai | 379 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRTRAS15082 | 343 |  | T822 | NGO4 | TFITTNGO403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | EIC to be Mapped | Chennai VR Mall | Chennai | 15571 | 2026-02-11 | 2026-02-11 | 0 | 15 | 2026-02-26 | 2026-05-31 |  | WIP |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED
TRTRAS15047 | 344 |  | 9428 | NFL8 | TRNDTNFL801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | EIC to be Mapped | Chennai Velachery | Chennai | 9300 | 2026-01-22 | 2026-01-22 | 0 | 15 | 2026-02-06 | 2026-05-31 |  | WIP |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED
TRTRAS15246 | 345 |  | TJ4E | QZRF | TRNDTQZRF00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai Urapakkam | Chennai | 15787 | 2026-02-23 | 2026-02-23 | 0 | 15 | 2026-03-10 | 2026-04-24 | 2026-04-28 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-28 | 2026-04-28 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15230 | 346 |  | TAV7 | QGSF | TFITTQGSF01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai TISB BB EA Mall | Chennai | 12000 | 2026-04-02 | 2026-04-02 | 0 | 15 | 2026-04-17 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
TRTRAS15020 | 347 |  | 8113 | NDA9 | TRNDTNDA902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | Yogesh Kapoor | Chennai Thiruvanmiur | Chennai | 12234 | 2026-01-22 | 2026-01-22 | 0 | 15 | 2026-02-06 | 2026-05-31 |  | WIP |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED
TRTRAS15222 | 348 |  | T1BF | QG6D | TFITTQG6D02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | EIC to be Mapped | Chennai Tana Street Purasawakkam | Chennai | 11515 | 2026-02-11 | 2026-02-11 | 0 | 15 | 2026-02-26 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-1 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRAS15219 | 349 |  | TQ56 | NE23 | TRNDTNE2302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai Sholinganallur OMR | Chennai | 10044 | 2026-03-18 | 2026-03-18 | 0 | 15 | 2026-04-02 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
TRTRAS15232 | 350 |  | 5748 | NP01 | TRNDTNP0102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | Satyendra singh PMC | Chennai Shanti Colny | Chennai | 8732 | 2026-02-09 | 2026-02-09 | 0 | 15 | 2026-02-24 | 2026-05-31 |  | WIP |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED
TRTRAS15119 | 351 |  | TA12 | NGT9 | TRNDTNGT902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai RIL Iypthngl | Chennai | 11344 | 2026-03-28 | 2026-03-28 | 0 | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
TRTRAS15034 | 352 |  | 8110 |  | TRNDTNDA601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai Perambur | Chennai | 9317 | [7 empty] | NRFC |  | Full Renovation |  |  |  | FY 26-27 | NON AOP
TRTRAS15098 | 353 |  | TEA6 | NCR5 | TFITTNCR501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  | Palanisamy Chelladurai | Chennai Pammal main road Krishna Nagar | Chennai | 12578 | 2026-03-04 | 2026-03-04 | 0 | 15 | 2026-03-19 | 2026-05-10 | 2026-05-22 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-22 | 2026-05-22 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRAS15044 | 354 |  | 8292 | NDO6 | TRNDTNDO602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  | Janarthanan Ekambaram | Chennai Pallikaranai | Chennai | 9990 | 2026-01-21 | 2026-01-21 | 0 | 15 | 2026-02-05 | 2026-05-10 | 2026-05-15 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRAS15221 | 355 |  | TSN8 | Q2PA | TFITTQ2PA01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai Padur | Chennai | 12200 | 2026-04-03 | 2026-04-03 | 0 | 15 | 2026-04-18 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP | APRIL 26 PLANNED
TRTRAS15118 | 356 |  | TW17 | NNM9 | TRNDTNNM903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai OMR | Chennai | 9190 | 2026-01-23 | 2026-02-23 | 0 | 15 | 2026-03-10 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
SCPCAK15254 | 357 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu |  |  | Chennai- MMLP FFDC (WH04) |  | 72449 |  |  | 0 |  |  |  |  | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP
FLDCAK15255 | 358 |  | SAX4 | QIBI | DCDCTQIBI00 | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu |  |  | Chennai- MMLP F&L DC (WH01A) | Chennai | 161441 | 2026-04-24 | 2026-05-21 | 75 |  | 2026-08-04 | 2026-08-04 |  | WIP | 7% |  |  |  |  | FY 26-27 | AOP | AUGUST 26 PLANNED
VADCAK15256 | 359 |  | SAWL | QIAD | DCDCTQIAD00 | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu |  | Ganesh B | Chennai- MMLP VFDC (with automation) (WH02) | Chennai | 320,693 | 2026-04-20 | 2026-04-28 | 90 |  | 2026-07-27 | 2026-07-27 |  | WIP | 12% |  |  |  |  | FY 26-27 | AOP | JULY 26 PLANNED
DIDCAK14855 | 360 |  | SAYH | QIBN | DCDCTQIBN00 | F. SCM | SCM BF | Digital DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu |  |  | Chennai- MMLP Digital DC (WH04) | Chennai | 215864 | 2026-05-07 |  | 75 |  | 2026-07-24 |  |  | YTS | 0% |  |  |  |  | FY 26-27 | AOP | JULY 26 PLANNED
TRTRAS15117 | 361 |  | TS82 | NXT6 | TRNDTNXT602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | EIC to be Mapped | Chennai Madhavaram R | Chennai | 8817 | 2026-01-31 | 2026-01-31 | 0 | 15 | 2026-02-15 | 2026-02-20 |  | On Hold |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP
TRTRAS15121 | 362 |  | FR2M | QEXJ | TRNFTQEXJ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | EIC to be Mapped | Chennai FBB Chennai Mount Poonamallee Rd | Chennai | 11170 | 2026-02-03 | 2026-02-03 | 0 | 15 | 2026-02-18 | 2026-04-05 | 2026-04-08 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TEAGAK13454 | 363 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu | Chennai | A Vasanth | Chennai- Earthing grid additional 50mm strip provision at all 5 OTs in line with Earthing adequacy study recommendations. | Chennai | 5000 | 2025-08-11 | 2025-08-11 | 0 | 80 | 2025-10-30 | 2026-05-15 |  | Partial WIP | 90% | WIP - On Hold |  |  |  | FY 26-27 | AOP
DIDCAK13828 | 364 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Chennai |  | Chennai B100 Marketplace -Modular to Civil Toilet Work | Chennai | 408 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRTRAS15106 | 365 |  | 8108 | NDA4 | TRNDTNDA401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai Ambattur | Chennai | 9985 | 2026-06-03 | 2026-06-03 |  | 50 | 2026-07-23 | 2026-07-23 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 | NON AOP | JULY 26 PLANNED
TRTRAS15140 | 366 |  | TG6N | QZXE |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai Aerohub Chennai Airport | Chennai | 13214 |  |  | 0 |  |  |  |  | Dropped |  | NO |  |  |  | FY 26-27 | NON AOP
TRTRAS15108 | 367 |  | TB26 | NVL4 | TRNDTNVL404 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | Satyendra singh PMC | Chennai 2nd Avenue | Chennai | 10215 | 2026-01-30 | 2026-01-30 | 0 | 15 | 2026-02-14 | 2026-05-31 |  | WIP |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED
TEAGAK13678 | 368 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu | Chennai | Vasanth A | Chennai - Schematic for Tank 6A & 6B - Recirculation Line | Chennai | 20000 |  |  | 0 | 120 |  |  |  | NRFC | 0% | NRFC |  |  |  | FY 26-27 | AOP
TEAGAK14681 | 369 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu |  | Vasant A | Chennai - Grating on strom water Drain Phase II | Chennai |  |  |  | 0 | 45 |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
TEAGAK14564 | 370 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu |  | Vasant A | Chennai - Enhancing Water Management with Garland Drain Installation Along Boundary Walls. |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
TEAGAK13452 | 371 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu | Chennai | Ganesh B | Chennai - Drivers Amenity Block to be constructed to provide basic facilities for drivers and cleaners. | Chennai | 20000 | 2025-05-19 | 2025-05-21 | 0 | 201 | 2025-12-06 | 2026-04-30 | 2026-05-12 | EPC Ready | 100% | EPC Ready | 2026-05-12 | 2026-05-12 | Launched | FY 26-27 | AOP | DECEMBER 25 PLANNED | MAY 26
TEAGAK13453 | 372 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | South | AK | Tamil Nadu | Chennai | Vasanth A | Chennai - Cement Concrete paving under pipeline manifold area at all 5 OTs. | Chennai |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
TRTRAS15223 | 373 |  | TI54 | NWE4 | TRNDTNWE401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  | Janarthanan | Chenai Periyar Nagar | Chennai | 8001 | 2026-02-12 | 2026-02-12 | 0 | 15 | 2026-02-27 | 2026-02-27 |  | On Hold |  | Cycle-1 EPC |  |  |  | FY 26-27 | NON AOP
SMRTBK14909 | 374 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | Chandrama Complex | Dhule |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSRT14788 | 375 | DS-DL-00320 | TBDT | QHGF | DARKDQHGF00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | RT | Delhi & NCR | Delhi | Sachin Jain | Chandani Mahal | Delhi | 3225 | 2026-01-16 | 2026-02-01 | 15 |  | 2026-02-16 | 2026-02-25 | 2026-02-28 | EPC Ready Previous FY | 100% | YTL | 2026-03-29 | 2026-04-07 | Launched | FY 25-26 | AOP
TRSTRT10912 | 376 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Small Town | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttarakhand | Dehradun |  | Chakrata Road, Selaqui, Dist Dehradun - New Option-Selaquai-UT | Dehradhun |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FFNSBK14953 | 377 |  | TBIL | QHKR | TRFFMQHKR00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra | Mojim Pathan | Centro Autade, Handewadi, Pune | Pune | 19890 | 2026-02-05 | 2026-02-08 | 45 | 15 | 2026-04-09 | 2026-05-12 | 2026-05-25 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
SMRTRT4342 | 378 |  | TFX9 | QYK5 |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Rajasthan |  |  | Capital Highstreets | Bikaner |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
BLSSRT10218 | 379 |  |  |  |  | C. Grocery | Grocery | Blushlace in Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Rajasthan |  |  | Capital Highstreets | Bikaner |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
SMRTBK14905 | 380 |  | TAJ6 | QGNB | SMRTEQGNB00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Madhya Pradesh |  |  | BTS Property near Sirmor Chowak at Univercity Road, Rewa | Rewa | 14354 | 2026-05-19 | 2026-05-21 | 35 |  | 2026-06-25 | 2026-06-25 |  | WIP | 15% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
GAPERT12959 | 381 |  | T5EV | QK8X | TGAP9QK8X00 | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab | Ludhiana | Tarjinder Singh | BRS, Downtown Ludhiana | Ludhiana | 4848 |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDCKC14911 | 382 |  | SLPR | QERK | CPC1HQERK06 | F. SCM | SCM BF | CPC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Haryana |  | Atul Garg | Boiled Chana,Sonipat | Sonipat | 745 | 2026-02-07 | 2026-02-19 | 35 | 0 | 2026-03-26 | 2026-04-06 | 2026-04-08 | EPC Ready | 100% | GRAP HOLD | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
SCDHAK14851 | 383 |  | S0DE | S0DE | DH-URLA-452-KA-S0DE | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | South | AK | Karnataka | Bangalore |  | Bidadi(Urban ladder) - Plot No.1 of Bidadi, 2nd Phase Industrial Area,Shanumanangala Village,Bidadi Hobli, Ramanagara, Ramnagar - 562109 | Ramnagar | 202000 | 2026-03-06 | 2026-03-06 | 0 | 35 | 2026-04-10 | 2026-04-30 | 2026-04-28 | EPC Ready | 100% |  | PENDING | 2026-04-28 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | APRIL 26
SMRTBK10364 | 384 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra | West Maharashtra |  | Bibewadi Solitaer Business Hub | Pune |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP
TEAGKC14845 | 385 |  |  |  |  | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | West | KC | Madhya Pradesh |  | Umesh Yadav | Bhopal - Provision of engineered pipeline supports (120 locations) | Bhopal |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
TEAGKC13450 | 386 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Terminal Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | West | KC | Madhya Pradesh | Bhopal | Umesh Kumar Yadav | Bhopal - Cement Concrete paving under pipeline manifold area at all 5 OTs. | Bhopal | 20000 | 2026-01-27 | 2026-01-27 | 0 | 120 | 2026-05-27 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | EPC Ready | PENDING | 2026-05-29 | Launched | FY 26-27 | AOP | MAY 26 PLANNED | MAY 26
MIAGKC14705 | 387 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | West | KC | Madhya Pradesh |  | Umesh Kumar Yadav | Bhopal - Additional Bay of Mix load works | Bhopal | 5500 | 2026-01-27 | 2026-01-27 | 0 | 75 | 2026-04-12 | 2026-06-15 |  | WIP | 80% | WIP |  |  |  | FY 26-27 | AOP | APRIL 26 PLANNED
MIAGAK14800 | 388 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Jharkhand |  |  | Bharagoda- Exhaust Stack to be provided for DG 82.5 KVA | Baharagora |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14801 | 389 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Jharkhand |  |  | Bharagoda - Louvers on FW Ph shed. Phase I (6 Depot’s) | Baharagora |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
VADCAK13739 | 390 |  | FREC | QGBP | DCDCKQGBP00 | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka | Bengaluru |  | Bengaluru Dasanpura - PTL Setup | Bengaluru | 221132 | 2026-02-12 | 2026-03-07 | 30 | 0 | 2026-03-30 | 2026-03-30 | 2026-03-26 | EPC Ready Previous FY | 100% | YTL | PENDING |  | YTL | FY 25-26 | AOP
FLDCAK14863 | 391 |  |  |  |  | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Karnataka |  |  | Belgaum FFDC - Mr. Mahadev Gokte Property - Kakati - Belgaum (Near by Welcomhotel By ITC Hotels, Belagavi) |  | 30450 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT10203 | 392 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttarakhand | Dehradun |  | BB Dehradun , Chakarta Road | Dehradun |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
VADCKC14917 | 393 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Punjab |  |  | Banur | Banur | 209993 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14895 | 394 |  | TBNV | QHOH | SMRTUQHOH00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  | Anand Prakash | BANSURI SQUARE, FATEHBAD ROAD, AGRA ,UP | Agra | 30099 | 2026-03-25 | 2026-03-27 | 35 |  | 2026-05-01 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MAY 26 PLANNED | MAY 26
TRTRAS15144 | 395 |  | 8048 | NCU9 | TRNDKNCU902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  | Raghu Kumar PMC | Bangalore RMM | Bangalore | 13052 | 2026-02-16 | 2026-02-16 | 0 | 15 | 2026-03-03 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAK15164 | 396 |  | T800 | NGN6 | TRNDKNGN602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Bangalore R T Nagar | Bangalore | 9690 | 2026-02-21 | 2026-02-21 | 0 | 15 | 2026-03-08 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED
TRTRAS15102 | 397 |  | 5906 | NP82 | TRNDKNP8201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  | Rahulkumar Mishra | Bangalore Nagarbhavi | Bangalore | 8503 | 2026-01-29 | 2026-01-29 | 0 | 15 | 2026-02-13 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRAK15149 | 398 |  | 8055 | NCV5 | TRNDKNCV503 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  | Westonsudhakar Veerla | Bangalore Malleswram | Bangalore | 13849 | 2026-02-06 | 2026-02-06 | 0 | 15 | 2026-02-21 | 2026-05-10 | 2026-05-11 | EPC Ready | 100% | Cycle-1 EPC | 2026-05-11 | 2026-05-11 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRAS15161 | 399 |  | TSK1 | Q2NO | TFITKQ2NO02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  | Dileep PMC | Bangalore Lulu Global Mall | Bangalore | 7029 | 2026-02-06 | 2026-02-06 | 0 | 15 | 2026-02-21 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRAS15146 | 400 |  | TSR9 | Q2PV | TFITKQ2PV03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  | Sachin Patil | Bangalore Hesaraghatta | Bangalore | 14996 | 2026-02-09 | 2026-02-09 | 0 | 15 | 2026-02-24 | 2026-05-10 | 2026-05-19 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRAS15160 | 401 |  | TSL4 | Q2OB | TFITKQ2OB03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  | EIC to be Mapped | Bangalore Haralur Road | Bangalore | 10043 | 2026-02-08 | 2026-02-08 | 0 | 15 | 2026-02-23 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRAK15163 | 402 |  | 1975 | NF96 | TRNDKNF9602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Bangalore Gandhi Bzr | Bangalore | 11664 | 2026-02-20 | 2026-02-20 | 0 | 15 | 2026-03-07 | 2026-05-10 | 2026-05-15 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRAS15152 | 403 |  | FR1W | QEXF | TRNFKQEXF02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  | EIC to be Mapped | Bangalore FBB Bengaluru Koramangala | Bangalore | 13660 | 2026-02-05 | 2026-02-05 | 0 | 15 | 2026-02-20 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-1 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
MIAGAK14799 | 404 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Jharkhand |  |  | Bahargora - Provision of Hazardous waste Shed. | Baharagora |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
MIAGAK14802 | 405 |  |  |  |  | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Jharkhand |  |  | Baharagora - Borewell Head Protection | Baharagora |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% | Vendor finalization - In Process |  |  |  | FY 26-27 | AOP
SMRTBK14900 | 406 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | Maharashtra |  |  | AYODHYA Brico Builders, Shaniwar Peth,Karad | Karad | 23406 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
YOTHRT13366 | 407 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Uttar Pradesh | Kanpur |  | Awas Vikas, Kanpur | Kanpur | 7421 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTRT14896 | 408 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Delhi & NCR |  |  | ATS Khyber Range, Landcraft Golf Link, NH 24 | Ghaziabad | 15000 |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
VADCSD13545 | 409 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | SD | West Bengal | Kolkata |  | Amta VFDC - Additional Work | Amta | 248326 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
AZORRT11616 | 410 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte Conversion | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi |  | Ambience Mall , Vasantkunj (Centro) | Delhi | 13088 |  |  | 60 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP
TRDSRT11239 | 411 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh |  |  | Ambala Road, Saharanpur | Saharanpur | 9635 |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC12737 | 412 |  | TAP3 | QGPT |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | GMU | Mumbai |  | Amar Harmony Panvel | Mumbai |  |  |  | 0 | 25 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
POSMRT10535 | 413 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Delhi & NCR | Delhi - NCR |  | amante-Vegas Mall | Delhi & Ncr | 529 |  |  | 0 | 7 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
POSMRT10533 | 414 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | POS Migration | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | North | RT | Haryana | Delhi - NCR |  | amante-Ardee Mall | Gurugram | 903 |  |  | 0 | 7 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRRFBK11065 | 415 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Gaurav Shinde | Ankush Hanwate | Refit | West | BK | Maharashtra | West Maharashtra |  | AMANORA PUNE | Pune |  |  |  | 0 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | NON AOP
AZCOBK14888 | 416 |  | TBIR | QHKV | TAZOGQHKV00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Azorte Conversion | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat |  | Kishan Joshi W | SBZ to Azorte Alpha One Ahmedabad | Ahmedabad | 13067 | 2026-02-10 | 2026-02-13 | 60 | 10 | 2026-04-24 | 2026-05-15 | 2026-05-15 | EPC Ready | 100% |  | 2026-05-29 | 2026-05-16 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26
AZORBK11618 | 417 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte Conversion | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Gujarat | Ahmedabad | Mayurdhwaj sinh | Alpha One | Ahmedabad | 14270 |  |  | 60 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP
FLDHKC12724 | 418 | PB-SM-ADH-901 |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Punjab |  |  | Ahmedgarh | Malerkotla |  |  |  | 0 | 25 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13151 | 419 | GJ-SM-AHM-102 | TO44 | ND07 |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Gujarat | Ahmedabad |  | Ahmedabad Scienc CT | Ahmedabad | 9563 |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13166 | 420 | GJ-SM-AHM-111-08 | TFF7 | QZF4 |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Gujarat | Ahmedabad |  | Ahmedabad Celebration City Centre | Ahmedabad | 11331 |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
TRFTRT13846 | 421 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh |  |  | Adj Yes Bank, Kutchehry Road, Raebareilly | Raebareilly |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTBK10349 | 422 |  | TAQM | QF7G | SMRTMQF7G00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | BK | GMU | Mumbai |  | Abhilasha Mall, Dombivali | Mumbai | 25638 | 2026-01-20 | 2026-05-18 | 35 |  | 2026-06-22 | 2026-06-22 |  | WIP | 35% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
SMRTRT14894 | 423 |  | TBL5 | QHNH | SMRTUQHNH00 | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | AAA Mall Etawah UP | Etawah | 24482 | 2026-05-15 | 2026-05-18 | 35 |  | 2026-06-22 | 2026-06-22 |  | WIP | 40% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
YOTHRT14882 | 424 |  |  | QHDS | TYOU9QHDS00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Punjab |  |  | 9th Avenue, Kharar, PB | Kharar | 8559 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRFTRT13837 | 425 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  |  | 9th Avenue, Kharar, Mohali | Mohali |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
FLDHKC13242 | 426 |  | T86S | QORY |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Maharashtra | West Maharashtra |  | 93 Avenue | Pune | 360 |  |  | 0 | 25 |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | AOP
TRDSRT4480 | 427 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends 3.0 | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi - NCR |  | 83 Avenue, Sector-83, Gurgaon | Gurugram |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GAPEBK11216 | 428 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | West Maharashtra |  | 2nd lane Rajarampuri > Waghule property > Kolhapur | Kolhapur | 4531 |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
GAPERT10694 | 429 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Delhi & NCR | Delhi |  | 24, Bungalow Road Kamla Nagar, Delhi | Delhi |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
TRSTBK10934 | 430 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Small Town | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | West | BK | Maharashtra | Vidarbha |  | Akot road > Sarda Complex (opt 2) | Anjangaon |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
ZIVART11329 | 431 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Zivame EBO | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab | Mohali | Sanjay Singh | VR Punjab, Mohali | Mohali | 482 |  |  | 15 |  |  |  |  | Pre SDR Site | 0% |  |  |  |  | FY 26-27 | AOP
SCPCAK15284 | 432 |  | S4ND | QY6B | DCDCWQY6B00 | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | West Bengal | Kolkata | Rajesh Das | Kolkata (Meri Chai) FFDC - Additional Works | Kolkata | 40197 | 2026-02-06 | 2026-02-06 | 45 | 0 | 2026-03-23 | 2026-03-25 | 2026-03-23 | EPC Ready Previous FY | 100% | YTL | 2026-05-07 |  | YTL | FY 25-26 | AOP
TRTRRT15288 | 433 |  | TCG7 | NAN0 | TRNDHNAN001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Jind Safidon Gate | Jind | 6772 | 2026-05-01 | 2026-05-01 |  | 15 | 2026-05-16 | 2026-05-16 | 2026-05-16 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRBK15289 | 434 |  | TJC0 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Khandwa Landmark One | Khandwa | 6955 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15290 | 435 |  | TCG8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Neemuch Fewara Chowk | Neemuch | 5776 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15291 | 436 |  | TZ82 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Dhar Trimuti Nagar | Dhar | 8693 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15292 | 437 |  | TAUZ |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Datia Opp Collectorate Office | Datia | 8488 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15293 | 438 |  | TAQO |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Bhopal Surbhi Smart City Awadhpuri | Bhopal | 7680 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15294 | 439 |  | TGD6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Uttarkashi Gyansu Gangotri Road | Uttarkashi | 8265.76 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15295 | 440 |  | TAP2 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Ghaziabad TJ Raj Nagar Extension KW6 | Ghaziabad | 1311 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15296 | 441 |  | TAWD |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Ambah TST Near SBI Ambah | Ambah | 5097 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15297 | 442 |  | TX4Q |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Khategaon TST | Khategaon | 3821 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15298 | 443 |  | TX7N |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Rajgarh TST Purana Falsa Pilani Road Bts | Rajgarh | 6582.94 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15299 | 444 |  | TER8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Bhilai TW Durg Supela | Bhilai | 1994 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15300 | 445 |  | TJF3 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Bageshwar TST | Bageshwar | 4044 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15301 | 446 |  | TN59 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Jabalpur TW AvenueMal | Jabalpur | 2141 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15302 | 447 |  | TAIY |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Badi Bareli TST Opp New Bus Stand | Badi Bareli | 3813 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15303 | 448 |  | TX4Z |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Surajpur TST | Surajpur | 4725 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15304 | 449 |  | TX6B |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Anjad TST CLF High-Tech City | Anjad | 3863 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15305 | 450 |  | TX8K |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Ghaziabad TW Pratap Vihar Vihan Shopping Plaza | Ghaziabad | 1500 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15306 | 451 |  | TL95 | NWN6 | TRNDMNWN601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Latur TM Surajmahal | Latur | 2449 | 2026-04-30 | 2026-04-30 | 0 | 15 | 2026-05-15 | 2026-05-15 | 2026-05-09 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRBK15307 | 452 |  | TJE3 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Shujalpur TST | Shujalpur | 4815 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15308 | 453 |  | TMJ1 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Kotdwar TST | Kotdwar | 9362 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15309 | 454 |  | TJZ4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Majalgaon TST | Majalgaon | 3802 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15310 | 455 |  | TTD2 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Mahendergarh TST | Mahendergarh | 6586 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15311 | 456 |  | TLM6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Rasra TST | Rasra | 5063.27 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15312 | 457 |  | TSY7 | Q2TC | TEXPMQ2TC02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Chikhali TST | Chikhali | 4808 | 2026-05-14 | 2026-05-14 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-24 | EPC Ready | 100% | Cycle-1 FM | 2026-05-24 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRBK15313 | 458 |  | TTY4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Nagpur TW Budhraja Complex | Nagpur | 1954 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15314 | 459 |  | TWVN | Q6W2 | TEXPMQ6W203 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Deglur TST | Deglur | 4920.65 | 2026-04-20 | 2026-04-20 | 0 | 15 | 2026-04-30 | 2026-05-05 | 2026-04-29 | EPC Ready | 100% | Cycle-1 FM | 2026-04-29 | 2026-04-29 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26
TRTRBK15315 | 460 |  | TAT2 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Nagpur TW Indora Square Sequel Ford | Nagpur | 2459.57 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15316 | 461 |  | TWUF |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Tumsar TST | Tumsar | 6453 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15317 | 462 |  | TFQ8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Domariyaganj TST | Domariyaganj | 4169 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15318 | 463 |  | TDP7 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Kareli TST | Kareli | 3459 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15319 | 464 |  | TSW9 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Saoner TST | Saoner | 4706 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15320 | 465 |  | TAL2 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Sehore | Sehore | 7580 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15321 | 466 |  | TAHI |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Muhammadabad TST | Muhammadabad | 6540 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15322 | 467 |  | T1QY |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Magam TST Ashaq Dar Property | Magam | 7933 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15323 | 468 |  | TGI8 | QYG1 | TEXPMQYG103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Ambejogai TST Hotel Regal Gajrai | Ambejogai | 4767 | 2026-04-30 | 2026-04-30 | 0 | 15 | 2026-05-15 | 2026-05-15 | 2026-05-09 | EPC Ready | 100% | Cycle-1 FM | 2026-05-09 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRBK15324 | 469 |  | TLJ3 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Itarsi TST | Itarsi | 6238 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15325 | 470 |  | TJY3 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Warora TST | Warora | 3728 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15326 | 471 |  | TX5D |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Kawardha TST Raipur Road | Kawardha | 4405 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15327 | 472 |  | TX7E |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Katghar Lalganj TST Asafaq Complex | Katghar Lalganj | 8000 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15328 | 473 |  | TAVA |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Bhind Trends | Bhind | 8075 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15329 | 474 |  | TTC1 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Barara TST | Barara | 4680 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15330 | 475 |  | T33U |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Digras TST Manora Chowk | Digras | 6026 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15331 | 476 |  | TFR6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Gharaunda TST | Gharaunda | 4376 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15332 | 477 |  | TGM1 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Gannaur TST | Gannaur | 4193 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15333 | 478 |  | TDU6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Bina TST | Bina | 6220 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15334 | 479 |  | TKB4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Naraingarh TST | Naraingarh | 4715 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15335 | 480 |  | TEQ4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Patti TST | Patti | 6161 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15336 | 481 |  | TA2F |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Gurgaon TW FBB Gurgaon Sector 14 | Gurugram | 2855 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15337 | 482 |  | TLM8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Sitarganj TST | Sitarganj | 5165.21 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15338 | 483 |  | TAFZ |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Rau TST A.B Road | Rau | 5650 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15339 | 484 |  | TWVI |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Bemetara TST Nr ICICI Bank Durg | Bemetara | 4691 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15340 | 485 |  | TG0M |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Katol TST Near Reliance Petrol Pump | Katol | 6170 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15341 | 486 |  | TSX6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Bandikui TST | Bandikui | 5813.64 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15342 | 487 |  | TTX6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Sarani TST | Sarani | 3660 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15343 | 488 |  | TEQ8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Utraula TST | Utraula | 5097 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15344 | 489 |  | TQA4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Kukshi TST | Kukshi | 3745 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15345 | 490 |  | TLJ2 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Champa TST | Champa | 5465 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15346 | 491 |  | TAFY |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Nowgoan TST | Nowgoan | 5673 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15347 | 492 |  | TX4Y |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Raisen TST Sagar Road | Raisen | 6080 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15348 | 493 |  | TCA0 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Kichha TST | Kichha | 4503 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15349 | 494 |  | TTG1 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Ghaziabad TW Raj Nagar Extension KW6 | Ghaziabad | 1812 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15350 | 495 |  | TKD6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Manglaur TST | Manglaur | 4818.5 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15351 | 496 |  | TLQ8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Kanker TST | Kanker | 4945 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15352 | 497 |  | TDB6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Jaora TST | Jaora | 3896 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15353 | 498 |  | TME4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Fatehpur TST Sikar | Fatehpur | 4187.77 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15354 | 499 |  | TAIW |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Agar TST Agar Malwa | Agar | 4370 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15355 | 500 |  | TWVP |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Mahmudabad TST Paintepur Rd | Mahmudabad | 4890.73 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15356 | 501 |  | TLN4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Manawar TST | Manawar | 4292 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15357 | 502 |  | TA2D |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Gurgaon TJ FBB Gurgaon Sector 14 | Gurugram | 2216 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15358 | 503 |  | TDZ4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Nanpara TST | Nanpara | 4006.47 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15359 | 504 |  | TWTA |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Nasrullaganj TST | Nasrullaganj | 5019 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15360 | 505 |  | TIZ8 | QXE1 | TEXPMQXE103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Karanja Lad TST | Karanja Lad | 4851 | 2026-05-07 | 2026-05-07 | 0 | 15 | 2026-05-22 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRRT15361 | 506 |  | TGI4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Nautanwa TST | Nautanwa | 5660.55 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15362 | 507 |  | TMG4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Vikas Nagar TST | Vikas Nagar | 4852.84 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15363 | 508 |  | TKR5 | QCJ0 | TFITRQCJ001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Udaipur Urban Square Mall | Udaipur | 9850.67 | 2026-05-06 | 2026-05-06 | 0 | 15 | 2026-05-21 | 2026-05-21 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-18 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRRT15364 | 509 |  | TR87 | QVAN | TEXP9QVAN02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Sushma Capital TST Zirakpur | Zirakpur | 9989 | 2026-05-01 | 2026-05-01 | 0 | 15 | 2026-05-16 | 2026-05-16 | 2026-05-12 | EPC Ready | 100% | Cycle-1 FM | 2026-05-11 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRBK15365 | 510 |  | TX5I |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Wadi TST Agarwal Complex Amravati Rd | Wadi | 6332 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15366 | 511 |  | R218 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Korba Palm Mall | Korba | 9811 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15367 | 512 |  | TV30 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Tundla TST | Tundla | 3504 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15368 | 513 |  | TFV7 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Dhamnod TST | Dhamnod | 5247 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15369 | 514 |  | TQD4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Kamptee TST | Kamptee | 4274 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15370 | 515 |  | TSZ9 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Himachal Pradesh |  |  | Dharamshala TST | Dharamshala | 9175 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15371 | 516 |  | TKB5 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Warud TST | Warud | 4008 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15372 | 517 |  | TCQ9 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Nakodar TST Jalandhar | Nakodar | 9599 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15373 | 518 |  | TOP4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Wani TST | Wani | 7237 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15374 | 519 |  | TAB1 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Ballarpur TST On Mancherial Chandrapur Nagpur Rd | Ballarpur | 6621 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15375 | 520 |  | TWQP |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Bilaspur Sarkanda | Bilaspur | 8986 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15376 | 521 |  | TWVB | Q6U8 | TEXPMQ6U802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Udgir TST Sattar Complex | Udgir | 6999 | 2026-04-19 | 2026-04-19 | 0 | 15 | 2026-04-30 | 2026-05-04 | 2026-04-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26
TRTRBK15377 | 522 |  | TJV4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Butibori TST | Butibori | 3480 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15378 | 523 |  | T11E |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Neerana TST Capital Galleria Neemrana | Neerana | 6669.8 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15379 | 524 |  | TW09 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | BHADRAVATI TST | Bhadravati | 3979 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15380 | 525 |  | TP92 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Rajura TST | Rajura | 4074 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15381 | 526 |  | TFA0 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Tanda TST | Tanda | 6443 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15383 | 527 |  | TLJ6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Pipariya TST | Pipariya | 5998 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15384 | 528 |  | T61P |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Chomu TST Metropolis | Chomu | 6036 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15385 | 529 |  | TAB3 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Murtijapur TST | Murtijapur | 4080 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15386 | 530 |  | TWTT |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Bijbehara TST | Bijbehara | 9351 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15387 | 531 |  | TXL4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Dabra TST | Dabra | 5777 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRBK15388 | 532 |  | TTB2 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Gadarwara TST | Gadarwara | 5715 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15389 | 533 |  | TEB6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Khatima TST | Khatima | 6241.61 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRRT15390 | 534 |  | TDV4 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Kotputli TST | Kotputli | 4951 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRAK15391 | 535 |  | 8002 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Guntur Arundelpet | Guntur | 6917 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRTRSD15392 | 536 |  | TX6D |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kirnahar TST | Kirnahar | 7649 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15393 | 537 |  | TX8Z |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nellore TW Nellore Ap Mr Hari Prasad Option 2 Krp | Nellore | 1440 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15394 | 538 |  | TTD8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Bolpur TW Dena Bank Option | Bolpur | 1442 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRAS15395 | 539 |  | TJQ0 | QWI1 | TJNRTQWI101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Salem TJ NM Arcade Above Trends Woman | Salem | 1490 | 2026-05-28 | 2026-05-28 | 0 | 15 | 2026-06-12 | 2026-06-12 |  | WIP |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP | JUNE 26 PLANNED
TRTRAK15396 | 540 |  | T9VI | QXMT | TWIWAQXMT01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijayawada TW Gurunank Colony | Vijayawada | 1508 | 2026-05-04 | 2026-05-04 | 0 | 15 | 2026-05-19 | 2026-05-19 | 2026-05-11 | EPC Ready | 100% | Cycle-1 FM | 2026-05-12 | 2026-05-12 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15397 | 541 |  | TA8K |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ilambazar TST | Ilambazar | 5141 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15398 | 542 |  | T9AM | QSAF | TMANAQSAF01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nellore TM Ramalingapuram | Nellore | 1264 | 2026-05-22 | 2026-05-22 | 0 | 15 | 2026-05-31 | 2026-06-06 | 2026-05-26 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAK15399 | 543 |  | T9VG | QXMS | TMANAQXMS01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijayawada TM Gurunank Colony | Vijayawada | 1350 | 2026-05-04 | 2026-05-04 | 0 | 15 | 2026-05-19 | 2026-05-19 | 2026-05-08 | EPC Ready | 100% | Cycle-1 FM | 2026-05-13 | 2026-05-13 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15400 | 544 |  | TR96 | NXN9 | TRNDNNXN903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Parigi TST | Parigi | 4342 | 2026-05-18 | 2026-05-18 | 0 | 15 | 2026-05-31 | 2026-06-02 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15401 | 545 |  | TGW3 | QXX1 | TEXPAQXX101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Palakonda TST | Palakonda | 3881 | 2026-05-06 | 2026-05-06 | 0 | 15 | 2026-05-21 | 2026-05-21 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAS15402 | 546 |  | TXT6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Mangalore TW Padavinangady Airport Road | Mangalore | 1818 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
TRTRAS15403 | 547 |  | TWSF |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Dindigul TW RM Colony | Dindigul | 1760 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRAS15404 | 548 |  | TTY6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Payyannur TW Magnum Mall | Payyannur | 1931 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15406 | 549 |  | TST8 | Q2RH | TEXPWQ2RH02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Tufanganj TST | Tufanganj | 5428 | 2026-05-15 | 2026-05-15 | 0 | 15 | 2026-05-30 | 2026-05-30 | 2026-05-31 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15407 | 550 |  | TSZ0 | Q2TF | TEXPAQ2TF03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kalyandurgam TST | Kalyandurgam | 4641 | 2026-05-28 | 2026-05-28 | 0 | 15 | 2026-06-12 | 2026-06-12 |  | WIP |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP | JUNE 26 PLANNED
TRTRAK15408 | 551 |  | TWUD |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Akiveedu TST West Godavari | Akiveedu | 4015 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15409 | 552 |  | TFC6 | QZC1 | TEXPAQZC101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Punganur TST | Punganur | 3988 | 2026-05-21 | 2026-05-21 | 0 | 15 | 2026-05-31 | 2026-06-05 | 2026-05-26 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15410 | 553 |  | TJV5 | QAB9 | TEXPWQAB901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Dhupguri TST | Dhupguri | 4918 | 2026-05-13 | 2026-05-13 | 0 | 15 | 2026-05-28 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAS15411 | 554 |  | TXK7 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Kanchipuram TJ CV Rajagopal Street | Kanchipuram | 2438 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15412 | 555 |  | TWTW |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Nagri TST Itki Road | Nagri | 4501 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15414 | 556 |  | TQ78 | NE31 | TRNDNNE3102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Ibrahimpatnam TST | Ibrahimpatnam | 3868 | 2026-05-08 | 2026-05-08 | 0 | 15 | 2026-05-23 | 2026-05-23 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | 2026-05-21 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAS15415 | 557 |  | TAQZ |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tiruvarur TW Vijayapuram | Tiruvarur | 2101 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRAS15416 | 558 |  | TJK8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Indi TST | Indi | 4514 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15418 | 559 |  | TJV2 | QAB6 | TEXPWQAB602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Guskara TST | Guskara | 6865 | 2026-05-12 | 2026-05-12 | 0 | 15 | 2026-05-27 | 2026-05-27 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAS15419 | 560 |  | TLW9 | QQB6 | TWIWVQQB601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thrissur TW Palace Rd | Thrissur | 1638 | 2026-05-09 | 2026-05-09 | 0 | 15 | 2026-05-24 | 2026-05-24 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15420 | 561 |  | TJK7 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ukhra TST | Ukhra | 5110 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15421 | 562 |  | TWUS | Q6T8 | TEXPWQ6T802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ratua TST Main Road | Ratua | 6450 | 2026-05-15 | 2026-05-15 | 0 | 15 | 2026-05-30 | 2026-05-30 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15422 | 563 |  | TKD0 | QAR2 | TEXPWQAR201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Aurangabad TST | Aurangabad | 4020 | 2026-05-14 | 2026-05-14 | 0 | 15 | 2026-05-29 | 2026-05-31 |  | WIP |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP | MAY 26 PLANNED
TRTRSD15423 | 564 |  | TPO4 | Q0OM | TEXPWQ0OM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ashigarh Bazar TST | Ashigarh Bazar | 4647 | 2026-05-05 | 2026-05-05 | 0 | 15 | 2026-05-20 | 2026-05-20 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15424 | 565 |  | TAT7 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Naxalbari TST Main Road | Naxalbari | 6297 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15425 | 566 |  | TTF3 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Behrampore TW Mohan's | Behrampore | 1797 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRAS15426 | 567 |  | TJM7 | QWK9 | TMANTQWK901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Salem TM Nm Arcade | Salem | 1500 | 2026-05-28 | 2026-05-28 | 0 | 15 | 2026-06-12 | 2026-06-12 |  | WIP |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP | JUNE 26 PLANNED
TRTRSD15428 | 568 |  | TTA3 | Q2TR | TEXPWQ2TR02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Chandipur TST | Chandipur | 5587 | 2026-05-11 | 2026-05-11 | 0 | 15 | 2026-05-26 | 2026-05-26 | 2026-05-23 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAK15429 | 569 |  | TCO8 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhubaneswar TM Utkal Galleria Mall | Bhubaneshwar | 2792 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15430 | 570 |  | TDO2 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Dhulian TST | Dhulian | 8406 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15431 | 571 |  | T174 | QG3S | TFITWQG3S02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Siliguri Salbari | Siliguri | 9228 | 2026-05-05 | 2026-05-05 | 0 | 15 | 2026-05-20 | 2026-05-20 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 | 2026-05-19 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAS15432 | 572 |  | TX8R |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Nagercoil TW Vansika Complex KP Road | Nagercoil | 1825 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRAS15434 | 573 |  | T91J | QOXO | TMANVQOXO02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thriprayar TM Y Mall | Thriprayar | 1678 | 2026-06-03 | 2026-06-03 | 0 | 15 | 2026-06-18 | 2026-06-18 |  | WIP |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP | JUNE 26 PLANNED
TRTRAS15435 | 574 |  | TWSP | Q6O4 | TWIWTQ6O401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Krishnagiri TW Bangalore Road | Krishnagiri | 1790 | 2026-05-09 | 2026-05-09 | 0 | 15 | 2026-05-24 | 2026-05-24 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15436 | 575 |  | TXZN | Q9OL | TFITWQ9OL02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Murshidabad Netaji Market | Murshidabad | 9134 | 2026-05-13 | 2026-05-13 | 0 | 15 | 2026-05-28 | 2026-05-31 |  | WIP |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP | MAY 26 PLANNED
TRTRAK15437 | 576 |  | TW34 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Viajayawada TJ PVP | Vijayawada | 1789.5 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15438 | 577 |  | TKB6 | QAN2 | TEXPNQAN201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Jadcherla TST | Jadcherla | 4391 | 2026-05-09 | 2026-05-09 | 0 | 15 | 2026-05-24 | 2026-05-24 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | 2026-05-21 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15439 | 578 |  | TEZ1 | QZG5 | TEXPNQZG501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Choutuppal TST | Choutuppal | 5581 | 2026-05-04 | 2026-05-04 | 0 | 15 | 2026-05-19 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15440 | 579 |  | TDO9 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kalna TST | Kalna | 7994 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
TRTRSD15442 | 580 |  | TTB0 | Q2TY | TEXPWQ2TY01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Mathabhanga TST | Mathabhanga | 5670 | 2026-05-14 | 2026-05-14 | 0 | 15 | 2026-05-29 | 2026-05-29 | 2026-05-17 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15443 | 581 |  | TDZ0 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Jangipur TST | Jangipur | 5715 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRTRSD15444 | 582 |  | TA2N | QGVI | TEXPWQGVI01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Islampur TST North Dinajpur | Islampur | 7395 | 2026-05-08 | 2026-05-08 | 0 | 15 | 2026-05-23 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15445 | 583 |  | TWVE | Q6V2 | TEXPWQ6V201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Borgachia TST | Borgachia | 4742 | 2026-05-10 | 2026-05-10 | 0 | 15 | 2026-05-25 | 2026-05-31 |  | WIP |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP | MAY 26 PLANNED
TRTRSD15446 | 584 |  | TJL0 | QWN1 | TEXPWQWN102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Dinhata TST | Dinhata | 5215 | 2026-05-13 | 2026-05-13 | 0 | 15 | 2026-05-28 | 2026-05-28 | 2026-05-24 | EPC Ready | 100% | Cycle-1 FM | 2026-05-24 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15447 | 585 |  | TLU3 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Durgapur TJ Jxn Mall | Durgapur | 1864 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15448 | 586 |  | TZUU | QDKM | TEXPQQDKM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Irba Ormanjhi TST | Irba Ormanjhi | 6192 | 2026-05-05 | 2026-05-05 | 0 | 15 | 2026-05-20 | 2026-05-20 | 2026-05-15 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15449 | 587 |  | TX6F | QA3O | TEXPWQA3O02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ramnagar TST | Ramnagar | 6602 | 2026-05-13 | 2026-05-13 | 0 | 15 | 2026-05-28 | 2026-05-28 | 2026-05-23 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15450 | 588 |  | TDY7 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Allagadda TST | Allagadda | 4380 |  |  | 0 |  |  |  |  | Dropped |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15451 | 589 |  | TLH3 | QIX0 | TEXPAQIX001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Giddaluru TST | Giddaluru | 3335 | 2026-05-11 | 2026-05-11 | 0 | 15 | 2026-05-26 | 2026-05-26 | 2026-05-13 | EPC Ready | 100% | Cycle-1 FM | 2026-05-13 | 2026-05-13 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRSD15452 | 590 |  | TDY6 |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Mihijam TST | Mihijam | 5051 |  |  | 0 |  |  |  |  | NRFC |  | Cycle-1 FM |  |  |  | FY 26-27 | NON AOP
TRTRSD15453 | 591 |  | TSV9 | Q2SB | TEXPAQ2SB01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Cumbum TST | Cumbum | 4258 | 2026-05-18 | 2026-05-18 | 0 | 15 | 2026-05-31 | 2026-06-02 | 2026-05-26 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRTRAK15457 | 592 |  | TEV8 | QZK9 | TFITKQZK902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  | Sunil B S | Mysore Double Road | Mysore | 9213 | 2026-02-09 | 2026-02-09 |  | 15 | 2026-02-24 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-21 | 2026-05-21 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRAK15458 | 593 |  | 8372 | NDU9 | TRNDKNDU901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  | Sunil B S | Mysore TIMS KRSTC | Mysore | 10551 | 2026-02-05 | 2026-02-05 |  | 15 | 2026-02-20 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-12 | 2026-05-12 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRSD15469 | 594 |  | T527 | NUU8 | TRNDBNUU803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  | Biswajit Samanta | Patna Patna Sahib Railway Station | Patna | 13534 | 2026-02-14 | 2026-02-14 |  | 15 | 2026-03-01 | 2026-03-01 |  | On Hold |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP
TRTRAS15470 | 595 |  | 9663 | NUG7 | TRNDVNUG702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kochi Kakkanad Infra | Kochi | 11923 | 2026-02-16 | 2026-02-16 |  | 15 | 2026-03-03 | 2026-04-24 | 2026-04-28 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-26 | 2026-04-26 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15473 | 596 |  | 9574 | NFS8 | TRNDVNFS800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kochi Kadavanthra | Kochi | 8777 | 2026-02-16 | 2026-02-16 |  | 15 | 2026-03-03 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15478 | 597 |  | 8344 | NDS5 | TRNDQNDS501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  | Debdas Dutta | Ranchi Sandhya Tower | Ranchi | 11277 | 2026-02-12 | 2026-02-12 |  | 15 | 2026-02-27 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-02 | 2026-04-02 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRSD15482 | 598 |  | 5799 | NP30 | TRNDBNP3001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Arrah Dindayal Cmplx | Arrah | 9042 | 2026-02-11 | 2026-02-11 |  | 15 | 2026-02-26 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-14 | 2026-04-14 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRSD15483 | 599 |  | 8093 | NCZ2 | TRNDYNCZ202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  | Gopal Krishna Pal | Shillong Marba Hub | Shillong | 9451 | 2026-02-11 | 2026-02-11 |  | 15 | 2026-02-26 | 2026-04-10 | 2026-04-11 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRSD15485 | 600 |  | 8330 | NDR6 | TRNDNNDR601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  | Shankar T | Khammam Kama Complex | Khammam | 10185 | 2026-02-13 | 2026-02-13 |  | 15 | 2026-02-28 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | APRIL 26
TRTRSD15487 | 601 |  | TGZ9 |  | TFITBQXS201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  | Kamlesh Vishwakarma | Siwan Rajendra Path | Siwan | 12650 |  |  |  | 15 | 1900-01-14 | 1900-01-14 |  | On Hold |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP
TRTRSD15489 | 602 |  | TH73 | NVX6 | TRNDANVX604 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  | Surya Teja Duddu | Srikaklm Palkonda Rd | Srikakulam | 13600 | 2026-02-12 | 2026-02-12 |  | 15 | 2026-02-27 | 2026-05-10 | 2026-05-14 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-14 | 2026-05-14 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
TRTRAS15495 | 603 |  | T9SK | QXJH | TEXPVQXJH02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  | EIC to be Mapped | Radha Complex TST Kondotty | Kondotty | 12175 | 2026-02-16 | 2026-02-16 |  | 15 | 2026-03-03 | 2026-04-30 | 2026-05-01 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-02 | 2026-05-02 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRAS15503 | 604 |  | TR58 | NXK3 | TRNDVNXK302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Nilambur TST | Nilambur | 10050 | 2026-02-16 | 2026-02-16 |  | 15 | 2026-03-03 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED
VADCKC15525 | 605 |  | S0IX | Q5FX | DCDCMQ5FX02 | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Maharashtra |  | Prashant Wankhede | Pune -Chakan-PTL Installation | Pune | 200285 | 2026-02-13 | 2026-02-17 | 30 | 0 | 2026-03-19 | 2026-05-31 | 2026-06-03 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | JUNE 26
EDAMRT15567 | 606 |  |  |  |  | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Delhi & NCR |  |  | DLF Avenue Saket Delhi | Delhi | 904.39 | [7 empty] | On Hold | [5 empty] | FY 26-27 | AOP |  |  | OCTOBER 25
EDAMRT15568 | 607 |  | TBLH | TBLH | EDMMUTBLH00 | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Uttar Pradesh |  | Jag Lal | Palssio , Lucknow | Lucknow | 403 | 2026-02-23 | 2026-03-01 | 35 |  | 2026-04-05 | 2026-05-08 | 2026-05-08 | EPC Ready | 100% |  | 2026-05-18 | 2026-05-16 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
EDAMRT15569 | 608 |  |  |  |  | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Rajasthan |  |  | Pink walk mall, Jaipur | Jaipur | 997.07 | [7 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
YOTHBK15572 | 609 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | GMU |  |  | Shop No. 1, Blue Empress, Mahavir Nagar, Next to Raghuleela Mall, Kandivali West, MUMBAI SUBURBAN, 400067 | Kandivali | [8 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | OCTOBER 25
YOTHBK15574 | 610 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Gujarat |  |  | GJ _ Jamnagar _ RIL Mall | Jamnagar | [8 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP
YOTHBK15590 | 611 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Maharashtra | West Maharashtra |  | Kolhapur Tapadia RIL Mall. | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
YOTHBK15591 | 612 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Maharashtra | West Maharashtra |  | Neil Mont, AU Estate. CS NO. 1747/1, Rajarampuri 5th Lane, Kolhapur - 418006 | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
YOTHRT15593 | 613 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Punjab |  |  | Opp Ramada Hotel, GTB Road, Jalandhar | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
YOTHRT15594 | 614 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Rajasthan |  |  | Pink walk mall, Jaipur | Jaipur | [8 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
YOTHRT15601 | 615 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Uttar Pradesh |  |  | Metropolitan Mall, Jhansi | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
TRTRRT15607 | 616 |  | TEG2 | NQY3 | TFITUNQY301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Kanpur Lal Bangla Defence Colony | Kanpur | 10451 | 2026-02-20 | 2026-02-20 |  | 15 | 2026-03-07 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15611 | 617 |  | TK49 | NWG3 | TRNDBNWG301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Patna Polytechnic | Patna | 10003 | 2026-02-19 | 2026-02-19 |  | 15 | 2026-03-06 | 2026-04-10 | 2026-04-15 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15616 | 618 |  | TM78 | NC20 | TRNDBNC2004 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Gaya G B Road | Gaya | 9466 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-07 | 2026-04-07 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15617 | 619 |  | TY52 | NB16 | TRNDBNB1601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Darbhanga Laheriasarai Tower VIP Rd | Darbhanga | 11566 | 2026-02-19 | 2026-02-19 |  | 15 | 2026-03-06 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15618 | 620 |  | 9089 | NFC4 | TMANBNFC401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Muzafarpur DRB Mall | Muzaffarpur | 9356 | 2026-02-17 | 2026-02-17 |  | 15 | 2026-03-04 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15619 | 621 |  | T39Q | QA4T | TEXPVQA4T03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Vaikom TST Kandathil Arcade | Vaikom | 11099 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-04-30 | 2026-05-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26
TRTRSD15623 | 622 |  | 8300 | NDP2 | TRNDANDP201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nellore Kondayapalem | Nellore | 10300 | 2026-02-17 | 2026-02-17 |  | 15 | 2026-03-04 | 2026-04-30 | 2026-05-04 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15624 | 623 |  | T809 | NVD2 | TRNDANVD204 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Rajmundry Prakas Ngr | Rajahmundry | 11243 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15626 | 624 |  | TO41 | ND04 | TRNDAND0402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kakinada SRMT Mall | Kakinada | 11901 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-05-10 | 2026-05-07 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-17 | 2026-05-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26 | JUNE 25
TRTRSD15627 | 625 |  | 5970 | NQ12 | TRND6NQ1202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Itanagar Zero Point | Itanagar | 14568 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-03 | 2026-05-03 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15630 | 626 |  | TST6 | Q2QL | TFITFQ2QL03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Guwahati Lal Ganesh | Guwahati | 14075 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15632 | 627 |  | 9647 | NUG6 | TFITVNUG601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Manjery Mallapuram Road/ Mallapuram | Manjery | 7707 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-05-10 | 2026-05-08 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRAS15633 | 628 |  | 9535 | NFP8 | TRNDVNFP801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Malapuram Down Hill | Malappuram | 8716 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15635 | 629 |  | FR1U | QEXE | TRNFWQEXE02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kolkata TV FBB Kolkata Konnagar Indiragandhi Sarani | Kolkata | 7802 | 2026-02-20 | 2026-02-20 |  | 15 | 2026-03-07 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | APRIL 25
TRTRAS15636 | 630 |  | TWUL | Q6T1 | TEXPVQ6T103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Mulanthuruthy TST Pallithazham Road | Mulanthuruthy | 7037 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26 | APRIL 25
TRTRAS15637 | 631 |  | TT99 | NZW5 | TRNDVNZW504 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Feroke TST | Feroke | 6710 | 2026-02-18 | 2026-02-18 |  | 15 | 2026-03-05 | 2026-05-10 |  | On Hold |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP
VADCSD15664 | 632 |  | S4ZK | QZ9F | DCDCFQZ9F00 | F. SCM | SCM BF | Value DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | SD | Assam & NE | Guwahati | Gopal Pal | Guwahati Madanpur VFDC - Phase II | Guwahati | 136878 | 2026-04-14 | 2026-04-14 |  | 45 | 2026-05-29 | 2026-06-15 |  | WIP | 85% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED
SCPCAK15665 | 633 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | Orissa | Bhubaneshwar |  | Bhubaneshwar FFDC | [9 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP
SCPCAK15666 | 634 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | South | AK | Tamil Nadu | Chennai |  | Chennai- MMLP FFDC (WH04) | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
SCDHAK15668 | 635 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | East | AK | Andhra Pradesh |  |  | Vijayawada F&L DC | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | JUNE 25
SCDHAK15669 | 636 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | East | AK | West Bengal |  |  | Bonhooghly Kolkata | [9 empty] | Pre Budget Dehire Site | [5 empty] | FY 26-27 | AOP
ULDCKC15671 | 637 |  |  |  |  | F. SCM | SCM BF | Urban Ladder DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Delhi & NCR |  |  | Tauru (Gurgaon) FC Storage Expansion | Gurgaon | [8 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | NON AOP |  |  | OCTOBER 25
MBSKKC15672 | 638 |  |  |  |  | F. SCM | SCM | Milk Basket | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Delhi & NCR |  |  | Bamnoli Delhi - Cold Room | Delhi | [8 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP
VADCKC15673 | 639 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Haryana |  |  | JHAJJAR(KULANA) - PTL Installation | Jhajjar | [8 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
JIDCKC15674 | 640 |  |  |  |  | F. SCM | SCM BF | Jio DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Gujarat |  |  | RAJKOT - FPS | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | NON AOP
VADCKC15675 | 641 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Gujarat |  |  | Vesu Road, Surat | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
DIDCKC15676 | 642 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Jammu & Kashmir |  |  | Jammu | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
DIDCKC15677 | 643 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  |  | Mumbai | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
SCWHKC15678 | 644 |  |  |  |  | F. SCM | SCM BF | WH | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  |  | Bhiwandi Dhamangaon | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
ULDCKC15679 | 645 |  |  |  |  | F. SCM | SCM BF | Urban Ladder DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  |  | Bhiwandi Dhamangaon | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | NON AOP
VADCKC15680 | 646 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  |  | Bhiwandi Shakti Logistics - Block R3 | [9 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | JUNE 25
SCWHKC15681 | 647 |  |  |  |  | F. SCM | SCM BF | WH | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  |  | K-Square Bhiwandi RBL DC | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
DIDCKC15682 | 648 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  |  | Saptshree Bhiwandi | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
VADCKC15683 | 649 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Maharashtra |  |  | Nagpur-Hingana | [9 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP |  |  | OCTOBER 25
DIDCKC15684 | 650 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | Maharashtra |  |  | Lonikand DC Sanghar, Pune | [9 empty] | On Hold | [5 empty] | FY 26-27 | AOP |  |  | APRIL 25
VADCKC15685 | 651 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | West | KC | GMU |  |  | Bhiwandi - Cold Room | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP
MARKKC15686 | 652 |  |  |  |  | F. SCM | SCM BF | Market Place | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Rajasthan |  |  | Digital DC Jaipur - Marketplace | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | NON AOP
VADCKC15687 | 653 |  |  |  |  | F. SCM | SCM BF | Value DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Uttar Pradesh |  |  | Lucknow | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
SCPCKC15688 | 654 |  |  |  |  | F. SCM | SCM BF | CPC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Uttar Pradesh |  |  | Lucknow-PTL Installation | [9 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | SEPTEMBER 25
DIDCKC15689 | 655 |  |  |  |  | F. SCM | SCM BF | Digital DC | Srinivas P | Purushottam M | Prasad Deshmukh | SCM | North | KC | Uttarakhand |  |  | Dehradun | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
SCDHKC15692 | 656 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Purushottam M | Prasad Deshmukh | Dehire | North | KC | Haryana |  |  | RBL Luhari | [9 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
SCDHKC15693 | 657 |  |  |  |  | F. SCM | SCM | SCM - Dehire | Srinivas P | Purushottam M | Prasad Deshmukh | Dehire | North | KC | Haryana |  |  | MP Luhari | [9 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
FLDCAK15695 | 658 |  | SLI1 | QF5Z | DCDCWQF5Z02 | F. SCM | SCM BF | F&L DC | Srinivas P | Santanu Halder | Chinmay Desai | SCM | East | AK | West Bengal |  |  | Kolkata Panchala consolidation project - Shelving area | Kolkata | 238407 | 2026-02-06 | 2026-02-06 | 30 | 0 | 2026-03-08 | 2026-06-30 |  | WIP | 58% |  |  |  |  | FY 26-27 | AOP | MARCH 26 PLANNED
TRTRBK15714 | 659 |  | T927 | NGQ9 | TRNDENGQ901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Gwalior DB City Mall | Gwalior | 6141 | 2026-02-21 | 2026-02-21 |  | 15 | 2026-03-08 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-07 | 2026-04-07 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | SEPTEMBER 25
TRTRSD15745 | 660 |  | 5805 | NP36 | TRNDBNP3601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Purnia Ayushi Comp | Purnia | 8904 | 2026-02-21 | 2026-02-21 |  | 15 | 2026-03-08 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-07 | 2026-04-07 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15748 | 661 |  | 9087 | NFC3 | TRNDANFC303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vizag Surya Bagh | Visakhapatnam | 5646 | 2026-02-22 | 2026-02-22 |  | 15 | 2026-03-09 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | OCTOBER 25
TRTRSD15750 | 662 |  | TL35 | NWL4 | TRNDBNWL402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Chapra Near Municipal Chowk | Chapra | 12614 | 2026-02-21 | 2026-02-21 |  | 15 | 2026-03-08 | 2026-04-24 | 2026-04-21 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JULY 25
TRTRSD15752 | 663 |  | T654 | NGI8 | TRNDANGI800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijaywda Bhavanipurm | Vijayawada | 9569 | 2026-02-22 | 2026-02-22 |  | 15 | 2026-03-09 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-04 | 2026-04-04 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15753 | 664 |  | 8094 | NCZ3 | TRNDONCZ305 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhubneswr Janpath | Bhubaneshwar | 26688 | 2026-02-22 | 2026-02-22 |  | 15 | 2026-03-09 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15755 | 665 |  | TXUC | Q8R5 | TFITFQ8R503 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Bongaigaon Universal Studio Mall | Bongaigaon | 10450 | 2026-02-22 | 2026-02-22 |  | 15 | 2026-03-09 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15758 | 666 |  | TZ27 | NAB4 | TRNDFNAB402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Biswanath | Biswanath | 11911 | 2026-02-22 | 2026-02-22 |  | 15 | 2026-03-09 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-04 | 2026-04-04 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15759 | 667 |  | 8397 | NDX1 | TRNDFNDX100 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Silchar Nazirapatty | Silchar | 5246 | 2026-02-21 | 2026-02-21 |  | 15 | 2026-03-08 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15766 | 668 |  | 8008 | NCQ6 | TRNDNNCQ602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Hyderabad SrinvasTwr | Hyderabad | 10947 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15768 | 669 |  | 5861 | NP66 | TRNDANP6602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Tirupati ByePass Rd | Tirupati | 10005 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | JUNE 26
TRTRSD15769 | 670 |  | TQ54 | NE21 | TRNDONE2101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Rourkela Forum Mall | Rourkela | 14979 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15771 | 671 |  | TJE2 | QWZ9 | TFITVQWZ902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Trivandrum Malankara Avenue Pattom | Trivandrum | 14510 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15773 | 672 |  | 5907 | NP83 | TRNDANP8301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nellore Felicity Mal | Nellore | 8956 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-30 | 2026-05-04 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15774 | 673 |  | 8381 | NDV8 | TRNDSNDV801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Gangtok Golden Plaza | Gangtok | 7340 | 2026-02-27 | 2026-02-27 |  | 15 | 2026-03-14 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15776 | 674 |  | T588 | NUW3 | TRNDNNUW304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Mehbubnagar Telanga | Mahbubnagar | 10171 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15777 | 675 |  | TZ58 | NAD8 | TRNDANAD802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vizag Gopalpatnam | Vizag | 9085 | 2026-02-23 | 2026-02-23 |  | 15 | 2026-03-10 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRAS15779 | 676 |  | T928 | NGR1 | TRNDVNGR101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Edappally United Mal | Edappal | 9352 | 2026-02-24 | 2026-02-24 |  | 15 | 2026-03-11 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-19 | 2026-05-19 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26 | JULY 25
TRTRSD15780 | 677 |  | 1994 | NG09 | TRNDANG0901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Cuddapah Koti Circle | Kadapa | 11004 | 2026-02-23 | 2026-02-23 |  | 15 | 2026-03-10 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-30 |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15781 | 678 |  | TE45 | NGZ7 | TRNDBNGZ700 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Madhubani Main Mkt | Madhubani | 10073 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-18 | 2026-04-21 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15782 | 679 |  | TG54 | NVT6 | TRNDWNVT600 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | QED Mall Kharagpur | Kharagpur | 8135 | 2026-03-01 | 2026-03-01 |  | 15 | 2026-03-16 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRAS15783 | 680 |  | 5700 | NO87 | TRNDVNO8701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kochi Centre Square | Kochi | 7370 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 |  | On Hold |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
TRTRSD15785 | 681 |  | TSK2 | Q2NP | TFITWQ2NP04 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Chandan Nagar Barabazaar Main Road | Chandan Nagar | 11334 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JULY 25
TRTRSD15786 | 682 |  | 8016 | NZK2 | TRNDNNZK202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Warangal Hanmakonda | Warangal | 10146 | 2026-03-03 | 2026-03-03 |  | 15 | 2026-03-18 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRSD15787 | 683 |  | 1882 | NF47 | TRNDFNF4703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Jorhat City Centre | Jorhat | 10703.2 | 2026-03-02 | 2026-03-02 |  | 15 | 2026-03-17 | 2026-04-10 | 2026-04-11 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15788 | 684 |  | TWQA | Q6H1 | TFITAQ6H103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Srikakulam Ramlaxshman Junction | Srikakulam | 13048 | 2026-02-23 | 2026-02-23 |  | 15 | 2026-03-10 | 2026-04-30 | 2026-04-28 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15790 | 685 |  | TR92 | NXN5 | TRNDSNXN502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Gangtok Vajra World | Gangtok | 10703 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | DECEMBER 25
TRTRSD15791 | 686 |  | 8398 | NDX2 | TRNDFNDX201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Dibrugrh RNC Path | Dibrugarh | 7862 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-24 | 2026-04-22 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-22 | 2026-04-22 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15792 | 687 |  | TPO3 | Q0OL | TFITAQ0OL03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Tirupati V V Mahal Rd | Tirupati | 12896 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED
TRTRSD15793 | 688 |  | 8311 | NDQ1 | TRNDFNDQ100 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Tinsukia GNB Road | Tinsukia | 8209 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15794 | 689 |  | TIY3 | QXH8 | TFITAQXH803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nellore Gandhi Nagar | Nellore | 12464 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-10 | 2026-05-26 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-28 |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15796 | 690 |  | TWPH | Q6E9 | TFITFQ6E902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Tinsukia Green Heights Mall | Tinsukia | 11246 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRSD15799 | 691 |  | TO42 | ND05 | TRNDAND0502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Gajuwaka SriRamNagar | Visakhapatnam | 5545 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAK15800 | 692 |  | T847 | NGP2 | TRNDTNGP201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  | Velayutham | Coimbator Thudiyalur | Coimbatore | 9479 | 2026-03-04 | 2026-03-04 |  | 15 | 2026-03-19 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED
TRTRSD15801 | 693 |  | 1879 | NF44 | TRNDONF4401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Brahmapur Church Rd | Brahmapur | 8154 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-10 | 2026-05-09 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-09 | 2026-05-09 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15802 | 694 |  | TXRN | Q8H9 | TFITWQ8H902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Asansol Horizon G T Road | Asansol | 12462 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15803 | 695 |  | TO85 | ND27 | TRNDWND2704 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Arambagh Gourhati | Arambagh | 9934 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15804 | 696 |  | 8299 | NDP1 | TRNDNNDP102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Warangal Jakotia Com | Warangal | 7643 | 2026-03-20 | 2026-03-20 | 0 | 15 | 2026-04-04 | 2026-05-10 | 2026-05-25 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-30 |  | YTL | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26
TRTRAS15805 | 697 |  | TQ79 | NE32 | TRNDVNE3202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Perumbavoor TMS Mall | Perumbavoor | 7976 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26 | APRIL 25
TRTRSD15806 | 698 |  | TX4I | QA1R | TFITFQA1R01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Silchar Rangirkhadi Point | Silchar | 11663 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-05 | 2026-04-03 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-03 | 2026-04-03 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15807 | 699 |  | TZVD | QDLQ | TFITVQDLQ02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kottakkal Chenakkal Tower Main Rd Malappuram | Kottakkal | 12557 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15808 | 700 |  | TSQ6 | Q2PR | TFITAQ2PR03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Ongole Kurnool Road | Ongole | 11453 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-10 | 2026-05-09 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-08 | 2026-05-08 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRAS15811 | 701 |  | FR2Y | QEUR | TRNFVQEUR01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kochi TV FBB Cochin Palarivattom | Kochi | 13550 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED
TRTRSD15812 | 702 |  | T88N | QOTU | TFITNQOTU01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Kammaguda Turkyamjal Malla Reddy Property | Kammaguda | 13352 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD15814 | 703 |  | TZ25 | NAB2 | TRNDQNAB203 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Giridih Centre Point Court Road | Giridih | 9141 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15815 | 704 |  | TH54 | NVX4 | TFITWNVX401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Raigunj Sudarshanpur | Raigunj | 8000 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | APRIL 25
TRTRSD15816 | 705 |  | TZ60 | NAD0 | TRNDWNAD001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Tamluk Downtown Enclave | Tamluk | 13710 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-08 | 2026-04-08 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRSD15817 | 706 |  | 5934 | NP95 | TRNDWNP9500 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Medinipur KhudiramRd | Medinipur | 10424 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15818 | 707 |  | TR54 | NXJ4 | TRNDWNXJ401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Malda English Bazar | Malda | 11920 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15819 | 708 |  | 8001 | NCP9 | TRNDANCP904 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Eluru Central Plaza | Eluru | 14446 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-2 EPC | 2026-06-30 |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15820 | 709 |  | TAU7 | QGRS | TFITAQGRS02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Guntur Gujajjaldula | Guntur | 18156 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-05 | 2026-04-08 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-08 | 2026-04-08 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15821 | 710 |  | 1989 | NG06 | TRNDANG0601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Ongole RIL Mall | Ongole | 9856 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-10 | 2026-05-09 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-09 | 2026-05-09 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15823 | 711 |  | T958 | NGR7 | TRNDANGR703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Tanuku Sajjapuram | Tanuku | 11185 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-04 | 2026-04-04 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15824 | 712 |  | 5908 | NP84 | TRNDQNP8401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Hazaribag Indralok | Hazaribag | 9728 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | APRIL 25
TRTRSD15825 | 713 |  | TSN9 | Q3YV | TFITQQ3YV02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Jamshedpur Basant Talkies Sakchi | Jamshedpur | 7130 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-05 | 2026-04-08 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-08 | 2026-04-08 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | APRIL 25
TRTRSD15826 | 714 |  | 8003 | NCQ2 | TRNDANCQ202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Guntu Lakshmipuram | Guntur | 14021 | 2026-02-23 | 2026-02-23 |  | 15 | 2026-03-10 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | OCTOBER 25
TRTRSD15830 | 715 |  | TTL4 | Q2XU | TFITNQ2XU02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Warangal Hanamkonda | Warangal | 13802 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15831 | 716 |  | TXP7 | Q9XA | TFITWQ9XA01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Durgapur Benachity | Durgapur | 11677 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15835 | 717 |  | 1903 | NF60 | TRNDFNF6003 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Guwahati Zoo Road | Guwahati | 12026 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD15837 | 718 |  | TMJ2 | QQU9 | TFITWQQU901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Howrah Uluberia | Howrah | 11388 | 2026-03-01 | 2026-03-01 |  | 15 | 2026-03-16 | 2026-04-24 | 2026-04-24 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-24 | 2026-04-24 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | APRIL 25
TRTRSD15838 | 719 |  | TMJ5 | QQV2 | TFITWQQV203 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Chinsurah G T Road Hooghly Milan Cinema | Chinsurah | 11770 | 2026-03-01 | 2026-03-01 |  | 15 | 2026-03-16 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRSD15839 | 720 |  | TKC3 | QAQ5 | TFITFQAQ501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Nagaon City Life | Nagaon | 8122 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRSD15842 | 721 |  | TAUT | QGBD | TFITWQGBD02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kalimpong 9th Mile Kalimpong | Kalimpong | 10243 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-04 | 2026-04-04 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15843 | 722 |  | T866 | NVF9 | TRNDFNVF902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Sibsagar Assam | Sibsagar | 9748 | 2026-03-03 | 2026-03-03 |  | 15 | 2026-03-18 | 2026-04-24 | 2026-04-23 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15844 | 723 |  | TKU3 | QDL0 | TFITNQDL002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Warangal Nayeem Nagar Hanmakonda | Warangal | 9884 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRSD15845 | 724 |  | TWPA | Q6E2 | TFITWQ6E202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Bandel Swapan Bhawal Option | Bandel | 12248 | 2026-03-01 | 2026-03-01 |  | 15 | 2026-03-16 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-08 | 2026-04-08 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15846 | 725 |  | 9532 | NFP5 | TRNDVNFP501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Malapuram UC Plaza | Malappuram | 9138 | 2026-02-24 | 2026-02-24 |  | 15 | 2026-03-11 | 2026-05-31 | 2026-05-23 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRSD15847 | 726 |  | TW35 | NNT5 | TRNDANNT502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Mandapeta TST | Mandapeta | 4480 | 2026-03-28 | 2026-03-28 | 0 | 15 | 2026-04-12 | 2026-04-12 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26
TRTRSD15848 | 727 |  | TS17 | QUU2 | TRNDWQUU202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Balurghat Hili More Mangalpur | Balurghat | 13063 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15850 | 728 |  | T38A | QCCS | TFITOQCCS01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhubaneswar Next To Falcone Marine Office | Bhubaneshwar | 15730 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15852 | 729 |  | TDG7 | NQS7 | TFITBNQS702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Supaul Hathkhola Rd | Supaul | 10536 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15853 | 730 |  | T28R | QW1R | TFITQQW1R02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Jugsalai Jamshedpur | Jugsalai | 9748 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-05 | 2026-04-08 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-07 | 2026-04-07 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15854 | 731 |  | TSR7 | QEQV | TFITNQEQV02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Nagole Bandlaguda Nagole | Nagole | 12090 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-30 |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26 | SEPTEMBER 25
TRTRSD15855 | 732 |  | TSZ6 | Q2TL | TEXPAQ2TL01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Narasapuram TST | Narasapuram | 5739 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS15857 | 733 |  | TP10 | ND35 | TRNDKND3502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Belgaum Tilakwadi | Belgaum | 9674 | 2026-03-02 | 2026-03-02 |  | 15 | 2026-03-17 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15861 | 734 |  | FR1D | QETS | TRNFFQETS01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Guwahati TV FBB Guwahati Paltan Bazaar | Guwahati | 10012.06 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-19 | 2026-04-19 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRSD15863 | 735 |  | TAHB | Q7DH | TEXPWQ7DH01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ghatal TST Ghatal Market | Ghatal | 9303 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD15864 | 736 |  | TK76 | NWH9 | TRNDNNWH902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Zaheerabad TST | Zaheerabad | 4321 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD15866 | 737 |  | TKN5 | QBX0 | TEXPNQBX001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Madhira TST | Madhira | 4194 | 2026-02-27 | 2026-02-27 |  | 15 | 2026-03-14 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED |  | SEPTEMBER 25
TRTRSD15869 | 738 |  | TSV3 | Q2RV | TEXPNQ2RV02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Sathupally TST | Sathupally | 6433 | 2026-02-27 | 2026-02-27 |  | 15 | 2026-03-14 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED
MIAGAK15906 | 739 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Mini Depo - Aug | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Rohin Chand | HUZURNAGAR MINI DEPO_Phase I Piping works | Huzurnagar | 20000 | 2026-02-25 | 2026-02-25 | 0 | 60 | 2026-04-26 | 2026-06-18 |  | WIP | 79% | WIP |  |  |  | FY 26-27 | AOP | APRIL 26 PLANNED
TRTRRT15911 | 740 |  | TA1W | QGUN | TFITUQGUN01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Lucknow TB BB Lucknow Sahara Mall | Lucknow | 12201 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRRT15915 | 741 |  | 9529 | NFP2 | TRNDUNFP200 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Bareilly Civil Lines | Bareilly | 9149 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-04-30 | 2026-05-03 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-01 | 2026-05-01 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26 | MAY 25
TRTRRT15916 | 742 |  | 8122 | NDB8 | TRNDUNDB802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Bareilly Phoenix Mal | Bareilly | 19105 | 2026-02-26 | 2026-02-26 |  | 15 | 2026-03-13 | 2026-05-10 | 2026-05-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-05 |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRRT15927 | 743 |  | TFD8 | QZD4 | TFIT9QZD401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Kapurthala Mall Road | Kapurthala | 11079 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15940 | 744 |  | TIR2 |  | TFIT9QXQ102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Pathankot Dalhousie Road | Pathankot | 10142 | 2026-03-02 | 2026-03-02 |  | 15 | 2026-03-17 | 2026-03-17 |  | On Hold |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRTRRT15943 | 745 |  | 8101 | NCZ8 | TRNDRNCZ800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Ajmer Cine Mall | Ajmer | 9004 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP | MARCH 26 PLANNED
TRTRRT15951 | 746 |  | TSP4 | Q8FI | TFITUQ8FI01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Unnao Moti Nagar | Unnao | 8969.964 | 2026-02-24 | 2026-02-24 |  | 15 | 2026-03-11 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRRT15961 | 747 |  | TL59 | NWM5 | TRNDUNWM500 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Mughalsarai Mughal M | Mughalsarai | 9600 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15962 | 748 |  | TG55 | NHO2 | TRNDUNHO200 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Mirzapur Gems Mall | Mirzapur | 9571 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15963 | 749 |  | 8343 | NZJ1 | TRND5NZJ102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Rudrapur Metropolis | Rudrapur | 6680 | 2026-03-06 | 2026-03-06 |  | 15 | 2026-03-21 | 2026-05-10 | 2026-05-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-06 |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26 | MAY 25
TRTRRT15965 | 750 |  | TQE8 | Q0XO | TFIT9Q0XO03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Moga Bansal Complex | Moga | 8144 | 2026-03-03 | 2026-03-03 |  | 15 | 2026-03-18 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15973 | 751 |  | TGC9 | QYI4 | TFITUQYI402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Kannauj Makrand Nagar | Kannauj | 13020 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15974 | 752 |  | TCN4 | NAT8 | TFITUNAT802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Azamgarh Civil Lines | Azamgarh | 12000 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15975 | 753 |  | TKN4 | QBW0 | TFITHQBW003 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Narnaul Opp Gold Cinema Near Hero Honda Chowk | Narnaul | 9000 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-30 | 2026-04-24 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-24 | 2026-04-24 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15976 | 754 |  | T629 | NGH1 | TRNDHNGH100 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Sirsa Dubwali | Sirsa | 6625 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26
TRTRRT15977 | 755 |  | 5933 | NP94 | TRNDHNP9401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Sonipat Atlus Road | Sonipat | 8360 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15978 | 756 |  | 5794 | NP25 | TRNDHNP2500 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Panipat Gohana | Panipat | 7230 | 2026-03-06 | 2026-03-06 |  | 15 | 2026-03-21 | 2026-04-18 | 2026-04-14 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15981 | 757 |  | TWUE | Q2UW | TEXPJQ2UW02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Doda TST Opposite Town Hall Doda Jammu | Doda | 6432 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-24 | 2026-04-23 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-22 | 2026-04-22 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15982 | 758 |  | T43C | QJSS | TFIT9QJSS01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Jalandhar PPR Mall | Jalandhar | 13075 | 2026-03-05 | 2026-03-05 |  | 15 | 2026-03-20 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15983 | 759 |  | TGI3 | QYF5 | TEXP9QYF502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Mukerian TST | Mukerian | 6130 | 2026-04-06 | 2026-04-06 |  | 15 | 2026-04-21 | 2026-05-10 | 2026-04-23 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-25 |  | YTL | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26
TRTRRT15984 | 760 |  | 5996 |  | TRNDRNQ2001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Bhilwara RIL Mall | Bhilwara | 8312 | [7 empty] | On Hold |  | Cycle-4 EPC |  |  |  | FY 26-27 | NON AOP
TRTRRT15991 | 761 |  | TIR5 | QXQ4 | TFITUQXQ402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Kasganj Soron Gate | Kasganj | 10340 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-04-30 | 2026-05-03 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-01 | 2026-05-01 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRTRRT15994 | 762 |  | 5988 | NQ15 | TRNDUNQ1502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Saharanpur Delhi Rd | Saharanpur | 8370.72 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-18 | 2026-04-30 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-02 | 2026-05-02 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15996 | 763 |  | TKZ2 | QFN0 | TFITUQFN001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Bhadohi Station Road | Bhadohi | 9309.03 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-24 | 2026-04-23 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-22 | 2026-04-22 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15997 | 764 |  | TOA3 | Q21D | TFITUQ21D03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Budaun Station Road | Budaun | 8000 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-24 | 2026-04-23 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-24 | 2026-04-24 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT15998 | 765 |  | TU31 | NHF7 | TRNDUNHF703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Padrauna P D City Mall | Padrauna | 7236 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-05 | 2026-04-05 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT16000 | 766 |  | TH81 | NYA9 | TRND5NYA904 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Haridwar Ranipur Rd | Haridwar | 7979 | 2026-03-07 | 2026-03-07 |  | 15 | 2026-03-22 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT16001 | 767 |  | T559 | NYB7 | TRND5NYB702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Almora Akashwani | Almora | 7341 | 2026-03-10 | 2026-03-10 |  | 15 | 2026-03-25 | 2026-04-24 | 2026-04-28 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-27 | 2026-04-27 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT16002 | 768 |  | TGZ6 | QXR8 | TFIT5QXR801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Roorkee Ramnagar Chowk | Roorkee | 10739.52 | 2026-03-07 | 2026-03-07 |  | 15 | 2026-03-22 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRRT16003 | 769 |  | TSP7 | Q6J2 | TFIT5Q6J202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Dehradun Jogiwala | Dehradun | 9643 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRRT16004 | 770 |  | TX3V | Q2E8 | TFIT5Q2E803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Dehradun Sehastradhara Road | Dehradun | 10609 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
GRDSKC16005 | 771 | DS-DL-00326 | TBEF | QHGT | DARKHQHGT00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Sushil Kumar Sahu | GGN-Ardee City | Gurugram | 1330 | 2026-02-25 | 2026-03-11 | 15 |  | 2026-03-26 | 2026-04-05 | 2026-04-08 | EPC Ready | 100% |  | PENDING | 2026-05-08 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
TRTRBK16007 | 772 |  | 8023 | NZK1 | TRNDCNZK100 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Surya Bhilainagar | Bhilai | 13837 | 2026-03-02 | 2026-03-02 |  | 15 | 2026-03-17 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-10 | 2026-04-10 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRKC16009 | 773 |  | TFI1 | QYZ4 | TFITEQYZ401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | KC | Madhya Pradesh |  |  | Betul Civil Lines | Betul | 9500 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-04-05 | 2026-04-02 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-02 | 2026-04-02 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRBK16012 | 774 |  | TN21 | NC43 | TRNDCNC4303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Raipur Centre Mall | Raipur | 10189 | 2026-02-28 | 2026-02-28 |  | 15 | 2026-03-15 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRKC16013 | 775 |  | TDU9 | NS51 | TFITENS5102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | KC | Madhya Pradesh |  |  | Balaghat Main Rd Nr Hanuman Chowk | Balaghat | 9000 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-04-05 | 2026-04-20 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRKC16014 | 776 |  | TDV3 | NS88 | TFITENS8802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | KC | Madhya Pradesh |  |  | Sagar Prince Jain property Makronia | Sagar | 11963 | 2026-02-27 | 2026-02-27 |  | 15 | 2026-03-14 | 2026-04-05 | 2026-04-20 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRBK16015 | 777 |  | TIR1 | QXP9 | TFITEQXP901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Mandla Jabalpur Road | Mandla | 8681 | 2026-03-03 | 2026-03-03 |  | 15 | 2026-03-18 | 2026-04-10 | 2026-04-11 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRKC16016 | 778 |  | TH39 | NHE1 | TRNDENHE100 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | KC | Madhya Pradesh |  |  | Burhanpur Station Rd | Burhanpur | 7910 | 2026-02-25 | 2026-02-25 |  | 15 | 2026-03-12 | 2026-04-24 | 2026-04-25 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-28 | 2026-04-28 | Launched | FY 26-27 | NON AOP | MARCH 26 PLANNED | APRIL 26
TRTRAS16038 | 779 |  | 8071 | NCX1 | TRNDVNCX102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thrissur Grand Mall | Thrissur | 18562 | 2026-03-04 | 2026-03-04 |  | 15 | 2026-03-19 | 2026-03-19 |  | On Hold |  | Cycle-4 EPC |  |  |  | FY 26-27
TRTRSD16039 | 780 |  | TSR0 | QENO | TFITNQENO01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Khammam BK Bazar | Khammam | 16589 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-05-31 | 2026-05-30 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16040 | 781 |  | T626 | NGG8 | TRNDONGG800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhadrak Roul Complex | Bhadrak | 7981 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16041 | 782 |  | T563 | NGE4 | TRNDNNGE400 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Siddipet PrashantNgr | Siddipet | 10970 | 2026-03-04 | 2026-03-04 |  | 15 | 2026-03-19 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-3 EPC | 2026-06-01 |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16042 | 783 |  | TQE9 | Q0XP | TFITAQ0XP04 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nandyal Padmavati Nagar | Nandyal | 13885 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16043 | 784 |  | 9673 | NUG9 | TRNDBNUG900 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Sitamarhi Kot Bazaar | Sitamarhi | 10684 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-24 | 2026-04-25 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-25 | 2026-04-25 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAK16044 | 785 |  | TU58 | NJS7 | TRNDTNJS702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  | Mohan Balaji | Salem Amdham Complex/ Saradha College road, Salem | Salem | 9087 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRAK16045 | 786 |  | TZ24 | NAB1 | TRNDBNAB103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Motihari Arya Samaj Road | Motihari | 11068 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-24 | 2026-04-25 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-25 | 2026-04-25 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAK16046 | 787 |  | 8285 | NDN9 | TRNDONDN901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Raurkela Main Road | Raurkela | 10764 | 2026-03-07 | 2026-03-07 |  | 15 | 2026-03-22 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRAK16047 | 788 |  | TSN1 | Q2OT | TFITFQ2OT01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Hojai Main Market | Hojai | 12127 | 2026-03-07 | 2026-03-07 |  | 15 | 2026-03-22 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-02 | 2026-05-02 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAK16049 | 789 |  | TGV6 | QXW3 | TFITWQXW304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Jhargram Opposite HDFC bank | Jhargram | 12476 | 2026-03-04 | 2026-03-04 |  | 15 | 2026-03-19 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-10 | 2026-04-10 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAK16050 | 790 |  | TXXN | Q9HG | TFITNQ9HG01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  | Murali Krishna Reddy | Siddipet Bharat nagar | Siddipet | 12611 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-27 |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRAK16051 | 791 |  | 8043 | NCU4 | TRNDKNCU403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Bangalore Banshankri | Bangalore | 19189 | 2026-03-05 | 2026-03-05 |  | 15 | 2026-03-20 | 2026-05-10 | 2026-05-22 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | MARCH 26 PLANNED | MAY 26 | MAY 25
TRTRAK16052 | 792 |  | 8058 | NCV7 | TRNDKNCV702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Gulbarga Asian Mall | Gulbarga | 13819 | 2026-03-06 | 2026-03-06 |  | 15 | 2026-03-21 | 2026-03-21 |  | On Hold |  | Cycle-2 EPC |  |  |  | FY 26-27
TRTRSD16053 | 793 |  | TS18 | QUU3 | TRNDNQUU304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Sangreddy Potireddy | Sangareddy | 10913 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAK16054 | 794 |  | TGV5 | QXW2 | TFITTQXW202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  | Janarthanan | Theni Periyakulam road | Theni | 11241 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRAS16055 | 795 |  | T51Y | QPMM | TFITKQPMM02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TC Palya Main Rd | Bangalore | 11536 | 2026-03-10 | 2026-03-10 |  | 15 | 2026-03-25 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16056 | 796 |  | 1941 | NF77 | TRNDANF7702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kurnool Budhawarpet | Kurnool | 11436 | 2026-03-04 | 2026-03-04 |  | 15 | 2026-03-19 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16057 | 797 |  | TC86 | NYB3 | TRNDBNYB301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Nalanda Chakajiyian | Biharsharif | 9376 | 2026-03-06 | 2026-03-06 |  | 15 | 2026-03-21 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-19 | 2026-04-19 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAK16058 | 798 |  | TLR9 | QMV0 | TFITKQMV002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Mandya 100Ft Road | Mandya | 12937 | 2026-03-10 | 2026-03-10 |  | 15 | 2026-03-25 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-21 | 2026-05-21 | Launched | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16059 | 799 |  | TE40 | NGZ6 | TRNDWNGZ600 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Haldia Bhawanipur | Haldia | 8749 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-10 | 2026-04-10 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16060 | 800 |  | 5912 | NP86 | TRNDANP8601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Narsaropet Sunita Pl | Narasaraopet | 8609 | 2026-03-04 | 2026-03-04 |  | 15 | 2026-03-19 | 2026-05-10 | 2026-05-26 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-30 |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16061 | 801 |  | TX4G | QA1M | TFITBQA1M02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Begusarai Near Hotel Blue Diamond | Begusarai | 10897 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-06 | 2026-04-06 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAK16062 | 802 |  | T0N8 | Q4FW | TFITTQ4FW01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  | Janarthanan | Coimbatore VMS Arcade Kavundampalayam | Coimbatore | 12860 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16063 | 803 |  | TFS4 | QYT4 | TEXPOQYT401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Jatani TST | Jatani | 6194 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16065 | 804 |  | T630 | NGH2 | TRNDWNGH200 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Purulia Raghavpur | Purulia | 9205 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | SEPTEMBER 25
TRTRSD16066 | 805 |  | TPK8 | Q0MN | TFITAQ0MN03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vishakhapatnam MVP Colony Road JK Silk Property | Visakhapatnam | 8800 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16067 | 806 |  | TJZ6 | QAH4 | TEXPBQAH401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Jamalpur TST | Jamalpur | 7914 | 2026-03-07 | 2026-03-07 |  | 15 | 2026-03-22 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16068 | 807 |  | TIR0 | QXP8 | TFITOQXP804 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bolangir Near Main market | Bolangir | 10162 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-10 | 2026-04-10 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRSD16069 | 808 |  | TSK9 | Q2NW | TFITBQ2NW01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Khagaria Beside Honda MG Road | Khagaria | 8429 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAS16071 | 809 |  | TJP4 | QWH4 | TFITVQWH402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Trivandrum Rashid Arcade Sreekaryam | Trivandrum | 11693 | 2026-03-10 | 2026-03-10 |  | 15 | 2026-03-25 | 2026-04-18 | 2026-04-21 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16073 | 810 |  | TAT5 | QGRJ | TEXPOQGRJ03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Balasore TST Near Remuna Square | Balasore | 9157 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-10 | 2026-04-12 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-12 | 2026-04-12 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | NOVEMBER 25
TRTRSD16074 | 811 |  | TJN0 | QWL3 | TEXPWQWL302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Bishnupur TST | Bishnupur | 6352 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAS16075 | 812 |  | TGV7 | QXW4 | TEXPVQXW401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Vadakanchery TST | Vadakanchery | 7436 | 2026-03-10 | 2026-03-10 |  | 15 | 2026-03-25 | 2026-05-10 | 2026-05-11 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16078 | 813 |  | TH52 | NVX3 | TRNDBNVX301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Gopalganj Station Road | Gopalganj | 9800 | 2026-03-06 | 2026-03-06 |  | 15 | 2026-03-21 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAS16085 | 814 |  | TDG1 | NQS3 | TWIWKNQS302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TW OMBR | Bangalore | 1848 | 2026-03-05 | 2026-03-05 |  | 15 | 2026-03-20 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRBK16088 | 815 |  | TFI6 | QYZ9 | TFITEQYZ902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Sidhi Opp District Hospital Jagsheel Complex | Sidhi | 8700 | 2026-03-07 | 2026-03-07 |  | 15 | 2026-03-22 | 2026-04-05 | 2026-04-02 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-02 | 2026-04-02 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRBK16090 | 816 |  | 1934 | NQM9 | TRND7NQM903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Goa |  |  | Virani Sales Goa | Panjim | 12085 | 2026-03-08 | 2026-03-08 |  | 15 | 2026-03-23 | 2026-04-05 | 2026-04-05 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-05 | 2026-04-05 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRBK16091 | 817 |  | T86W | QOSB | TFITCQOSB01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Chattisgarh |  |  | Dhamtari Beside Shri Balaji Plaza Jagdalpur Rd | Dhamtari | 9606 | 2026-03-07 | 2026-03-07 |  | 15 | 2026-03-22 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-10 | 2026-04-10 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRBK16092 | 818 |  | TX1R | Q2QR | TFITEQ2QR02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Chhatarpur Trends | Chhatarpur | 8328 | 2026-03-06 | 2026-03-06 |  | 15 | 2026-03-21 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16115 | 819 |  | 1979 | NF99 | TRNDNNF9901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Hyderabad Mythri ngr | Hyderabad | 11442 | 2026-06-01 | 2026-06-01 |  | 50 | 2026-07-21 | 2026-07-21 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JULY 26 PLANNED |  | MAY 25
TRTRAS16116 | 820 |  | TX72 | NA32 | TRNDKNA3202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Nelamangala | Bangalore | 7531 | 2026-03-15 | 2026-03-15 |  | 15 | 2026-03-30 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16117 | 821 |  | 8013 | NCR2 | TRNDANCR205 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijaywda BenzCircle | Vijayawada | 17170 | [7 empty] | NRFC |  | Full Renovation |  |  |  | FY 26-27 |  |  |  | APRIL 25
TRTRSD16118 | 822 |  | TC87 | NGY8 | TRNDONGY800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhubneswr ForumEspln | Bhubaneshwar | 10266 | 2026-05-08 | 2026-05-08 |  | 50 | 2026-06-27 | 2026-06-27 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JUNE 26 PLANNED
TRTRSD16119 | 823 |  | TSP6 | Q6J1 | TFITOQ6J102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Anugul Sangul | Anugul | 13417 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-27 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRAS16120 | 824 |  | TL34 | NWL3 | TRNDVNWL302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Palakkad Metro Square | Palakkad | 11248 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16121 | 825 |  | 5784 | NP19 | TRNDNNP1901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Nalgonda Meerbagh | Nalgonda | 6716 | 2026-03-14 | 2026-03-14 |  | 15 | 2026-03-29 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16122 | 826 |  | TV28 | NLY6 | TRNDNNLY602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Karimnagar Mukrampur | Karimnagar | 9499 | 2026-03-15 | 2026-03-15 |  | 15 | 2026-03-30 | 2026-05-31 | 2026-05-31 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26 | MAY 25
TRTRSD16123 | 827 |  | 9666 | NFY6 | TRNDANFY600 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Tenali Ratna Arcade | Tenali | 6930 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAS16124 | 828 |  | TU87 | NKV4 | TRNDKNKV402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Doddaballapura TST | Doddaballapura | 7118 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-10 | 2026-05-11 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-11 | 2026-05-11 | Launched | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16125 | 829 |  | TDS6 | NM73 | TFITBNM7302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Dehri Gandhi Nagar | Dehri | 13000 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-19 | 2026-04-19 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16126 | 830 |  | TWPT | Q6G2 | TFITTQ6G201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Kundrathur Kolachery Kanchipuram | Kundrathur | 14036 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-31 | 2026-05-23 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26 | JUNE 25
TRTRAS16127 | 831 |  | TFA8 | QZI3 | TEXPVQZI301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Cherthala TST | Cherthala | 6237 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRAS16128 | 832 |  | 5757 | NP06 | TRNDVNP0602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kochi Grand Centre | Kochi | 8882 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED |  | MAY 25
TRTRAS16129 | 833 |  | TMG1 | QQP1 | TFITVQQP102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Alappuzha Near YMCA | Alappuzha | 10895 | 2026-03-19 | 2026-03-19 |  | 15 | 2026-04-03 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | APRIL 25
TRTRSD16130 | 834 |  | TG88 | NVU8 | TRNDNNVU800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Suryapet Kuda Road | Suryapet | 9794 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16131 | 835 |  | T531 | NUV1 | TRNDBNUV103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Hajipur Cine Plaza | Hajipur | 11037 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | JULY 25
TRTRSD16132 | 836 |  | 5879 | NP75 | TRNDWNP7501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Alipurduar Cnrt Plaz | Alipurduar | 10174 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | AUGUST 25
TRTRAK16133 | 837 |  | T863 | NVF7 | TFITKNVF703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Dharwad Modern Hall Mall | Dharwad | 6893 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED |  | AUGUST 25
TRTRAK16134 | 838 |  | 1982 | NG02 | TRNDTNG0201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Erode RIL Rana Hall | Erode | 7598 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED |  | APRIL 25
TRTRSD16135 | 839 |  | TB55 | NGV9 | TRNDANGV900 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Guntur Naaz Centre | Guntur | 9645 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-05-10 | 2026-05-24 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-27 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16136 | 840 |  | TIS1 | QXR1 | TEXPOQXR102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Semiliguda TST | Semiliguda | 11661 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-04-05 | 2026-04-08 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-08 | 2026-04-08 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | NOVEMBER 25
TRTRSD16137 | 841 |  | TS25 | QUW3 | TRNDNQUW304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Hyderabad L&T Mall | Hyderabad | 11736 | 2026-03-13 | 2026-03-13 |  | 15 | 2026-03-28 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-27 |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRAK16138 | 842 |  | TQE5 | Q0XL | TFITTQ0XL02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbatore Lakshmi Mills | Coimbatore | 15659 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-05-10 | 2026-05-20 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-20 | 2026-05-20 | Launched | FY 26-27 |  | MARCH 26 PLANNED | MAY 26 | NOVEMBER 25
TRTRAK16139 | 843 |  | TSM2 | Q2OJ | TFITKQ2OJ03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Mangalore Karuna Pride Falnir | Mangalore | 16523 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSD16140 | 844 |  | 5967 | NQ10 | TRNDANQ1002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kakinada Bhanugudi | Kakinada | 7515 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-05-10 | 2026-05-22 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26 | JULY 25
TRTRSD16141 | 845 |  | TZVB | QDLO | TFITAQDLO03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kakinada Next to Big V Store Main Road | Kakinada | 12958 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-05-10 | 2026-05-20 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-19 | 2026-05-19 | Launched | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16142 | 846 |  | 5872 | NP72 | TRNDWNP7200 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Raniganj NSB Road | Raniganj | 8536 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-16 | 2026-04-16 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16143 | 847 |  | TL36 | NWL5 | TRNDQNWL503 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Dumka Royal Majestic | Dumka | 8500 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | APRIL 25
TRTRAK16144 | 848 |  | T0AH | Q4LQ | TFITTQ4LQ02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Erode VIP Shopping Centre | Erode | 12551 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16145 | 849 |  | T1OG | Q2E7 | TFITAQ2E702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Guntur Phoenix Mall GT Road | Guntur | 15062 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-05-10 | 2026-05-22 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-22 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16146 | 850 |  | TY29 | NA93 | TRNDQNA9301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Ramgarh Co located with Smart Hazaribagh Rd | Ramgarh | 10000 | 2026-03-14 | 2026-03-14 |  | 15 | 2026-03-29 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAS16147 | 851 |  | TJA4 | QXE7 | TEXPKQXE702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Devanahalli TST | Devanahalli | 6066 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-12 | 2026-05-12 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16148 | 852 |  | 5743 | NO96 | TRNDNNO9601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Karimnagr RIL Mall | Karimnagar | 8151 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-2 EPC | 2026-06-01 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | APRIL 25
TRTRSD16149 | 853 |  | TC54 | NGX4 | TRNDANGX401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijaywda TW PVP Mall | Vijayawada | 1930 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16150 | 854 |  | TCY1 | NQG9 | TFITWNQG901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Durgapur City Centre Ambedkar Sarani | Durgapur | 11056 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | SEPTEMBER 25
TRTRSD16151 | 855 |  | 5753 | NP04 | TRNDANP0404 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Anantapur Kamla Ngr | Anantapur | 3546 | 2026-03-09 | 2026-03-09 |  | 15 | 2026-03-24 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRAS16152 | 856 |  | 8067 | NCW6 | TRNDVNCW601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kollam K Mall | Kollam | 17176 | 2026-03-13 | 2026-03-13 |  | 15 | 2026-03-28 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED |  | MAY 25
TRTRSD16153 | 857 |  | 8012 | NCR1 | TRNDANCR102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Rajmundr AlcotGardn | Rajahmundry | 11816 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-10 | 2026-05-19 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 |  | MARCH 26 PLANNED | MAY 26 | AUGUST 25
TRTRAK16154 | 858 |  | T956 | NGR5 | TRNDTNGR501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Trichy VOC Road | Trichy | 10500 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED |  | JULY 25
TRTRSD16155 | 859 |  | 8015 | NCR4 | TRNDANCR403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vizag Bochupeta | Vizianagaram | 10767 | [7 empty] | NRFC |  | Full Renovation |  |  |  | FY 26-27 |  |  |  | JUNE 25
TRTRSD16156 | 860 |  | TDS7 | NM83 | TFITWNM8301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Bankura Machantala | Bankura | 11375 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD16157 | 861 |  | TU37 | NHU5 | TRNDBNHU503 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Aurangabad Old GT Rd | Aurangabad | 13033 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAK16158 | 862 |  | TV43 | NMK3 | TRNDTNMK303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Trichy NearABTMaruti | Trichy | 14518 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | MARCH 26 PLANNED
TRTRSD16159 | 863 |  | 8041 | NCU2 | TRNDQNCU202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Jamshedpr Bombay Twr | Jamshedpur | 13089 | 2026-03-14 | 2026-03-14 |  | 15 | 2026-03-29 | 2026-05-10 | 2026-05-20 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-20 |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRSD16160 | 864 |  | TW46 | NNY6 | TRNDWNNY604 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Katwa TST | Katwa | 8253 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD16161 | 865 |  | TDH1 | NQS9 | TFITNNQS901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Wanaparthy KDR Nagar | Wanaparthy | 9430 | 2026-03-14 | 2026-03-14 |  | 15 | 2026-03-29 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | APRIL 25
TRTRSD16162 | 866 |  | TX21 | NXF6 | TEXPANXF601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kavali TST | Kavali | 7558 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-04-30 | 2026-05-04 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRAK16163 | 867 |  | T806 | NGN7 | TRNDKNGN701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Hubli TIMS UrbnOasis | Hubli | 10005 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-18 |  | On Hold |  | Cycle-4 EPC |  |  |  | FY 26-27
TRTRAK16164 | 868 |  | T631 | NGH3 | TRNDTNGH302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Dindigul Venus Cmplx | Dindigul | 6707 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-16 |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26 | JUNE 25
TRTRSD16165 | 869 |  | TKT9 | QDH0 | TEXPWQDH001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Rampurhat TST | Rampurhat | 8000 | 2026-03-14 | 2026-03-14 |  | 15 | 2026-03-29 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
TRTRSD16167 | 870 |  | TU28 | NGT1 | TRNDWNGT103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Asansol Galaxy Mall | Asansol | 9100 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JULY 25
TRTRSD16168 | 871 |  | TJV1 | QAB5 | TEXPWQAB502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Chakdah TST | Chakdah | 6736 | 2026-03-13 | 2026-03-13 |  | 15 | 2026-03-28 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16169 | 872 |  | TFM6 | QYW3 | TEXPAQYW302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Ramachandrapuram TST | Ramachandrapuram | 7000 | 2026-03-11 | 2026-03-11 |  | 15 | 2026-03-26 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | JULY 25
TRTRSD16170 | 873 |  | TKE9 | QAT3 | TEXPAQAT301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Peddapuram TST | Peddapuram | 7016 | 2026-03-10 | 2026-03-10 |  | 15 | 2026-03-25 | 2026-04-10 | 2026-04-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-06 | 2026-04-06 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16172 | 874 |  | TTW1 | Q3DN | TEXPWQ3DN02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Baruipur TST | Baruipur | 6228 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRAS16173 | 875 |  | TTW0 | Q3DM | TEXPKQ3DM02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Avalahalli TST | Avalahalli | 7702 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16174 | 876 |  | 8134 | NDC9 | TRNDWNDC901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Darjiling/Darjeeling Rink Mall | Darjiling | 8526 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26
TRTRSD16175 | 877 |  | TP21 | ND43 | TRNDNND4302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Shadnagar TST | Shadnagar | 5786 | 2026-03-06 | 2026-03-06 |  | 15 | 2026-03-21 | 2026-04-05 | 2026-04-05 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-06 | 2026-04-06 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | JULY 25
TRTRSD16176 | 878 |  | TP15 | ND38 | TRNDNND3802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Gadwal TST | Gadwal | 4100 | 2026-03-12 | 2026-03-12 |  | 15 | 2026-03-27 | 2026-04-05 | 2026-04-04 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-04 | 2026-04-04 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD16178 | 879 |  | TJC2 | QXB8 | TFITQQXB802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Khunti Near Bhagat Singh Chowk | Khunti | 9000 | 2026-03-18 | 2026-03-18 |  | 15 | 2026-04-02 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-13 | 2026-04-13 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRAS16179 | 880 |  | TWTH | Q6Q5 | TEXPKQ6Q502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Sankeshwar TST Gokak Sankeshwar Rd | Sankeshwar | 6789 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-05-10 | 2026-05-09 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRAS16180 | 881 |  | TQ97 | NE33 | TEXPKNE3302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Gokak TST Falls Road | Gokak | 6000 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-05-10 | 2026-05-07 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JULY 25
TRTRAS16181 | 882 |  | TTE1 | Q2VG | TWIWKQ2VG02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TW KR Puram | Bangalore | 1533 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | NOVEMBER 25
TRTRAS16182 | 883 |  | TTG0 | QGXX | TWIWKQGXX03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TW Kaggadasapura main road | Bangalore | 1846 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16186 | 884 |  | TY5D | QCKS | TFITWQCKS02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Rashbehari Avenue, Kolkata | Kolkata | 12693 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD16187 | 885 |  | TK57 | NWH2 | TRNDNNWH202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Hyderbd Erumanzil | Hyderabad | 10164 | 2026-03-13 | 2026-03-13 |  | 15 | 2026-03-28 | 2026-04-30 | 2026-04-29 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-29 | 2026-04-29 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | MAY 25
COPUAK16106 | 886 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Rohin Chand | CP - TSRTC - Bhadrachalam Canopy works | Bhadrachalam | 538 | 2026-03-30 | 2026-03-30 |  | 45 | 2026-05-14 | 2026-05-30 |  | Partial WIP | 14% | WIP - On Hold |  |  |  | FY 26-27 |  |  |  | MAY 25
COPUAK16107 | 887 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | East | AK | Telangana |  | Rohin Chand | CP - TSRTC - Sattupalli Canopy works | Sattupalli | 538 | 2026-03-30 | 2026-03-30 |  | 45 | 2026-05-14 | 2026-05-14 | 2026-05-16 | EPC Ready | 100% | EPC Ready | 2026-05-16 | 2026-05-16 | Launched | FY 26-27 |  | MAY 26 PLANNED | MAY 26 | MAY 25
COPUKC16108 | 888 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  |  | CP - UPSRTC - Hardoi Canopy works | Hardoi | [8 empty] | Budget Approved - RFC Awaited |  | Vendor finalization - In Process |  |  |  | FY 26-27 |  |  |  | JUNE 25
COPUKC16109 | 889 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  |  | CP - UPSRTC - Gola Canopy works | Gola | [8 empty] | Budget Approved - RFC Awaited |  | Vendor finalization - In Process |  |  |  | FY 26-27
COPUKC16110 | 890 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  |  | CP - UPSRTC - Siddarthnagar Canopy works | Siddarthnagar | [8 empty] | Budget Approved - RFC Awaited |  | Vendor finalization - In Process |  |  |  | FY 26-27 |  |  |  | JULY 25
COPUKC16111 | 891 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Uttar Pradesh |  |  | CP - UPSRTC - Banda Canopy works | Banda | [8 empty] | Budget Approved - RFC Awaited |  | Vendor finalization - In Process |  |  |  | FY 26-27 |  |  |  | MAY 25
COPUKC16112 | 892 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Haryana |  |  | CP - HRTC - Palwal | Palwal | [8 empty] | Budget Approved - RFC Awaited |  | YTS |  |  |  | FY 26-27 |  |  |  | MAY 25
COPUKC16113 | 893 |  |  |  |  | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Haryana |  |  | CP - HRTC - Asandh | Asandh | [8 empty] | Budget Approved - RFC Awaited |  | YTS |  |  |  | FY 26-27 |  |  |  | MAY 25
COPUKC16114 | 894 |  | Not Applicable | Not Applicable | Not Applicable | I. Petro | Petro | Consumer Pump | Anand P | Teja Anvesh | Dhananjay Raut | Petro | North | KC | Haryana |  | Anand Singh | CP - HRTC - Rohtak | Rohtak | 600 | 2026-05-04 | 2026-05-04 |  | 45 | 2026-06-18 | 2026-06-18 |  | WIP | 78% | WIP |  |  |  | FY 26-27 |  | JUNE 26 PLANNED |  | JUNE 25
GRDSKC16195 | 895 | DS-MP-00007 | TBF5 | QHIH | DARKEQHIH00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Madhya Pradesh | Indore | Subhro Ghose | Silicon City, indore | Indore | 2409.84 | 2026-03-21 | 2026-03-23 | 15 |  | 2026-04-07 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% |  | PENDING | 2026-05-11 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16196 | 896 |  | TWQH | Q6H7 | TFITWQ6H703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kolkata City Market (Mart) Humayun Place Dharmatala | Kolkata | 12489 | 2026-04-27 | 2026-04-27 |  | 50 | 2026-06-16 | 2026-06-16 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JUNE 26 PLANNED |  | JULY 25
TRTRAS16197 | 897 |  | R217 | NGA8 | TRNDKNGA803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore ComercilSt | Bangalore | 17758 | 2026-06-03 | 2026-06-03 |  | 50 | 2026-07-23 | 2026-07-23 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JULY 26 PLANNED |  | JULY 25
TRTRSD16198 | 898 |  | 8138 | NDD4 | TRNDWNDD401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kolkata IdealRegency | Kolkata | 12909 | 2026-05-21 | 2026-05-21 |  | 50 | 2026-07-10 | 2026-07-10 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JULY 26 PLANNED |  | OCTOBER 25
TRTRSD16199 | 899 |  | 8139 | NDD5 | TRNDWNDD501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kolkata DCN Mall | Kolkata | 16430 | [7 empty] | On Hold |  | Full Renovation |  |  |  | FY 26-27 |  |  |  | OCTOBER 25
TRTRSD16200 | 900 |  | 8136 | NDD2 | TRNDWNDD201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kolkata Axis Mall | Kolkata | 15965 | 2026-05-03 | 2026-05-03 |  | 50 | 2026-06-22 | 2026-06-22 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JUNE 26 PLANNED |  | APRIL 25
TRTRSD16201 | 901 |  | 8137 | NDD3 | TRNDWNDD303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kolkata Avani | Kolkata | 28469 | 2026-05-03 | 2026-05-03 |  | 50 | 2026-06-22 | 2026-06-22 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JUNE 26 PLANNED |  | APRIL 25
TRTRSD16202 | 902 |  | 8306 | NDP6 | TRNDBNDP602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Patna Ambition Saphr | Patna | 14222 | 2026-05-20 | 2026-05-20 |  | 50 | 2026-07-09 | 2026-07-09 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JULY 26 PLANNED |  | OCTOBER 25
TRTRSD16203 | 903 |  | 8133 | NDC8 | TRNDWNDC800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Burdwan Curzon Gate | Burdwan | 9334 | 2026-05-02 | 2026-05-02 |  | 50 | 2026-06-21 | 2026-06-21 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JUNE 26 PLANNED |  | APRIL 25
TRTRSD16204 | 904 |  | 8141 | NDD7 | TRNDWNDD702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Siliguri City Center | Siliguri | 14262 | 2026-05-15 | 2026-05-15 |  | 50 | 2026-07-04 | 2026-07-04 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JULY 26 PLANNED |  | APRIL 25
TRTRSD16205 | 905 |  | 8307 | NDP7 | TRNDONDP702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhubneswr Z Tower | Bhubaneshwar | 14599 | 2026-05-08 | 2026-05-08 |  | 50 | 2026-06-27 | 2026-06-27 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JUNE 26 PLANNED |  | MAY 25
TRTRSD16206 | 906 |  | 8039 | NCT9 | TRNDQNCT901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Bokaro Bokaro Mall | Bokaro | 9962 | 2026-05-11 | 2026-05-11 |  | 50 | 2026-06-30 | 2026-06-30 |  | WIP |  | Full Renovation |  |  |  | FY 26-27 |  | JUNE 26 PLANNED |  | MAY 25
TRTRSD16207 | 907 |  | T596 | NGF5 | TRNDBNGF500 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Patna Kankarbagh | Patna | 10557 | [7 empty] | On Hold |  | Full Renovation |  |  |  | FY 26-27 |  |  |  | JULY 25
TRTRSD16208 | 908 |  | 8000 | NCP8 | TRNDANCP802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Bhimavrm City Cntr | Bhimavaram | 8180 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-27 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | AUGUST 25
TRTRAK16209 | 909 |  | TOB2 | Q21W | TFITTQ21W01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbatore Kuniymtur | Coimbatore | 16646 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-05-31 | 2026-05-25 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-24 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRAS16210 | 910 |  | 1930 | NF73 | TRNDTNF7301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tirunlvli RILPalymkt | Tirunelveli | 10005 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAS16211 | 911 |  | 9555 | NFR2 | TRNDVNFR201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kodngalur MalabarTWR | Kodungallur | 13293 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-10 | 2026-05-15 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-25 | 2026-05-25 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRAK16212 | 912 |  | TX42 | NXH7 | TRNDTNXH703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbatore Vadavalli | Coimbatore | 12700 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSD16213 | 913 |  | TQE6 | Q0XM | TFITNQ0XM03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Jagityal Krishna Property | Jagityal | 13949 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JUNE 25
TRTRAS16214 | 914 |  | TA1M | QGUD | TRNDTQGUD01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Mayiladuthurai Pattamangalam street | Mayiladuthurai | 10548 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16215 | 915 |  | TH51 | NHE7 | TRNDANHE701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Madnpale Ring Road | Madanapalle | 7908 | 2026-03-22 | 2026-03-22 |  | 15 | 2026-04-06 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRAS16216 | 916 |  | T509 | NGB9 | TRNDVNGB902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thrissur Akkara | Irininjalakuda | 10085 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-05-25 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRAS16217 | 917 |  | T76N | QKCK | TEXPVQKCK01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Poojappura TST Commercial Complex | Poojappura | 10600 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-11 | 2026-04-11 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16218 | 918 |  | TPM9 | Q0NR | TFITAQ0NR04 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Chittoor KR Palli | Chittoor | 12377 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRSD16219 | 919 |  | TGC7 | QYI2 | TFITAQYI202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Amalapuram High School Rd | Amalapuram | 11445 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-05-10 | 2026-05-15 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-17 | 2026-05-17 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRSD16220 | 920 |  | TSO9 | Q2PE | TFITBQ2PE02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Sasaram Near Madhya Gramin Bank | Sasaram | 12218 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-19 | 2026-04-19 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRAS16221 | 921 |  | TAPQ | QF5W | TFITKQF5W02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Shimoga Shivamurthy Circle Savalanga Road | Shimoga | 14090 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JUNE 25
TRTRAK16222 | 922 |  | T41X | QIQQ | TFITTQIQQ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Salem Bharathi Complex | Salem | 11774 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JUNE 25
TRTRAS16223 | 923 |  | TC83 | NGY4 | TRNDTNGY402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Gumidpndi GNT Road | Gummidipoondi | 7470 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-09 |  | On Hold |  | Cycle-3 EPC |  |  |  | FY 26-27 |  |  |  | JULY 25
TRTRSD16224 | 924 |  | T9GK | QVAW | TFITOQVAW01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Rourkela F2 Arcade | Rourkela | 11275 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-21 | 2026-05-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRTRAS16225 | 925 |  | TY30 | NA94 | TRNDTNA9403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Dharmapuri Salem Rd | Dharmapuri | 7713 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRAK16226 | 926 |  | TPU3 | Q0RC | TFITTQ0RC02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbatore App Sai Baba NSR | Coimbatore | 10062 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-05-10 | 2026-05-14 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16227 | 927 |  | 5819 | NP46 | TRNDONP4600 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Puri Bijaya Subudhi | Puri | 5000 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16228 | 928 |  | T1BH | QG6F | TFITAQG6F03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Tirupathi Karakambadi Road | Tirupati | 14616 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-30 | 2026-05-05 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-05 | 2026-05-05 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JULY 25
TRTRSD16229 | 929 |  | 9221 | NFL4 | TRNDANFL402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Adoni NGO Colony | Adoni | 9634 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-06-02 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | JUNE 26 | JUNE 25
TRTRSD16230 | 930 |  | TV40 | NMJ9 | TRNDNNMJ902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Trends Armoor | Armoor | 10800 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-10 | 2026-05-20 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRAS16231 | 931 |  | T76K | QKCH | TEXPTQKCH02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Sulur TST Trichy Main Road | Sulur | 10296 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JUNE 25
TRTRAK16232 | 932 |  | T503 | NGB5 | TRNDTNGB501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Nagercoil RIL PO Rd | Nagercoil | 6265 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRAK16233 | 933 |  | TGC5 | QYH9 | TFITTQYH901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Tirunlvli Visak Bvan | Tirunelveli | 12000 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRAK16234 | 934 |  | 5687 | NO82 | TRNDTNO8204 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Vellore Gandhi Nagar | Vellore | 9616 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRSD16235 | 935 |  | TPO2 | Q0OK | TFITNQ0OK02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Nizamabad Venu mall | Nizamabad | 9961 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAK16236 | 936 |  | 9518 | NFO5 | TRNDTNFO501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Thanjavur R R Nagar | Thanjavur | 10205 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-10 | 2026-05-14 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-26 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRTRAK16237 | 937 |  | 5797 | NP28 | TRNDTNP2803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Thiruvallur JN Road | Thiruvallur | 10250 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JUNE 25
TRTRAK16238 | 938 |  | T990 | NVG9 | TRNDTNVG901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chengalpattu GST Rd | Chengalpattu | 10278 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRAK16239 | 939 |  | 9586 | NFT7 | TRNDTNFT701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Vellore SR Arcade | Vellore | 10643 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAK16240 | 940 |  | TS29 | QUX5 | TRNDTQUX501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Namakkal Salem Rd | Namakkal | 13723 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAS16241 | 941 |  | TWPI | Q6F1 | TFITTQ6F102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tiruvannamalai Vengikkal | Tiruvannamalai | 10453 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRSD16242 | 942 |  | TDN8 | NE86 | TFITANE8602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijayawad Airport Rd | Vijayawada | 14693 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JULY 25
TRTRSD16243 | 943 |  | TSN6 | Q2OY | TFITWQ2OY02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Suri Besides Bequest Hotel | Suri | 11211 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16244 | 944 |  | TLS1 | QMX0 | TFIT6QMX001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Pachighat Upper Banskota | Pasighat | 12254 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-04-24 | 2026-04-27 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-27 | 2026-04-27 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16245 | 945 |  | TDG4 | NQS4 | TFITANQS402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Dharmavaram Parthasarathi Nagar | Dharmavaram | 10120 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | JUNE 26
TRTRSD16246 | 946 |  | TV41 | NMK1 | TRNDNNMK101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Siricilla Opp Old Bus Stand | Siricilla | 10007 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-31 | 2026-05-30 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16247 | 947 |  | TV93 | NNH5 | TRNDANNH505 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Anakapalli TST | Anakapalli | 8476 | 2026-03-16 | 2026-03-16 |  | 15 | 2026-03-31 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-28 |  | YTL | FY 26-27 |  | MARCH 26 PLANNED | MAY 26
TRTRAS16248 | 948 |  | T9ME | QXDH | TEXPTQXDH02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Thirumazhisai TST T.H Road | Thirumazhisai | 11382 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16249 | 949 |  | TO07 | NWS6 | TRNDVNWS603 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pattambi Matilakam | Pattambi | 10932 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRAS16250 | 950 |  | TZUR | QDJZ | TEXPVQDJZ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Balarampuram TST | Balarampuram | 6928 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-04-10 | 2026-04-14 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16251 | 951 |  | TSV7 | Q2RZ | TEXPAQ2RZ03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Payakaraopet TST | Payakaraopet | 9952 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRTRAS16252 | 952 |  | 1981 | NSP6 | TRNDVNSP604 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Alleppey RIL Mall | Alleppey | 10069 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-15 | 2026-05-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16253 | 953 |  | TGD3 | QYI8 | TFITWQYI803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Bangaon Fashion Mart | Bangaon | 8000 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-04-18 | 2026-04-15 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16254 | 954 |  | TEW3 | QZL5 | TFITOQZL501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Cuttack Chauliganj | Cuttack | 10800 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-10 | 2026-05-06 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16255 | 955 |  | TML0 | QQX6 | TFITOQQX603 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Dhenkanal Dakhina Kali Rd | Dhenkanal | 10500 | 2026-03-22 | 2026-03-22 |  | 15 | 2026-04-06 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16256 | 956 |  | TX3O | QA1E | TFITVQA1E01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kollam Near Brand Factory Kadappakkada Kollam | Kollam | 10992 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-04-30 | 2026-05-02 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JULY 25
TRTRSD16257 | 957 |  | TIY0 | QXH2 | TFITBQXH202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Bhabua Suraj Tower | Bhabua | 12000 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16258 | 958 |  | TWUA | Q6S7 | TEXPVQ6S702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kottiyam TST | Kottiyam | 8727 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-26 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRAS16259 | 959 |  | TW64 | NOJ5 | TEXPTNOJ501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Arakkonam TST | Arakkonam | 4400 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JULY 25
TRTRSD16260 | 960 |  | TEY9 | QZG3 | TEXPNQZG301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Gajwel TST | Gajwel | 5386 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-10 | 2026-04-25 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD16261 | 961 |  | TGH9 | QYF1 | TFITAQYF103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vizianagaram 3 lanterns | Vizianagaram | 10735 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JULY 25
TRTRAS16262 | 962 |  | TU89 | NKW2 | TRNDTNKW204 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tindivanam TST | Tindivanam | 7264 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JULY 25
TRTRSD16263 | 963 |  | TW91 | NSP1 | TRNDANSP102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Palasa TST | Palasa | 5549 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-4 EPC | 2026-06-01 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JULY 25
TRTRSD16264 | 964 |  | TO67 | ND17 | TRND6ND1704 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Naharlagun TST | Naharlagun | 7917 | 2026-03-19 | 2026-03-19 |  | 15 | 2026-04-03 | 2026-04-30 | 2026-04-28 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JUNE 25
TRTRSD16265 | 965 |  | TGZ8 | QXS1 | TFITOQXS104 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Jagatsinghpur Nr Bhoomika Eye Hospital | Jagatsinghpur | 5407 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-04-24 | 2026-04-26 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-26 | 2026-04-26 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16266 | 966 |  | TSU3 | Q2RM | TEXPAQ2RM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Bobbili TST | Bobbili | 5124 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-19 | 2026-04-19 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | AUGUST 25
TRTRSD16267 | 967 |  | TW88 | NSB7 | TRNDANSB703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Rajam TST | Rajam | 4159 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-17 | 2026-04-17 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16268 | 968 |  | TSU1 | Q2RK | TEXPOQ2RK03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Jajpur TST Byasanagar | Jajpur | 6644 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-30 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16269 | 969 |  | TMA2 | QQJ0 | TFITQQQJ002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Lohardaga Ranchi Lohardaga | Lohardaga | 10500 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-30 | 2026-04-27 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRSD16270 | 970 |  | TAA3 | NAI6 | TRNDONAI601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Talcher TST | Talcher | 5135 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-28 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRSD16271 | 971 |  | TCH7 | NAO0 | TRNDBNAO002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Lakhisarai AD Mall | Lakhisarai | 10000 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-24 | 2026-04-23 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-22 | 2026-04-22 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16272 | 972 |  | TM07 | NWO7 | TRNDTNWO701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Palladam TST | Palladam | 4863 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-18 | 2026-04-21 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRAS16273 | 973 |  | TTL6 | Q2YM | TEXPTQ2YM03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Sriperumbudur TST | Sriperumbudur | 4940 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | AUGUST 25
TRTRSD16274 | 974 |  | TWUU | Q6U1 | TEXPAQ6U102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Hanuman Junction TST Bapulapadu | Hanuman Junction | 9585 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRAS16275 | 975 |  | TEQ9 | QZY9 | TEXPTQZY903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Thiruttani TST | Thiruttani | 9913 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRSD16276 | 976 |  | TTB1 | Q2TZ | TEXPOQ2TZ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Umarkote TST | Umarkote | 10750 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16277 | 977 |  | TFU7 | QYO5 | TFITQQYO501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Godda Jaiswal Building Bhagalpur Road | Godda | 8756 | 2026-03-17 | 2026-03-17 |  | 15 | 2026-04-01 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16278 | 978 |  | TXYQ | Q9MG | TEXPTQ9MG01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Ponneri TST | Ponneri | 5455 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-09 |  | On Hold |  | Cycle-4 EPC |  |  |  | FY 26-27
TRTRSD16279 | 979 |  | TFR3 | QYU4 | TFITOQYU404 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Jeypore TST Shree Laxmi Homes | Jeypore | 9644 | 2026-03-23 | 2026-03-23 |  | 15 | 2026-04-07 | 2026-05-10 | 2026-05-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-10 | 2026-05-10 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRAS16280 | 980 |  | TWUX | Q6U4 | TEXPTQ6U401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Manapparai TST | Manapparai | 5574 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAS16281 | 981 |  | TH78 | NVX9 | TRNDKNVX903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bailhongal TST | Bailhongal | 3600 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-10 | 2026-04-11 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16282 | 982 |  | TPN5 | Q0NY | TJNRTQ0NY01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Coimbatr TJ Tank St | Coimbatore | 1458 | 2026-03-25 | 2026-03-25 |  | 15 | 2026-04-09 | 2026-04-10 | 2026-04-11 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAK16283 | 983 |  | TKT2 | QCY0 | TWIWTQCY001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai TW PMD Nagar Kovilambakkam | Chennai | 2615 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-04-24 | 2026-04-28 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAK16286 | 984 |  | TA11 | NGT8 | TRNDTNGT802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbator TW NSR Rd | Coimbatore | 2319 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JULY 25
TRTRAK16287 | 985 |  | 9654 | NFX9 | TRNDTNFX902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Coimbator TW RSPuram | Coimbatore | 3319 | 2026-03-20 | 2026-03-20 |  | 15 | 2026-04-04 | 2026-04-18 | 2026-04-21 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRAS16288 | 986 |  | T52E | QPSS | TMANKQPSS02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TM Kothnur Main Rd Jp Nagar | Bangalore | 2072 | 2026-03-21 | 2026-03-21 |  | 15 | 2026-04-05 | 2026-04-10 | 2026-04-11 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16293 | 987 |  | 9617 | NFV7 | TRNDKNFV701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Hospet College Rd | Hospet | 10700 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16294 | 988 |  | TSS9 | Q2QF | TFITTQ2QF02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Cuddalore V Square Mall Bharathi Rd | Cuddalore | 10477 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | OCTOBER 25
TRTRSD16295 | 989 |  | T532 | NUV2 | TRNDONUV203 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Keonjhar Mining Road | Keonjhar | 12552 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-24 | 2026-04-22 | EPC Ready | 100% | Cycle-2 EPC | 2026-04-22 | 2026-04-22 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16296 | 990 |  | 5965 | NQ08 | TRNDTNQ0802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Pollachi Scheme Road | Pollachi | 7036 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16297 | 991 |  | TDX4 | NW64 | TFITQNW6402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Daltonganj Redma Chowk | Daltonganj | 11637 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-05 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16298 | 992 |  | TV61 | NMW8 | TRNDANMW801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Proddatur SS Mall | Proddatur | 11508 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-31 | 2026-05-30 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16299 | 993 |  | TDN5 | NE70 | TFITVNE7001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Vadakara Nesto Center | Vadakara | 10368 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-10 | 2026-05-08 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | OCTOBER 25
TRTRSZFO16300 | 994 |  | 6147 | NQ66 | TRNDVNQ6601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thrissur Shoba City | Thrissur | 9857 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16301 | 995 |  | T0S3 | Q4HH | TFITTQ4HH02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tirupur Palladam Road Nochipalayam | Tirupur | 14377 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16302 | 996 |  | 9510 | NUF1 | TRNDTNUF102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Hosur Bagalur Rd | Hosur | 11653 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16303 | 997 |  | TPU7 | Q0RX | TEXPTQ0RX03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Pattukottai TST | Pattukottai | 6306 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16304 | 998 |  | TE51 | NVQ4 | TRNDONVQ401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Baripada Station Rd | Baripada | 9100 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-04-24 | 2026-04-27 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-27 | 2026-04-27 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | SEPTEMBER 25
TRTRSZFO16305 | 999 |  | TP11 | ND36 | TRNDKND3603 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Chitradurga P B Rd | Chitradurga | 9000 | 2026-04-14 | 2026-04-14 |  | 15 | 2026-04-29 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16306 | 1000 |  | TN20 | NC42 | TRNDTNC4201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tirverumbr Kattur | Trichy | 9331 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-20 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-26 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRTRSD16307 | 1001 |  | TG71 | NVU6 | TRNDONVU600 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bargarh Canal Rd | Bargarh | 10700 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-26 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16308 | 1002 |  | TW37 | NNU4 | TRNDTNNU401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Kallakurchi TST | Kallakurchi | 6000 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JULY 25
TRTRSD16309 | 1003 |  | TSR1 | QENP | TFITAQENP02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Chilakaluripet Chowthra Center | Chilakaluripet | 14441 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-30 | 2026-04-28 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-03 | 2026-05-03 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16310 | 1004 |  | TSP1 | Q2PG | TFITTQ2PG01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Thanjavur Medical college | Thanjavur | 14112 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16311 | 1005 |  | TN03 | NC35 | TRNDNNC3502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Mancherial StationRd | Mancherial | 8235 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16312 | 1006 |  | T825 | NGO6 | TRNDVNGO601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Trivandrm Attingal | Attingal | 9291 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-04-30 | 2026-05-04 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16313 | 1007 |  | TP79 | ND72 | TEXPTND7202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Walajapet TST | Walajapet | 5756 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JULY 25
TRTRSZFO16314 | 1008 |  | T1BR | QG6W | TFITKQG6W02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Raichur Gandhi Chowk | Raichur | 14169 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16315 | 1009 |  | TWPN | Q6F5 | TFITOQ6F501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Rayagada Station Road Near Housing Board Colony | Rayagada | 10011 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-10 | 2026-05-08 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-08 | 2026-05-08 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16316 | 1010 |  | T89Q | QOWJ | TFITAQOWJ03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Bapatla Radham Road | Bapatla | 10819 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16317 | 1011 |  | TSQ9 | QENN | TFITNQENN01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Trends Ramagundam | Ramagundam | 14723 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-30 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16318 | 1012 |  | T669 | NGJ8 | TRNDTNGJ801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai TW Forum Mal | Chennai | 2444 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-04-30 | 2026-05-02 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-02 | 2026-05-02 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16319 | 1013 |  | TEW5 | QZL7 | TFITKQZL702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bnglr Orion OMR | Bangalore | 12471 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAK16320 | 1014 |  | TU41 | NIC2 | TRND8NIC202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Karaikal Bharathiyar | Karaikal | 7027 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRSD16321 | 1015 |  | 8335 | NDS1 | TRNDONDS101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Sambalpur RIL Mall | Sambalpur | 9200 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-26 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | AUGUST 25
TRTRAK16322 | 1016 |  | T1HB | Q2QY | TFITTQ2QY01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Tuticorin WGC Road | Tuticorin | 8781 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-2 EPC | 2026-05-15 | 2026-05-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16323 | 1017 |  | TW87 | NRW7 | TRNDNNRW701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Adilabd Ambedkr chwk | Adilabad | 15400 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16324 | 1018 |  | TR99 | NXO3 | TRNDVNXO301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Angamaly TST | Angamaly | 6464 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16325 | 1019 |  | TTR6 | Q3BA | TEXPAQ3BA03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Rajampet TST | Rajampet | 7613 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-13 | 2026-05-13 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16326 | 1020 |  | TH98 | NVZ5 | TRNDKNVZ501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Gadag Mulgund Road | Gadag | 11272 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 | 2026-05-30 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16327 | 1021 |  | TXQ3 | Q9XF | TEXPTQ9XF02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Thirumangalam TST | Thirumangalam | 9177 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16328 | 1022 |  | T1DL | Q2QN | TFITAQ2QN01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijayawada Gollapudi | Vijayawada | 12612 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16329 | 1023 |  | 8379 | NDV7 | TRNDQNDV701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Ranchi TIMS Maru Twr | Ranchi | 6751 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-24 | 2026-04-23 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-23 | 2026-04-23 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16330 | 1024 |  | TQ23 | ND96 | TRNDVND9601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Ottapalam TST | Ottapalam | 6512 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16331 | 1025 |  | TBA5 | NAJ5 | TEXPANAJ501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kadiri TST | Kadiri | 8480 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-24 | 2026-04-22 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-20 | 2026-04-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16332 | 1026 |  | TX1Z | Q2QX | TFITAQ2QX02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kurnool Nandyal Road Srinagar Colony | Kurnool | 11214 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16333 | 1027 |  | TY55 | NB19 | TEXPANB1901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Tadepalli TST | Tadepalli | 8631 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-15 | 2026-04-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JULY 25
TRTRSD16334 | 1028 |  | TY60 | NB24 | TEXPANB2401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Puttur TST | Puttur | 4886 | 2026-03-24 | 2026-03-24 |  | 15 | 2026-04-08 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16335 | 1029 |  | TT20 | NXX3 | TRNDNNXX303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Palavancha TST | Palavancha | 4725 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 | 2026-05-30 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16336 | 1030 |  | TME3 | QQN4 | TEXPTQQN401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Virudhachalam TST | Virudhachalam | 5136 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-04-30 | 2026-05-04 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16337 | 1031 |  | TWTG | Q6Q4 | TEXPAQ6Q401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Palakollu TST | Palakollu | 7498 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-30 | 2026-04-21 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-03 | 2026-05-03 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16338 | 1032 |  | TW74 | NOQ3 | TRNDANOQ304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Ravulapalem TST | Ravulapalem | 6636 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-04-30 | 2026-04-29 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-01 | 2026-05-01 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16339 | 1033 |  | TLR4 | QMP0 | TEXPKQMP002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Chintamani TST | Chintamani | 5500 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | OCTOBER 25
TRTRSD16340 | 1034 |  | TP16 | ND39 | TRNDAND3902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Rayachoti TST | Rayachoti | 5013 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | OCTOBER 25
TRTRSD16341 | 1035 |  | TK78 | NWI2 | TRNDANWI202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Guntur TST | Guntur | 5243 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16342 | 1036 |  | TM92 | NC30 | TRNDTNC3003 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Thuraiyur TST | Thuraiyur | 6150 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16343 | 1037 |  | FR1Z | QEUD | TRNFAQEUD01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kadapa TV FBB Kadapa Pavan Arcade | Kadapa | 9800 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-30 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16344 | 1038 |  | TFR1 | QYU2 | TEXPTQYU202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Neyveli TST | Neyveli | 6429 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-10 | 2026-05-09 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16345 | 1039 |  | TJM1 | QWK5 | TWIW8QWK501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Pondicherry TW Jawaharlal Nehru Street | Pondicherry | 3200 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-11 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-15 | 2026-05-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16346 | 1040 |  | TR59 | NXK4 | TRNDVNXK403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Koyilandy TST | Koyilandy | 9000 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-10 | 2026-05-11 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-15 | 2026-05-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16347 | 1041 |  | TK61 | NWH5 | TRNDVNWH504 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thriprayar TW Y Mall | Thriprayar | 2383 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-10 | 2026-05-08 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | AUGUST 25
TRTRSZFO16348 | 1042 |  | TLB3 | QGR0 | TEXPVQGR002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kundara TST | Kundara | 5972 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-04-30 | 2026-05-02 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16349 | 1043 |  | TJY8 | QAG6 | TEXPTQAG602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Mettupalayam TST | Mettupalayam | 5600 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16350 | 1044 |  | TZUQ | QDKA | TEXPVQDKA02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Guruvayur TST | Guruvayur | 4926 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-20 | 2026-05-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16351 | 1045 |  | TWTK | Q6Q8 | TEXPKQ6Q802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Kundapura TST | Kundapura | 8749 | 2026-04-09 | 2026-04-09 |  | 15 | 2026-04-24 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16352 | 1046 |  | TY13 | NA73 | TRNDANA7302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kurnool TM VarietyMal | Kurnool | 2985 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-18 | 2026-04-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-19 | 2026-04-19 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16353 | 1047 |  | TP80 | ND73 | TRNDTND7302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tiruchengode TST | Tiruchengode | 7413 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16354 | 1048 |  | TC61 | NGX6 | TRNDKNGX602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TW Kengeri | Bangalore | 1800 | 2026-04-05 | 2026-04-05 |  | 15 | 2026-04-20 | 2026-04-24 | 2026-04-24 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | DECEMBER 25
TRTRSD16355 | 1049 |  | TPO7 | Q0OP | TEXPAQ0OP01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Thatipaka TST | Thatipaka | 4409 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | NOVEMBER 25
TRTRSZFO16356 | 1050 |  | TL87 | NWM8 | TRNDKNWM803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TM Kengeri | Bangalore | 2500 | 2026-04-05 | 2026-04-05 |  | 15 | 2026-04-20 | 2026-04-30 | 2026-05-02 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | OCTOBER 25
TRTRSD16357 | 1051 |  | TAQL | QF6W | TFITOQF6W03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Malkangiri Malkangiri Main Market | Malkangiri | 13285 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-10 | 2026-05-10 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-10 | 2026-05-10 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | OCTOBER 25
TRTRSD16358 | 1052 |  | TKZ0 | QFI0 | TFITOQFI002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhawanipatna Near Balaji Temple | Bhawanipatna | 14223 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-10 | 2026-05-19 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | OCTOBER 25
TRTRSD16359 | 1053 |  | TDO1 | NE89 | TFITONE8902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Sundergr Sankar City | Sundergarh | 7823 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-17 | 2026-05-17 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16360 | 1054 |  | TWTM | Q6R1 | TEXPKQ6R101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Sira TST | Sira | 5552 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16361 | 1055 |  | TTF5 | Q2VR | TWIWTQ2VR02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Kumbakonam TW Kumbeshwarar South Street | Kumbakonam | 2322 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | OCTOBER 25
TRTRSZFO16362 | 1056 |  | TTY0 | Q3EJ | TFITKQ3EJ03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Haveri PB road | Haveri | 10046 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JULY 25
TRTRSZFO16363 | 1057 |  | TA2L | QGVG | TRNDKQGVG02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Raichur Mantralayam Road | Raichur | 10292 | 2026-04-09 | 2026-04-09 |  | 15 | 2026-04-24 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JUNE 25
TRTRSD16364 | 1058 |  | 9410 | NFL6 | TRNDNNFL600 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Nizamabad RIL Mall | Nizamabad | 10066 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16365 | 1059 |  | TLU9 | QOA0 | TEXPNQOA002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Metpalle TST | Metpalle | 5000 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-10 | 2026-04-29 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | MAY 25
TRTRSZFO16366 | 1060 |  | TDU4 | NQ79 | TEXPVNQ7903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Vadanapally TST | Vadanapally | 7000 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-12 | 2026-05-12 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16367 | 1061 |  | TP64 | ND61 | TRNDTND6103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Ottanchathiram TST | Ottanchathiram | 4000 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16368 | 1062 |  | TSZ7 | Q2TM | TEXPKQ2TM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Mulbagal TST | Mulbagal | 6784 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16369 | 1063 |  | TSX1 | Q2SO | TEXPAQ2SO03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Narsipatnam Santhi nagar | Narsipatnam Santhi Nagar | 7621 | 2026-03-27 | 2026-03-27 |  | 15 | 2026-04-11 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-4 EPC | 2026-06-01 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16370 | 1064 |  | TGY5 | QXV1 | TEXPAQXV101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Piduguralla TST | Piduguralla | 7971 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-10 | 2026-04-21 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSD16371 | 1065 |  | TFR5 | QYU6 | TEXPNQYU601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Bodhan Mandal TST | Bodhan Mandal | 6500 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-10 | 2026-04-29 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-05 | 2026-05-05 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | DECEMBER 25
TRTRSZFO16372 | 1066 |  | TP20 | ND42 | TRNDTND4202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Gobichettipalayam TST | Gobichettipalayam | 7000 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSZFO16373 | 1067 |  | TTC4 | Q2UM | TEXPVQ2UM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kodakara TST | Kodakara | 6311 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16374 | 1068 |  | TL88 | NWM9 | TRNDANWM902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Chirala TST | Chirala | 4597 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-05-10 | 2026-05-06 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-05 | 2026-05-05 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16375 | 1069 |  | TSX8 | Q2ST | TEXPAQ2ST01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Malikipuram TST | Malikipuram | 4277 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-04-30 | 2026-04-28 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16376 | 1070 |  | TIR7 | QXQ6 | TEXPKQXQ602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bhatkal TST | Bhatkal | 9750 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-23 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16377 | 1071 |  | TLB5 | QGT0 | TWIWTQGT001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Coimbatore TW VG Cmplx | Coimbatore | 2200 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-05-10 | 2026-05-08 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZFO16378 | 1072 |  | T9XT | QXOT | TWIWTQXOT01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Coimbatore TW Fun Republic Mall | Coimbatore | 1797 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16379 | 1073 |  | TX9B | QJTT | TWIWKQJTT02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TW Singasandra | Bangalore | 2162 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-10 | 2026-04-11 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16380 | 1074 |  | TWQV | Q6J4 | TJNRKQ6J402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TJ Seeta Circle Srinivas Nagar | Bangalore | 2001 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-04-14 | 2026-04-04 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16381 | 1075 |  | T75E | QKBD | TMANKQKBD02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TM Devasandra Village KR Puram Hobli | Bangalore | 1642 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-24 | 2026-04-28 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16382 | 1076 |  | TWSH | Q6N5 | TWIWTQ6N501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai TW Paruthipattu Avadi Main Road | Chennai | 1933 | 2026-03-26 | 2026-03-26 |  | 15 | 2026-04-10 | 2026-04-10 | 2026-04-07 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | APRIL 25
TRTRSZFO16383 | 1077 |  | TTF1 | Q5PU | TWIWTQ5PU01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Coimbatore TW Race Course Road | Coimbatore | 1880 | 2026-03-28 | 2026-03-28 |  | 15 | 2026-04-12 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16384 | 1078 |  | TMA6 | QQJ5 | TJNRTQQJ501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai TJ Forum Mal | Chennai | 1783 | 2026-03-30 | 2026-03-30 |  | 15 | 2026-04-14 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JUNE 25
FLDHKC16385 | 1079 |  | TATF | TATF | DH-ZIVA-419-RJ-TATF | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Rajasthan |  |  | Zivame Capital Mall Bhiwadi,Unit / Shop No 40 & 41 On Gr Floor, Riico Industrial Area Dist Alwar | Bhiwadi | 494 | 2026-03-11 | 2026-03-11 | 0 | 25 | 2026-04-05 | 2026-04-05 | 2026-04-07 | EPC Ready | 100% |  | 2026-04-20 | 2026-04-07 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRRT16386 | 1080 |  | T33J | QA7N | TFITJQA7N02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Srinagar Sanat Nagar Rawalpora By Pass Srinagar | Sriniagar | 11430 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-04-24 | 2026-04-26 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
SBREBK16388 | 1081 |  | FR60 | Q4PE | RSBZGQ4PE03 | C. Grocery | Grocery | Smart Bazar - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Gujarat |  | Mayurdhwajsinh Solanki | Alpha One Mall Resize Phase 2 | Ahmedabad | 37902 | 2026-04-03 | 2026-04-03 |  | 35 | 2026-05-08 | 2026-06-05 |  | WIP | 85% |  |  |  |  | FY 26-27 |  | MAY 26 PLANNED
TRTRSZFO16390 | 1082 |  | TG0D | QXQA | TFITTQXQA02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Ramanathapuram Patinamkathan Mandapam NH Rd | Ramanathapuram | 10516 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16391 | 1083 |  | TSQ0 | Q2PL | TFITKQ2PL03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Madikeri Coorg Centre Karnangeri Vlg | Madikeri | 11922 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRSZFO16392 | 1084 |  | TP78 | ND71 | TRNDVND7102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Ettumanoor TST | Ettumanoor | 9051 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-04 | 2026-05-04 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JUNE 25
TRTRSZFO16393 | 1085 |  | T0W2 | Q2PJ | TFIT8Q2PJ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Pondicherry Reddiyarpalayam | Pondicherry | 12171 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSZFO16394 | 1086 |  | TX4K | QGWQ | TEXPTQGWQ03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Arupukottai TST | Arupukottai | 6717 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAK16395 | 1087 |  | 5793 | NP24 | TRNDTNP2405 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | KanchipuramVellal | Kanchipuram | 13161 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAK16396 | 1088 |  | TC84 | NGY5 | TRNDTNGY501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai Perambalur | Perambalur | 7650 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | SEPTEMBER 25
TRTRAK16397 | 1089 |  | 5765 | NP12 | TRNDKNP1202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Bijapur Padmavathi | Bijapur | 10701 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | APRIL 25
TRTRSZFO16398 | 1090 |  | TU88 | NKW1 | TRNDTNKW103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | ATTUR TST | Attur | 6000 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSD16399 | 1091 |  | TFN1 | QYW8 | TEXPAQYW801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Pulivendula TST | Pulivendula | 5430 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-10 | 2026-05-05 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-05 | 2026-05-05 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16400 | 1092 |  | TPK9 | Q0MO | TEXPAQ0MO02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Pileru TST | Pileru | 4379 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-10 | 2026-05-08 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-12 | 2026-05-12 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRSZFO16401 | 1093 |  | TDE2 | NQK3 | TFITKNQK302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Ranibennur Old PB Road | Ranibennur | 13089 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16402 | 1094 |  | T9HK | QWAR | TFITKQWAR03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bidar Gumpa Road | Bidar | 11329 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | MAY 25
TRTRSZFO16403 | 1095 |  | TFZ5 | QYM3 | TEXPKQYM301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Malur TST | Malur | 4239 | 2026-03-29 | 2026-03-29 |  | 15 | 2026-04-13 | 2026-05-31 | 2026-05-30 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | MAY 25
TRTRSZFO16404 | 1096 |  | TN75 | NC73 | TRNDTNC7302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Valliyur TST | Valliyur | 5006 | 2026-03-31 | 2026-03-31 |  | 15 | 2026-04-15 | 2026-05-10 | 2026-05-22 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-26 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | AUGUST 25
TRTRSD16405 | 1097 |  | TY65 | NB27 | TRNDANB2704 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Badvel TST | Badvel | 4943 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-10 |  | On Hold |  | Cycle-4 EPC |  |  |  | FY 26-27 |  |  |  | DECEMBER 25
TRTRSD16406 | 1098 |  | TSW8 | Q2SK | TEXPAQ2SK01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Gudur TST | Gudur | 7943 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-30 | 2026-04-30 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16407 | 1099 |  | TW38 | NNU5 | TRNDVNNU502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thalayolaparambu TST | Thalayolaparambu | 5754 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16408 | 1100 |  | TKU1 | QDJ0 | TEXPAQDJ001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kuppam TST | Kuppam | 4500 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-18 | 2026-05-18 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRAK16409 | 1101 |  | TX8Q | Q2WB | TWIWKQ2WB03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Nagarbhavi TW Bangalore | Nagarbhavi | 2055 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-04-30 | 2026-05-05 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-05 | 2026-05-05 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRBK16410 | 1102 |  | TFV1 | QY09 | TFITEQYO901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Madhya Pradesh |  |  | Shahdol K Square Bhudhar Road | Shahdol | 8306 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-04-18 | 2026-04-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-04-18 | 2026-04-18 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZFO16411 | 1103 |  | TFM9 | QYW6 | TEXPTQYW601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tenkasi TST | Tenkasi | 7099 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16412 | 1104 |  | TP81 | ND74 | TEXPTND7401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tirupathur TST | Tirupathur | 6110 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16413 | 1105 |  | 5760 | NP09 | TRNDONP0902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Jharsguda SarbahalRd | Jharsuguda | 8017 | 2026-04-03 | 2026-04-03 |  | 15 | 2026-04-18 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | SEPTEMBER 25
TRTRAK16414 | 1106 |  | TSP0 | Q2PF | TFITTQ2PF02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Karaikudi TVS Showroom Green Road | Karaikudi | 10943 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16415 | 1107 |  | TQ24 | ND97 | TRNDTND9703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Udumalaipettai TST | Udumalaipettai | 5350 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | SEPTEMBER 25
TRTRSZFO16416 | 1108 |  | TP63 | ND60 | TEXPTND6001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Arani TST | Arani | 5973 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | SEPTEMBER 25
TRTRSD16417 | 1109 |  | TZ93 | NAH8 | TRNDONAH801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Subrnpur Bolangir Rd | Subarnapur | 12223 | 2026-04-03 | 2026-04-03 |  | 15 | 2026-04-18 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSD16418 | 1110 |  | TS04 | QUS3 | TEXPAQUS301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vinukonda TST | Vinukonda | 5390 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZFO16419 | 1111 |  | TXV5 | Q9J4 | TEXPTQ9J402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Harur TST Thiru Vi Ka Nagar Bus Stop | Harur | 7189 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
SMPTKC16435 | 1112 |  | TBH2 | QHKL | SMPTGQHKL00 | C. Grocery | Grocery | Smart Point | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | West | KC | Gujarat |  |  | Airforce Station , Bhuj | Bhuj | 2297 | 2026-04-27 | 2026-05-01 | 21 |  | 2026-05-22 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% |  | PENDING | 2026-06-01 | Launched | FY 26-27 |  | MAY 26 PLANNED | JUNE 26
GRREBK16436 | 1113 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Chattisgarh |  |  | Bilaspur, CG | Bilaspur | 33733 | [7 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27
SMRTRT16437 | 1114 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Shanmuga Rajan | Ayush Shetiye | NSO | North | RT | Uttar Pradesh |  |  | Gaddopur Phaphamau | PRAYAGRAJ | 30,713 | [7 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27
AZCORT16438 | 1115 |  | TBMG | QHNM | TAZO2QHNM00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Azorte Conversion | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Punjab |  | Sanjay Singh | SBZ to Azorte Elante Mall | Chandigarh | 13620 | 2026-04-01 | 2026-04-01 | 60 | 15 | 2026-06-15 | 2026-06-30 |  | WIP | 50% |  |  |  |  | FY 26-27 |  | JUNE 26 PLANNED
TRTRAK16439 | 1116 |  | TCG4 | NAN7 | TRNDKNAN704 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Karwar MM Rd | Karwar | 9200 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | DECEMBER 25
TRTRSZ FO16440 | 1117 |  | TWPR | Q6F9 | TFITKQ6F902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bagalkot Kalidasa Circle | Bagalkot | 13839 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16441 | 1118 |  | T820 | NGO2 | TRNDKNGO202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Tumkur Sira Gate | Tumkur | 9000 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSZ FO16442 | 1119 |  | TPW9 | Q0TG | TEXPKQ0TG02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Sarjapura TST | Sarjapura | 10757 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-10 | 2026-05-08 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16443 | 1120 |  | TQ48 | NE12 | TRNDKNE1202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Sindhanur TST | Sindhanur | 5800 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16444 | 1121 |  | TM30 | NC12 | TRNDVNC1202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kozhikode Ace Atria | Kozhikode | 10441 | 2026-04-03 | 2026-04-03 |  | 15 | 2026-04-18 | 2026-04-30 | 2026-05-06 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-05 | 2026-05-05 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | NOVEMBER 25
TRTRSZ FO16445 | 1122 |  | T88O | QOTV | TFITKQOTV02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Robertsonpete Soorajmull circle | Robertsonpete | 8838 | 2026-04-18 | 2026-04-18 |  | 15 | 2026-05-03 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | MAY 26 PLANNED |  | OCTOBER 25
TRTRSZ FO16446 | 1123 |  | TS06 | QUS5 | TRNDKQUS502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | SIRSI TST | Sirsi | 5294 | 2026-04-05 | 2026-04-05 |  | 15 | 2026-04-20 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | JUNE 26
TRTRAK16447 | 1124 |  | TI68 | NWF1 | TRNDTNWF102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Hosur Sipcot Housing | Hosur | 14693 | 2026-04-02 | 2026-04-02 |  | 15 | 2026-04-17 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRAK16448 | 1125 |  | TKH3 | QAV5 | TFITKQAV502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Kolar MG Road | Kolar | 10546 | 2026-04-07 | 2026-04-07 |  | 15 | 2026-04-22 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | SEPTEMBER 25
TRTRAK16449 | 1126 |  | T782 | NGN2 | TRNDTNGN203 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Tirupur Avinashi Rd | Tirupur | 14120 | 2026-04-03 | 2026-04-03 |  | 15 | 2026-04-18 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16450 | 1127 |  | TWPW | Q6G5 | TFITKQ6G502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bhadravati Trends Bhadravati | Bhadravati | 10269 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | SEPTEMBER 25
TRTRSZ FO16451 | 1128 |  | TL37 | NHG6 | TRNDKNHG604 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Jamakhandi TST | Jamakhandi | 8205 | 2026-04-01 | 2026-04-01 |  | 15 | 2026-04-16 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | JUNE 25
TRTRSZ FO16452 | 1129 |  | TY58 | NB22 | TRNDTNB2201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Kambam TST | Kambam | 5800 | 2026-04-03 | 2026-04-03 |  | 15 | 2026-04-18 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | SEPTEMBER 25
TRTRSZ FO16453 | 1130 |  | TJL7 | QWK1 | TEXPKQWK101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Anekal TST | Anekal | 6380 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRTRSZ FO16454 | 1131 |  | TDO8 | NE96 | TEXPKNE9602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Lingasugur TST | Lingasugur | 5000 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-10 | 2026-05-11 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16455 | 1132 |  | TX1M | QG2Q | TFITVQG2Q01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Chalappuram Hindustan Prakashan Trust | Chalappuram | 11612 | 2026-04-03 | 2026-04-03 |  | 15 | 2026-04-18 | 2026-05-10 | 2026-05-23 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-25 | 2026-05-25 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16456 | 1133 |  | TX8A | QCBK | TEXPVQCBK02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Perambra TST Hill Pearl Calicut Main Rd | Perambra | 9608 | 2026-04-07 | 2026-04-07 |  | 15 | 2026-04-22 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-15 | 2026-05-15 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16457 | 1134 |  | TEU4 | QZP8 | TEXPVQZP803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Mukkam TST | Mukkam | 7450 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-10 | 2026-05-14 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-25 | 2026-05-25 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRTRSZ FO16458 | 1135 |  | TV95 | NNH7 | TRNDKNNH702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Gangavathi TST | Gangavathi | 5297 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-04-19 | 2026-04-21 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | JULY 25
TRTRSZ FO16459 | 1136 |  | TU86 | NKV3 | TRNDKNKV303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Channarayapatna TST | Channarayapatna | 7945 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | APRIL 25
TRTRAK16460 | 1137 |  | TX44 | NYF2 | TRNDKNYF202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Moodubidiri, MUDBIDRI, Mangalore TST | Mangalore | 4406 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSZ FO16461 | 1138 |  | TWTL | Q6Q9 | TEXPKQ6Q902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Pavagada TST | Pavagada | 6831 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16462 | 1139 |  | TWSG | Q6N4 | TWIWVQ6N401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kozhikode TW Gokulam Mall | Kozhikode | 2359 | 2026-04-03 | 2026-04-03 |  | 15 | 2026-04-18 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% | Cycle-4 EPC | 2026-04-21 | 2026-04-21 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZ FO16463 | 1140 |  | TWRV | Q6M3 | TMANKQ6M302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore TM Akshaynagar Arekere | Bangalore | 2225 | 2026-04-04 | 2026-04-04 |  | 15 | 2026-04-19 | 2026-04-19 | 2026-04-11 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | NOVEMBER 25
TRTRAK16464 | 1141 |  | TTF4 | Q2VQ | TWIWKQ2VQ02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Bangalore TW BEML Layout RR Nagar | Bangalore | 2721 | 2026-04-07 | 2026-04-07 |  | 15 | 2026-04-22 | 2026-05-10 | 2026-05-13 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-13 | 2026-05-13 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | AUGUST 25
TRTRSZ FO16465 | 1142 |  | TWQO | Q6I5 | TFITKQ6I504 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Manipal Udupi Trends | Manipal-Udupi | 13247 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | SEPTEMBER 25
TRTRSZ FO16466 | 1143 |  | 1973 | NF94 | TRNDKNF9401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bellary Teja Complex | Bellary | 6786 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16467 | 1144 |  | TFM7 | QYW4 | TEXPKQYW401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Kushalnagar TST | Kushalnagar | 5200 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16468 | 1145 |  | TCV3 | NQE6 | TFITKNQE602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Yadagir Chittapur Rd | Yadagir | 7450 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRAK16469 | 1146 |  | TER5 | QZZ6 | TWIWKQZZ602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Bangalore TW JP Nagr | Bangalore | 1492 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
GRDSKC16470 | 1147 | DS-DL-00340 | TBPE | QHPK | DARKDQHPK00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Arun Bhati | Rohini Sector 31 | Delhi | 3306 | 2026-04-06 | 2026-04-15 | 15 |  | 2026-04-30 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% |  | PENDING | 2026-05-31 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
GRDSKC16471 | 1148 | DS-DL-00335 | TBN5 | QHON | DARKDQHON00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  | Arun Bhati | Dilshad colony, Seemapuri Delhi | Delhi | 1608 | 2026-04-03 | 2026-04-16 | 15 |  | 2026-05-01 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% |  | PENDING | 2026-05-24 | Launched | FY 26-27 |  | MAY 26 PLANNED | MAY 26
DIGSBK16492 | 1149 |  | TBO4 | QHPI | CDITGQHPI00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Gujarat |  | Anil Nakum | CDIT CAROLINA MALL NAVSARI GJ | Navsari | 7104 | 2026-04-06 | 2026-04-10 | 35 |  | 2026-05-15 | 2026-06-05 |  | WIP | 90% |  |  |  |  | FY 26-27 |  | MAY 26 PLANNED |  | DECEMBER 25
DIGCSZ FO16493 | 1150 |  | TC6G | QV5K | CDITKQV5K00 | A. Consumer Electronics & Jewels | Consumer Electronics | Compact Digital | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Karnataka |  | Mohammad Saddam Khan PMC | Kaikamba Bantwal | Bantwal | 4476 | 2026-04-27 | 2026-04-29 | 35 |  | 2026-06-03 | 2026-06-15 |  | WIP | 35% |  |  |  |  | FY 26-27 |  | JUNE 26 PLANNED
GRPRRT16475 | 1151 |  | TEU0 | QZP4 | SMRT9QZP402 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Punjab |  | Maninder Kahlon | SMT PB Kapurthala Walia Palace | Kapurthala | 14867 | 2026-04-12 | 2026-04-12 |  | 21 | 2026-05-03 | 2026-05-03 | 2026-05-22 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 |  | MAY 26 PLANNED | MAY 26 | JULY 25
GRPRRT16476 | 1152 |  | TY87 | NB47 | SMRTRNB4703 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Rajasthan |  | Navas Navab | SMT RJ Churu Shyam Cinema | Churu | 15706 | 2026-04-13 | 2026-04-13 |  | 21 | 2026-05-04 | 2026-05-04 | 2026-05-21 | EPC Ready | 100% |  | 2026-05-18 |  | YTL | FY 26-27 |  | MAY 26 PLANNED | MAY 26 | APRIL 25
GRPRRT16477 | 1153 |  | TNC6 | Q05Y | SMRT9Q05Y03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Punjab |  | Maninder Kahlon | SMT MKT PB Jalandhar Puda Multiplex | Jalandhar Puda | 34787 | 2026-04-12 | 2026-04-12 |  | 21 | 2026-05-03 | 2026-05-03 | 2026-05-21 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 |  | MAY 26 PLANNED | MAY 26 | APRIL 25
FLDHKC16494 | 1154 |  | 8024 | 8024 | DH-TRND-419-CG-8024 | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Chattisgarh |  | Abhay Srivastava | 8024 City Center Mall CG Trends | Raipur | 14957 | 2026-04-17 | 2026-04-17 |  | 25 | 2026-05-12 | 2026-05-12 | 2026-05-24 | EPC Ready | 100% |  | 2026-05-26 | 2026-05-24 | Launched | FY 26-27 |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16495 | 1155 |  | T536 | NUV3 | TRNDKNUV303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Davangere AVK Rd | Davangere | 10000 | 2026-04-11 | 2026-04-11 |  | 15 | 2026-04-26 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSZ FO16496 | 1156 |  | TX6P | QA3W | TEXPVQA3W03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | TRIO Mall TST Taliparamba | Taliparamba | 10708 | 2026-04-14 | 2026-04-14 |  | 15 | 2026-04-29 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | AUGUST 25
TRTRSZ FO16497 | 1157 |  | TN08 | NC40 | TRNDVNC4004 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Talasery Harbour Mal | Thalassery | 12060 | 2026-04-14 | 2026-04-14 |  | 15 | 2026-04-29 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16498 | 1158 |  | TWWT | Q6Z6 | TEXPVQ6Z602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kayamkulam TST R Mall K P Road | Kayamkulam | 11963 | 2026-04-14 | 2026-04-14 |  | 15 | 2026-04-29 | 2026-05-10 | 2026-05-21 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16499 | 1159 |  | R215 | NGA6 | TRNDKNGA601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Udupi City Centre | Udupi | 7505 | 2026-04-12 | 2026-04-12 |  | 15 | 2026-04-27 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16500 | 1160 |  | T826 | NGO7 | TRNDVNGO700 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pathanamt Kunithotat | Pathanamthitta | 7032 | 2026-04-10 | 2026-04-10 |  | 15 | 2026-04-25 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-24 | 2026-05-24 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | DECEMBER 25
TRTRSZ FO16501 | 1161 |  | TJZ1 | QAG9 | TEXPKQAG902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Chandapura TST | Chandapura | 8500 | 2026-04-12 | 2026-04-12 |  | 15 | 2026-04-27 | 2026-05-10 | 2026-05-09 | EPC Ready | 100% | Cycle-3 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16502 | 1162 |  | T86A | QOQS | TFITVQOQS01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kannur Secura Mall | Kannur | 9615 | 2026-04-14 | 2026-04-14 |  | 15 | 2026-04-29 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16503 | 1163 |  | FR2S | QEXM | TRNFVQEXM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kollam TV FBB Kollam | Kollam | 11704 | 2026-04-14 | 2026-04-14 |  | 15 | 2026-04-29 | 2026-05-31 |  | WIP |  | Cycle-3 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16504 | 1164 |  | TCQ8 | NQA7 | TRNDVNQA701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thiruvalla Edmanikal | Thiruvalla | 18339 | 2026-04-12 | 2026-04-12 |  | 15 | 2026-04-27 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16505 | 1165 |  | T501 | NGB3 | TRNDKNGB302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Karnataka |  |  | Shimoga City Centre | Shimoga | 8500 | 2026-04-13 | 2026-04-13 |  | 15 | 2026-04-28 | 2026-05-31 |  | WIP |  | Cycle-2 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16506 | 1166 |  | TDZ1 | NY68 | TEXPVNY6803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Ranni TST | Ranni | 6325 | 2026-04-11 | 2026-04-11 |  | 15 | 2026-04-26 | 2026-05-10 | 2026-05-22 | EPC Ready | 100% | Cycle-3 EPC | 2026-05-25 | 2026-05-25 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16507 | 1167 |  | TCT2 | NQC6 | TRNDVNQC603 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | HARIPAD TST | Haripad | 5509 | 2026-04-10 | 2026-04-10 |  | 15 | 2026-04-25 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-25 | 2026-05-25 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16508 | 1168 |  | TL16 | NWK5 | TRNDKNWK504 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Puttur Madikkeri Rd | Puttur | 10500 | 2026-04-13 | 2026-04-13 |  | 15 | 2026-04-28 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16509 | 1169 |  | TBA0 | NAJ8 | TEXPKNAJ802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Channapatna TST | Channapatna | 6000 | 2026-04-09 | 2026-04-09 |  | 15 | 2026-04-24 | 2026-05-31 | 2026-06-02 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | JUNE 26
TRTRSZ FO16510 | 1170 |  | TXXF | Q9GF | TEXPVQ9GF02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Mannar TST Arikupuram Arcade | Mannar | 5535 | 2026-04-11 | 2026-04-11 |  | 15 | 2026-04-26 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | JUNE 26
TRTRSZ FO16511 | 1171 |  | TO38 | NC97 | TRNDKNC9703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Karkala TST | Karkala | 3600 | 2026-04-10 | 2026-04-10 |  | 15 | 2026-04-25 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
TRTRSZ FO16512 | 1172 |  | TIS3 | QXR3 | TEXPVQXR302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Varkala TST | Varkala | 5958 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-02 | 2026-05-02 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
TRTRSZ FO16513 | 1173 |  | TO83 | ND25 | TRNDVND2502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Anchal TST | Anchal | 5432 | 2026-04-08 | 2026-04-08 |  | 15 | 2026-04-23 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26
TRTRSZ FO16514 | 1174 |  | TEZ0 | QZG4 | TEXPVQZG402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pazhayangadi TST | Pazhayangadi | 3869 | 2026-04-14 | 2026-04-14 |  | 15 | 2026-04-29 | 2026-05-31 |  | WIP |  | Cycle-4 EPC |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
DIGSAS10469 | 1175 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Karnataka | Bengaluru |  | Yelahanka 2nd store - Bangalore (OPP Bata) | Bengaluru |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
DIGSAS14986 | 1176 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu |  |  | WGC Road, Tuticorin TN |  |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
FLDHAK13055 | 1177 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | East | AK | Telangana | Warangal |  | VRK Khammam | Khammam | 8244 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
TRFTAS13354 | 1178 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Tamil Nadu | Chennai | Chandra Mohan | VR Mall Chennai | Chennai |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP
GRREAS13391 | 1179 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Andhra Pradesh |  |  | Vizianagaram | Vizayanagaram |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
DIRFAS13559 | 1180 |  | 8943 | NEX1 | CDITTNEX104 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | South | SZ FO | Tamil Nadu | Coimbatore | Vignesh Ravichandran | Vishal Mall, Madurai | Madurai | 8220 | 2025-07-17 | 2025-07-17 | 0 | 120 | 2025-11-14 | 2025-12-07 | 2026-02-17 | EPC Ready Previous FY | 100% |  | PENDING |  | YTL | FY 25-26 | AOP
DIGSAS11667 | 1181 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu | Coimbatore |  | Vellakinaru Pirivu, MTP road, Coimbatore | Coimbatore |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
DIGSAS12889 | 1182 |  | TC0R | QV0R | CDITKQV0R00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Karnataka | Bangalore | Muddasir | Vartur ( Gunjur ) - Opposite to CROMA - Bangalore | Bengaluru | 8251 | 2026-04-10 | 2026-04-12 | 35 |  | 2026-05-17 | 2026-06-07 |  | WIP | 65% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED
JICEBK11518 | 1183 |  |  |  |  | J. Jio Business | Jio Business | Jio Centre | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Gujarat | Surat |  | Varachha mall, Surat | Surat |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
MIRERT14584 | 1184 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | North | RT | Delhi & NCR |  |  | UL - Sector 14, Gurgoan | Gurgaon | 3907 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FLDHSD13051 | 1185 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | East | AK | Assam & NE |  |  | Udharband TST | Udharband | 5932 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
TRD3SD13689 | 1186 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar | Patna |  | UB Tower, Muzaffarpur (Full Renovation) | Patna |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
FLDHAK12793 | 1187 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | East | AK | Bihar |  |  | TST Centretainment Complex, Forbesganj | Forbesganj | 7200 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
FLDHAK13028 | 1188 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Karnataka | Bengaluru |  | Trends, Vijaynagar, Bengaluru, KA | Bengaluru | 13246 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
TRFTAS13353 | 1189 |  | 8263 | NDM4 | FOOTTNDM401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Madurai | Hari Bhaskar PMC | Trends footwear-Renovation - Vishaal De Mall, Madurai | Madurai | 4302 | 2026-03-04 | 2026-03-12 | 0 | 65 | 2026-05-16 | 2026-06-10 |  | WIP | 65% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED |  | APRIL 25
TRD3SD11583 | 1190 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | TRENDS 3.0 Renovation-Medinipur Khudiramrd | Medinipur |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3SD11582 | 1191 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal | Kolkata |  | Trends 3.0 Renovation-Ideal Regency,Kolkata | Kolkata |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3SD11647 | 1192 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal | Kolkata | Nilava Choudhury | Trends 3.0 Renovation-Axis Mall Kolkata | Kolkata |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3AS11648 | 1193 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala | Kozhikode |  | Trends 3.0 Renovation(Partial)-Ace Atria, Kozhikode | Kozhikode |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3AS11471 | 1194 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Chennai |  | Trends 3.0 Renovation - TN-Chennai-VR Mall-1st & 2nd Flr- Renovation. | Chennai |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3AS11472 | 1195 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka | Bengaluru |  | Trends 3.0 Renovation - KA-Blr-Commercial street-Basement-GF-1st -2nd-Terrace Floor | Bengaluru |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
TRD3AS13779 | 1196 |  | TBCN | QHEY | TRNDTQHEY00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends 3.0 | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Tamil Nadu | Chennai | Senthil Muthhaiah | Trends 3.0 - Pursaiwakkam 1/PURASAIVAKKAM/ Purusaiwakkam/ Purasawalkam High Road, Chennai, TN | Chennai | 10192 | 2026-01-19 | 2026-01-31 | 45 |  | 2026-03-17 | 2026-04-30 | 2026-05-04 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
TRD3SD13487 | 1197 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa | Bhubaneshwar |  | TRENDS 2.O to 3.O Renovation - Z Tower Patia, Bhubaneswar (Full Renovation) | Bhubaneshwar |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3AS13515 | 1198 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Chennai |  | TRENDS 2.O to 3.O Renovation - VR Mall, Chennai | Chennai |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3AS13360 | 1199 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Madurai |  | TRENDS 2.O to 3.O Renovation - Vishaal Mall, Madurai | Madurai |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3AS13707 | 1200 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | TRENDS 2.O to 3.O Renovation - Thillai Nagar, Trichy | Trichi |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3AS13535 | 1201 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | TRENDS 2.O to 3.O Renovation - RIL Mall, Salem (Full Renovation) | Salem |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3AS13706 | 1202 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | TRENDS 2.O to 3.O Renovation - Providence Mall, Pondichery (Full Renovation) | Pondichery |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13490 | 1203 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Chennai |  | TRENDS 2.O to 3.O Renovation - PMC, Chennai (Full Renovation) | Chennai |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13705 | 1204 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | TRENDS 2.O to 3.O Renovation - PLA Complex, Karur (Full Renovation) | Karur |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13527 | 1205 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | TRENDS 2.O to 3.O Renovation - Padmavathi, Bijapur (Full Renovation) | Bijapur |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13536 | 1206 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | TRENDS 2.O to 3.O Renovation - O Mall (Full Renovation) | Kochin |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13323 | 1207 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka | Bengaluru |  | TRENDS 2.O to 3.O Renovation - Mantri Mall, Bangalore, KA | Bengaluru |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3SD13516 | 1208 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal | Kolkata |  | TRENDS 2.O to 3.O Renovation - LIC Nehru, Kolkata (Full Renovation) | Kolkata |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3SD13525 | 1209 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRENDS 2.O to 3.O Renovation - L&T Mall, Punjagutta, Hyderabad (Full Renovation) | Hyderabad |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13330 | 1210 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala | Thiruvananthapuram |  | TRENDS 2.O to 3.O Renovation - Kowdiar, Trivandrum | Thiruvananthapuram |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3AS13537 | 1211 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka | Bengaluru |  | TRENDS 2.O to 3.O Renovation - Kankpur Road, Bangalore (Full Renovation) | Bengaluru |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3SD13533 | 1212 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar | Patna |  | TRENDS 2.O to 3.O Renovation - Kankarbagh, Patna (Full Renovation) | Patna |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13481 | 1213 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | TRENDS 2.O to 3.O Renovation - Kamla Nagar, Anantpur (Full Renovation) | Anantapur |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3AS13331 | 1214 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | TRENDS 2.O to 3.O Renovation - K Mall, Kollam | Kollam |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3SD13346 | 1215 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRENDS 2.O to 3.O Renovation - JP Blaza, Maithry Nagar, Hyderabad | Hyderabad |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
TRD3SD13518 | 1216 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal | Kolkata |  | TRENDS 2.O to 3.O Renovation - JN/ Junction Mall, Barasat, Kolkata (Full Renovation) | Kolkata |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
TRD3SD13480 | 1217 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRENDS 2.O to 3.O Renovation - Habsiguda, Hyderabad (Full Renovation) | Hyderabad |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | OCTOBER 25
TRD3AS13332 | 1218 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala | Cochin |  | TRENDS 2.O to 3.O Renovation - Grand Mall, Thrissur | Thrissur |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
TRD3SD13701 | 1219 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRENDS 2.O to 3.O Renovation - Forum Mall, Kukatpally, Hyderabad (Full Renovation) | Hyderabad |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
TRD3AS13340 | 1220 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa | Cuttack |  | TRENDS 2.O to 3.O Renovation - Dolamundi, Cuttack | Cuttack |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
TRD3AS13694 | 1221 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | TRENDS 2.O to 3.O Renovation - Deviprasad Central, Tumkur (Full Renovation) | Tumkur |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | DECEMBER 25
TRD3SD13367 | 1222 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal | Kolkata |  | TRENDS 2.O to 3.O Renovation - DCN Mall, Kolkata | Kolkata |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3SD13368 | 1223 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | TRENDS 2.O to 3.O Renovation - Curzon Residency, Burdwan | Burdwan |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3AS13307 | 1224 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh | Vishakhapatnam |  | TRENDS 2.O to 3.O Renovation - CMR, Vizag (Full Renovation) | Vishakhapatnam |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRD3SD13517 | 1225 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal | Silliguri |  | TRENDS 2.O to 3.O Renovation - City Centre Mall, Siliguri | Siliguri |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13359 | 1226 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Chennai |  | TRENDS 2.O to 3.O Renovation - Chrompet, Chennai | Chennai |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3SD13712 | 1227 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | TRENDS 2.O to 3.O Renovation - Chandra Kamala Apartment, Khudiram Bose Road, Midnapore (Full Renovation) | Midnapore |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
TRD3SD13345 | 1228 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRENDS 2.O to 3.O Renovation - Centrum, Hyderabad | Hyderabad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
TRD3AS13704 | 1229 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | TRENDS 2.O to 3.O Renovation - Bypass Road, Ponmeni, Madurai (Full Renovation) | Madurai |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13324 | 1230 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka | Bengaluru |  | TRENDS 2.O to 3.O Renovation - BSR Complex, Kammanahalli, Bangalore | Bengaluru |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13489 | 1231 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Coimbatore |  | TRENDS 2.O to 3.O Renovation - Brookefield, Coimbatore (Full Renovation) | Coimbatore |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3AS13485 | 1232 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | TRENDS 2.O to 3.O Renovation - Bijapur (Full Renovation) | Bijapur |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3SD13370 | 1233 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal | Kolkata |  | TRENDS 2.O to 3.O Renovation - Avani, Kolkata | Kolkata |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
TRD3SD13488 | 1234 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRENDS 2.O to 3.O Renovation - AS Rao Nagar, Hyderabad (Full Renovation) | Hyderabad |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
TRD3SD13526 | 1235 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar | Patna |  | TRENDS 2.O to 3.O Renovation - Ambition Sapphire, Bihar, Patna (Full Renovation) | Patna |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
TRD3AS13361 | 1236 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Chennai |  | TRENDS 2.O to 3.O Renovation - Ambattur, Chennai | Chennai |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3AS13310 | 1237 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | TRENDS 2.O to 3.O Renovation - Airport Byepass Road, Lakshmi Puram Cricle, New Indira Nagar, Tirupati | Tirupati |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
TRD3SD13713 | 1238 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE | Guwahati |  | TRENDS 2.O to 3.O Renovation - Star City, Guwahati, Assam (Full Renovation) | Guwahati |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | DECEMBER 25
FLDHAK14462 | 1239 |  | TG9B | TG9B | DH-TGAP-419-KA-TG9B | B. Fashion & Lifestyle | Trends & Allied Formats (Part B) | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Karnataka |  |  | Trends Bhartiya City Mall | Bengaluru | 15626 | 2026-05-08 | 2026-05-08 | 0 | 25 | 2026-05-31 | 2026-05-31 | 2026-05-11 | EPC Ready | 100% |  | 2026-05-12 | 2026-05-11 | Launched | FY 26-27 | AOP | MAY 26 PLANNED | MAY 26 | JUNE 25
TRRFSD10768 | 1240 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRDSRS_TG_HYDERABAD_DSL VIRTUE MALL | Hyderabad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | OCTOBER 25
TRRFSD10769 | 1241 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | TRDSRS_TG_HYDERABAD_AMR PLANET_MOULALI | Hyderabad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
DIGSSD10459 | 1242 |  | T1BZ | QG7M | CDITWQG7M00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | West Bengal | Kolkata | Shukdev Dey | TN Mukherjee Road, Dankuni | Kolkata | 7820 | 2025-04-20 | 2025-04-22 | 35 | 300 | 2026-03-23 | 2026-03-31 | 2026-03-31 | EPC Ready Previous FY | 100% |  | OTHER ISSUES |  | YTL | FY 25-26 | AOP |  |  | MAY 25
SMRTAS13402 | 1243 |  | TAIK | QFVQ | SMRTTQFVQ00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu | Coimbatore | Vetrivel K | Tiruppur Road, Kottampatti, Pollachi | Pollachi | 25401 | 2026-01-13 | 2026-01-27 | 35 |  | 2026-03-03 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% |  | PENDING | 2026-04-30 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
SEVEBK11345 | 1244 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai |  | Times Square - Stall 1 | Mumbai | 251 |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
GRDSAK14694 | 1245 | DS-TN-00075 | TBGC | QHIM | DARKTQHIM00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu | Chennai | Ganesh B | Thiruverkadu | Chennai | 2413 | 2026-04-06 | 2026-04-10 | 15 |  | 2026-04-25 | 2026-05-12 | 2026-05-12 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26 | JULY 25
GRDSAK14697 | 1246 | DS-TN-00073 |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu |  |  | Thiruvalluvar Street | Coimbatore | 2310 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
YOTHSD13530 | 1247 |  |  | QT3F | TYOUBQT3F00 | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Bihar | Patna |  | The Sun Square, Kankerbagh, Patna | Patna | 6756 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
JESABK10426 | 1248 |  |  |  |  | A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels SAS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra | West Maharashtra |  | The Cube Shop No.1 Venus Corner, E Ward, Kolhapur | Kolhapur |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | MAY 25
SMRTAS10276 | 1249 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala | Thiruvananthapuram |  | Thayas Buildings, Medical college | Thiruvananthapuram |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
BLSSAS10296 | 1250 |  |  |  |  | C. Grocery | Grocery | Blushlace in Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala | Thiruvananthapuram |  | Thayas Buildings, Medical college | Thiruvananthapuram |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
FLDHAK14104 | 1251 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part B) | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | East | AK | Andhra Pradesh | Vishakhapatnam |  | TF Alcot Gardens | Rajamundry | 2589 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DIGSSD11666 | 1252 |  | TC3I | QV3T | CDITSQV3T00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | West Bengal |  |  | Tadong, Gangtok, Sikkim | Gangtok |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
YOTHAS13782 | 1253 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala | Kozhikode |  | Sulthan bathery PO,Wayanad , 673592 | Calicut |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRREAS13392 | 1254 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Andhra Pradesh |  |  | SS Mall, Proddutur | Proddutur |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
TRSTAS10763 | 1255 |  | TBH0 | QHKC | TRNDAQHKC00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends 3.0 | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Andhra Pradesh | Kadapa | Md Ifranuddin - PMC | SRIKALAHASTI | Tirupati | 8150 | 2026-02-07 | 2026-02-09 | 45 |  | 2026-03-26 | 2026-05-08 | 2026-05-16 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
GRDHAK10321 | 1256 |  | U771 | Q1KQ | DH-SMPT-451-AP-U771 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Andhra Pradesh |  | Sridhar Babu Gummadi | SP Kalyana Mandapam Property Naidup | Naidupeta | 3040 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHSD11985 | 1257 |  | U3EL | QDAG | DH-SMPT-451-WB-U3EL | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | West Bengal |  |  | SP WB Jiaganj Azimganj SBI Ban | Jiaganj-Azimganj | 1933 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHSD11970 | 1258 |  | U2IV | QAFS | DH-SMPT-451-WB-U2IV | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | West Bengal |  |  | SP WB Dharampur BSF Road Dhara | Dharampur | 3578 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | NOVEMBER 25
GRDHSD12008 | 1259 |  | U3FV | QDGM | DH-SMPT-451-WB-U3FV | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | West Bengal |  |  | SP Tamluk Mechada | Mecheda | 2909 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
GRDHAK11873 | 1260 |  | U2XH | QATZ | DH-SMPT-451-BH-U2XH | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Bihar | Gaya | Avinandan Kumar | SP Sumitra Complex Bodhgaya | Gaya | 5922 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHAK12521 | 1261 |  | U1SY | Q7HG | DH-SMPT-451-TN-U1SY | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | South | AK | Tamil Nadu |  |  | SP ROTN Nagercoil JPR Complex | Nagercoil | 5831 |  |  | 0 | 15 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
GRDHAK12637 | 1262 |  | U3BX | QCWK | DH-SMPT-451-TN-U3BX | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | South | AK | Tamil Nadu |  |  | SP ROTN Aranthangi MalarTirumanaMandapam | Aranthangi | 4952 |  |  | 0 | 15 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHAK12455 | 1263 |  | U28Y | QCPG | DH-SMPT-451-OR-U28Y | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Orissa |  |  | SP OD Balikuda A K Market Complex B | Balikuda | 4000 |  |  | 0 | 15 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | OCTOBER 25
GRDHAK12382 | 1264 |  | U189 | Q15P | DH-SMPT-451-KA-U189 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | South | AK | Karnataka | Bengaluru |  | SP KN Blr Ananthanagar | Bengaluru | 3150 |  |  | 0 | 15 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHAK11887 | 1265 |  | U1JN | Q5O6 | DH-SMPT-451-BH-U1JN | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Bihar | Patna | Rohin Chand | SP BH Samastipur Tajpur Patna | Samastipur | 3500 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
GRDHAK11885 | 1266 |  | U3EM | QDAH | DH-SMPT-451-BH-U3EM | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Bihar |  | Ranjit Sinha | SP BH Gopalganj Shiv Bachan Si | Gopalganj | 4277 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHAK11876 | 1267 |  | U3MJ | QD4J | DH-SMPT-451-BH-U3MJ | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Bihar | Patna | Rohin Chand | SP BH Adapur Agarwal Market | Adapur | 3800 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDHSD12170 | 1268 |  | U734 | Q1JG | DH-SMPT-451-WB-U734 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | West Bengal | Kolkata |  | SP Bakrahat Kokata | Kolkata | 2525 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
SMRTAS13875 | 1269 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Orissa |  |  | SMART, NEAR STATION SQUARE, BERHAMPUR, ODISHA | Berhampur |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTSD13928 | 1270 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Assam & NE | Guwahati |  | Smart Zoo Road - Existing V Mart Option | Guwahati |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTSD10382 | 1271 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | West Bengal |  |  | Smart WB Howrah, ULUBERIA | Uluberia |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS10385 | 1272 |  | TI5Q | QZNG | SMRTTQZNG00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu |  | Senthil Muthhaiah | Smart Tiruchengode Road, Sankari | Salem | 17077 | 2026-02-24 | 2026-03-09 | 35 |  | 2026-04-13 | 2026-05-13 | 2026-05-25 | EPC Ready | 100% |  | PENDING | 2026-05-31 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
SMRTSD13867 | 1273 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | West Bengal |  |  | Smart Sodepur W.B Rathindra Cinema Hall Option |  |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS13933 | 1274 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu |  |  | Smart Periyakulam | Periyakulam |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTSD10402 | 1275 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Assam & NE |  |  | Smart Imphal Churachandpur | Manipur |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
SMRTAS10280 | 1276 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Smart Bharannikkavu, Kollam | Bharannikkavu |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP
SBRESD10230 | 1277 |  | FRAU | Q4VD | RSBZQQ4VD03 | C. Grocery | Grocery | Smart Bazar - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand | Jamshedpur |  | Smart Bazaar - Jamshedpur-P & M Mall | Jamshedpur |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
SMRTAS10360 | 1278 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | SMART Ambalathara TVM | Ambalathara |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS13931 | 1279 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala | Thiruvananthapuram |  | Smart @ Venjarammoodu (Additional Network), Trivandrum | Thiruvananthapuram |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS10310 | 1280 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Smart @ Konni -Pathanamthitta | Pathanamthitta |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS10273 | 1281 |  | T8EN | QR3R | SMRTVQR3R00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  | Monish Raju PMC | Smart @ Kilimanoor TVM | Kilimanoor | 20844 | 2026-03-10 | 2026-03-14 | 35 |  | 2026-04-18 | 2026-05-12 | 2026-05-09 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26 | JUNE 25
SMRTAS13930 | 1282 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Smart @ Kattappana |  |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS14932 | 1283 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Karnataka |  |  | SMART - Colaco Trust Property, Bondel, Mangalore- no. 133/SMRT-11/UC6/Z2-52/Jun-24 | Bangalore |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
GRDHAK11938 | 1284 |  | TUI1 | Q3JP | DH-SMRT-451-TN-TUI1 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | South | AK | Tamil Nadu | Coimbatore |  | SKDS Kuniamuthur | Coimbatore | 12500 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
GRRESD15273 | 1285 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | Signature to Go Fresh Conversion - Utsa Complex | Kolkata |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | NON AOP |  |  | DECEMBER 25
DIGSRT14970 | 1286 |  | TBI6 | QHLK | CDITUQHLK00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Delhi & NCR | NCR | Irshad Ahmad | Shipra Mall, Ghaziabad, NCR | Ghaziabad | 7229 | 2026-01-17 | 2026-01-27 | 35 |  | 2026-03-03 | 2026-04-05 | 2026-04-03 | EPC Ready | 100% |  | 2026-04-27 | 2026-04-30 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
FLDHAK12813 | 1287 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Karnataka | Shimoga |  | Shimoga Avantara | Shimoga | 1005 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
CFVRSD14927 | 1288 | AP-SM-HYD-2063 | TBYJ | QIBJ | CENFNQIBJ00 | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana |  | Rupesh Dussa | SD Road Patny Center, Secunderabad | Hyderabad | 3135 | 2026-05-16 | 2026-05-18 | 35 |  | 2026-06-22 | 2026-06-22 |  | WIP | 30% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
GRDHAK15274 | 1289 |  | FR45 | Q4MP | RSBZKQ4MP08 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | South | AK | Karnataka |  |  | SBZ Banshankari (2nd floor surrender) | Bangalore | 27000 | 2026-04-23 | 2026-04-23 | 0 | 21 | 2026-05-14 | 2026-05-31 | 2026-06-02 | EPC Ready | 100% |  | PENDING | 2026-06-02 | Launched | FY 26-27 | NON AOP | MAY 26 PLANNED | JUNE 26 | DECEMBER 25
GRDHAK11898 | 1290 |  |  |  |  | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Bihar | Patna | Jitendra Kr. Gupta | SBZ - PATNA-EXHIBITION ROAD | Patna | 34150 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
CEDHSD13283 | 1291 |  | TUX0 | Q3WN | DH-CDIT-452-BH-TUX0 | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | East | AK | Bihar | Patna |  | SB Patna Sahib | Patna | 9221 |  |  | 0 | 21 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
CEDHAK13557 | 1292 |  | TSD9 | Q3KJ | DH-CDIT-452-TN-TSD9 | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | South | AK | Tamil Nadu | Chennai |  | SB Express Avenue Mall, Chennai | Chennai |  |  |  | 0 | 21 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
CFVRSD14929 | 1293 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana |  |  | Sattva Mall – Kavadiguda - Secunderabad | Hyderabad |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTSD13929 | 1294 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Bihar |  |  | SASARAM | Sasaram |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
EDAMSD14919 | 1295 |  | TL8M | TL8M | EDMMNTL8M00 | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana | Hyderabad | Mohammed Fazal Ur Rahman | Sarath City Capital Mall, Whitefields, HiTec City 3F-13 B, Third floor, Gachibowli, Kondapur | Hyderabad | 907 | 2026-01-30 | 2026-02-01 | 35 |  | 2026-03-08 | 2026-04-05 | 2026-04-06 | EPC Ready | 100% |  | 2026-04-09 | 2026-04-09 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
CSRTSD15265 | 1296 |  | T56A | QOXR | COVRNQOXR01 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad | Mohammed Fazal Ur Rahman | Cover Story Sarath City Capital Mall | Hyderabad | 1675 | 2026-02-11 | 2026-02-13 | 0 | 45 | 2026-03-30 | 2026-05-10 | 2026-05-18 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MARCH 26 PLANNED | MAY 26
GRDSAK14525 | 1297 | DS-KL-00019 | TBFB | QHHI | DARKVQHHI00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Kerala |  | Dijeesh P D | Santhipuram | Kochi | 2162 | 2026-01-30 | 2026-02-02 | 15 |  | 2026-02-17 | 2026-02-23 | 2026-02-23 | EPC Ready Previous FY | 100% | YTL | PENDING |  | YTL | FY 25-26 | AOP |  |  | APRIL 25
SMRTAS13932 | 1298 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu |  |  | Sankari Main Road | Tiruchengode |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
MIREBK15075 | 1299 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | Rupa Solitare, Koparkhairane - Relay Work | Koparkhairane | 847 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
CEDHKC13554 | 1300 |  | TR66 | NXM6 | DH-CDIT-452-MH-TR66 | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | West | KC | GMU | Mumbai |  | Runwal Anthurium, Mulund | Mumbai |  |  |  | 0 | 21 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
CVRFSD14965 | 1301 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana |  |  | RTC X Roads, Odeon Mall | Hyderabad |  |  |  | 15 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
TRD3SD13512 | 1302 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | RIL Mall, Ongole (Full Renovation) | Ongole |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
URBLKC14062 | 1303 |  |  |  |  | E. Other Business | Other Business | Furniture - Mid Premium Store (UL) | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Gujarat |  |  | RIL- Jamnagar Retail Mall | Jamnagar | 6000 |  |  | 35 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | AOP
DIGSBK14978 | 1304 |  | TL9X | QZ3E | CDITMQZ3E00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra |  |  | RD Rankala, Kolhapur, M | Kolhapur | 8045 | 2026-04-30 | 2026-05-02 | 35 |  | 2026-06-06 | 2026-06-15 |  | WIP | 25% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
SMRTAS10180 | 1305 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Rawther Building, Peroorkkada | Peroorkkada | 15539 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
BLSSAS10181 | 1306 |  |  |  |  | C. Grocery | Grocery | Blushlace in Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Rawther Building, Peroorkkada | Peroorkkada |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
SMRTAS13872 | 1307 |  | TF5K | QX9D | SMRTKQX9D00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Karnataka | Shimoga | Vengatesh Prabhu Gopalan | Rangikatte, Bhatkal | Bhaktal | 21895 | 2026-01-02 | 2026-01-07 | 35 |  | 2026-02-11 | 2026-02-28 | 2026-03-04 | EPC Ready Previous FY | 100% |  | PENDING | 2026-05-17 | Launched | FY 25-26 | AOP |  |  | SEPTEMBER 25
DIGCRT14988 | 1308 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Compact Digital | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Uttar Pradesh |  |  | Ramnath Colony,Civil Lines,Badaun |  |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | SEPTEMBER 25
DIGSSD14936 | 1309 |  | T9J8 | Q7J0 | CDITNQ7J000 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Telangana |  | Rupesh Dussa | Rajendra Nagar, Hyderabad | Hyderabad | 11191 | 2025-12-18 | 2025-12-20 | 35 | 9 | 2026-02-02 | 2026-02-11 | 2026-02-11 | EPC Ready Previous FY | 100% | YTL | PENDING |  | YTL | FY 25-26 | AOP |  |  | NOVEMBER 25
DIGSBK11549 | 1310 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU | Mumbai |  | R Mall, Thane | Thane |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | OCTOBER 25
SMRTSD13868 | 1311 |  | TBKR | QHMI | SMRT6QHMI00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Assam & NE | NE | Nirupam Das | Puna Hida, Ziro, Arunachal Pradesh | Ziro | 15240 | 2026-01-30 | 2026-02-05 | 35 |  | 2026-03-12 | 2026-04-20 | 2026-03-31 | EPC Ready Previous FY | 100% |  | PENDING | 2026-04-30 | Launched | FY 25-26 | AOP |  |  | MAY 25
GRDHAK14826 | 1312 |  |  |  |  | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | South | AK | Kerala |  |  | Pulleppady, Thammanam Road, DD Rush Ernakulam | Ernakulam |  |  |  | 0 |  |  |  |  | No EPC Work - F&F | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
TRMNSD13844 | 1313 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Man | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | West Bengal |  |  | PRM Centre Point Mall, Malda | Malda |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
GRDSAK14341 | 1314 | DS-TN-00024 | TBGD | QHIN | DARKTQHIN00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu | Coimbatore | M Velayutham Balaji | PN Palayam Rd | Coimbatore | 3370 | 2025-12-26 | 2025-12-29 | 15 |  | 2026-01-13 | 2026-02-20 | 2026-02-21 | EPC Ready Previous FY | 100% | YTL | 2026-05-30 | 2026-05-08 | Launched | FY 25-26 | AOP
FLDHSD12805 | 1315 |  | TWC0 | Q5XO | DH-TSAR-419-WB-TWC0 | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | East | AK | West Bengal |  |  | Platina Mall Bangabasi Mall, Howrah | Howrah | 3668 |  |  | 0 | 25 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | APRIL 25
DIRFBK14977 | 1316 |  |  |  | CDITMNEU803 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | West | BK | Maharashtra |  |  | Phoenix Market City, Ahmednagar, Pune | Pune | 7624 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
JOHNAS11091 | 1317 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Johnplayer EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Andhra Pradesh |  |  | Phoenix Mall & Multiplex, Srinivasaraopet, Guntur, AP | Guntur |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
PERSSD10774 | 1318 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | Jharkhand | Ranchi |  | Performax SIS -CT-RANCHI-SAVYRAJ MALL | Ranchi |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
PERSSD10785 | 1319 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | Bihar | Patna |  | Performax SIS -CT-PATNA-THE MALL-FRAZER ROAD | Patna |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
PERSAS10773 | 1320 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | South | SZ FO | Karnataka | Bengaluru |  | Performax SIS -CT-MYSORE-BANGALORE NILGIRI RO | Bengaluru |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
PERSAS10783 | 1321 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | South | SZ FO | Karnataka |  |  | Performax SIS -CT-MANGALORE-ATTAVR VILLAGE-PA | Mangalore |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | APRIL 25
PERSAS10784 | 1322 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | South | SZ FO | Kerala | Cochin |  | Performax SIS -CT-KOCHI-M G ROAD-CENTRE SQUAR | Kochi |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
PERSSD10778 | 1323 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | Telangana | Hyderabad |  | Performax SIS -CT-HYDERABAD-KUKATPALLY | Hyderabad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
PERSSD10771 | 1324 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | Telangana | Hyderabad |  | Performax SIS -CT-HYDERABAD-GSM MALL-CHANDANAGAR | Hyderabad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
PERSSD10775 | 1325 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | Telangana | Hyderabad |  | Performax SIS -CT-HYDERABAD-GACHIBOWLI | Hyderabad |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
PERSSD10776 | 1326 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | Assam & NE | Guwahati |  | Performax SIS -CT-GUWAHATI-EXOTICA GREENS | Guwahati |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
PERSAS10779 | 1327 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | Orissa | Bhubaneshwar |  | Performax SIS -CT-BHUBANESWAR-SAHEED NAGAR | Bhubaneshwar |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
PERSAS10777 | 1328 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | South | SZ FO | Karnataka | Bengaluru |  | Performax SIS -CT-BENGALURU-YELAHANKA | Bengaluru |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
PERSAS10780 | 1329 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | South | SZ FO | Karnataka | Bengaluru |  | Performax SIS -CT-BENGALURU-SPECTRUM MALL-BAN | Bengaluru |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
PERSAS10781 | 1330 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | South | SZ FO | Karnataka | Bengaluru |  | Performax SIS -CT-BENGALURU-SOUL SPACE SPIRIT | Bengaluru |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
PERSSD10772 | 1331 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | East | SD | West Bengal | Silliguri |  | Performax SIS -CT Cosmos Mall Siliguri | Siliguri |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
ADOFAS11743 | 1332 |  |  |  |  | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka | Bengaluru |  | Performax Category room – At IBC Tower B, 4th Floor | Bengaluru | 862 |  |  | 55 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
LEECAS13308 | 1333 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Lee Cooper EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Andhra Pradesh | Vishakhapatnam |  | Payless to Lee Cooper (F) - CMR, Vizag | Vishakhapatnam | 1849 |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
LEECAS13333 | 1334 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Lee Cooper EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala |  |  | Payless to Lee Cooper - RP Mall, Kollam | Kollam | 1502 |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
CATWSD13347 | 1335 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Catwalk | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana | Hyderabad |  | Payless to Catwalk - Sarath city, Hydebarad | Hyderabad | 1422 |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
FLDHAK14103 | 1336 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part B) | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | East | AK | Andhra Pradesh | Vishakhapatnam |  | Payless CMR Mall | Vishakhapatnam | 2001 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
FLDHAK14108 | 1337 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part B) | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Kerala |  |  | Payless Chinnakada | Kollam | 1502 |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
DIGSAS14985 | 1338 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu |  |  | Palani Road , DINDIGUL, TAMIL NADU |  |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
DIGSAS14987 | 1339 |  |  | QHHK | CDITTQHHK00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu |  | Karthikeyan C PMC | Padur, Chennai, TAMIL NADU | Chennai | 12221 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | DECEMBER 25
SMRTAS13985 | 1340 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Andhra Pradesh |  |  | P227, Panduranga Street, Babuji Colony, Sai Nagar, Sullurpeta, Tirupathi, AP | Sullurpeta |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
DIGSRT10415 | 1341 |  | T5CT | QK7J | CDITUQK7J00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Uttar Pradesh |  |  | Opp Mega Shop, Gorakhnath, Gorakhpur | Gorakhpur | 8807 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DIGSRT10478 | 1342 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Uttar Pradesh | Agra |  | Opp IDFC First Bank, Sikandra Bodla Road, Sikandra, Agra | Agra |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
PHCOKC14704 | 1343 |  |  |  |  | D. Pharma Format | Pharma Format | Pharma COCO Store (SP Fix Setup) | Amit C | Arju Tiwari | Kiran Patil | Refit | West | KC | GMU |  |  | ONLINE NETMED STORE_BHANDUP METRO | Mumbai |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
SEVEBK15078 | 1344 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | One World, Lower Parel, Mumbai | Lower Parel |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
SEVEBK15079 | 1345 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | One International, Lower Parel, Mumbai | Lower Parel |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
ADOFRT10637 | 1346 |  |  |  |  | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | North | RT | Delhi & NCR | Delhi - NCR |  | Okhla Office | Delhi & Ncr |  |  |  | 55 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
SMPTAS10305 | 1347 |  |  |  |  | C. Grocery | Grocery | Smart Point | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Andhra Pradesh |  |  | NR Complex, Chandra Sekhar Reddy Property, Chennur | Chennur |  |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | OCTOBER 25
JICEBK11752 | 1348 |  |  |  |  | J. Jio Business | Jio Business | Jio Centre | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU | Mumbai |  | Norther Supremus, Dahisar East | Mumbai |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
SMRTSD10343 | 1349 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Assam & NE |  |  | Nongmensong Maonmarket | Shillong |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
DIGSBK14979 | 1350 |  | TBAP | QHDM | CDITMQHDM00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra | West Maharashtra | Rajesh Gavale | NH 4 Highway Hotel Sangam Building ,Karad,Satara | Satara | 7394 | 2026-02-02 | 2026-02-05 | 35 |  | 2026-03-12 | 2026-05-20 | 2026-05-21 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | MAY 26 | AUGUST 25
TRRFAS14036 | 1351 |  | T67H | QICK | TSARKQICK02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka | Bangalore | Dileep Sp | NEXUS FALCON CITY MALL,BANGALORE | Bangalore | 2826 | 2026-01-05 | 2026-01-19 | 0 | 35 | 2026-02-23 | 2026-05-08 | 2026-05-12 | EPC Ready | 100% |  | 2026-05-21 | 2026-05-12 | Launched | FY 26-27 | NON AOP | FEBRUARY 26 PLANNED | MAY 26
DIGSBK10477 | 1352 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU | Mumbai |  | Neelkanth Dham, Plot No. 17C-1, Sector 16E, Kalamboli | Panvel |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
FFNSSD11130 | 1353 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana | Hyderabad |  | Near Smart Bazar, Kompally, Hyderabad, Telangana. | Hyderabad |  |  |  | 45 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | OCTOBER 25
GRDSAK14572 | 1354 | DS-TN-00070 | TBDX | QHGM | DARKTQHGM00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu | Chennai | Ganesh B | Nanganallur Catchment | Chennai | 1735 | 2026-03-02 | 2026-03-10 | 15 |  | 2026-03-25 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
GRDSAK15008 | 1355 |  | TBKI | QHMC | DARKTQHMC00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu |  | Palanisamy Chelladurai | Nandhanam- Annasalai GR Complex | Chennai | 1828 | 2026-01-27 | 2026-02-05 | 15 |  | 2026-02-20 | 2026-02-27 | 2026-03-12 | EPC Ready Previous FY | 100% |  | 2026-05-10 | 2026-04-02 | Launched | FY 25-26 | AOP
DIGSRT14989 | 1356 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Uttar Pradesh |  |  | Nagina Road, Bijnor, UP |  |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
SMRTAS13926 | 1357 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Andhra Pradesh |  |  | Murali Theatre, KADAPA | Kadapa |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSAK15249 | 1358 |  | TBCA | QHEL | DARKKQHEL00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Karnataka | Bangalore | Mukesh Mukul | Munivenkatappa Layout, Bilekahalli | Bangalore | 3043 | 2026-02-23 | 2026-04-02 | 15 |  | 2026-04-17 | 2026-05-12 | 2026-05-17 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
DIGCRT12949 | 1359 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Compact Digital | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Haryana |  |  | MG Road, Stadium Colony Safidon | Safidon | 3034 |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
YOTHSD14878 | 1360 |  |  | QHED | TYOUNQHED00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana |  |  | Medipally village (Erstwhile Boduppal) | Hyderabad | 7060 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRRESD13394 | 1361 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand | Ranchi |  | Maroo Tower Ranchi | Ranchi |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
YOTHSD13519 | 1362 |  |  | QHGZ | TYOUWQHGZ00 | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | West Bengal |  |  | Marlin Maximus, 618, Barrackpore Trunk Rd, No. 3 Deshbondhu Nagar, Sodepur, Khardaha, West Bengal 700115 | Sodepur | 6109 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS10182 | 1363 |  | T1UC | Q3A5 | SMRTVQ3A500 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  | Arun Mahesh | Marks Tower, Kalady | Kalady | 16161 | 2025-10-14 | 2025-10-31 | 35 |  | 2025-12-05 | 2026-01-15 | 2026-01-19 | EPC Ready Previous FY | 100% |  | PENDING | 2026-05-30 | Launched | FY 25-26 | AOP |  |  | MAY 25
SMRTAS10191 | 1364 |  | T81Q | QNFD | SMRTVQNFD00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  | Shabarish Narayan | Mariyam Arcade, Koyilandy | Koyilandy | 17441 | 2025-08-06 | 2025-09-20 | 35 |  | 2025-10-25 | 2025-11-18 | 2025-11-11 | EPC Ready Previous FY | 100% |  | 2026-01-22 | 2026-04-30 | Launched | FY 25-26 | AOP |  |  | MAY 25
SEVEBK10628 | 1365 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai |  | Marathon Future X | Mumbai | 666 |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
JICEBK11520 | 1366 |  |  |  |  | J. Jio Business | Jio Business | Jio Centre | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU | Mumbai |  | Manisha Corporate park -Mulund | Mumbai |  |  |  | 45 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
DIGSSD10458 | 1367 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Jharkhand | Jamshedpur |  | Mango Chowk, Jamshedpur | Jamshedpur |  |  |  | 35 |  |  |  |  | ML Received - Business Issue | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
DIGSSD14969 | 1368 |  | TBIP | QHKT | CDITAQHKT00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Andhra Pradesh |  | Mahesh Reddy - PMC | Mangalam, Tirupati | Tirupati | 7847 | 2026-02-15 | 2026-02-17 | 35 |  | 2026-03-24 | 2026-04-24 | 2026-04-27 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26 | JUNE 25
TRRFSD10752 | 1369 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana | Hyderabad |  | Malakpet | Malakpet |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRD3SD13369 | 1370 |  | T9GG | QVAG | TFITWQVAG00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends 3.0 | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | West Bengal | Kolkata |  | Mahua Cinema, Garia, Kolkata | Kolkata | 20852 |  |  | 45 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | MAY 25
TRFTAS13358 | 1371 |  | TBMP | QHNS | FOOTTQHNS00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Tamil Nadu |  | Senthil Muthhaiah | Leecooper to Trends Footwear - Thillai Nagar, Trichy | Trichi | 1398 | 2026-02-19 | 2026-02-27 | 35 | 15 | 2026-04-18 | 2026-05-08 | 2026-05-07 | EPC Ready | 100% |  | PENDING | 2026-05-07 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26 | JUNE 25
TRD3AS13684 | 1372 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Lakshmipuran, Guntur (Full Renovation) | Guntur |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
DIGCSD12201 | 1373 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Compact Digital | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Bihar |  |  | Lakhisarai-Chitranhan Road | Lakhisarai |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
CATWSD13523 | 1374 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Catwalk | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana | Hyderabad |  | Lakeshore, Gateway Mall, Hyderabad | Hyderabad | 659 |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
CFVRSD14689 | 1375 |  | TBNH | QHOA | CENFNQHOA00 | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana | Hyderabad | Shankar T | Lakeshore Mall | Hyderabad | 4622 | 2026-03-02 | 2026-04-13 | 35 |  | 2026-05-18 | 2026-06-10 |  | WIP | 65% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED |  | JUNE 25
GRDSAK14546 | 1376 | DS-KA-00084 |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Karnataka |  |  | Kurlappa Layout | Bangalore | 3610 |  |  | 15 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRBSAS14701 | 1377 |  |  |  |  | C. Grocery | Grocery | Grocery Bismi | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Kunnamangalam, Calicut | Calicut | 10335 |  |  | 60 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
JICERT12850 | 1378 |  | Not Applicable | Not Applicable | RRJ-KOTA-JCO-S-0001 | J. Jio Business | Jio Business | Jio Centre | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Rajasthan | Kota | Balram Soni | Kota | Kota | 9593 | 2026-03-23 | 2026-03-28 | 45 |  | 2026-05-12 | 2026-06-15 |  | WIP | 70% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED |  | JULY 25
GRDSAK14029 | 1379 | DS-TN-00020 |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu |  |  | Kondappanayakkanpatti | Salem |  |  |  | 15 |  |  |  |  | Pre SDR Site | 0% |  |  |  |  | FY 26-27 | AOP |  |  | OCTOBER 25
DIRFSD15263 | 1380 |  | 8661 | NEF3 | CDITNNEF304 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | East | SD | Telangana | Hyderabad | Pavankumar Lankadasula | Kompally | Hyderabad | 11373 | 2026-02-06 | 2026-02-07 | 0 | 35 | 2026-03-14 | 2026-04-05 | 2026-04-02 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
SEVEBK15001 | 1381 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kohinoor World Tower, Pimpri Chinchwad | Pune |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
DI3KAS13468 | 1382 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital 3K | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu | Chennai |  | Kodambakkam, Chennai | Chennai |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
JESABK11399 | 1383 |  |  |  |  | A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels SAS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Madhya Pradesh | Bhopal |  | KK Tower, Malviya Nagar, Bhopal | Bhopal | 5384 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
GRDSAK14828 | 1384 |  | TBI4 | QHLH | DARKTQHLH00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu | Chennai | Ganesh B | Kizhkattalai | Chennai | 2835 | 2026-02-24 | 2026-03-09 | 15 |  | 2026-03-24 | 2026-05-12 | 2026-05-12 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | MAY 26 | AUGUST 25
SEVEBK12642 | 1385 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra | West Maharashtra |  | Kiosk-Solitaire Business Hub ,Viman Nagar 2 | Pune | 160 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK12858 | 1386 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra | West Maharashtra |  | Kiosk-Avanche 1, Hinjewadi | Pune | 160 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14527 | 1387 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Kiosk Reliable Tech Park, Airoli-1 | Mumbai |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14695 | 1388 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Panchshil Vantage, Kharadi | Pune |  |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14549 | 1389 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Panchshil EON W-Wakad | Pune |  |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14548 | 1390 |  | TBZI | QIBY | 7ICRMQIBY00 | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  | Nishant Narsapur | Kiosk Panchshil Business Tech Park ,Viman Nagar | Pune | 732 | 2026-04-21 | 2026-05-25 | 35 |  | 2026-06-29 | 2026-06-29 |  | WIP | 40% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
SEVEBK14696 | 1391 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Panchshil Business Hub (Kharadi 40) Kharadi | Pune |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14678 | 1392 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Kiosk Mindspace Gigaplex , Airoli W | Airoli |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14014 | 1393 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai |  | Kiosk Marathon, FutureX, Lower Parel -Mumbai-1 | Mumbai |  |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14530 | 1394 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Kiosk Fortis Mulund | Mumbai |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14528 | 1395 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Commerzone Yerwada | Pune |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK14529 | 1396 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Commerzone Kharadi | Pune |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK13813 | 1397 |  | TBLG | QHMT | 7ICRMQHMT00 | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai | Rajesh Nikalje | Kiosk BITS- Kalyan 6&7 | Mumbai | 675 | 2026-03-02 | 2026-03-02 | 35 |  | 2026-04-06 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% |  | 2026-05-05 | 2026-04-10 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | APRIL 26
SEVEBK13812 | 1398 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai |  | Kiosk 247 Embassy, Vikhroli, Mumbai-1 | Mumbai |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DIGSBK14980 | 1399 |  | TBPS | QHPX | CDITMQHPX00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra |  | Rahul Atal/Mithilesh Kumar | Khemani Complex, Nashik, MH | Nashik | 12135 | 2026-04-17 | 2026-04-19 | 35 |  | 2026-05-24 | 2026-06-10 |  | WIP | 65% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED
GRDSAK14556 | 1400 | DS-KA-00149 |  | QABZ | DARKKQABZ00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Karnataka |  |  | Kasavanahalli | Bangalore | 1443 |  |  | 15 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
CFVRSD14447 | 1401 |  | TBJP | QHLQ | CENFNQHLQ00 | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana | Hyderabad | Chandra Mohan | Karmanghat | Hyderabad | 5427 | 2026-02-09 | 2026-02-11 | 35 | 8 | 2026-03-26 | 2026-04-30 | 2026-05-02 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | MAY 26
DIGSSD15071 | 1402 |  | TC7D | QV5R | CDITNQV5R00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Telangana | Hyderabad | Chandra Mohan | Karmanghat | Hyderabad | 7191 | 2026-01-30 | 2026-02-01 | 35 |  | 2026-03-08 | 2026-04-18 | 2026-04-22 | EPC Ready | 100% |  | OTHER ISSUES |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
DIGSBK13475 | 1403 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU | Mumbai |  | Kanchan Avenue, Palghar | Mumbai |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
TRRFAS10748 | 1404 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka | Bengaluru |  | Kanakpura | Bengaluru |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDSAK14398 | 1405 | DS-TN-00055 |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu |  |  | Kalapatti | Coimbatore | 3679 |  |  | 15 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
TRD3AS13688 | 1406 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kakatiya Nagar, Reddy Nagar, Narasaraopeta (Full Renovation) | Narasaraopeta |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDSSD14457 | 1407 | DS-AS-00014 |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | Assam & NE |  |  | Kahilipara | Guwahati | 2505 |  |  | 15 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRDSAK14582 | 1408 | DS-KA-00115 | TBAY | QHDQ | DARKKQHDQ00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Karnataka |  | Mukesh Mukul | Kadugodi | Bangalore | 2393 | 2026-04-30 | 2026-05-19 | 15 |  | 2026-06-03 | 2026-06-08 |  | WIP | 70% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
DIGSBK10471 | 1409 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU | Mumbai |  | JVM Corner Stone, Hairniwas Cirlce, Thane - West | Thane |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
YOTHAS13328 | 1410 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka | Bengaluru |  | JP Nagar, Kothanur Main Road, Bangalore | Bengaluru | 8440 |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | MAY 25
SMRTSD4332 | 1411 |  | TZOK | QDBK |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | West Bengal |  |  | Jayanti Cinema-GT Road | Rishra |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JUNE 25
GRREAK14488 | 1412 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Tiruchengode |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
GRREAK14493 | 1413 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Sangeetha Shopping Erode |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14491 | 1414 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Sampathnagar Erode |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14487 | 1415 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Rasipuram |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14485 | 1416 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Perundurai Road Branch Erode |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | OCTOBER 25
GRREAK14483 | 1417 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Perundurai |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14492 | 1418 |  | TXY2 | Q9O2 | JVPLTQ9O201 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Namakkal | Namakkal | 15642 | 2026-06-01 | 2026-06-01 | 0 | 7 | 2026-06-08 | 2026-06-08 |  | WIP | [5 empty] | FY 26-27 | NON AOP | JUNE 26 PLANNED
GRREAK14484 | 1419 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Kollampalayam Erode |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14490 | 1420 |  |  |  |  | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA In and Out Erode |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14486 | 1421 |  | TXY8 | Q9O8 | JVPLTQ9O801 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Bhavani | Bhavani | 8842 | 2026-05-13 | 2026-05-13 | 0 | 7 | 2026-05-20 | 2026-06-05 |  | WIP | [5 empty] | FY 26-27 | NON AOP | MAY 26 PLANNED
GRREAK14489 | 1422 |  | TXY9 | Q9O9 | JVPLTQ9O901 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | JAY SURYA Anthiyur | Anthiyur | 6569 | 2026-05-19 | 2026-05-19 | 0 | 7 | 2026-05-26 | 2026-06-05 |  | WIP | [5 empty] | FY 26-27 | NON AOP | MAY 26 PLANNED
SMRTAS13876 | 1423 |  | TBNS | QHOE | SMRTOQHOE00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Orissa |  | Sukhen Das | Janta City Center, Berhampur | Berhampur | 27793 | 2026-02-25 | 2026-02-27 | 35 |  | 2026-04-03 | 2026-04-25 | 2026-04-24 | EPC Ready | 100% |  | PENDING | 2026-04-30 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | APRIL 26
JICEBK11519 | 1424 |  |  |  |  | J. Jio Business | Jio Business | Jio Centre | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Gujarat |  |  | Jamnagar | Jamnagar |  |  |  | 45 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
CEDHSD12133 | 1425 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | East | AK | West Bengal | Kolkata |  | Jadhavpur SMART | Kolkata | 10884 |  |  | 0 | 21 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRREAS13401 | 1426 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Tamil Nadu |  |  | IYYAPANTHANGAL | Iyyapanthangal |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | NOVEMBER 25
ADOFAS10639 | 1427 |  | ZYM6 | QCDJ | DCDCKQCDJ00 | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka | Bengaluru |  | IBC Knowledge Park-Tower B 1st, 3rd & 7th Floor | Bengaluru |  |  |  | 55 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | NOVEMBER 25
ADOFAS11354 | 1428 |  | S0IR | Q5EU | DCDCKQ5EU00 | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka | Bengaluru |  | IBC Knowledge Park-Category room- Tower D Additional Work | Bengaluru |  |  |  | 55 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP
ADOFAS10640 | 1429 |  | S0IS | Q5EV | DCDCKQ5EV00 | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka | Bengaluru |  | IBC Knowledge Park Tower A - 5th | Bengaluru |  |  |  | 55 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP
MIDHAK15077 | 1430 |  |  |  |  | E. Other Business | Other Business | Misc - Dehire | Amit C | Arju Tiwari | Kiran Patil | Dehire | South | AK | Kerala |  |  | Home and Décor, Kumaranalloor Store | Kumaranalloor | 2731 |  |  | 0 |  |  |  |  | SDR In Progress | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
SMRTSD14934 | 1431 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | West Bengal |  |  | Hilton Residency | Bankura |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
CEDHKC13555 | 1432 |  | 8740 | NEK9 | DH-CDIT-452-MH-8740 | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | West | KC | GMU | Mumbai |  | Gulmohar Plaza, Virar, Mumbai | Mumbai |  |  |  | 0 | 21 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
CFVRSD14926 | 1433 |  | TCGL | QIKR | CENFAQIKR00 | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Andhra Pradesh |  |  | GNT Road, Ongole | Ongole |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DIRFRT11501 | 1434 |  | TP32 | ND50 | CDITUND5003 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | North | RT | Delhi & NCR | Delhi - NCR |  | Gaur City Mall | Noida | 9715 |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DMSSSD15264 | 1435 |  | 3591 | NL96 | MDXPWNL9602 | A. Consumer Electronics & Jewels | Consumer Electronics | DMS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | West Bengal |  |  | Ganpathpur, Basirhat | Kolkata | 544 | 2026-05-15 | 2026-05-17 | 35 |  | 2026-06-21 | 2026-06-21 |  | WIP | 25% |  |  |  |  | FY 26-27 | NON AOP | JUNE 26 PLANNED |  | AUGUST 25
GRDHAK14081 | 1436 |  |  |  |  | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Assam & NE |  |  | Gangtok | Gangtok | 18500 |  |  | 0 |  |  |  |  | Pre Budget Dehire Site | 0% |  |  |  |  | FY 26-27 | NON AOP
EDAMAS14920 | 1437 |  | T9D7 | T9D7 | EDMMVT9D700 | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala | Cochin | Shabarish Narayan | Forum Mall, Kochi Forum Mall NH-47, Vytilla- Aroor Bypass Near Kundannur Junction, Maradu PO Kochi- 682304 | Kochi | 663 | 2026-01-29 | 2026-02-03 | 35 |  | 2026-03-10 | 2026-04-18 | 2026-04-21 | EPC Ready | 100% |  | 2026-05-07 | 2026-05-08 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
CVRFSD14712 | 1438 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Andhra Pradesh |  |  | Façade Upliftment - Guntur | Guntur |  |  |  | 0 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
TRRFAS10747 | 1439 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka | Bengaluru |  | Façade -2.0 to 3.0 - Indiranagar | Bengaluru |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
DIGSBK10484 | 1440 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra | Vidarbha |  | Empress Mall, Nagpur | Nagpur |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
GRBSAS13865 | 1441 |  |  |  |  | C. Grocery | Grocery | Grocery Bismi | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Emirates Mall ,Near Govt Hospital,Vadakara Road,NadapuramP O ,Kozhikode 673504 | Kozhikode |  |  |  | 60 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
AZCOSD15247 | 1442 |  | TBGI | QHIR | TAZOWQHIR00 | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte Conversion | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | West Bengal | Kolkata | Nilava Choudhury | ELGIN ROAD-TVM5-KOLKATA | Kolkata | 10561 | 2026-02-08 | 2026-02-08 | 60 |  | 2026-04-09 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% |  | 2026-05-01 | 2026-04-09 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26
ECKSAS10770 | 1443 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Ecko SIS | Srinivas P | Jitendra Talreja | Nitesh Warhade | SIS | South | SZ FO | Karnataka | Bengaluru |  | Ecko SIS CENTRO-BLR-3,SOUL SPACE | Bengaluru |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
SMRTAS13400 | 1444 |  | TANS | QF3S | SMRTTQF3S00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu | Coimbatore | Senthil Muthhaiah | Dindugal Main road, Thanthonimalai, Karur | Karur | 15482 | 2026-01-19 | 2026-01-27 | 35 |  | 2026-03-03 | 2026-04-05 | 2026-04-05 | EPC Ready | 100% |  | PENDING | 2026-04-30 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26 | SEPTEMBER 25
DIGSSD14990 | 1445 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | West Bengal |  |  | Digital, Link Road, Arambag, WB, | Arambagh |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
DIGSRT14971 | 1446 |  | TC4R | QV4V | CDITDQV4V00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Delhi & NCR |  | Prakhar Singh | Digital, DLF Midtown, Delhi, | Delhi | 4313 | 2026-01-29 | 2026-02-17 | 35 |  | 2026-03-24 | 2026-05-15 | 2026-05-21 | EPC Ready | 100% |  | 2026-06-02 | 2026-05-28 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | MAY 26
SMRTSD13927 | 1447 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Assam & NE |  |  | Dharmanagar, Tripura | Tripura |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SEVDKC15004 | 1448 |  | T1JL | T1JL | DH-7ICR-451-9132-MH-T1JL | E. Other Business | Other Business | 7-Eleven - Dehire | Amit C | Arju Tiwari | Kiran Patil | Dehire | West | KC | GMU | Mumbai | Ajay Kumar | Dehire-Smart Bazaar, Xperial Mall, Dombivali | Dombivali | 698 | 2026-03-14 | 2026-03-14 | 0 | 15 | 2026-03-29 | 2026-05-30 | 2026-05-28 | EPC Ready | 100% |  | PENDING | 2026-05-28 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | MAY 26
SEVDKC15003 | 1449 |  | T1IY | T1IY | DH-7ICR-451-9132-MH-T1IY | E. Other Business | Other Business | 7-Eleven - Dehire | Amit C | Arju Tiwari | Kiran Patil | Dehire | West | KC | GMU | Mumbai | Ajay Kumar | Dehire-Smart Bazaar, Orion mall | Panvel | 600 | 2026-03-12 | 2026-03-12 | 0 | 15 | 2026-03-27 | 2026-04-19 | 2026-04-21 | EPC Ready | 100% |  | 2026-04-22 | 2026-04-21 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
SEVDKC15005 | 1450 |  | T52V | T52V | DH-7ICR-451-9132-MH-T52V | E. Other Business | Other Business | 7-Eleven - Dehire | Amit C | Arju Tiwari | Kiran Patil | Dehire | West | KC | Maharashtra | West Maharashtra | Prashant Wankhede | Dehire-Smart Bazaar, Kothrud Road, Pune | Pune | 495 | 2026-03-15 | 2026-03-15 | 0 | 15 | 2026-03-30 | 2026-05-15 | 2026-05-16 | EPC Ready | 100% |  | PENDING | 2026-05-16 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | MAY 26 | OCTOBER 25
SEVDKC15002 | 1451 |  | TAXP | TAXP | DH-7ICR-451-9132-MH-TAXP | E. Other Business | Other Business | 7-Eleven - Dehire | Amit C | Arju Tiwari | Kiran Patil | Dehire | West | KC | GMU | Mumbai | Hareshprasad M | Dehire-D'Victoria Mall, Borivali | Borivali | 450 | 2026-03-16 | 2026-03-16 | 0 | 15 | 2026-03-31 | 2026-04-30 | 2026-04-30 | EPC Ready | 100% |  | PENDING | 2026-04-30 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
CEDHBK12132 | 1452 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | West | KC | GMU | Mumbai |  | Dattani Mall , Vasai | Vasai | 8307 |  |  | 0 | 21 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
DIGCSD14982 | 1453 |  |  | QHDK | CDITOQHDK00 | A. Consumer Electronics & Jewels | Consumer Electronics | Compact Digital | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Orissa |  |  | Dakhinakali Road,Dhenkanal | Dhenkanal | 5587 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
JERFAS10427 | 1454 |  |  |  |  | A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | East | SD | Orissa | Cuttack |  | Cuttack, Orissa | Cuttack |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
DIGSAS14925 | 1455 |  | TL0Z | QY5O | CDITTQY5O00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu |  | Vignesh Ravichandran | Cumbam | Cumbam | 5031 | 2025-12-15 | 2025-12-15 | 35 |  | 2026-01-19 | 2026-01-22 | 2026-01-21 | EPC Ready Previous FY | 100% | YTL | PENDING | 2026-04-17 | Launched | FY 25-26 | AOP
GRREAS13398 | 1456 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa | Cuttack |  | College Square, Sahoo, Cuttack | Cuttack |  |  |  | 0 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
POSMSD10596 | 1457 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand | Jamshedpur |  | CLOVIA JAMSHEDPUR | Jamshedpur |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
POSMAS10585 | 1458 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa | Bhubaneshwar |  | CLOVIA BHUBANESWAR | Bhubaneshwar |  |  |  | 0 | 7 |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
SMRTAS13492 | 1459 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu |  |  | Chinnalampatti, Dindigul | Dindigul |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
DIGSSD14960 | 1460 |  | TBIK | QHKQ | CDITWQHKQ00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | West Bengal | Kolkata | Shukdev Dey | Chinar Park | Kolkata | 9844 | 2025-12-26 | 2025-12-30 | 35 |  | 2026-02-03 | 2026-02-22 | 2026-03-17 | EPC Ready Previous FY | 100% | YTL | OTHER ISSUES | 2026-04-09 | Launched | FY 25-26 | AOP
YOTHAS13322 | 1461 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka | Bengaluru |  | Channasandra, Whitefiled, Bangalore | Bengaluru | 8301 |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
DIGSAS14976 | 1462 |  | TBLJ | QHMW | CDITKQHMW00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Karnataka | Bengaluru | Manikandan PMC | Channasandra, Bangalore, Karnataka | Bangalore | 8413 | 2026-04-15 |  | 35 |  | 2026-05-23 |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
DIGSAS11551 | 1463 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Karnataka |  |  | Channapatna Town |  |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
URBSAS14526 | 1464 |  | TF4E | QX7E | URLAKQX7E00 | E. Other Business | Other Business | Urban Ladder SIS | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka | Bangalore | Sh. Debkamal B | Centro Bellandur, Bangalore (Partial area Partition & Fixture Works) | Bangalore | 948 | 2026-01-15 | 2026-03-11 | 0 | 21 | 2026-04-01 | 2026-05-30 | 2026-05-31 | EPC Ready | 100% |  | 2026-06-01 | 2026-05-31 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26
TRD3AS13686 | 1465 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Central Plaza, Eluru (Full Renovation) | Eluru |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
ADOFRT10638 | 1466 |  |  |  |  | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | North | RT | Delhi & NCR | Delhi |  | CBD Shahadra | Delhi & Ncr |  |  |  | 55 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | OCTOBER 25
DIRFRT12137 | 1467 |  | 8843 | NEQ9 | CDITDNEQ903 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | North | RT | Delhi & NCR | Delhi | Brajesh Kumar | CBD Shahadara, Delhi | Delhi | 13524 | 2026-02-05 | 2026-02-05 | 0 | 45 | 2026-03-22 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% |  | 2026-05-07 | 2026-05-07 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
DIGSBK11544 | 1468 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra | Vidarbha |  | Capital One, JP Nagar Metro Station, Wardha Road, Nagpur | Nagpur |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
SEVEBK11344 | 1469 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai |  | Capital Mall, Vasai | Vasai | 523 |  |  | 35 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | AOP
DIGSRT11755 | 1470 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Delhi & NCR | Delhi - NCR |  | Capital Business Park, Sohna Road, Gurugram | Gurugram |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
DIRFSD15261 | 1471 |  | 6400 | NZP8 | CDITQNZP803 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | East | SD | Jharkhand | Dhanbad | Saddam Hussain | Bokaro | Bokaro | 7788.52 | 2026-02-06 | 2026-02-07 | 0 | 35 | 2026-03-14 | 2026-03-31 | 2026-03-31 | EPC Ready Previous FY | 100% |  | 2026-05-12 | 2026-05-12 | Launched | FY 25-26 | AOP |  |  | AUGUST 25
CFVRSD14928 | 1472 | AP-SM-HYD-2064 |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana |  |  | BOD UPPAL - Hyderabad | Hyderabad |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP
GRREAK14469 | 1473 |  | T0M5 | Q4FM | BISMVQ4FM02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Vytilla | Vytilla | 13300 | 2026-04-20 | 2026-04-20 | 0 | 7 | 2026-04-27 | 2026-05-12 | 2026-05-01 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26
GRREAK14479 | 1474 |  | T0M4 | Q4FL | BISMVQ4FL02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Vengara | Vengara | 33500 | 2026-05-01 | 2026-05-01 | 0 | 7 | 2026-05-08 | 2026-05-31 | 2026-05-25 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
GRREAK14466 | 1475 |  | T0CN | Q4OP | BISMVQ4OP01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Thrissur | Thrissur | 10175 | 2026-05-26 | 2026-05-26 | 0 | 7 | 2026-06-02 | 2026-06-05 |  | WIP | [5 empty] | FY 26-27 | NON AOP | JUNE 26 PLANNED
GRREAK14481 | 1476 |  | T0L8 | Q4FG | BISMVQ4FG02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Thodupuzha |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14475 | 1477 |  | T0BW | Q4NQ | BISMVQ4NQ01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Thiruvalla |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14477 | 1478 |  | T0CL | Q4ON | BISMVQ4ON01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Thalayolaparambu | Thalayolaparambu | 6100 | 2026-05-06 | 2026-05-06 | 0 | 7 | 2026-05-13 | 2026-05-13 | 2026-05-14 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
GRREAK14470 | 1479 |  | T0M3 | Q4FK | BISMVQ4FK02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Perinthalmanna | Perinthalmanna | 29327 | 2026-05-05 | 2026-05-05 | 0 | 7 | 2026-05-12 | 2026-05-12 | 2026-05-14 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
GRREAK14474 | 1480 |  | T0ME | Q4VL | BISMVQ4VL01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Palarivattom |  |  |  |  | 0 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
GRREAK14471 | 1481 |  | T0L7 | Q4FF | BISMVQ4FF02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Palakkad | Palakkad | 21804 | 2026-04-20 | 2026-04-20 | 0 | 7 | 2026-04-27 | 2026-05-12 | 2026-05-14 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | APRIL 26 PLANNED | MAY 26 | JUNE 25
GRREAK14482 | 1482 |  | T0M2 | Q4FJ | BISMVQ4FJ02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Netoor | Netoor | 3000 | 2026-04-24 | 2026-04-24 | 0 | 7 | 2026-05-01 | 2026-05-08 | 2026-05-01 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26 | SEPTEMBER 25
GRREAK14473 | 1483 |  | T0CP | Q4OR | BISMVQ4OR02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Muvattupuzha |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
GRREAK14478 | 1484 |  | T0CO | Q4OQ | BISMVQ4OQ01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Mulanthuruthy |  |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JUNE 25
GRREAK14467 | 1485 |  | T0CM | Q4OO | BISMVQ4OO01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI Kozhikode | Kozhikode | 11433 | 2026-05-21 | 2026-05-21 | 0 | 7 | 2026-05-28 | 2026-06-06 |  | WIP | [5 empty] | FY 26-27 | NON AOP | MAY 26 PLANNED |  | JUNE 25
GRREAK14468 | 1486 |  | T0L4 | Q4FC | BISMVQ4FC02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Kaloor | Kaloor | 11550 | 2026-04-16 | 2026-04-16 | 0 | 7 | 2026-04-23 | 2026-04-30 | 2026-04-29 | EPC Ready | 100% |  | 2026-05-08 | 2026-05-08 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26 | SEPTEMBER 25
GRREAK14476 | 1487 |  | T0L5 | Q4FD | BISMVQ4FD02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Kalamaserry | Kalamaserry | 17300 | 2026-04-20 | 2026-04-20 | 0 | 7 | 2026-04-27 | 2026-04-30 |  | On Hold | [5 empty] | FY 26-27 | NON AOP
GRREAK14480 | 1488 |  | T0L3 | Q4FB | BISMVQ4FB02 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Elamakkara | Elamakkara | 1330 | 2026-04-21 | 2026-04-21 | 0 | 7 | 2026-04-28 | 2026-04-30 | 2026-04-29 | EPC Ready | 100% |  | 2026-05-06 | 2026-05-06 | Launched | FY 26-27 | NON AOP | APRIL 26 PLANNED | APRIL 26 | SEPTEMBER 25
GRREAK14472 | 1489 |  | T0M1 | Q4FI | BISMVQ4FI01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  |  | BISMI DD Rush |  |  |  |  | 0 |  |  |  |  | Dropped | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
DIBSAS14974 | 1490 |  | TBGY | QHJF | CDITVQHJF00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Bismi | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Kerala |  | Muhammed Afzal PMC | Bismi Changuvetty, Kottakkal, Kerala | Kottakkal | 7465 | 2026-04-04 | 2026-04-06 | 35 |  | 2026-05-11 | 2026-06-15 |  | WIP | 60% |  |  |  |  | FY 26-27 | NON AOP | MAY 26 PLANNED
GRREAK14465 | 1491 |  | T0L6 | Q4FE | BISMVQ4FE01 | C. Grocery | Grocery | Grocery - SLP Works | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Kerala |  | Dijeesh PD | BISMI Alappuzha | Alappuzha | 8200 | 2026-05-04 | 2026-05-04 | 0 | 7 | 2026-05-11 | 2026-05-11 | 2026-05-18 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | NON AOP | MAY 26 PLANNED | MAY 26
TRD3AS13685 | 1492 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Bhudhawarpet , Kurnool (Full Renovation) | Kurnool |  |  |  | 0 |  |  |  |  | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27 | NON AOP
SMRTAS14063 | 1493 |  | TANU | QF3U | SMRTTQF3U00 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu |  | Senthil Muthhaiah | Beard Sell Garden, Mettur | Mettur | 18771 | 2026-02-17 | 2026-03-09 | 35 |  | 2026-04-13 | 2026-05-30 | 2026-05-31 | EPC Ready | 100% |  | PENDING | 2026-05-31 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26
DIGSBK13473 | 1494 |  | T8XH | QT7R | CDITMQT7R00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra | Marathwada | Rahul Atal | Barmera Complex Parbhani | Parbhani | 6293 | 2026-05-22 | 2026-05-25 | 35 |  | 2026-06-29 | 2026-06-29 |  | WIP | 65% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED |  | AUGUST 25
GRDHAK13550 | 1495 |  |  |  |  | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Andhra Pradesh |  |  | Bapulapadu | Bapulapadu |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | JULY 25
GRDSAK14698 | 1496 | DS-KA-00156 | TBFN | QHHV | DARKKQHHV00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Karnataka |  | Sunil B S | Bannimatap | Mysuru | 4559 | 2026-01-05 | 2026-02-06 | 15 |  | 2026-02-21 | 2026-03-05 | 2026-03-10 | EPC Ready Previous FY | 100% | YTL | PENDING | 2026-04-30 | Launched | FY 25-26 | AOP |  |  | SEPTEMBER 25
GRDSAK14708 | 1497 | DS-KA-00155 | TBGM | QHIT | DARKKQHIT00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Karnataka | Bangalore | Mukesh Mukul | Bangarpete | Bangalore | 3389 | 2026-03-16 | 2026-04-09 | 15 |  | 2026-04-24 | 2026-05-12 | 2026-05-12 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | MAY 26 | SEPTEMBER 25
GRDSAK14685 | 1498 | DS-KA-00153 | TBFA | QHHG | DARKKQHHG00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Karnataka |  | Jeevan H G | Balagere | Bangalore | 3607 | 2026-01-19 | 2026-01-27 | 15 |  | 2026-02-11 | 2026-03-05 | 2026-03-10 | EPC Ready Previous FY | 100% | YTL | PENDING |  | YTL | FY 25-26 | AOP |  |  | AUGUST 25
GRDSSD14677 | 1499 | DS-TL-00081 | TBFZ | QHIF | DARKNQHIF00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | AK | Telangana |  | Venkateshwar Rao N | Bachupally | Hyderabad | 2390 | 2026-03-10 | 2026-03-11 | 15 |  | 2026-03-26 | 2026-04-10 | 2026-04-09 | EPC Ready | 100% |  | 2026-05-13 | 2026-04-30 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26 | AUGUST 25
YOCOAS13321 | 1500 |  | TBCT | QHFG | TYOUKQHFG00 | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta Conversion | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka | Bangalore | Vengatesh Prabhu Gopalan | Avantra to Yousta - TS Commercial street, Bangalore | Bengaluru | 10271 | 2026-01-28 | 2026-01-29 | 35 | 60 | 2026-05-04 | 2026-05-30 |  | Partial WIP | 68% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
TRFTAS14945 | 1501 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala |  |  | AVANTRA TO FOOTWEAR --O Mall Cochin, Kerala | Cochin | 3619 |  |  |  | 0 |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
TRRFAS10755 | 1502 |  | T1UO | Q2Y9 | TSARTQ2Y901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | Srinivas P | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu | Chennai |  | Avantra Refit - Marina Mall, Chennai | Chennai | 6978 | 2025-04-02 | 2025-04-10 | 0 | 45 |  |  |  | On Hold | 19% |  |  |  |  | FY 26-27 | NON AOP
FLDHAK12811 | 1503 |  | FR3L | QEVA |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Karnataka |  |  | Avantra - City Center, Mangalore (FR3L | Mangalore | 4288 |  |  | 0 | 25 |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
SEVEBK10612 | 1504 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Gujarat | Surat |  | Avadh Kontina | Surat |  |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK10611 | 1505 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai |  | Aum Supreme, Kalyan | Kalyan |  |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK10609 | 1506 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Gujarat | Surat | Anil Nakum | Ashirwad High Street | Surat |  |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
DIGSBK14973 | 1507 |  |  | QHDO | CDIT7QHDO00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Goa |  |  | Annex Pios, Mapusa, Goa | Goa |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP
SMRTSD13403 | 1508 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | West Bengal |  |  | Alipurduar | Alipurduar |  |  |  | 35 |  |  |  |  | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP
ADOFAS11458 | 1509 |  |  |  |  | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka | Bengaluru |  | Ajio Studio | Bengaluru |  |  |  | 55 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
SEVEBK15080 | 1510 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | AIMS Hospital, Dombivli | Dombivali |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
DIGSRT11547 | 1511 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Haryana |  |  | Agra Chowk, NH-2, Palwal | Palwal |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
SEVEBK10630 | 1512 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra | West Maharashtra |  | Adi Elementis | Pune | 1245 |  |  | 35 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP
DIGSRT14983 | 1513 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Punjab |  |  | 9th Avenue, Kharar, Mohali Punjab | Mohali |  |  |  | 35 |  |  |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | SEPTEMBER 25
ADOFRT12644 | 1514 |  |  |  |  | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | North | RT | Delhi & NCR | Delhi |  | 7th floor (Prakshdeep Building ) | Delhi |  |  |  | 55 |  |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | NON AOP
GRDSAK14580 | 1515 | DS-KL-00020 | TBFC | QHHJ | DARKVQHHJ00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Kerala |  | Dijeesh PD | Vytilla | Kochi | 3921 | 2026-04-11 | 2026-04-21 | 15 |  | 2026-05-06 | 2026-05-30 | 2026-06-02 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | MAY 26 PLANNED | JUNE 26
FLDHAK12776 | 1516 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Karnataka | Bengaluru |  | T2Y-HSR Layout, Bangalore | Bengaluru | 7693 |  |  | 0 | 25 |  |  |  | On Hold | 0% |  |  |  |  | FY 26-27 | AOP |  |  | SEPTEMBER 25
DIGSRT10482 | 1517 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Rajasthan |  |  | Jaipur Road, Bikaner | Bikaner |  |  |  | 35 |  |  |  |  | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
DIGSBK14981 | 1518 |  | TBIT | QHKX | CDITMQHKX00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU |  | Rajesh Nikalje | Digital, Trident Avalon, Badlapur E, Mumbai, | Badlapur | 8500 | 2026-04-03 | 2026-04-07 | 35 |  | 2026-05-12 | 2026-06-11 |  | WIP | 65% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED
DIGSAS14975 | 1519 |  | T9F3 | Q5L0 | CDITKQ5L000 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Karnataka | Gulbarga | Chand Hussain | BVB College Road, Bidar, Karnataka, | Bidar | 7263 | 2026-02-14 | 2026-02-15 | 35 |  | 2026-03-22 | 2026-04-05 | 2026-04-02 | EPC Ready | 100% |  | PENDING | 2026-04-14 | Launched | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26 | OCTOBER 25
SMRTSD14933 | 1520 |  | TAH5 | QGMD | SMRTAQGMD01 | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Andhra Pradesh |  |  | BTS Property for SMART @ TSR Plaza, J P Road, Bhimavaram, AP, West Godavari Dist., AP - (T C V Narsimha Rao Property) | Bhimavaram | 17666 | 2026-05-22 |  | 35 |  |  |  |  | YTS | 0% |  |  |  |  | FY 26-27 | AOP | #N/A |  | JULY 25
DIGSRT14972 | 1521 |  | TBI9 | QHLN | CDITUQHLN00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Delhi & NCR |  | Saket Sharma | Artha Mart, Noida, DL NCR, | Noida | 8035 | 2026-04-03 | 2026-04-03 | 35 |  | 2026-05-08 | 2026-06-06 |  | WIP | 85% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED |  | JULY 25
DIRFSD15262 | 1522 |  | 6368 | NS55 | CDITBNS5503 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | East | SD | Bihar | Gaya | Subir Singh | APR City Centre, Gaya | Gaya | 8037 | 2026-02-06 | 2026-02-07 | 0 | 60 | 2026-04-08 | 2026-04-10 | 2026-04-13 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 | AOP | APRIL 26 PLANNED | APRIL 26 | JULY 25
DIRFSD15276 | 1523 |  | 8928 | NEV5 | CDITONEV505 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | East | SD | Orissa | Bhubaneshwar | Abhijit Hazra | Kharvelnagar | Bhubaneshwar | 8200 | 2026-02-06 | 2026-02-07 | 0 | 60 | 2026-04-08 | 2026-04-24 | 2026-04-27 | EPC Ready | 100% |  | 2026-05-09 | 2026-05-09 | Launched | FY 26-27 | AOP | APRIL 26 PLANNED | APRIL 26 | NOVEMBER 25
DIRFSD15277 | 1524 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | East | SD | Telangana |  |  | Inorbit Mall, Hyderabad, | Hyderabad | 7631 | 2026-02-06 |  | 0 |  | 2026-02-09 |  |  | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
MIREBK15280 | 1525 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC Initiative _Chaturbhuj Kharghar | Mumbai |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
MIREBK15281 | 1526 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC Initiative _Samrin Heritage | Mumbai |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
MIREBK15282 | 1527 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC Initiative _Sai Miracle In homes Kharghar | Mumbai |  |  |  | 0 |  |  |  |  | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
DIGSSD15285 | 1528 |  | TBI1 | QHLE | CDITNQHLE00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Telangana | Hyderabad | Shankar T | Boduppal, Hyderabad, TG | Hyderabad | 7060 | 2026-02-10 | 2026-02-12 | 35 |  | 2026-03-19 | 2026-04-18 | 2026-04-22 | EPC Ready | 100% |  | OTHER ISSUES |  | YTL | FY 26-27 | AOP | MARCH 26 PLANNED | APRIL 26
SEVEBK15459 | 1529 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Urmi Real Estate, Lower Parel, Mumbai | Mumbai | [8 empty] | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP |  |  | AUGUST 25
SEVEBK15462 | 1530 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Peninsula Business Park, Lower Parel, Mumbai | Mumbai | [8 empty] | Budget Submitted - Approval Awaited | 0% |  |  |  |  | FY 26-27 | AOP |  |  | JULY 25
MIREBK15463 | 1531 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC-Haware Centurion | Mumbai | [8 empty] | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
SIGNSD15464 | 1532 |  |  |  |  | C. Grocery | Grocery | Signature | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Assam & NE |  |  | PRM Centrpoint Mall | Agartala | 4888 | [7 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
MIREBK15560 | 1533 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC Initiative _Giriraj Seawoods | Mumbai | [8 empty] | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | SEPTEMBER 25
MIREBK15561 | 1534 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC Initiative _Platinum Experio Kalamboli | Mumbai | [8 empty] | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | AUGUST 25
MIREBK15562 | 1535 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC Initiative _Shree Siddhivinayak Koperkhairane | Mumbai | [8 empty] | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP
MIREBK15563 | 1536 |  |  |  |  | E. Other Business | Other Business | Misc - Refit | Amit C | Arju Tiwari | Kiran Patil | Refit | West | BK | GMU |  |  | HVAC Initiative _Mulund Munish Apartment | Mumbai | [8 empty] | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 | NON AOP |  |  | DECEMBER 25
GRREAS15564 | 1537 |  |  |  |  | C. Grocery | Grocery | Grocery Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Kerala |  |  | Remodel Smart Palai | Ernakulam | [8 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | #N/A |  |  | NOVEMBER 25
GRREAS15565 | 1538 |  |  |  |  | C. Grocery | Grocery | Grocery Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Tamil Nadu |  |  | Remodel Smart Vellore | Vellore | [8 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | #N/A |  |  | AUGUST 25
AZORAS15566 | 1539 |  | TBFH | QHHM | TAZOKQHHM00 | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka | Bangalore | Debkamal B | No 2326 17th cross HSR layout Sector 1 Bangalore 560102 | Bangalore | 10996 | 2026-02-18 | 2026-03-06 | 60 |  | 2026-05-05 | 2026-05-08 | 2026-05-12 | EPC Ready | 100% |  | PENDING | 2026-05-08 | Launched | FY 26-27 | AOP | MAY 26 PLANNED | MAY 26 | AUGUST 25
TRFTSD15570 | 1540 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Andhra Pradesh |  |  | GNT Road, Visakhapatnam | Visakhapatnam | [8 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
TRD4SD15571 | 1541 |  | TBLK | QHMX | TRNDAQHMX00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends 4.0 | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Andhra Pradesh |  |  | Guntakal | Guntakal | 12546 | 2026-04-30 | 2026-05-04 | 45 |  | 2026-06-18 | 2026-06-18 |  | WIP | 45% |  |  |  |  | FY 26-27 | NON AOP | JUNE 26 PLANNED
SD15573 | 1542 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Assam & NE |  |  | Old Motor Stand Rd, Santipara, Dhaleswar, Agartala, Tripura 799001 | Agartala | [8 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | #N/A |  |  | AUGUST 25
TRDSSD15575 | 1543 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Jharkhand |  |  | Ozone High Street Bank More Dhanbad, 826001.Jharkhand | Dhanbad | [8 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
AZORAS15576 | 1544 |  | TBUQ | QHWT | TAZOKQHWT00 | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka | Bangalore | Kumaran | PMC, Whitefield, Bangalore | Bangalore | 13125 | 2026-03-15 | 2026-03-26 | 60 |  | 2026-05-25 | 2026-06-10 |  | WIP | 70% |  |  |  |  | FY 26-27 | AOP | MAY 26 PLANNED |  | JULY 25
TRFTAS15577 | 1545 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | Portico to Footwear Royal Meenakshi Mall,Bannergatta Road,Bangalore,KA | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
TRFTAS15578 | 1546 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | Portico to Footwear Hennur Bagalur Main Road, Bangalore | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
TRFTAS15579 | 1547 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | Inorbit mall – Gokul Road – Hubli. | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
AZORAS15580 | 1548 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | HRBR Layout Kalyan Nagar – Bangalore | [9 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
TRSAAS15581 | 1549 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Avantra | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | HSR Layout,Bangalore | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | OCTOBER 25
TRFTAS15582 | 1550 |  | TBN6 | QHOP | FOOTKQHOP00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | Shankarpura, Mandya - Next to Croma, MC Road, Bandigowda Layout | Mandya | 2420 | 2026-04-25 | 2026-04-30 | 35 |  | 2026-06-04 | 2026-06-14 |  | WIP | 60% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED |  | AUGUST 25
GAPEAS15583 | 1551 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | PMC Whitefield – Bangalore | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | SEPTEMBER 25
TRDSAS15584 | 1552 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | Begur road , Hongasandra , Bangalore | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | SEPTEMBER 25
TRDSAS15585 | 1553 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Karnataka |  |  | BEML Layout Rajarajeshwari nagar Bangalore 560098 | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
PERFAS15586 | 1554 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Performax | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala |  |  | Emad Builders Pvt Ltd , Capitol Mall , N H Road ,Civil station PO, Kannur ,PIN 670002 | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
TRD4AS15587 | 1555 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Trends 4.0 | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala |  |  | MR Building, Karunagappally | [9 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | NON AOP |  |  | OCTOBER 25
YOTHAS15588 | 1556 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala |  |  | MR Building, Karunagappally | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | SEPTEMBER 25
YOTHAS15589 | 1557 |  | TL5D | QY9B | TYOUVQY9B00 | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Kerala |  |  | Capitol Mall -Kannur, Kerela | Kannur | 7222 | 2026-04-27 | 2026-05-04 | 35 |  | 2026-06-08 | 2026-06-30 |  | WIP | 30% |  |  |  |  | FY 26-27 | AOP | JUNE 26 PLANNED
TRDSSD15592 | 1558 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Orissa |  |  | Nayapali,BBSR–ODISHA | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
YOCOAS15595 | 1559 |  | TBZF | QIBT | TYOUTQIBT00 | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta Conversion | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Tamil Nadu |  |  | Gap + Avantra Conversion to Yousta - Marina Mall, Chennai | Chennai | 5661 | 2026-05-14 | 2026-05-25 | 35 | 15 | 2026-07-14 | 2026-07-14 |  | WIP | 10% |  |  |  |  | FY 26-27 | NON AOP | JULY 26 PLANNED |  | OCTOBER 25
YOTHAS15596 | 1560 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | South | SZ FO | Tamil Nadu |  |  | Junction Main Road, Near 5 Roads junction, Salem | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
YOTHSD15597 | 1561 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana |  |  | Alwal, Hyderabad | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | SEPTEMBER 25
YOTHSD15598 | 1562 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana |  |  | AS Rao Nagar, Secunderabad, Telangana. | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | NOVEMBER 25
GAPESD15599 | 1563 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | GAP EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana |  |  | Irrum Manzil Mall, Hyderabad, Telangana | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | JULY 25
AZORSD15600 | 1564 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Azorte | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Telangana |  |  | Suncity, Hyderabad ( League Mall) | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP |  |  | AUGUST 25
YOTHSD15602 | 1565 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | West Bengal |  |  | Sentrum Mall Beside Zudio, Asansol | [9 empty] | ML Received - Design WIP | [5 empty] | FY 26-27 | AOP
TRDSSD15603 | 1566 |  |  |  |  | B. Fashion & Lifestyle | Trends & Allied Formats | Trends | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | West Bengal |  |  | Sree Cinema,Kolkata | [9 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 | AOP
TRD4SD15604 | 1567 |  |  |  | TRNDWQHXS00 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends 4.0 | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | West Bengal |  |  | Alcove Triveni Mall,Srirampur,Hooghly,WB | Srirampur | 10162 | [7 empty] | Budget Approved - RFC Awaited | [5 empty] | FY 26-27 | NON AOP
SEVEBK15761 | 1568 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Bhavan's College Andheri | [9 empty] | On Hold | 0% |  |  |  |  | FY 26-27 | AOP |  |  | NOVEMBER 25
URBLSD15762 | 1569 |  |  |  |  | E. Other Business | Other Business | Furniture - Mid Premium Store (UL) | Amit C | Arju Tiwari | Kiran Patil | NSO | East | SD | Bihar |  |  | RPS More , Patna - Second Floor | [9 empty] | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27 | AOP
GRDSAK15765 | 1570 |  | TCAM | QIDW | DARKTQIDW00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu |  |  | Thudiyalur | Coimbatore | 2323 | 2026-06-01 |  | 15 |  | 2026-06-19 |  |  | YTS | [5 empty] | FY 26-27 | AOP | JUNE 26 PLANNED |  | DECEMBER 25
SEVEBK16026 | 1571 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Twin Tower- RCP, Ghansoli . | [9 empty] | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 |  |  |  | SEPTEMBER 25
GRDSSD16027 | 1572 |  |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | Jharkhand |  |  | Giridih | [9 empty] | Pre SDR Site | [5 empty] | FY 26-27
GRDSSD16028 | 1573 |  |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | Jharkhand |  |  | Ganpati Traders | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 |  |  |  | JULY 25
GRDSSD16029 | 1574 |  |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | Jharkhand |  |  | Bank More- Center Point | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 |  |  |  | JULY 25
GRDSAK16030 | 1575 |  |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | South | AK | Tamil Nadu |  |  | Thiruvanmiyur | [9 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 |  |  |  | JULY 25
MIDXSD16031 | 1576 |  | TBN7 | QHOT | MDXPNQHOT00 | A. Consumer Electronics & Jewels | Consumer Electronics | DMS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Telangana |  | Rupesh Dussa | Mini DX, Malkajgiri, Hyderabad | Hyderabad | 445 | 2026-02-24 | 2026-03-06 |  | 21 | 2026-03-27 | 2026-04-18 | 2026-04-16 | EPC Ready | 100% |  | 2026-05-02 | 2026-04-25 | Launched | FY 26-27 |  | MARCH 26 PLANNED | APRIL 26 | JULY 25
MIDXBK16093 | 1577 |  | 3560 | NL66 | MDXPGNL6601 | A. Consumer Electronics & Jewels | Consumer Electronics | DMS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Gujarat |  | Akshay Prajapati | Karelibagh Vadodara | Vadodara | 708 | 2026-03-17 | 2026-03-17 |  | 21 | 2026-04-07 | 2026-04-20 | 2026-04-17 | EPC Ready | 100% |  | OTHER ISSUES |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | NOVEMBER 25
DIGSAS16094 | 1578 |  | QHGU | QHGU | CDITTQHGU00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu |  | Rajendrakumar PMC | Digital, Bagalur Road, Hosur, TN, | Hosur | 8905 | 2026-03-16 | 2026-03-17 | 35 |  | 2026-04-21 | 2026-06-10 |  | WIP | 79% |  |  |  |  | FY 26-27 |  | APRIL 26 PLANNED |  | OCTOBER 25
CFVRSD16095 | 1579 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Andhra Pradesh |  |  | Avantra - Amalapuram | Amalapuram | [8 empty] | Dropped | [5 empty] | FY 26-27
CFVRSD16096 | 1580 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Andhra Pradesh |  |  | Avantra - Kadapa | Kadapa | [8 empty] | Budget Submitted - Approval Awaited | [5 empty] | FY 26-27 |  |  |  | JUNE 25
GRDHKC16097 | 1581 |  |  |  |  | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | West | KC | Gujarat |  |  | VRPL Surat Reliance Mall Udhana SS | Udhana | [8 empty] | Pre Budget Dehire Site | [5 empty] | FY 26-27 |  |  |  | JUNE 25
GRDHKC16098 | 1582 |  | 2193 | 2193 | DH-SMPT-451-MH-2193 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | West | KC | Maharashtra |  | Prashant Wankhede | SP ROM Pune Mont-Vert-Pashan Rd | Pune | 3558 | 2026-04-13 | 2026-04-13 |  | 15 | 2026-04-28 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% |  | PENDING | 2026-05-28 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | NOVEMBER 25
SMRTRT16099 | 1583 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | North | RT | Uttarakhand |  |  | Raghunath City Mall | Almora | [8 empty] | SDR in Progress | [5 empty] | FY 26-27 |  |  |  | AUGUST 25
SMRTRT16100 | 1584 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | North | RT | Uttarakhand |  |  | Ramnagar Road, Kashipur | Udam Singh Nagar | [8 empty] | SDR in Progress | [5 empty] | FY 26-27 |  |  |  | SEPTEMBER 25
GRDHKC16101 | 1585 |  |  |  |  | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | North | KC | Delhi & NCR |  |  | SIG NDLS Madhuban Road Dayanand Block | Delhi | [8 empty] | Pre Budget Dehire Site | [5 empty] | FY 26-27 |  |  |  | AUGUST 25
GRDHKC16102 | 1586 |  | 2763 | 2763 | DH-DARK-451-DL-2763 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | North | KC | Delhi & NCR |  | Anil Singh | Kichripur | Delhi | 2405 | 2026-04-07 | 2026-04-07 |  | 15 | 2026-04-22 | 2026-05-08 | 2026-04-30 | EPC Ready | 100% |  | 2026-05-30 | 2026-04-30 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26 | SEPTEMBER 25
GRDHAK16103 | 1587 |  | 3032 | 3032 | DH-SIGN-451-OR-3032 | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Orissa |  | Balaram Sahu | SIG OD Cuttack Cantonment Road | Cuttack | 3765 | 2026-04-09 | 2026-04-09 |  | 15 | 2026-04-24 | 2026-05-10 | 2026-05-14 | EPC Ready | 100% |  | PENDING | 2026-05-14 | Launched | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | AUGUST 25
GRBSAS16105 | 1588 |  |  |  |  | C. Grocery | Grocery | Grocery Bismi | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Palakkad Ponnani Rd, Pattambi | Pattambi | [8 empty] | SDR Done - ML Pending | [5 empty] | FY 26-27 |  |  |  | AUGUST 25
SEVEBK16192 | 1589 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | DAKC, Ghansoli | [9 empty] | Budget Approved - RFC Awaited | 0% |  |  |  |  | FY 26-27 |  |  |  | AUGUST 25
JESART16194 | 1590 |  | TBMV | QHNY | JEWEUQHNY00 | A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels SAS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Uttar Pradesh |  | Deepak Srivastava | Umesh South Point, Gole Market, Mahanagar | Lucknow | 7330 | 2026-03-22 | 2026-03-24 | 35 |  | 2026-04-28 | 2026-05-18 | 2026-05-21 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | MAY 26 | SEPTEMBER 25
SEVEBK16290 | 1591 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Godrej II, Vikhroli | [9 empty] | On Hold | 0% |  |  |  |  | FY 26-27
JIDGKC16291 | 1592 |  | NA | NA | JMDHR000650 | J. Jio Business | Jio Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | North | KC | Haryana |  |  | Cosmoss Gadget | Panipat | 891 | 2026-05-13 | 2026-05-13 | 7 |  | 2026-05-20 | 2026-05-20 | 2026-05-15 | EPC Ready | 100% |  | 2026-05-15 | 2026-05-15 | Launched | FY 26-27 |  | MAY 26 PLANNED | MAY 26
JIDGKC16292 | 1593 |  | NA | NA | JMDRJ000675 | J. Jio Business | Jio Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | North | KC | Rajasthan |  |  | DB DIGITAL MART | Dholpur | 770 | 2026-04-29 | 2026-04-29 | 7 |  | 2026-05-06 | 2026-05-06 | 2026-05-02 | EPC Ready | 100% |  | 2026-05-02 | 2026-05-02 | Launched | FY 26-27 |  | MAY 26 PLANNED | MAY 26
DIRFRT16387 | 1594 |  | 8950 | NEX8 | CDITUNEX803 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | North | RT | Uttar Pradesh |  | Abarar Ahmad | Halwasiya Court, Lucknow, UP. Phase 3 | Lucknow | 7988 | 2026-03-17 | 2026-03-17 |  | 35 | 2026-04-21 | 2026-04-24 | 2026-04-24 | EPC Ready | 100% |  | 2026-05-06 |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
DIRFSD16389 | 1595 |  | 8955 | NEY4 | CDITWNEY404 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | East | SD | West Bengal |  | Rupankar Das | Axis Mall, Kolkata Phase 2 | Kolkata | 13753 | 2026-04-18 | 2026-04-18 |  | 45 | 2026-05-31 | 2026-05-31 | 2026-05-21 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 |  | MAY 26 PLANNED | MAY 26
MIDHAK16420 | 1596 |  |  |  |  | E. Other Business | Other Business | Misc - Dehire | Amit C | Arju Tiwari | Kiran Patil | Dehire | South | AK | Tamil Nadu |  |  | EA Office Space - 5th Floor - Netmeds Office, Chennai | Chennai | [8 empty] | ML Received - Design WIP | 0% |  |  |  |  | FY 26-27
SEVEBK16421 | 1597 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Pune Metro Wipro Station | Pune | [8 empty] | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27
SEVEBK16422 | 1598 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Pune Metro Infosys Station | Pune | [8 empty] | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27
SEVEBK16423 | 1599 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Pune Metro Pall India Station | Pune | [8 empty] | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27
SEVEBK16424 | 1600 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Pune Metro Wakad Chowk | Pune | [8 empty] | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27
SEVEBK16425 | 1601 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Kiosk Pune Metro- Agriculture Station | Pune | [8 empty] | On Hold | 0% |  |  |  |  | FY 26-27
SEVEBK16426 | 1602 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Bhumi World, Bhiwandi Bypass | Mumbai | [8 empty] | SDR Done - ML Pending | 0% |  |  |  |  | FY 26-27
SEVEBK16427 | 1603 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Snooze House, Amantran, Dombivli | Mumbai | [8 empty] | On Hold | 0% |  |  |  |  | FY 26-27
SEVEBK16428 | 1604 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Gabi Business Park, Bhivandi Bypass | Mumbai | [8 empty] | On Hold | 0% |  |  |  |  | FY 26-27
DIGSRT16429 | 1605 |  | TBMR | QHNV | CDITUQHNV00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | North | RT | Uttar Pradesh |  | Shashi Kant Sharma | Bansuri Square , Fatehabad Road, Agra | Agra | 8234 | 2026-03-20 | 2026-03-24 | 35 |  | 2026-04-28 | 2026-06-10 |  | WIP | 78% |  |  |  |  | FY 26-27 |  | APRIL 26 PLANNED
DIGSSZ FO16430 | 1606 |  | TBMS | QHNW | CDITTQHNW00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | South | SZ FO | Tamil Nadu |  | Ranjit E PMC | Sarvanampatti, Coimbatore TN | Coimbatore | 8682 | 2026-04-01 | 2026-04-01 | 35 |  | 2026-05-06 | 2026-06-15 |  | WIP | 65% |  |  |  |  | FY 26-27 |  | MAY 26 PLANNED
RESQBK16431 | 1607 |  | TBHG | QHJN | RESQMQHJN00 | A. Consumer Electronics & Jewels | Consumer Electronics | RESQ | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU |  | Sunil Grandhe | Lower Ground Floor, Trends, Hill Road, Bandra. | Bandra | 1985 | 2026-03-17 | 2026-03-20 | 35 |  | 2026-04-24 | 2026-04-24 | 2026-04-23 | EPC Ready | 100% |  | PENDING |  | YTL | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
JICEBK16432 | 1608 |  | JC08 | JC08 | RMU-IA53-JCO-M-JC08 | J. Jio Business | Jio Business | Jio Centre | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU |  | Sunil Grandhe | Andheri | Andheri | 4890 | 2026-03-17 | 2026-03-28 | 45 |  | 2026-05-12 | 2026-06-15 |  | WIP | 75% |  |  |  |  | FY 26-27 |  | MAY 26 PLANNED
CEDHKC16433 | 1609 |  | TIY8 | TIY8 | DH-CDIT-452-MH-TIY8 | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | West | KC | Maharashtra |  | Subhash Chaudhari | 93 Avenue, Pune | Pune | 7895 | 2026-03-28 | 2026-03-28 |  | 21 | 2026-04-18 | 2026-04-18 | 2026-04-20 | EPC Ready | 100% |  | PENDING | 2026-04-20 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
CEDHAK16434 | 1610 |  | T6HD | T6HD | DH-BISMI-452-KE-T6HD | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | South | AK | Kerala |  | Dijeesh PD | Kathrikadavu | Kathrikadavu | 11546 | 2026-03-27 | 2026-03-27 |  | 21 | 2026-04-17 | 2026-04-18 | 2026-04-17 | EPC Ready | 100% |  | 2026-05-29 | 2026-04-17 | Launched | FY 26-27 |  | APRIL 26 PLANNED | APRIL 26
SEVEBK16515 | 1611 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Chaitanya ,Viman Nagar -Pune. | Pune | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16516 | 1612 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Keppel Tensteps Kharadi Pune | Pune | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16517 | 1613 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Godrej, Koregaon Park, Pune | Pune | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16518 | 1614 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Aqua Line - MIDC | Mumbai | [8 empty] | On Hold | 0%
SEVEBK16519 | 1615 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Aqua Line - BKC | Mumbai | [8 empty] | On Hold | 0%
SEVEBK16520 | 1616 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Aqua Line - Dadar | Mumbai | [8 empty] | On Hold | 0%
SEVEBK16521 | 1617 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Aqua Line - Worli | Mumbai | [8 empty] | On Hold | 0%
SEVEBK16522 | 1618 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Aqua Line - CSMT | Mumbai | [8 empty] | On Hold | 0%
SEVEBK16523 | 1619 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Line 2&7 - Andheri W | Mumbai | [8 empty] | On Hold | 0%
SEVEBK16524 | 1620 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Line 2&7 - Gundavali | Mumbai | [8 empty] | On Hold | 0%
SEVEBK16525 | 1621 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro -Line 2&7 - Dahisar | Mumbai | [8 empty] | On Hold | 0%
JIDGAK16526 | 1622 |  | NA | NA | JMDKA000666 | E. Other Business | Other Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | South | AK | Karnataka |  |  | Sri Electronics | Nanjangud | 233 | 2026-04-27 | 2026-04-27 | 7 |  | 2026-05-04 | 2026-05-04 | 2026-05-02 | EPC Ready | 100% |  | 2026-05-02 | 2026-05-02 | Launched |  |  | MAY 26 PLANNED | MAY 26
URBSSD16527 | 1623 |  |  |  |  | E. Other Business | Other Business | Urban Ladder SIS | Amit C | Arju Tiwari | Kiran Patil | NSO | East | SD | Bihar |  |  | Centro, Patna | Patna | [8 empty] | Budget Submitted - Approval Awaited | 0%
URBSBK16528 | 1624 |  |  |  |  | E. Other Business | Other Business | Urban Ladder SIS | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Centro, Thakur Mall Dahisar | Mumbai | [8 empty] | Budget Submitted - Approval Awaited | 0%
DMSBK16529 | 1625 |  | 7954 | NCK7 | MDXPMNCK701 | A. Consumer Electronics & Jewels | Consumer Electronics | DMS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra |  | Rahul Atal/Mithilesh Kumar | Deolali Plaza , Nashik, MH | Nashik | 331 | 2026-04-15 | 2026-04-17 | 21 |  | 2026-05-08 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
DIGSSD16530 | 1626 |  | TBVA | QHXO | CDITQQHXO00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Jharkhand |  | Chandra Mohan | Deoghar | Deoghar | 7180 | 2026-04-15 | 2026-04-17 | 35 |  | 2026-05-22 | 2026-06-10 |  | WIP | 75% | [6 empty] | MAY 26 PLANNED
JESABK16531 | 1627 |  | TCED | QIHV | JEWEMQIHV00 | A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels SAS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | GMU | Mumbai | Sunil Grandhe | R City Mall Jewels | Mumbai | 1200 | 2026-04-14 | 2026-04-25 | 35 |  | 2026-05-30 | 2026-06-08 |  | WIP | 65% | [6 empty] | MAY 26 PLANNED
DIRFRT16532 | 1628 |  | 8676 | NEG2 | CDITDNEG203 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | North | RT | Delhi & NCR |  | Manish Rai | Tata Motors Najafgarh | Delhi | 9662 | 2026-04-20 | 2026-04-20 |  | 35 | 2026-05-25 | 2026-06-10 |  | WIP | 65% | [6 empty] | MAY 26 PLANNED
DMSBK16533 | 1629 |  | 7674 | NBH1 | MDXPMNBH102 | A. Consumer Electronics & Jewels | Consumer Electronics | DMS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra |  | Rahul Atal | Nashik College Road | Nashik | 230 | 2026-04-28 | 2026-04-28 | 21 |  | 2026-05-19 | 2026-06-02 | 2026-05-29 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
DMSBK16534 | 1630 |  |  |  | MDXPMNBO501 | A. Consumer Electronics & Jewels | Consumer Electronics | DMS | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | West | BK | Maharashtra |  | Rahul Atal | Nashik Kajal Aparment | Nashik | [8 empty] | Budget Approved - RFC Awaited
DIRFBK16535 | 1631 |  |  |  |  | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | West | BK | Maharashtra |  |  | Star zone Nashik | Nashik | [8 empty] | Budget Approved - RFC Awaited
DIRFBK16536 | 1632 |  | 8919 | NEU8 | CDITMNEU803 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | West | BK | Maharashtra |  | Akshay Kshirsagar | PMC Vimanagar | Pune | 7624 | 2026-04-27 | 2026-04-29 |  | 50 | 2026-06-18 | 2026-06-18 |  | WIP | 48% | [6 empty] | JUNE 26 PLANNED
GRDSSD16537 | 1633 | DS-BR-00010 | TCBI | QIFE | DARKBQIFE00 | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | Bihar |  | Vikas Tripathi | Hajipur | Patna | 2320 | 2026-04-29 | 2026-05-07 | 15 |  | 2026-05-22 | 2026-05-29 | 2026-06-02 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
GRDSSD16538 | 1634 |  |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | West Bengal |  |  | Bolpur | Bolpur | 2027 | [7 empty] | Budget Submitted - Approval Awaited
GRDSSD16539 | 1635 |  |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | West Bengal |  |  | New Daltonganj | Daltonganj | 2542.05 | [7 empty] | Budget Submitted - Approval Awaited
CFVRSZ FO16540 | 1636 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Tamil Nadu |  |  | Palladium Mall, Phoenix Market City, Velachery | Chennai | 5718 | [7 empty] | ML Received - Design WIP
FRSPSZ FO16541 | 1637 |  |  |  |  | C. Grocery | Grocery | FreshPik | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Kerala |  |  | Hi LiTE Boulevard | Kochi | 5743 | [7 empty] | SDR Done - ML Pending
SGFPSD16542 | 1638 |  |  |  |  | C. Grocery | Grocery | Go Fresh | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | West Bengal |  |  | Omega Mall | Kolkata | 2004.98 | [7 empty] | SDR in Progress
GRPRRT16543 | 1639 |  | TNC1 | Q05T | SMRT5Q05T05 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Uttarakhand |  |  | SMT MKT UK Ddn GMS Road | Dehradun | 38358 | 2026-04-20 | 2026-04-20 |  | 21 | 2026-05-11 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
GRPRRT16544 | 1640 |  | U052 | Q06U | SMPTRQ06U06 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Rajasthan |  | Navas Navab | SP RJ Jaipur Avni Plaza | Jaipur | 2246.5 | 2026-04-15 | 2026-04-15 |  | 21 | 2026-05-06 | 2026-05-06 | 2026-05-22 | EPC Ready | 100% |  | 2026-05-21 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
GRPRRT16545 | 1641 |  |  |  | SMPTRNJ8804 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Rajasthan |  |  | SP RJ Jodhpur Mandore Road | Jodhpur | 3358 |  |  |  | 21 |  |  |  | On Hold
GRPRBK16546 | 1642 |  | TNA8 | Q05G | SMRTGQ05G06 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | KC | Gujarat |  | Tushar Nagar | SMT MKT GJ Ahmd Advance Mills | Ahmedabad | 59469 | 2026-04-16 | 2026-04-16 |  | 21 | 2026-05-07 | 2026-06-05 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRBK16547 | 1643 |  | TND5 | Q06H | SMRTGQ06H05 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | KC | Gujarat |  | Ashvin Prajapati | SMT MKT GJ Surat Vesu | Surat | 54569 | 2026-04-16 | 2026-04-16 |  | 21 | 2026-05-07 | 2026-06-05 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRBK16548 | 1644 |  | TND1 | Q06D | SMRTGQ06D04 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | KC | Gujarat |  | Nilesh N Shah | SMT MKT GJ Rajkot Nana Mava | Rajkot | 47857 | 2026-04-16 | 2026-04-16 |  | 21 | 2026-05-07 | 2026-06-05 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRBK16549 | 1645 |  | TEI0 | QZW5 | SMRTEQZW503 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Madhya Pradesh |  |  | SMT MP Satna Modi Tower | Satna | 12721 | 2026-04-21 | 2026-04-21 |  | 21 | 2026-05-12 | 2026-06-05 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRBK16550 | 1646 |  | U085 | Q10S | SMPTEQ10S06 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Madhya Pradesh |  |  | SP MP Jabalpur S R Mall | Jabalpur | 4349 | 2026-04-27 | 2026-04-27 |  | 21 | 2026-05-18 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% |  | 2026-05-30 |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
GRPRBK16551 | 1647 |  | U331 | Q29L | SMPTEQ29L05 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Madhya Pradesh |  | Jagdish Dugaya | SP MP Bhopal Signature City | Bhopal | 2871 | 2026-04-10 | 2026-04-10 |  | 21 | 2026-05-01 | 2026-05-01 | 2026-05-20 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
GRPRBK16552 | 1648 |  | TJX1 | QAD5 | SMRTCQAD503 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Chattisgarh |  | Mukesh Verma | SMT CG Ambikapur Chandgiram Plaza | Ambikapur | 13075 | 2026-04-16 | 2026-04-16 |  | 21 | 2026-05-07 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
GRPRBK16553 | 1649 |  | TEL4 | QUK1 | SMRTMQUK105 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | GMU |  | Vaibhav Jadhav | SMT MUM Thane Raj Icon Palghar | Palghar | 22513 | 2026-04-15 | 2026-04-15 |  | 21 | 2026-05-06 | 2026-06-15 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRBK16554 | 1650 |  | 2876 | NI96 | SMPTGNI9603 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | KC | Gujarat |  |  | SP GJ Ahmd Shahibaugh | Ahmedabad | 4627 | 2026-04-19 | 2026-04-19 |  | 21 | 2026-05-10 | 2026-06-05 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRBK16555 | 1651 |  | 2774 | NI53 | SMPTGNI5305 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | KC | Gujarat |  |  | SP GJ Ahmd Maninagar Adani | Ahmedabad | 3895 | 2026-04-17 | 2026-04-17 |  | 21 | 2026-05-08 | 2026-06-22 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRBK16556 | 1652 |  | 2861 | NI92 | SMPTENI9203 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Madhya Pradesh |  |  | SP MP Ujjain Kanthal | Ujjain | 5322 | 2026-04-17 | 2026-04-17 |  | 21 | 2026-05-08 | 2026-06-05 |  | WIP | [7 empty] | MAY 26 PLANNED
GRREBK16557 | 1653 |  | TF14 | NHB3 | SMRTMNHB303 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | GMU |  | Hitesh Mahtre | Centrepoint Mall Panvel | Navi Mumbai | 20048 | 2026-04-14 | 2026-04-14 |  | 60 | 2026-06-13 | 2026-06-13 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRREBK16558 | 1654 |  | 6210 | NR25 | SMRTMNR2505 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | GMU |  |  | CCM Mall | Mumbai | 21514 | 2026-05-21 | 2026-05-21 |  | 60 | 2026-07-20 | 2026-07-20 |  | WIP | [7 empty] | JULY 26 PLANNED
SMRTSD16559 | 1655 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Bihar |  |  | D&G Mall | Bhagalpur | 22933.53 | [7 empty] | SDR Done - ML Pending
TRTFSD16560 | 1656 |  | 8019 | NCR8 | TRNDBNCR802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  | Roshan Kumar | MuzafarpurUB Tower | Muzaffarpur | 13215 | 2026-04-22 | 2026-04-22 |  | 50 | 2026-06-11 | 2026-06-11 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSD16561 | 1657 |  | 8095 | NCZ4 | TRNDONCZ403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  | Kamlesh Viswakarma | Cuttack Dolamundi Sq | Cuttack | 15400 | 2026-05-01 | 2026-05-01 |  | 50 | 2026-06-20 | 2026-06-20 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSZ FO16562 | 1658 |  | 5735 | NO92 | TRNDVNO9201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Trivandrm Kowdiar | Trivandrum | 16215 | 2026-04-27 | 2026-04-27 |  | 50 | 2026-06-16 | 2026-06-16 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSZ FO16563 | 1659 |  | 8068 | NCW7 | TRNDVNCW702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kottayam Vettiyil | Kottayam | 12450 | 2026-05-09 | 2026-05-09 |  | 50 | 2026-06-28 | 2026-06-28 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSZ FO16564 | 1660 |  | 8070 | NCW9 | TRNDVNCW901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Payyannur P Mall | Payyannur | 11980 | 2026-04-27 | 2026-04-27 |  | 50 | 2026-06-16 | 2026-06-16 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSD16565 | 1661 |  | 1935 |  | TRNDWNF7400 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Kolkata Nehru Rd | Kolkata | 10294 | [7 empty] | On Hold |  | Full Renovation
TRTFSZ FO16566 | 1662 |  | 8059 | NCV8 | TRNDKNCV802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Hubli U Mall | Hubli | 11426 | 2026-05-07 | 2026-05-07 |  | 50 | 2026-06-26 | 2026-06-26 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSZ FO16567 | 1663 |  | 8312 | NDQ2 | TRNDKNDQ204 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Tumkur Deviprasad | Tumkur | 8049 | 2026-05-06 | 2026-05-06 |  | 50 | 2026-06-25 | 2026-06-25 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSD16568 | 1664 |  | 8040 | NCU1 | TRNDQNCU101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Dhanbad Ozone Mall | Dhanbad | 13320 | 2026-05-08 | 2026-05-08 |  | 50 | 2026-06-27 | 2026-06-27 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSD16569 | 1665 |  | 8014 |  | TRNDANCR304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vizag CMR Central | Visakhapatnam | 17956 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16570 | 1666 |  | 8045 |  | TRNDKNCU604 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore Mantri Mal | Bangalore | 16967 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16571 | 1667 |  | 8061 |  | TRNDKNCW103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Mangalore CityCentre | Mangalore | 12184 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16572 | 1668 |  | 8053 | NCV3 | TRNDKNCV305 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Bangalore Kamanahali | Bangalore | 21057 | 2026-05-09 | 2026-05-09 |  | 50 | 2026-06-28 | 2026-06-28 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFSZ FO16573 | 1669 |  | 8107 |  | TRNDTNDA304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai Chrompet | Chennai | 17703 | [7 empty] | On Hold |  | Full Renovation
TRTFSZ FO16574 | 1670 |  | 4827 |  | TRNDTNO7503 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Chennai P Mkt City | Chennai | 9817 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16575 | 1671 |  | 8318 |  | TRNDTNDQ501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Salem RIL Mall | Salem | 13240 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16576 | 1672 |  | 1972 |  | TRNDTNF9304 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Madurai Bye Pass Rd | Madurai | 12603 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16577 | 1673 |  | 8111 |  | TRNDTNDA703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai TH Road | Chennai | 13411 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16578 | 1674 |  | 5844 |  | TRNDTNP6003 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Chennai Lotus Avadi | Chennai | 12515 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16579 | 1675 |  | 8116 |  | TRNDTNDB302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Karur PLA Complex | Karur | 12571 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16580 | 1676 |  | 8117 |  | TRNDTNDB402 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Madurai Vishaal Mall | Madurai | 15679 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16581 | 1677 |  | 8118 |  | TRNDTNDB501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | AK | Tamil Nadu |  |  | Trichy Thillainagar | Tiruchirappalli | 14430 | [7 empty] | NRFC |  | Full Renovation
TRTFSZ FO16582 | 1678 |  | 1966 |  | TRND8NF8902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Puduchery Providence | Pondicherry | 12145 | [7 empty] | NRFC |  | Full Renovation
TRTFRT16583 | 1679 |  | 8035 |  | TRNDHNCT505 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Gurgaon Ambience Mal | Gurgaon | 21462 | [7 empty] | NRFC |  | Cycle-4 EPC
TRTFRT16584 | 1680 |  | 8345 | NDS6 | TRNDUNDS600 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  | Deepak Srivastava/Suresh Kumar | Kanpur Z Square Mall | Kanpur | 9412 | 2026-04-05 | 2026-04-05 |  | 50 | 2026-05-25 | 2026-05-31 | 2026-06-02 | EPC Ready | 100% | Full Renovation | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
TRTFRT16585 | 1681 |  | 8121 | NDB7 | TRNDUNDB700 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Allahabad SP Marg | Allahabad | 9625 | 2026-05-08 | 2026-05-08 |  | 50 | 2026-06-27 | 2026-06-27 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFRT16586 | 1682 |  | TK56 | NWH1 | TRNDUNWH102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Luknow Ring Road | Lucknow | 15024.6 | 2026-05-12 | 2026-05-12 |  | 50 | 2026-07-01 | 2026-07-01 |  | WIP |  | Full Renovation | [5 empty] | JULY 26 PLANNED
TRTFRT16587 | 1683 |  | 8021 | NCS1 | TRND2NCS102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Chandgrh Elante Mall | Chandigarh | 15191 | 2026-05-11 | 2026-05-11 |  | 50 | 2026-06-30 | 2026-06-30 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFRT16588 | 1684 |  | 5811 | NP42 | TRNDRNP4200 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Jaipur GT Central | Jaipur | 10113 | 2026-05-11 | 2026-05-11 |  | 50 | 2026-06-30 | 2026-06-30 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFRT16589 | 1685 |  | 4826 |  | TRNDDNO7404 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Delhi RIL Mal Dwarka | Delhi | 13239 | [7 empty] | On Hold |  | Full Renovation
TRTFRT16590 | 1686 |  | TE92 |  | TRNDUNVR103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Delhi & NCR |  |  | Noida Citycenter Mal | Greater Noida | 11324 | [7 empty] | NRFC |  | Full Renovation
TRTFBK16591 | 1687 |  | 1885 | NF50 | TRNDMNF5001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Pune Seasons Mall | Pune | 11032 | 2026-04-23 | 2026-04-23 |  | 50 | 2026-06-12 | 2026-06-12 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFBK16592 | 1688 |  | 8322 | NDQ9 | TRNDGNDQ901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Gujarat |  |  | Rajkot RIL Mall | Rajkot | 11145 | 2026-05-07 | 2026-05-07 |  | 50 | 2026-06-26 | 2026-06-26 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFBK16593 | 1689 |  | 8034 | NCT4 | TRNDGNCT403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Gujarat |  |  | Vadodara Cine Mall | Vadodara | 17301 | 2026-04-22 | 2026-04-22 |  | 50 | 2026-06-11 | 2026-06-11 |  | WIP |  | Full Renovation | [5 empty] | JUNE 26 PLANNED
TRTFBK16594 | 1690 |  | 8088 |  | TRNDMNCY702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Pune Phnx MarketCity | Pune | 19020 | [7 empty] | NRFC |  | Full Renovation
TRTFBK16595 | 1691 |  | 8286 |  | TRNDMNDO103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | GMU |  |  | Mumbai Viviana Thane | Mumbai | 15794 | [7 empty] | NRFC |  | Full Renovation
TRTFBK16596 | 1692 |  | 8087 |  | TRNDMNCY602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Full) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Nasik CityCentre Mal | Nashik | 18222 | [7 empty] | NRFC |  | Full Renovation
GRDSKC16597 | 1693 |  | TBKP | QHMG | DARKMQHMG00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU | Mumbai | Hareshprasad Mishra | Simran Residency, Sector 7, Kharghar | Mumbai | 2125 | 2026-03-27 | 2026-04-22 | 15 |  | 2026-05-07 | 2026-05-10 | 2026-05-12 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16598 | 1694 |  | 5731 | NO89 | TRNDVNO8903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pala Dream Mall | Palai | 9468 | 2026-04-21 | 2026-04-21 |  | 15 | 2026-05-06 | 2026-05-31 |  | WIP |  | Cycle-3 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16599 | 1695 |  | TR97 | NXO1 | TRNDVNXO102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kattappana TST | Kattappana | 6245 | 2026-04-20 | 2026-04-20 |  | 15 | 2026-05-05 | 2026-05-31 |  | WIP |  | Cycle-3 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16600 | 1696 |  | TX4C | Q3M8 | TFITVQ3M801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kannur Near Kannur Mall | Kannur | 18045 | 2026-04-22 | 2026-04-22 |  | 15 | 2026-05-07 | 2026-05-31 |  | WIP |  | Cycle-2 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16601 | 1697 |  | 8305 | NDP5 | TRNDVNDP501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pala Puthetu Arcade | Pala | 9905 | 2026-04-21 | 2026-04-21 |  | 15 | 2026-05-06 | 2026-05-31 | 2026-06-02 | EPC Ready | 100% | Cycle-2 EPC | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
TRTRSZ FO16602 | 1698 |  | TO17 | QVAL | TFITVQVAL01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kottayam Kodimatha | Kottayam | 12865 | 2026-04-21 | 2026-04-21 |  | 15 | 2026-05-06 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSD16603 | 1699 |  | TFR0 | QYU1 | TEXPOQYU102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Paradeep TST | Paradeep | 7432 | 2026-04-22 | 2026-04-22 |  | 15 | 2026-05-07 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-30 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16604 | 1700 |  | TQD5 | Q0WO | TEXPKQ0WO02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Kanakpura TST | Kanakpura | 12418 | 2026-04-17 | 2026-04-17 |  | 15 | 2026-05-02 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16605 | 1701 |  | TTD6 | Q2US | TEXPVQ2US01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Chingavanam TST | Chingavanam | 8193 | 2026-04-22 | 2026-04-22 |  | 15 | 2026-05-07 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16606 | 1702 |  | TPN7 | Q0OC | TEXPVQ0OC05 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Ponkunnam TST | Ponkunnam | 6331 | 2026-04-22 | 2026-04-22 |  | 15 | 2026-05-07 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
URBLBK16607 | 1703 |  |  |  |  | E. Other Business | Other Business | Furniture - Mid Premium Store (UL) | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Creaticity - Pune | Pune | [8 empty] | SDR Done - ML Pending | 0%
URBLSZ FO16608 | 1704 |  |  |  |  | E. Other Business | Other Business | Furniture - Mid Premium Store (UL) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka |  |  | Electronic City, Hosur Road | Bangalore | [8 empty] | SDR Done - ML Pending | 0%
FLDHKC16609 | 1705 |  | T9XE | T9XE | DH-ZIVA-419-RJ-T9XE | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | North | KC | Rajasthan |  |  | T9XE,Zivame,Udaipur,Urban Square Mall,RJ | Udaipur | 556 | 2026-04-22 | 2026-04-22 |  | 25 | 2026-05-17 | 2026-05-17 | 2026-05-17 | EPC Ready | 100% |  | 2026-05-18 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16610 | 1706 |  | TJX6 | QWF2 | TFITVQWF201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Paravur Zams Mall | Paravur | 9162 | 2026-04-23 | 2026-04-23 |  | 15 | 2026-05-08 | 2026-05-31 | 2026-06-02 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
TRTRSZ FO16611 | 1707 |  | TEW7 | QZL9 | TEXPVQZL902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Adimali TST | Adimali | 7043 | 2026-04-28 | 2026-04-28 |  | 15 | 2026-05-13 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16612 | 1708 |  | TU85 | NKU7 | TRNDKNKU703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Kunigal TST | Kunigal | 5869 | 2026-04-22 | 2026-04-22 |  | 15 | 2026-05-07 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16613 | 1709 |  | TEW8 | QZM1 | TEXPVQZM102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Parippally TST | Parippally | 6772 | 2026-04-28 | 2026-04-28 |  | 15 | 2026-05-13 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16614 | 1710 |  | 5686 | NO81 | TRNDVNO8100 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Wayanad Mint Mall | Kozhikode | 6575 | 2026-04-27 | 2026-04-27 |  | 15 | 2026-05-12 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16615 | 1711 |  | TLB4 | QGS0 | TEXPKQGS001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Karnataka |  |  | Sagara TST | Sagara | 5325 | 2026-04-25 | 2026-04-25 |  | 15 | 2026-05-10 | 2026-05-10 | 2026-05-16 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16616 | 1712 |  | TW06 | NNK8 | TRNDVNNK802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kothamangalam TST | Kothamangalam | 4928 | 2026-04-27 | 2026-04-27 |  | 15 | 2026-05-12 | 2026-05-12 | 2026-05-18 | EPC Ready | 100% | Cycle-4 EPC | 2026-05-24 | 2026-05-24 | Launched |  |  | MAY 26 PLANNED | MAY 26
SEVEBK16617 | 1713 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Agastya Corporate Park, Piramal Realty, Kurla | Mumbai | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16618 | 1714 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Wah Punjab, Pune | Pune | [8 empty] | Dropped | 0%
SEVEBK16619 | 1715 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Runwal Garden, Dombivli | Mumbai | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16620 | 1716 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | One BKC, Mumbai | Mumbai | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16621 | 1717 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Yashwant Prestige, Virar | Mumbai | [8 empty] | SDR Done - ML Pending | 0%
DIGSSD16623 | 1718 |  | TM1L | QZ3Z | CDITBQZ3Z00 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | Amit C | Dyaneshwar Wagh | Aditya Dawre | NSO | East | SD | Bihar |  | Roshan Kumar | Sitamarhi | Sitamarhi | 7425 | 2026-04-23 | 2026-04-25 | 35 |  | 2026-05-30 | 2026-06-10 |  | WIP | 73% | [6 empty] | MAY 26 PLANNED
TRTRSZ FO16624 | 1719 |  | TCR4 | NQO3 | TFITVNQO303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kasargod MG Road | Kasargod | 10100 | 2026-04-30 | 2026-04-30 |  | 15 | 2026-05-15 | 2026-05-31 |  | WIP |  | Cycle-3 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16625 | 1720 |  | 9661 | NFY4 | TRNDVNFY401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Changnsry D Square | Changanassery | 11946 | 2026-04-30 | 2026-04-30 |  | 15 | 2026-05-15 | 2026-05-31 |  | WIP |  | Cycle-3 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16626 | 1721 |  | 5694 | NO86 | TRNDVNO8601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Trivandrm Mozhiyathu | Adoor | 5734 | 2026-04-30 | 2026-04-30 |  | 15 | 2026-05-15 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16627 | 1722 |  | TW70 | NON6 | TRNDVNON603 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | KARUKACHAL TST | Karukachal | 7844 | 2026-04-30 | 2026-04-30 |  | 15 | 2026-05-15 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16628 | 1723 |  | TBA9 | NAJ7 | TRNDVNAJ701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kanjirapally TST | Kanjirapally | 8393 | 2026-04-30 | 2026-04-30 |  | 15 | 2026-05-15 | 2026-05-31 |  | WIP |  | Cycle-4 EPC | [5 empty] | MAY 26 PLANNED
TRTRBK16629 | 1724 |  | 8357 | NDT7 | TRNDMNDT701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Aurngabad RIL Garkh | Aurangabad | 9844 | 2026-05-02 | 2026-05-02 |  | 15 | 2026-05-17 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-4 EPC | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16630 | 1725 |  | TX8O | Q2VZ | TWIWUQ2VZ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Allahabad TW SP Marg Civil Lines Prayagraj | Allahabad | 1167 | 2026-05-01 | 2026-05-01 |  | 15 | 2026-05-16 | 2026-05-16 | 2026-05-15 | EPC Ready | 100% | Cycle-1 FM | 2026-05-14 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16631 | 1726 |  | TFE5 | QZE2 | TFITUQZE202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Lalitpur Chowk market Near elite cinema | Lalitpur | 8917.54 | 2026-05-01 | 2026-05-01 |  | 15 | 2026-05-16 | 2026-05-16 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRBK16632 | 1727 |  | TZNU | QDAO | TEXPMQDAO02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Shahada TST | Shahada | 6490 | 2026-04-28 | 2026-04-28 |  | 15 | 2026-05-13 | 2026-05-13 | 2026-05-09 | EPC Ready | 100% | Cycle-1 FM | 2026-05-09 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRBK16633 | 1728 |  | TWWC | Q6X7 | TEXPMQ6X703 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Uran Islampur TST Peth Sangli Road | Uran Islampur | 5357 | 2026-05-01 | 2026-05-01 |  | 15 | 2026-05-16 | 2026-05-16 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16634 | 1729 |  | TFC0 | QZB5 | TFIT9QZB503 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Rupnagar Chotti Haveli Bela Rd | Ropar (Rupnagar) | 5474 | 2026-05-01 | 2026-05-01 |  | 15 | 2026-05-16 | 2026-05-16 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-20 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16635 | 1730 |  | T670 | NGJ9 | TRNDJNGJ900 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Jammu Jayadev Cmplex | Jammu | 8068 | 2026-05-01 | 2026-05-01 |  | 15 | 2026-05-16 | 2026-05-16 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
JIDGAK16636 | 1731 |  | NA | NA | JMDTG000669 | J. Jio Business | Jio Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | South | AK | Telangana |  |  | ANJANEYA MOBILES | Gadwal | 299 | 2026-05-22 | 2026-05-22 | 7 |  | 2026-05-29 | 2026-05-29 | 2026-05-25 | EPC Ready | 100% |  | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
JIDGKC16637 | 1732 |  | NA | NA | JMDRJ000676 | J. Jio Business | Jio Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | North | KC | Rajasthan |  |  | METHI INDUSTRIES | Sawaimadhopur | 600 | 2026-05-03 | 2026-05-03 | 7 |  | 2026-05-10 | 2026-05-10 | 2026-05-07 | EPC Ready | 100% |  | 2026-05-07 | 2026-05-07 | Launched |  |  | MAY 26 PLANNED | MAY 26
DIRFSZ FO16638 | 1733 |  | 8755 | NEM2 | CDITTNEM204 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | South | SZ FO | Tamil Nadu | Chennai | Ganesh B | Perambur | Chennai | 8369 | 2026-04-30 | 2026-04-30 |  | 35 | 2026-06-04 | 2026-06-10 |  | WIP | 65% | [6 empty] | JUNE 26 PLANNED
FFNSRT16639 | 1734 |  | TBMH | QHNO | TRFFUQHNO00 | B. Fashion & Lifestyle | Trends & Allied Formats (Part A) | Fashion Factory | Srinivas P | Gaurav Shinde | Ankush Hanwate | NSO | North | RT | Uttar Pradesh |  | Abrar Ahmed | Arbit 36, Gorakhpur | Gorakhpur | 18995 | 2026-04-27 | 2026-05-07 | 45 |  | 2026-06-21 | 2026-06-21 |  | WIP | 39% | [6 empty] | JUNE 26 PLANNED
FLDHAK16640 | 1735 |  | 1914 | 1914 | DH-FOOT-419-KA-1914 | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Karnataka |  |  | 1914,Footwear ,BANGALORE,FW MSR Elements Mall THANISANDRA BANGALORE KA,KA | Bangalore | 2303 | 2026-05-06 | 2026-05-06 |  | 25 | 2026-05-31 | 2026-05-31 | 2026-05-21 | EPC Ready | 100% |  | 2026-05-21 | 2026-05-21 | Launched |  |  | MAY 26 PLANNED | MAY 26
GRDSKC16641 | 1736 |  | TCDN | QIHO | DARKMQIHO00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU | Mumbai |  | Shankeshwar Pallazo - Ulwe | Mumbai | 3156 | 2026-04-23 | 2026-04-30 | 15 |  | 2026-05-15 | 2026-05-15 | 2026-05-25 | EPC Ready | 100% |  | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16642 | 1737 |  | T64N | QADA | TEXP6QADA02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Along TST Tummar Bagra | Along | 4030 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-13 | EPC Ready | 100% | Cycle-1 FM | 2026-05-12 | 2026-05-12 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16643 | 1738 |  | TFS1 | QYT1 | TEXPVQYT101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Piravom TST | Piravom | 5000 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-11 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16644 | 1739 |  | TTB9 | Q2UH | TEXP4Q2UH01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Kumarghat TST | Kumarghat | 3866 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-13 | EPC Ready | 100% | Cycle-1 FM | 2026-05-13 | 2026-05-13 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16645 | 1740 |  | TJQ3 | QWI4 | TEXPYQWI401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | WilliamNagar TST | Williamnagar | 6000 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16646 | 1741 |  | TPH6 | Q0LG | TEXPYQ0LG02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Nongmysong TST | Nongmysong | 5691 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16647 | 1742 |  | T86D | QOQW | TEXP6QOQW02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Ziro TST HM Commercial Complex | Ziro | 5542 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-07 | EPC Ready | 100% | Cycle-1 FM | 2026-05-06 | 2026-05-06 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16648 | 1743 |  | TANL | QF3W | TMANAQF3W02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vijayawada TM Gandhi Nagar | Vijayawada | 1742 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-08 | EPC Ready | 100% | Cycle-1 FM | 2026-05-08 | 2026-05-08 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16649 | 1744 |  | TTB5 | Q2UD | TEXP4Q2UD01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Belonia TST | Belonia | 3783 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-18 | 2026-05-18 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16650 | 1745 |  | TO27 | NWT7 | TRNDNNWT702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Khammam Kaman Bazar | Khammam | 10213 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16651 | 1746 |  | TGV4 | QXW1 | TFITBQXW101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Bagaha West Champarn | Bagaha | 10000 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | 2026-05-28 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16652 | 1747 |  | TZ26 | NAB3 | TRNDLNAB301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Kohima Bayavu Colony | Kohima | 11977 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-11 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16653 | 1748 |  | TGL8 | QYC8 | TEXPBQYC801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Rosera TST | Rosera | 6600 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16654 | 1749 |  | TWTE | Q6Q2 | TEXPFQ6Q201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Udalguri TST | Udalguri | 5845 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-31 | 2026-05-28 | EPC Ready | 100% | Cycle-1 FM | 2026-05-28 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16655 | 1750 |  | TPO6 | Q0OO | TEXPBQ0OO02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Mahua TST | Mahua | 4739 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16656 | 1751 |  | TPZ8 | Q0UR | TEXPFQ0UR01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Tangla TST | Tangla | 5842 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | 2026-05-21 | 2026-05-21 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16657 | 1752 |  | T1RA | Q2O9 | TEXPOQ2O902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Cuttack TST Niali | Cuttack | 7130 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-31 | 2026-05-08 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16658 | 1753 |  | TW36 | NNT7 | TEXPANNT701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vuyyuru TST | Vuyyuru | 5810 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | 2026-05-20 | 2026-05-20 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16659 | 1754 |  | TX4R | QGWV | TEXP4QGWV01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Khowai TST Subhash Park Rd | Khowai | 3905 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16665 | 1755 |  | TWRH | Q6K7 | TJNRRQ6K702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Udaipur TJ Panchvati | Udaipur | 1920.19 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-13 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16666 | 1756 |  | TLT8 | QNQ0 | TEXPHQNQ001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Assandh TST | Assandh | 3772 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-16 | EPC Ready | 100% | Cycle-1 FM | 2026-05-15 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16667 | 1757 |  | T193 | QG4M | TFITRQG4M02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Hindaun Hotel Jamana Palace Station Rd | Hindaun | 9348 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16668 | 1758 |  | TFQ1 | QYR9 | TFITJQYR901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Jammu College Road Kathua | Jammu | 8157 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRBK16669 | 1759 |  | T86F | QOQU | TEXPMQOQU01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Gargoti TST Hindtara Complex | Gargoti | 5420 | 2026-04-05 | 2026-04-05 |  | 15 | 2026-04-20 | 2026-05-10 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | APRIL 26 PLANNED | MAY 26
TRTRRT16670 | 1760 |  | T3IM | T3IM | T3IM | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Kargil Bemathang Baroo Ladakh | Kargil | 8484 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16671 | 1761 |  | TDE8 | NQM0 | TFIT9NQM002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Faridkot Circular Road | Faridkot | 8686 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-23 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16672 | 1762 |  | TKY2 | QEY0 | TFIT9QEY002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Tarn Taran Sahib | Tarn Taran Sahib | 9809 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-20 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-12 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16673 | 1763 |  | 9409 | NUA4 | TRNDINUA400 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Himachal Pradesh |  |  | Kangra Mahesraj Twr | Kangra | 9943 | 2026-05-05 | 2026-05-05 |  | 15 | 2026-05-20 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-1 FM | 2026-05-26 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16674 | 1764 |  | TDV9 | NT72 | TFITRNT7201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Bikaner JNV Colony | Bikaner | 9900 | 2026-05-05 | 2026-05-05 |  | 30 | 2026-06-04 | 2026-06-04 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16675 | 1765 |  | TFD8 | QZD4 | TFIT9QZD401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Kapurthala Mall Road | Kapurthala | 11299 | 2026-04-24 | 2026-04-24 |  | 30 | 2026-05-24 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | MAY 26 PLANNED
TRTRRT16676 | 1766 |  | TH81 | NYA9 | TRND5NYA904 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Haridwar Ranipur Rd | Haridwar | 8253 | 2026-05-06 | 2026-05-06 |  | 30 | 2026-06-05 | 2026-06-05 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16677 | 1767 |  | TSP7 | Q6J2 | TFIT5Q6J202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Dehradun Jogiwala | Dehradun | 9962 | 2026-05-04 | 2026-05-04 |  | 30 | 2026-06-03 | 2026-06-03 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRBK16678 | 1768 |  | 5943 | NQ02 | TRNDMNQ0203 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Mumbai InfinityMalad | Mumbai | 12938 | 2026-04-16 | 2026-04-16 |  | 15 | 2026-05-01 | 2026-05-08 | 2026-05-14 | EPC Ready | 100% | Phase -02 | 2026-05-14 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
URBLSZ FO16679 | 1769 |  |  |  |  | E. Other Business | Other Business | Furniture - Mid Premium Store (UL) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Karnataka |  |  | Airport road , Hunsmaranhalli, Bangalore | Bangalore | [8 empty] | SDR Done - ML Pending | 0%
ADOFSZ FO16680 | 1770 |  |  |  |  | K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | Amit C | Arju Tiwari | Kiran Patil | NSO | South | SZ FO | Tamil Nadu |  |  | Rk salai - 8105 Trends 2nd floor, Chennai | Chennai | [8 empty] | SDR In Progress | 0%
SEVEBK16681 | 1771 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Pizza Hut, Versova- Mumbai | Mumbai | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16682 | 1772 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Vastu Viva Building, Wakad, Pune | Pune | [8 empty] | SDR Done - ML Pending | 0%
SEVEBK16683 | 1773 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | 93 Avenue, Pune | Pune | [8 empty] | SDR Done - ML Pending | 0%
JIDGAK16684 | 1774 |  | NA | NA | JMDKL000661 | J. Jio Business | Jio Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | South | AK | Kerala |  |  | Impulse Mobiles | Idukki | 985 | 2026-05-15 | 2026-05-15 | 7 |  | 2026-05-22 | 2026-05-28 | 2026-05-18 | EPC Ready | 100% |  | 2026-05-18 | 2026-05-18 | Launched |  |  | MAY 26 PLANNED | MAY 26
SEVEBK16685 | 1775 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Piramal Mahalaxmi , Mumbai | Mumbai | [8 empty] | SDR Done - ML Pending
SEVEBK16686 | 1776 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Piramal Byculla , Mumbai | Mumbai | [8 empty] | SDR Done - ML Pending
SEVEBK16687 | 1777 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | Maharashtra |  |  | Flame University, Pune Campus. | Pune | [8 empty] | On Hold
SEVEBK16688 | 1778 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | KIMS, Hospital -Thane | Mumbai | [8 empty] | SDR Done - ML Pending
SEVEBK16689 | 1779 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Plutonium Business Park, Turbhe | Mumbai | [8 empty] | SDR Done - ML Pending
SEVEBK16690 | 1780 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Ace Signature, Thane | Mumbai | [8 empty] | SDR Done - ML Pending
SEVEBK16691 | 1781 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU |  |  | Mumbai Metro Station, Andheri (W), Line2A - Yellow Line | Mumbai | [8 empty] | SDR In Progress
JIDGKC16692 | 1782 |  | NA | NA | JMDMH000658 | J. Jio Business | Jio Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | West | KC | Maharashtra |  |  | Sandesh Agencies | Pune | 753 | 2026-05-22 | 2026-05-22 | 7 |  | 2026-05-29 | 2026-05-29 | 2026-05-23 | EPC Ready | 100% |  | 2026-05-23 | 2026-05-23 | Launched |  |  | MAY 26 PLANNED | MAY 26
JIDGAK16693 | 1783 |  | NA | NA | JMDKA000670 | J. Jio Business | Jio Business | Jio Mart Digital | Amit C | Arju Tiwari | Kiran Patil | NSO | South | AK | Karnataka |  |  | NEXUS ENTERPRISES | Bangalore | 227 | 2026-06-01 | 2026-06-01 | 7 |  | 2026-06-08 | 2026-06-08 |  | WIP | 10% | [6 empty] | JUNE 26 PLANNED
SEVEBK16694 | 1784 |  |  |  |  | E. Other Business | Other Business | 7-Eleven | Amit C | Arju Tiwari | Kiran Patil | NSO | West | BK | GMU | Mumbai |  | Capital Mall, Vasai/Nalasopara | [9 empty] | SDR Done - ML Pending
GRDSSD16876 | 1785 |  |  |  |  | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | Telangana |  |  | DS Nalgonda | Nalgonda | 2373 | [7 empty] | Budget Submitted - Approval Awaited
DIRFRT16877 | 1786 |  | 8701 | NEI1 | CDITRNEI104 | A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | Amit C | Dyaneshwar Wagh | Aditya Dawre | Refit | North | RT | Rajasthan |  | Sujit M | Celibration mall Udaipur | Udaipur | 9062 | 2026-05-25 | 2026-05-27 |  | 35 | 2026-07-01 | 2026-07-01 |  | WIP | 10% | [6 empty] | JULY 26 PLANNED
GRPRSD16695 | 1787 |  |  |  | SMRTANLF803 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Andhra Pradesh |  |  | SMT AP Proddatur SS Mall | Proddatur | 12674.79 |  |  |  | 21 |  |  |  | On Hold
GRPRSD16696 | 1788 |  | TNC4 | Q05W | SMRTFQ05W05 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Assam & NE |  |  | SMT MKT AS Guwahati Beltola | Guwahati | 42417 | 2026-05-04 | 2026-05-04 |  | 21 | 2026-05-25 | 2026-06-05 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRSD16697 | 1789 |  | TCE7 | NAN3 | SMRTFNAN303 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Assam & NE |  |  | SMT AS Dibrugarh Mankata lane | Dibrugarh | 10888 | 2026-05-11 | 2026-05-11 |  | 21 | 2026-06-01 | 2026-06-15 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16698 | 1790 |  | TIU6 | QXJ6 | SMRTQQXJ604 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand |  |  | SMT JH Dumka | Dumka | 17169 | 2026-05-21 | 2026-05-21 |  | 21 | 2026-06-11 | 2026-06-11 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16699 | 1791 |  | TKX4 | QEQ0 | SMRTQQEQ004 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand |  |  | SMT JH Godda Opp Hotel Rajdarbar | Godda | 14236 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-12 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16700 | 1792 |  | U290 | Q24G | SMPTQQ24G04 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand |  |  | SP JH Jamshedpur Mahendra Center | Jamshedpur | 3485 | 2026-05-21 | 2026-05-21 |  | 21 | 2026-06-11 | 2026-06-11 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16701 | 1793 |  | U082 | Q10N | SMPTQQ10N03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand |  |  | SP JH Ranchi PM Mall | Ranchi | 2459 | 2026-05-18 | 2026-05-18 |  | 21 | 2026-06-08 | 2026-06-08 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16702 | 1794 |  | TH95 | NHF4 | SMPTQNHF406 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand |  |  | SP JH Ranchi RPS Towers | Ranchi | 3959 | 2026-05-17 | 2026-05-17 |  | 21 | 2026-06-07 | 2026-06-07 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16703 | 1795 |  |  |  | SMRTKQXX403 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SMT KN Kanakapura Kodihalli rd | Kanakapura | 11259 |  |  |  | 21 |  |  |  | Dropped
GRPRSZ FO16704 | 1796 |  | TX71 | NA31 | SMRTKNA3102 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SMT KN Hassan Venkatadri Convention Hall | Hassan | 15336 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-17 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16705 | 1797 |  | TND0 | Q06C | SMRTKQ06C03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SMT MKT KN Raichur Basaveshwara Circle | Raichur | 32926 | 2026-05-29 | 2026-05-29 |  | 21 | 2026-06-19 | 2026-06-19 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16706 | 1798 |  | TNC8 | Q06A | SMRTKQ06A06 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SMT MKT KN Mysuru Hunsur Road | Mysore | 47918 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-16 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16707 | 1799 |  | TNC0 | Q05S | SMRTKQ05S03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SMT MKT KN Davanagere P B. Road | Davanagere | 44536 | 2026-05-29 | 2026-05-29 |  | 21 | 2026-06-19 | 2026-06-19 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16708 | 1800 |  | TMZ6 | Q04P | SMRTKQ04P03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SMT KN Blr Vignannagar | Bangalore | 13364 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-12 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16709 | 1801 |  | TEY6 | QZF9 | SMPTKQZF906 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SP KN Kolar | Kolar | 3123 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-10 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16710 | 1802 |  | 2853 | NI89 | SMPTKNI8904 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SP KN Mysuru VijayNagar-2nd Stage | Mysore | 3132 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-12 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16711 | 1803 |  | T920 | NGQ3 | SMPTKNGQ304 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Karnataka |  |  | SP KN Mysuru Dattagali | Mysore | 3660 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-19 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16712 | 1804 |  |  |  | SMRTVNFF702 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Kerala |  |  | SMT KL Chengannur Bethel Jn | Chengannur | 7300 |  |  |  | 21 |  |  |  | Budget Approved - RFC Awaited
GRPRSZ FO16713 | 1805 |  | TO19 | NC83 | SMRTVNC8304 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Kerala |  |  | SMT KL Kottayam MC Road | Kottayam | 19633 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-10 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16714 | 1806 |  | TIX7 | QXG8 | SMRTOQXG804 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SMT OD Rayagada VK Central | Rayagada | 17726 | 2026-05-27 | 2026-05-27 |  | 21 | 2026-06-17 | 2026-06-17 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16715 | 1807 |  | TO36 | NC95 | SMRTONC9502 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SMT OD Cuttack Buxi Bazaar | Cuttack | 14373 | 2026-05-24 | 2026-05-24 |  | 21 | 2026-06-14 | 2026-06-14 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16716 | 1808 |  | TIQ4 | QXP3 | SMRTOQXP303 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SMT OD Cuttack Sai Complex | Cuttack | 9265 | 2026-05-24 | 2026-05-24 |  | 21 | 2026-06-14 | 2026-06-14 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16717 | 1809 |  | TAA1 | NAI4 | SMRTONAI403 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SMT OD Dhenkanal Telecom Clny | Dhenkanal | 14289 | 2026-05-21 | 2026-05-21 |  | 21 | 2026-06-11 | 2026-06-11 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16718 | 1810 |  |  |  | SMRTOQYH703 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SMT OD Sundargarh Parbati Bhavan | Sundargarh | 12510 |  |  |  | 21 |  |  |  | On Hold
GRPRSD16719 | 1811 |  | U148 | Q12L | SMPTOQ12L05 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SP OD Jajapur Road | Jajpur | 4179 | 2026-05-26 | 2026-05-26 |  | 21 | 2026-06-16 | 2026-06-16 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16720 | 1812 |  | TGV1 | QXV7 | SMRTOQXV704 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SMT OD Baripada KMBM Rd | Baripada | 15574 | 2026-05-27 | 2026-05-27 |  | 21 | 2026-06-17 | 2026-06-17 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16721 | 1813 |  | TH93 | NVZ1 | SMRTONVZ104 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SMT OD Rourkela Forum Galleria | Rourkela | 20967 | 2026-05-26 | 2026-05-26 |  | 21 | 2026-06-16 | 2026-06-16 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16722 | 1814 |  |  |  | SMPTOQ0DI03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SP OD Semiliguda Damanjodi | Semiliguda | 3086 |  |  |  | 21 |  |  |  | Budget Approved - RFC Awaited
GRPRSD16723 | 1815 |  | 2562 | NH91 | SMPTONH9104 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SP OD Cuttack Mahanadi Vihar | Cuttack | 2810 | 2026-05-21 | 2026-05-21 |  | 21 | 2026-06-11 | 2026-06-11 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16724 | 1816 |  | 2908 | NJ15 | SMPTONJ1507 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Orissa |  |  | SP OD Bbnsr Mahatab Road | Bhubaneswar | 2273 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-10 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16725 | 1817 |  | TR86 | NXN1 | SMRTSNXN103 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | SMT SK Gangtok Vajra World | Gangtok | 15465 | 2026-05-11 | 2026-05-11 |  | 21 | 2026-06-01 | 2026-06-12 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16726 | 1818 |  |  |  | SMRTTNAL902 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Tamil Nadu |  |  | SMT TN Cuddalore Amirtha site | Cuddalore | 18055 |  |  |  | 21 |  |  |  | Budget Approved - RFC Awaited
GRPRAK16727 | 1819 |  | TND6 | Q06I | SMRTTQ06I03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | SMT MKT ROTN Tirunelveli Palayamkottai | Tirunelveli | 39398 | 2026-05-26 | 2026-05-26 |  | 21 | 2026-06-16 | 2026-06-16 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16728 | 1820 |  | TKW4 | QEB0 | SMRTTQEB004 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Tamil Nadu |  |  | SMT TN Chn Ambattur Kalikuppam | Chennai | 16786 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-17 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSZ FO16729 | 1821 |  | TNB8 | Q05Q | SMRTTQ05Q06 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Tamil Nadu |  |  | SMT MKT TN Chn Madhavaram | Chennai | 56720 | 2026-05-20 | 2026-05-20 |  | 21 | 2026-06-10 | 2026-06-12 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRAK16730 | 1822 |  | TNP9 | Q16G | SMRTTQ16G03 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | SMT ROTN Sivagangai Gandhi Veethi | Sivaganga | 10060 | 2026-05-29 | 2026-05-29 |  | 21 | 2026-06-19 | 2026-06-19 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRAK16731 | 1823 |  |  |  | SMPTTNH9504 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | SP ROTN Madurai Anna Nagar | Madurai | 4034 |  |  |  | 21 |  |  |  | Budget Approved - RFC Awaited
GRPRSD16732 | 1824 |  | TNC9 | Q06B | SMRTNQ06B06 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Telangana |  |  | SMT MKT TG Nizamabad Vinayak Nagar | Nizamabad | 48085 | 2026-05-21 | 2026-05-21 |  | 21 | 2026-06-11 | 2026-06-11 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16733 | 1825 |  | TEI1 | QZW6 | SMRTWQZW603 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | SMT WB Jaigaon Paragna Purba madari | Jaigaon | 13456 | 2026-05-11 | 2026-05-11 |  | 21 | 2026-06-01 | 2026-06-12 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16734 | 1826 |  | TK74 | NYA3 | SMRTWNYA303 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | SMT WB Purulia Raghavpur More | Purulia | 13178 | 2026-05-15 | 2026-05-15 |  | 21 | 2026-06-05 | 2026-06-05 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16735 | 1827 |  | U143 | Q12G | SMPTWQ12G05 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | SP WB Kol Ranihati Howrah | Kolkata | 2650 | 2026-05-10 | 2026-05-10 |  | 21 | 2026-05-31 | 2026-06-15 |  | WIP | [7 empty] | MAY 26 PLANNED
GRPRSD16736 | 1828 |  | 2316 | NH25 | SMPTWNH2504 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | SP WB Kol Barasat Colony More | Kolkata | 3078 | 2026-05-16 | 2026-05-16 |  | 21 | 2026-06-06 | 2026-06-06 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRPRSD16737 | 1829 |  | TZ78 | NAG6 | SMPTWNAG605 | C. Grocery | Grocery | Grocery - Refit (Partial) | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | SP WB Kol Southwinds | Kolkata | 4181 | 2026-05-11 | 2026-05-11 |  | 21 | 2026-06-01 | 2026-06-15 |  | WIP | [7 empty] | JUNE 26 PLANNED
SMRTSD16738 | 1830 |  |  |  |  | C. Grocery | Grocery | Smart | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana |  |  | Bheemgal, Nizamabad | Nizamabad | 23430.56 | [7 empty] | Budget Submitted - Approval Awaited
CFVRSD16739 | 1831 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | East | SD | Telangana |  |  | Pragati Nagar | Hyderabad | 3497 | [7 empty] | SDR Done - ML Pending
GRRERT16740 | 1832 |  |  |  | SMRTDNR3904 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Delhi & NCR |  |  | SMT DL NDLS Dwarka City center | Delhi | 24965 | [7 empty] | Budget Approved - RFC Awaited
GRREBK16741 | 1833 |  |  |  | SMRTGNR1711 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Gujarat |  |  | SMT GJ Ahmd ISKCON | Ahmedabad | 31450 | [7 empty] | SDR Done - ML Pending
GRREBK16742 | 1834 |  |  |  | SMRTMNR3005 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | Maharashtra |  |  | SMT ROM Pune Aundh | Pune | 48869.0121 | [7 empty] | SDR Done - ML Pending
GRREBK16743 | 1835 |  |  |  | SMRTMNK3101 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | GMU |  |  | SMT SB MUM Mum Bandra | Mumbai | 10970 | [7 empty] | Budget Approved - RFC Awaited
GRREBK16744 | 1836 |  |  |  | SMRTMNR2909 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | GMU |  |  | SMT MUM Mum Acme Mall | Mumbai | 41835.0664 | [7 empty] | Budget Approved - RFC Awaited
GRREBK16745 | 1837 |  | 6221 | NR32 | SMRTMNR3207 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | West | BK | GMU |  |  | SMT MUM Mum D Victoria Mall | Mumbai | 9458 | 2026-05-20 | 2026-05-20 |  | 60 | 2026-07-19 | 2026-07-19 |  | WIP | [7 empty] | JULY 26 PLANNED
GRRERT16746 | 1838 |  | TCD7 | NAL0 | SMRT9NAL002 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Punjab |  |  | SMT PB Rupnagar RLJS Tower Ropar | Rupnagar | 18688 | 2026-05-06 | 2026-05-06 |  | 60 | 2026-07-05 | 2026-07-05 |  | WIP | [7 empty] | JULY 26 PLANNED
GRRERT16747 | 1839 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Shanmuga Rajan | Ayush Shetiye | Refit | North | RT | Rajasthan |  |  | SMT RJ Bhiwadi Capital Mall | Bhiwandi | [8 empty] | SDR Done - ML Pending
GRRESD16748 | 1840 |  | 6201 | NR16 | SMRTANR1605 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Andhra Pradesh |  |  | SMT AP Tirupati Abhi Tower | Tirupati | 12811.8146 | 2026-05-21 | 2026-05-21 |  | 60 | 2026-07-20 | 2026-07-20 |  | WIP | [7 empty] | JULY 26 PLANNED
GRRESD16749 | 1841 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Jharkhand |  |  | SMT JH Ranchi Maru Tower | Ranchi | [8 empty] | SDR Done - ML Pending
GRRESZ FO16750 | 1842 |  |  |  |  | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | SZ FO | Kerala |  |  | SMT KL Thrissur East Fort | Thrissur | [8 empty] | ML Received - Design WIP
GRREAK16751 | 1843 |  |  |  | SMRTTNL1804 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | South | AK | Tamil Nadu |  |  | SMT ROTN Nagercoil nr nagaraja temple | Nagercoil | 17450 | [7 empty] | ML Received - Design WIP
GRRESD16752 | 1844 |  |  |  | SMRTNNJ7306 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | Telangana |  |  | SMT TG Nalgonda Metro Complex | Nalagonda | 14260 | [7 empty] | ML Received - Design WIP
GRRESD16753 | 1845 |  |  |  | SMRTWNC5505 | C. Grocery | Grocery | Grocery - Refit | Ketan S | Saurav Sagar | Ayush Shetiye | Refit | East | SD | West Bengal |  |  | SMT WB Siliguri Dwarika | Siliguri | 17419 | [7 empty] | ML Received - Design WIP
EDAMSD16754 | 1846 |  |  |  |  | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | East | SD | Andhra Pradesh |  |  | Inorbit Mall | Vishakhapatnam | 733 | [7 empty] | SDR Done - ML Pending
EDAMRT16755 | 1847 |  |  |  |  | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | North | RT | Rajasthan |  |  | Pacific Mall | Jaipur | 745 | [7 empty] | Budget Submitted - Approval Awaited
EDAMBK16756 | 1848 |  |  |  |  | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Maharashtra |  |  | PMC Pune | Pune | [8 empty] | SDR Done - ML Pending
FLDHKC16757 | 1849 |  | FR2K | FR2K | DH-TRFF-419-MH-FR2K | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Maharashtra |  |  | FF nagpur, Eternity Mall | Nagpur | 6548 | 2026-04-29 | 2026-04-29 |  | 25 | 2026-05-24 | 2026-05-24 | 2026-05-01 | EPC Ready | 100% |  | 2026-05-26 | 2026-05-01 | Launched |  |  | MAY 26 PLANNED | MAY 26
FLDHKC16758 | 1850 |  | T3IN | T3IN | DH-TYOU-419-GJ-T3IN | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Gujarat |  |  | Ashirwad Highstreet, Surat | Surat | 7471 | 2026-05-10 | 2026-05-10 |  | 25 | 2026-05-31 | 2026-06-04 | 2026-05-29 | EPC Ready | 100% |  | PENDING | 2026-05-29 | Launched |  |  | MAY 26 PLANNED | MAY 26
FLDHAK16759 | 1851 |  | TZA0 | TZA0 | DH-TYOU-419-KA-TZA0 | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | South | AK | Karnataka |  |  | Pragathi Business, Manipal | Manipal | 7443 | 2026-05-13 | 2026-05-13 |  | 25 | 2026-05-31 | 2026-06-07 | 2026-05-26 | EPC Ready | 100% |  | PENDING | 2026-05-26 | Launched |  |  | MAY 26 PLANNED | MAY 26
CEDHAK16760 | 1852 |  | TO11 | TO11 | DH-CDIT-452-WB-TO11 | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | East | SD | West Bengal |  |  | Forum Rangoli, Kolkata | Kolkata | 9811 | 2026-05-11 | 2026-05-11 |  | 21 | 2026-06-01 | 2026-06-05 |  | WIP | 90% | [6 empty] | JUNE 26 PLANNED
CEDHKC16761 | 1853 |  | 8945 | 8945 | DH-CDIT-452-UP-8945 | A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | Amit C | Dyaneshwar Wagh | Aditya Dawre | Dehire | North | KC | Delhi & NCR |  |  | Shipra Mall, Ghaziabad, NCR | Ghaziabad | 14370 | 2026-05-23 | 2026-05-23 |  | 21 | 2026-06-13 | 2026-06-13 |  | WIP | 30% | [6 empty] | JUNE 26 PLANNED
SCDHAK16762 | 1854 |  | TCQ7 | TCQ7 | DH-JEWEL-DC-454-WB-TCQ7 | F. SCM | SCM | SCM - Dehire | Srinivas P | Santanu Halder | Chinmay Desai | Dehire | East | AK | West Bengal |  |  | Axis Multicomplex Kolkata Jewels DC | Kolkata | 3531 | 2026-05-11 | 2026-05-11 |  | 35 | 2026-06-15 | 2026-06-15 |  | WIP | 70% | [6 empty] | JUNE 26 PLANNED
GRDSKC16763 | 1855 | DS-DL-00339 | TBW3 | QHZO | DARKDQHZO00 | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  |  | Jeevan Park, Uttam Nagar | Delhi | 1348 | 2026-05-11 | 2026-05-20 | 15 |  | 2026-06-04 | 2026-06-10 |  | WIP | 46% | [6 empty] | JUNE 26 PLANNED
TRTRSD16764 | 1856 |  | T1BW | QG7B | TEXPWQG7B02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Haringhata TST Subarnapur | Haringhata | 4693 | 2026-05-10 | 2026-05-10 |  | 15 | 2026-05-25 | 2026-05-25 | 2026-05-23 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16765 | 1857 |  | TAPI | QF5O | TEXPFQF5O01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Dhing TST Dhing Town | Dhing | 5511 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-27 | 2026-05-16 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16766 | 1858 |  | TZTV | QDGR | TEXPWQDGR01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Madanpur TST | Madanpur | 4259 | 2026-05-10 | 2026-05-10 |  | 15 | 2026-05-25 | 2026-05-25 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16767 | 1859 |  | TX8I | QGRU | TMANFQGRU01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Tezpur TM Krishna Mall Mission Chirali | Tezpur | 2343 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-27 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-15 | 2026-05-15 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16768 | 1860 |  | T17U | QA1P | TRNDSQA1P02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Namchi Bhutia Busty Rd Agam Gram | Namchi | 11670 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-22 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16769 | 1861 |  | TPU8 | Q0RY | TEXPFQ0RY02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Duliajan TST | Duliajan | 4048 | 2026-05-18 | 2026-05-18 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16770 | 1862 |  | TPW7 | Q0TE | TEXPFQ0TE02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Moran Hat TST | Moranhat | 7067 | 2026-05-18 | 2026-05-18 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16771 | 1863 |  | T83H | QNPK | TEXPWQNPK01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Majdia TST | Majdia | 3757 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-28 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16772 | 1864 |  | TWWG | Q6Y2 | TEXPFQ6Y201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Bokhahat TST Standalone | Bokhahat | 5020 | 2026-05-14 | 2026-05-14 |  | 15 | 2026-05-29 | 2026-05-29 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16773 | 1865 |  | TE50 | NHA1 | TRNDVNHA101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thrissur TW Selx Mal | Thrissur | 2421 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-22 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16774 | 1866 |  | TTA8 | Q2TW | TEXPAQ2TW01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Podili TST | Podili | 4393 | 2026-05-19 | 2026-05-19 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 | 2026-05-19 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16775 | 1867 |  | TXV4 | Q9J3 | TEXPFQ9J301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Jonai TST | Jonai | 4429 | 2026-05-16 | 2026-05-16 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 | 2026-05-19 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16776 | 1868 |  | TX7G | QQ1Q | TEXPFQQ1Q02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Bijni TST Kuklung Road | Bijni | 6137 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-15 | 2026-05-15 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16777 | 1869 |  | TX7Q | QV1W | TEXPNQV1W02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Kothakota TST | Kothakota | 6246 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-10 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16778 | 1870 |  | TGA7 | QYN6 | TEXPWQYN601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Taherpur TST | Taherpur | 6077 | 2026-05-10 | 2026-05-10 |  | 15 | 2026-05-25 | 2026-05-25 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16779 | 1871 |  | TTL1 | Q2XN | TEXPBQ2XN01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Sherghati TST | Sherghati | 5736 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 | 2026-05-19 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16780 | 1872 |  | TWRP | Q6L5 | TJNRQQ6L501 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Jamshedpur TJ P&M Mall | Jamshedpur | 1297 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 | 2026-05-19 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16781 | 1873 |  | TX6Q | QA3X | TEXP4QA3X02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Kailashahar TST | Kailashahar | 6056 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-27 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16782 | 1874 |  | T52D | QPRR | TMANAQPRR01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Gudivada TM Gudivada | Gudivada | 2037 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-26 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | 2026-05-18 | 2026-05-18 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16783 | 1875 |  | TAQG | QF6R | TEXPAQF6R02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Vissannapeta TST Opp MRO Office | Vissannapeta | 4303 | 2026-05-21 | 2026-05-21 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-24 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16784 | 1876 |  | TLJ1 | QJP0 | TEXPFQJP001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Bokajan TST | Bokajan | 4300 | 2026-05-16 | 2026-05-16 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16785 | 1877 |  | TKB0 | QAM6 | TEXPFQAM601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Kharupatia TST | Kharupatia | 6111 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-27 | 2026-05-15 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16786 | 1878 |  | T1DX | Q1B6 | TEXPFQ1B603 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Teok TST Telia Goan | Teok | 5332 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-27 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16787 | 1879 |  | TWWN | Q6Y9 | TEXPFQ6Y902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Tinsukia TST Margherita | Tinsukia | 5729 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16788 | 1880 |  | T1CO | QG7W | TEXPNQG7W02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Chennur TST | Chennur | 6428 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-28 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | 2026-05-20 | 2026-05-20 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16789 | 1881 |  | TATB | QGAL | TFITNQGAL01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Mahbubnagar | Mahbubnagar | 9050 | 2026-05-09 | 2026-05-09 |  | 15 | 2026-05-24 | 2026-05-24 | 2026-05-22 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16790 | 1882 |  | TMG3 | QQP3 | TEXPFQQP301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Baihata Chariali TST | Baihata Chariali | 5000 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-13 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16791 | 1883 |  | TTA6 | Q2TU | TEXPFQ2TU02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Barpeta Road TST | Barpeta Road | 7766 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16792 | 1884 |  | TMK1 | QQW7 | TEXPNQQW701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | NagarKurnool TST | Nagarkurnool | 5669 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16793 | 1885 |  | TX6I | Q3N3 | TEXPAQ3N302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Achutapuram TST Achutapuram | Achutapuram | 6512 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-15 | EPC Ready | 100% | Cycle-1 FM | 2026-05-17 | 2026-05-17 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16794 | 1886 |  | TLM5 | QLA0 | TEXPFQLA002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Rangiya TST | Rangiya | 4156 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16795 | 1887 |  | TX6J | QA3Q | TEXPVQA3Q02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kunnamangalam TST | Kunnamangalam | 8716 | 2026-05-22 | 2026-05-22 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-22 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16796 | 1888 |  | TWVX | Q6X3 | TEXPVQ6X302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Parappanangadi TST | Parappanangadi | 9863 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-22 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16797 | 1889 |  | TAHC | Q7DI | TEXPVQ7DI02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Paravur TST Near Private Bus Stand | Paravur | 7399 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16798 | 1890 |  | TR09 | NE30 | TRNDNNE3003 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Vikarabad TST | Vikarabad | 5460 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | 2026-05-20 | 2026-05-20 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16799 | 1891 |  | TWSY | Q6P5 | TEXPVQ6P502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Bharanikkavu TST | Bharanikkavu | 5486 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-16 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16800 | 1892 |  | TDY9 | NY21 | TEXPANY2101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Markapur TST | Markapur | 6318 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-26 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 | 2026-05-19 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16801 | 1893 |  | T9NB | QXDX | TEXPNQXDX01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Nagarkurnool TST Kalwakurthy Town | Nagarkurnool | 4689 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-27 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-15 | 2026-05-15 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16802 | 1894 |  | TTA7 | Q2TV | TEXPVQ2TV02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pothencode TST | Pothencode | 5110 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-12 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16803 | 1895 |  | TTR7 | Q3BB | TEXPAQ3BB03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Tekkali TST | Tekkali | 4979 | 2026-05-06 | 2026-05-06 |  | 15 | 2026-05-21 | 2026-05-21 | 2026-05-11 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16804 | 1896 |  | TDY1 | NX36 | TEXPVNX3603 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Ponnani TST | Ponnani | 6500 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-23 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16805 | 1897 |  | TX8B | QCBL | TEXPVQCBL01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Wandoor TST ETM Plaza | Wandoor | 7803 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-12 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16806 | 1898 |  | TSY9 | Q2TE | TEXPNQ2TE03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Achampet TST | Achampet | 4362 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16807 | 1899 |  | TDO5 | NE93 | TEXPBNE9301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Daudnagar TST | Daudnagar | 6000 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 | 2026-05-19 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16808 | 1900 |  | TTO7 | Q2ZO | TEXPFQ2ZO02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Dudhnoi TST | Dudhnoi | 4116 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-15 | 2026-05-15 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16809 | 1901 |  | TWVR | Q6W6 | TEXPWQ6W601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ranaghat TST GNPC Rd Beside Durgadas Park | Ranaghat | 5461 | 2026-05-10 | 2026-05-10 |  | 15 | 2026-05-25 | 2026-05-25 | 2026-05-17 | EPC Ready | 100% | Cycle-1 FM | 2026-05-20 | 2026-05-20 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16810 | 1902 |  | TWVL | Q6V9 | TEXPNQ6V901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Moinabad TST | Moinabad | 7972 | 2026-05-06 | 2026-05-06 |  | 15 | 2026-05-21 | 2026-05-21 | 2026-05-12 | EPC Ready | 100% | Cycle-1 FM | 2026-05-15 | 2026-05-15 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16811 | 1903 |  | TFZ8 | QYM6 | TEXPNQYM601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Banswada TST | Banswada | 4621 | 2026-05-21 | 2026-05-21 |  | 15 | 2026-05-31 | 2026-05-31 | 2026-05-23 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 | 2026-05-25 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16812 | 1904 |  | TX7M | QU1D | TEXPAQU1D01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kaikaluru TST Opp To Kumari Talkies | Kaikaluru | 7052 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-28 | 2026-05-14 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 | 2026-05-16 | Launched |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16813 | 1905 |  | TKC9 | QAR1 | TEXPWQAR102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Taki TST | Taki | 5000 | 2026-05-15 | 2026-05-15 |  | 15 | 2026-05-30 | 2026-05-30 | 2026-05-31 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16814 | 1906 |  | TY12 | NA72 | TRNDANA7201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kurnool TW VarietyMal | Kurnool | 1950 | 2026-05-19 | 2026-05-19 |  | 15 | 2026-06-03 | 2026-06-03 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16815 | 1907 |  | TSQ7 | Q2PS | TRNDBQ2PS01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Sitamarhi V2 Aditya Vision Rajopatti | Sitamarhi | 10207 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16816 | 1908 |  | T1QZ | Q2O8 | TEXPOQ2O802 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | JAGATPUR TST | Jagatpur | 7547 | 2026-05-06 | 2026-05-06 |  | 15 | 2026-05-21 | 2026-05-31 | 2026-05-24 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16817 | 1909 |  | T38C | QCCT | TEXPWQCCT01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Machlandapur TST | Machlandapur | 4240 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
TRTRSD16818 | 1910 |  | TX5O | QA3A | TEXPOQA3A02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Junagarh Or TST Kalampur Square | Junagarh | 7841 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16819 | 1911 |  | TDV0 | NS70 | TEXPBNS7001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Sheohar TST | Sheohar | 6000 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 | 2026-05-30 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16820 | 1912 |  | TTQ1 | Q2ZW | TJNRBQ2ZW02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Bhagalpur TJ Besides Bank of Baroda | Bhagalpur | 2038 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16821 | 1913 |  | TAN4 | QGOY | TEXPOQGOY02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Kesinga TST Kesinga Kalahandi | Kesinga Tst | 4905 | 2026-05-21 | 2026-05-21 |  | 15 | 2026-06-05 | 2026-06-05 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16822 | 1914 |  | T1RC | Q2P2 | TEXPWQ2P201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | SHYAMPUR TST | Shyampur | 5225 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16823 | 1915 |  | TAJJ | QFWZ | TEXPWQFWZ03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Ghatakpur TST Ghatakpukur Bazar LL A Molla | Ghatakpur | 6841 | 2026-05-10 | 2026-05-10 |  | 15 | 2026-05-25 | 2026-05-31 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16824 | 1916 |  | TJV3 | QAB7 | TEXPAQAB701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Chipurapalli TST | Chipurapalli | 4617 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 | 2026-05-26 | EPC Ready | 100% | Cycle-1 FM | 2026-06-01 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16825 | 1917 |  | TLM2 | QKX0 | TEXPFQKX003 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Nazira TST Dhodar Ali Road | Nazira | 8107 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16826 | 1918 |  | TW90 | NSG3 | TRNDANSG303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Dhone TST | Dhone | 3691 | 2026-05-18 | 2026-05-18 |  | 15 | 2026-06-02 | 2026-06-02 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16827 | 1919 |  | TGA3 | QYN2 | TEXPAQYN201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nidadhavole TST | Nidadhavole | 5342 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-31 | 2026-05-23 | EPC Ready | 100% | Cycle-1 FM | 2026-06-01 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16828 | 1920 |  | TKC5 | QAQ7 | TFITFQAQ701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Dhemaji | Dhemaji | 10739 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16829 | 1921 |  | T9XA | QXOA | TEXPNQXOA01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Kagaznagar TST | Kagaznagar | 8471 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-31 | 2026-05-23 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16830 | 1922 |  | TLX4 | QQG7 | TEXPAQQG701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Gooty TST | Gooty | 5485 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16831 | 1923 |  | TLA3 | QGH0 | TFITFQGH001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Diphu MG Road | Diphu | 10274 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16832 | 1924 |  | TSS0 | Q2PW | TFITNQ2PW02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Warangal Nakkal Gutta Hanamkonda | Warangal | 19633 | 2026-05-10 | 2026-05-10 |  | 15 | 2026-05-25 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16833 | 1925 |  | TX7J | QA4G | TEXPNQA4G01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Shankarpally TST | Shankarpally | 9884 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16834 | 1926 |  | TJE0 | QWZ7 | TEXPOQWZ701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Salepur TST | Salepur | 5955 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16835 | 1927 |  | T33V | Q30I | TEXPNQ30I01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Isnapur TST | Isnapur | 6948 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16836 | 1928 |  | TV96 | NNI5 | TRNDANNI503 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kandukuru TST | Kandukuru | 3755 | 2026-05-18 | 2026-05-18 |  | 15 | 2026-05-31 | 2026-06-02 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | 2026-05-27 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16837 | 1929 |  | TX5R | QA3F | TEXPOQA3F03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Rajsunakhala TST Near Ganesh Bazar Next to Ganesh Temple | Rajsunakhala | 6678 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 | 2026-05-24 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16838 | 1930 |  | TGI5 | QYF7 | TEXPNQYF701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Nakrekal TST | Nakrekal | 5662 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16839 | 1931 |  | TARK | QF9D | TEXPAQF9D02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Kanigiri TST | Kanigiri | 5146 | 2026-05-23 | 2026-05-23 |  | 15 | 2026-05-31 | 2026-06-07 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16840 | 1932 |  | TJ95 | NWF7 | TRNDANWF702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Yemmiganur TST | Yemmiganur | 3873 | 2026-05-12 | 2026-05-12 |  | 15 | 2026-05-27 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16841 | 1933 |  | T64O | QADB | TEXPAQADB01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Chodavaram TST A P KSNS Raju Property | Chodavaram | 5567 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16842 | 1934 |  | TJH9 | QWR2 | TEXPWQWR203 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Gobardanga TST | Gobardanga | 5000 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 | 2026-06-01 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
TRTRSD16843 | 1935 |  | TXA1 | Q9QF | TEXPOQ9QF01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Balugaon TST | Balugaon | 7744 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16844 | 1936 |  | TWTI | Q6Q6 | TEXPOQ6Q604 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Jaraka TST Near to daily Hat | Jaraka | 4166 | 2026-05-21 | 2026-05-21 |  | 15 | 2026-06-05 | 2026-06-05 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16845 | 1937 |  | TSU5 | Q2RO | TEXPOQ2RO01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Gunupur TST | Gunupur | 6458 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-31 | 2026-05-17 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16846 | 1938 |  | TDU8 | NS26 | TEXPBNS2601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Bihar |  |  | Islampur TST | Islampur | 6600 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16847 | 1939 |  | TKT8 | QDG0 | TEXPFQDG001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Assam & NE |  |  | Pathsala TST | Pathsala | 6784 | 2026-05-14 | 2026-05-14 |  | 15 | 2026-05-29 | 2026-05-31 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16848 | 1940 |  | TGW0 | QXW7 | TEXPQQXW702 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Jharkhand |  |  | Gomia TST | Gomia | 5203 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 | 2026-05-12 | EPC Ready | 100% | Cycle-1 FM | 2026-05-30 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16849 | 1941 |  | TJJ7 | QWO7 | TEXPOQWO704 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Soro TST Partha Sarathi Theatre | Soro | 5098 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 | 2026-05-11 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16850 | 1942 |  | TWVF | Q6V3 | TEXPWQ6V301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Rani Hati Howrah TST Lalchand Option Near Smart Point | Rani Hati Howrah | 3720 | 2026-05-10 | 2026-05-10 |  | 15 | 2026-05-25 | 2026-05-31 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16851 | 1943 |  | TWUT | Q6T9 | TEXPRQ6T901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Salumber TST | Salumber | 5827.8 | 2026-05-06 | 2026-05-06 |  | 15 | 2026-05-21 | 2026-05-21 | 2026-05-16 | EPC Ready | 100% | Cycle-1 FM | 2026-05-15 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16852 | 1944 |  | TPN0 | Q0NS | TJNRRQ0NS01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Bhilwara TJ RIL Mall | Bhilwara | 2000 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-16 | EPC Ready | 100% | Cycle-1 FM | 2026-05-14 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16853 | 1945 |  | TLA6 | QGK0 | TFITRQGK001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Dungarpur Musafir Khana Complex | Dungarpur | 9446 | 2026-05-08 | 2026-05-08 |  | 15 | 2026-05-23 | 2026-05-23 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | 2026-05-16 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRBK16854 | 1946 |  | TV36 | NMA6 | TRNDMNMA604 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Pusad TST | Pusad | 4883 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | 2026-05-25 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16855 | 1947 |  | T587 | NGE8 | TRNDINGE800 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Himachal Pradesh |  |  | Shimla SecretaritRd | Shimla | 5910 | 2026-05-11 | 2026-05-11 |  | 15 | 2026-05-26 | 2026-05-26 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | 2026-05-18 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16856 | 1948 |  | TTB3 | TTB3 | TTB3 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Himachal Pradesh |  |  | Chamba TST | Chamba | 7852 | 2026-05-09 | 2026-05-09 |  | 15 | 2026-05-24 | 2026-05-24 | 2026-05-19 | EPC Ready | 100% | Cycle-1 FM | 2026-05-19 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRRT16857 | 1949 |  | TSL1 | Q2NY | TFITRQ2NY01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Rajasthan |  |  | Kota Platina Maharana Pratap Circle | Kota | 11147 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-31 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | 2026-05-26 |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRBK16858 | 1950 |  | TO86 | ND28 | TRNDMND2805 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | West | BK | Maharashtra |  |  | Gadhinglaj TST | Gadhinglaj | 3251 | 2026-05-19 | 2026-05-19 |  | 15 | 2026-06-03 | 2026-06-03 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRRT16859 | 1951 |  | TG66 | NSU8 | TRNDUNSU801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Rampur Mandiyan Bagh | Rampur | 13734 | 2026-05-08 | 2026-05-08 |  | 30 | 2026-06-07 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16860 | 1952 |  | TLK1 | QJZ0 | TFITUQJZ001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Moradabad Kanth Road | Moradabad | 9025.18 | 2026-05-07 | 2026-05-07 |  | 30 | 2026-06-06 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16861 | 1953 |  | T33J | QA7N | TFITJQA7N02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Jammu & Kashmir |  |  | Srinagar Sanat Nagar Rawalpora By Pass Srinagar | Srinagar | 11430 | 2026-05-09 | 2026-05-09 |  | 30 | 2026-06-08 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16862 | 1954 |  | T62K | QA2B | TFIT9QA2B01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Punjab |  |  | Jalandhar Johal Complex | Jalandhar | 11516 |  |  |  | 30 |  |  |  | On Hold |  | Façade Work
TRTRRT16863 | 1955 |  | TDT1 | NN29 | TFITUNN2901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Shamli Opp Naya Bazaar | Shamli | 11000.49 | 2026-05-08 | 2026-05-08 |  | 30 | 2026-06-07 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16864 | 1956 |  | TG56 | NHB9 | TRNDUNHB901 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttar Pradesh |  |  | Hapur FreeGanj | Hapur | 6974 | 2026-05-08 | 2026-05-08 |  | 30 | 2026-06-07 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16865 | 1957 |  | TKN4 | QBW0 | TFITHQBW003 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Haryana |  |  | Narnaul Opp Gold Cinema Near Hero Honda Chowk | Narnaul | 9000 | 2026-05-09 | 2026-05-09 |  | 30 | 2026-06-08 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
TRTRRT16866 | 1958 |  | TX3V | Q2E8 | TFIT5Q2E803 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Srinivas P | Purushottam M | Raj Shende | Refit | North | RT | Uttarakhand |  |  | Dehradun Sehastradhara Road | Dehradun | 10609 | 2026-05-09 | 2026-05-09 |  | 30 | 2026-06-08 | 2026-05-31 |  | WIP |  | Façade Work | [5 empty] | JUNE 26 PLANNED
CFVRSZ FO16867 | 1959 |  |  |  |  | C. Grocery | V Retail | Centro Footwear (V Retail) | Ketan S | Saurav Sagar | Ayush Shetiye | NSO | South | SZ FO | Karnataka |  |  | Inorbit Mall, Hubli | Hubli | [8 empty] | SDR In Progress
GRDHKC16868 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | West | KC | Maharashtra |  |  | Nagpur Shagun Indian Air Station | Nagpur | 2373 | [7 empty] | Pre Budget Dehire Site
GRDHAK16869 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Andhra Pradesh |  |  | SBZ AP Nellore GB FELICITY MALL | Nellore | [8 empty] | Pre Budget Dehire Site
GRDHKC16870 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | West | KC | Madhya Pradesh |  |  | SBZ MP Ujjain Cosmos Mall | Ujjain | [8 empty] | Pre Budget Dehire Site
GRDHAK16871 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | East | AK | Telangana |  |  | SBZ TG Hyd SAIDABAD-ARIHANT TWRS | Hyderabad | [8 empty] | Pre Budget Dehire Site
GRDHKC16872 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | West | KC | Maharashtra |  |  | SBZ ROM Pune PIMPRI-PREMIER PLAZA | Pune | [8 empty] | Pre Budget Dehire Site
GRDHKC16873 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | West | KC | Madhya Pradesh |  |  | SMT MP Indore Citadel Indore | Indore | [8 empty] | Pre Budget Dehire Site
GRDHKC16874 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Shanmuga Rajan | Ayush Shetiye | Dehire | West | KC | Chhattisgarh |  |  | SBZ CG Bhilai Surya Treasure Island Jun | Bhilai | [8 empty] | Pre Budget Dehire Site
GRDHAK16875 | [5 empty] | C. Grocery | Grocery | Grocery - Dehire | Ketan S | Saurav Sagar | Ayush Shetiye | Dehire | South | Ak | Karnataka |  |  | SMT KN Mangaluru Karuna Pride | Mangalore | [8 empty] | Pre Budget Dehire Site
GRDSSD16878 | [5 empty] | L. Dark Store | Dark Store | Dark Store | Amit C | Santanu Halder | Chinmay Desai | NSO | East | SD | West Bengal |  |  | Metiabruz | Kolkata | [8 empty] | SDR In Progress
EDAMBK16879 | [5 empty] | M. Brands | Brands | Ed-A-Mamma EBO | Srinivas P | Jitendra Talreja | Nitesh Warhade | NSO | West | BK | Madhya Pradesh |  |  | Pheonix Citadel Indore, INDORE, MADHYA PRADESH | [9 empty] | ML Received - Design WIP
FLDHKC16880 |  |  | TATU | TATU | DH-FOOT-419-MH-TATU | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Maharashtra |  |  | TATU Grand HighStreet Mall MH Footwear | Pune | 2625 | 2026-05-08 | 2026-05-08 |  | 25 | 2026-05-31 | 2026-06-02 | 2026-05-18 | EPC Ready | 100% |  | PENDING | 2026-05-18 | Launched |  |  | MAY 26 PLANNED | MAY 26
FLDHAK16881 |  |  | TJ5K | TJ5K | DH-TAZO-419-TG-TJ5K | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | East | AK | Telangana |  |  | TJ5K Aparna Mal Hyd TG Azorte | Hyderabad | 21507 | 2026-05-27 | 2026-05-27 |  | 35 | 2026-07-01 | 2026-07-01 |  | WIP | [7 empty] | JULY 26 PLANNED
FLDHKC16882 |  |  | 9545 | 9545 | DH-FOOT-419-GJ-9545 | B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | Srinivas P | Jitendra Talreja | Nitesh Warhade | Dehire | West | KC | Gujarat |  |  | 9545 1st Floor, VR Mall, Dumas Road, Surat, SURAT, SOUTH GUJARAT GJ Footprint | Surat | 1698 | 2026-05-29 | 2026-05-29 |  | 25 | 2026-06-23 | 2026-06-23 |  | WIP | [7 empty] | JUNE 26 PLANNED
GRDSKC16883 |  | DS-MP-00011 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Madhya Pradesh |  |  | Bharut Nagar, Satna | Satna | [8 empty] | Budget Approved - RFC Awaited
GRDSKC16884 |  | DS-GMU-00113 (Add. Area) |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU |  |  | Indus Power, Dombivali (Additional Space) | Mumbai | [8 empty] | Budget Submitted - Approval Awaited
GRDSKC16885 |  | DS-RJ-00040 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Rajasthan |  |  | Ratandeep, Gopalbari Jaipur | Jaipur | [8 empty] | Budget Submitted - Approval Awaited
GRDSKC16886 |  | DS-UP-00075 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Uttar Pradesh |  |  | Saket Nagar Colony, Naria, Varanasi | Varanasi | [8 empty] | ML Received - Design WIP
GRDSKC16887 |  | DS-GMU-00195 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU |  |  | Golden Tobacco House, Vile Parle (W), Mumbai (Cold Room) | Mumbai | [8 empty] | ML Received - Design WIP
GRDSKC16888 |  | DS-GMU-00043 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU |  |  | Parichay Borivali West (Milk Basket) | Mumbai | [8 empty] | SDR Done - ML Pending
GRDSKC16889 |  | DS-DL-00345 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  |  | Vasant Vihar, New Delhi | Delhi | [8 empty] | SDR Done - ML Pending
GRDSKC16890 |  | DS-GMU-00186 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | GMU |  |  | Smart bazaar KachPada Malad | Mumbai | [8 empty] | SDR Done - ML Pending
GRDSKC16891 |  | DS-MH-00200 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Maharashtra |  |  | Bansali House, Dharampeth | Nagpur | [8 empty] | SDR Done - ML Pending
GRDSKC16892 |  | DS-DL-00329 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  |  | Dwarka | Delhi | [8 empty] | SDR Done - ML Pending
GRDSKC16893 |  | DS-GJ-00009 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | West | KC | Gujrat |  |  | Shoolin Exotica, Isanpur, Ahmedabad | Ahmedabad | [8 empty] | SDR In Progress
GRDSKC16894 |  | DS-DL-00351 |  |  |  | L. Dark Store | Dark Store | Dark Store | Srinivas P | Purushottam M | Prasad Deshmukh | NSO | North | KC | Delhi & NCR |  |  | GGN-Sushant Lok | Delhi | [8 empty] | SDR In Progress
TRTRSD16895 |  |  | TX5Y | QA3K | TEXPNQA3K01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Narayankhed TST | Narayankhed | 8959 | 2026-05-28 | 2026-05-28 |  | 15 | 2026-06-12 | 2026-06-12 | 2026-06-02 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSD16896 |  |  | TWUJ | Q2VB | TEXPNQ2VB02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Aswaraopeta TST | Aswaraopeta | 4865 | 2026-05-27 | 2026-05-27 |  | 15 | 2026-05-31 | 2026-06-11 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16897 |  |  | TWVG | Q6V4 | TEXPNQ6V401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Sadashivpet TST | Sadashivpet | 7585 | 2026-05-25 | 2026-05-25 |  | 15 | 2026-05-31 | 2026-06-09 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16898 |  |  | TX4M | QGXW | TEXPNQGXW01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Yellandu TST Yellandu | Yellandu | 7852 | 2026-05-25 | 2026-05-25 |  | 15 | 2026-05-31 | 2026-06-09 | 2026-05-25 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16899 |  |  | TK77 | NWI1 | TRNDANWI102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Jaggayapet TST | Jaggayapet | 3107 | 2026-05-27 | 2026-05-27 |  | 15 | 2026-05-31 | 2026-06-11 | 2026-05-28 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16900 |  |  | TA2X | QGVX | TEXPAQGVX01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Darsi TST | Darsi | 8074 | 2026-05-19 | 2026-05-19 |  | 15 | 2026-05-31 | 2026-06-03 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16901 |  |  | TSY3 | Q2SY | TEXPAQ2SY01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nandigama TST | Nandigama | 7018 | 2026-05-28 | 2026-05-28 |  | 15 | 2026-05-31 | 2026-06-12 | 2026-05-30 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16902 |  |  | TPZ2 | Q0UL | TEXPAQ0UL02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Macherla TST | Macherla | 5059 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-05-31 | 2026-06-10 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16903 |  |  | TN60 | NC62 | TRNDANC6202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Nuzvid TST | Nuzvid | 4240 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-05-31 | 2026-06-08 | 2026-05-20 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16904 |  |  | TX5C | QGZJ | TEXPNQGZJ02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Bhainsa TST | Bhainsa | 2390 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-05-31 | 2026-06-08 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16905 |  |  | T33T | Q30G | TJNRVQ30G01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thrissur TJ Selex Mall East Fort | Thrissur | 1717 | 2026-05-07 | 2026-05-07 |  | 15 | 2026-05-22 | 2026-05-22 | 2026-06-02 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
TRTRSZ FO16906 |  |  | TTR8 | Q3BD | TJNRTQ3BD01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Pollachi TJ Venkatramana round Rd Mahalingapuram | Pollachi | 1466 | 2026-05-18 | 2026-05-18 |  | 15 | 2026-05-31 | 2026-06-02 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16907 |  |  | TX8F | Q3N1 | TMANVQ3N101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kollam TM D Mall Punalur | Kollam | 2718 | 2026-05-20 | 2026-05-20 |  | 15 | 2026-05-31 | 2026-06-04 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16908 |  |  | TX8P | Q2WA | TWIWVQ2WA01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kollam TW | Kollam | 2369 | 2026-05-22 | 2026-05-22 |  | 15 | 2026-05-31 | 2026-06-06 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16909 |  |  | TGJ1 | QYG4 | TEXPVQYG401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Kuravilangad TST | Kuravilangad | 4323 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-06-10 | 2026-06-10 | 2026-06-01 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSZ FO16910 |  |  | TCV4 | NQE7 | TRNDTNQE701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Kangeyam TST | Kangeyam | 4941 | 2026-04-30 | 2026-04-30 |  | 15 | 2026-05-15 | 2026-05-15 | 2026-05-08 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16911 |  |  | T80R | QMFK | TEXPNQMFK01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Ramayampet TST | Ramayampet | 5500 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-05-31 | 2026-06-10 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16912 |  |  | TTO8 | Q2ZP | TEXPNQ2ZP03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Toopran TST | Toopran | 6033 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-05-31 | 2026-06-10 | 2026-05-29 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16913 |  |  | TJQ6 | QWI7 | TWIWTQWI701 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Tirupur TW Kumaran Rd | Tirupur | 1429 | 2026-05-02 | 2026-05-02 |  | 15 | 2026-05-17 | 2026-05-17 | 2026-05-08 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16914 |  |  | TSZ4 | Q2TJ | TEXPVQ2TJ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Charummoodu TST | Charummoodu | 5803 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-28 | 2026-05-21 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16915 |  |  | TWUI | Q2VA | TEXPVQ2VA02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Puthuppally TST | Puthuppally | 5885 | 2026-05-20 | 2026-05-20 |  | 15 | 2026-05-31 | 2026-06-04 | 2026-05-27 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16916 |  |  | TTE4 | Q2SM | TEXPTQ2SM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Bargur TST | Bargur | 5761 | 2026-05-15 | 2026-05-15 |  | 15 | 2026-05-30 | 2026-05-30 | 2026-05-18 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16917 |  |  | T43H | QA5F | TEXPVQA5F01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pathiripala TST PM Arcade Palakkad Ponnani Rd | Pathiripala | 4588 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-06-10 | 2026-06-10 | 2026-06-03 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSZ FO16918 |  |  | TP77 | ND70 | TRNDVND7000 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thamarassery TST | Thamarassery | 6250 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-06-08 | 2026-06-08 | 2026-06-02 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSZ FO16919 |  |  | TJE4 | QXA2 | TEXPVQXA202 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Mundakayam TST | Mundakayam | 7116 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 | 2026-06-01 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSZ FO16920 |  |  | TA2O | QGVJ | TWIWTQGVJ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Erode TW Perundurai Road | Erode | 1700 | 2026-05-09 | 2026-05-09 |  | 15 | 2026-05-24 | 2026-05-24 | 2026-05-24 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16921 |  |  | TU01 | NZW6 | TRNDVNZW602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Edakkara TST | Edakkara | 5094 | 2026-05-13 | 2026-05-13 |  | 15 | 2026-05-28 | 2026-05-28 | 2026-06-03 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | JUNE 26
TRTRSZ FO16922 |  |  | TLN3 | QLI0 | TEXPVQLI001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Koothattukkulam TST | Koothattukkulam | 6765 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 | 2026-06-01 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSZ FO16923 |  |  | TIZ9 | QXE2 | TEXPVQXE201 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Alathur TST | Alathur | 7770 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-06-08 | 2026-06-08 | 2026-06-03 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSZ FO16924 |  |  | TWWA | Q6X6 | TEXPVQ6X601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Olavakode TST Olavakkode Palakkad | Olavakode | 7904 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-06-10 | 2026-06-10 | 2026-06-03 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | JUNE 26 PLANNED | JUNE 26
TRTRSZ FO16925 |  |  | TO39 | NC98 | TRNDTNC9804 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Dharapuram TST | Dharapuram | 5410 | 2026-04-30 | 2026-04-30 |  | 15 | 2026-05-15 | 2026-05-15 | 2026-05-08 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16926 |  |  | TED4 | NQV5 | TEXPTNQV502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Periyanaickenpalayam TST | Periyanaickenpalayam | 5628 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 | 2026-05-08 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSZ FO16927 |  |  | T35G | QA4N | TEXPTQA4N01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Sathyamangalam TST Bazaar Road | Sathyamangalam | 5946 | 2026-05-06 | 2026-05-06 |  | 15 | 2026-05-21 | 2026-05-21 | 2026-05-11 | EPC Ready | 100% | Cycle-1 FM | PENDING |  | YTL |  |  | MAY 26 PLANNED | MAY 26
TRTRSD16928 |  |  | TFZ3 | QYM1 | TEXPNQYM101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Husnabad TST | Husnabad | 4076 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16929 |  |  | TXYI | Q9LE | TEXPAQ9LE01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Venkatgiri TST | Venkatgiri | 5891 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-06-10 | 2026-06-10 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16930 |  |  | TX7H | QA4E | TEXPNQA4E01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Kondamallepally TST | Kondamallepally | 5800 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16931 |  |  | TX3Q | Q1T5 | TFITNQ1T502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Asifabad K B Chowk | Asifabad | 10469 | 2026-05-26 | 2026-05-26 |  | 15 | 2026-06-10 | 2026-06-10 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16932 |  |  | TL89 | NWN1 | TRNDNNWN102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Korutla TST | Korutla | 4773 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16933 |  |  | TTY3 | Q3EM | TJNRVQ3EM02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Payyannur TJ Magnum Mall | Payyannur | 1830 | 2026-05-25 | 2026-05-25 |  | 15 | 2026-06-09 | 2026-06-09 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16934 |  |  | TX8V | QH1K | TWIWVQH1K01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Nalanchira TW Trivandrum | Trivandrum | 2575 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16935 |  |  | TLH1 | QIV0 | TJNRTQIV002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Trichy TJ Lawsons Rd | Trichy | 2035 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16936 |  |  | TKA0 | QAH8 | TWIWTQAH801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Trichy TW Lawsons Rd | Trichy | 2900 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSD16937 |  |  | T49Q | QA5K | TEXPNQA5K01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Godkondla TST Mall Town | Godkondla | 5203 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16938 |  |  | TWTN | Q6R3 | TEXPNQ6R301 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Telangana |  |  | Wyra TST | Wyra | 5944 | 2026-05-22 | 2026-05-22 |  | 15 | 2026-06-06 | 2026-06-06 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16939 |  |  | TWVU | Q6W9 | TEXPAQ6W902 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Jammalamadugu TST | Jammalamadugu | 5738 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16940 |  |  | TXZT | Q9PM | TEXPAQ9PM01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Penugonda TST | Penugonda | 5629 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16941 |  |  | TWTX | Q6S4 | TEXPTQ6S401 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Pochampalli TST | Pochampalli | 5446 | 2026-05-18 | 2026-05-18 |  | 15 | 2026-06-02 | 2026-06-02 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16942 |  |  | TGQ9 | QXX6 | TEXPVQXX602 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Cherpulassery TST | Cherpulassery | 5807 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16943 |  |  | TKB7 | QAN3 | TEXPTQAN303 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Sankagiri TST Sankari | Sankagiri | 5229 | 2026-05-09 | 2026-05-09 |  | 15 | 2026-05-24 | 2026-05-24 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16944 |  |  | TJZ2 | QAH0 | TEXPVQAH001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Ramanattukara TST | Ramanattukara | 5152 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-06-08 | 2026-06-08 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16945 |  |  | T196 | QG4P | TEXPVQG4P02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Chittur Thathamangalam TST | Chittur Thathamangalam | 7289 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16946 |  |  | T39S | QA4V | TEXPVQA4V02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Thiruvankulam TST V T Jacob Arcade | Thiruvankulam | 7311 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16947 |  |  | T558 | NGE1 | TRNDTNGE102 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Trichy TW ThillaiNgr | Trichy | 1670 | 2026-05-04 | 2026-05-04 |  | 15 | 2026-05-19 | 2026-05-19 |  | WIP |  | Cycle-1 FM | [5 empty] | MAY 26 PLANNED
TRTRSZ FO16948 |  |  | TX6Y | QJ1K | TEXPVQJ1K02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Poovattuparamba TST Kozhikode | Poovattuparamba | 6470 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16949 |  |  | TEZ8 | QZH3 | TEXPVQZH302 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Ambalapuzha TST | Ambalapuzha | 8200 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16950 |  |  | TW89 | NSC8 | TRNDVNSC801 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Pathanpuram TST | Pathanpuram | 8321 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16951 |  |  | TO63 | ND09 | TRNDTND0903 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Perundurai TST | Perundurai | 4345 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-06-08 | 2026-06-08 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16952 |  |  | TAB5 | QGJI | TEXPTQGJI01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Thirukoilur TST West Street | Thirukoilur | 8139 | 2026-06-03 | 2026-06-03 |  | 15 | 2026-06-18 | 2026-06-18 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16953 |  |  | TW45 | NNY1 | TRNDTNNY103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Salem TW NM Arcade | Salem | 2444 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-06-08 | 2026-06-08 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16954 |  |  | T88Q | QOTX | TEXPOQOTX02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Rajkhariar TST Boden Chowk | Rajkhariar | 6599 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16955 |  |  | TTA2 | Q2TQ | TEXPWQ2TQ02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | West Bengal |  |  | Baidyanathpur TST | Baidyanathpur | 4496 | 2026-05-21 | 2026-05-21 |  | 15 | 2026-06-05 | 2026-06-05 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16956 |  |  | TWVM | Q6W1 | TEXPOQ6W103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Nilagiri TST Nilagiris | Nilagiri | 5000 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16957 |  |  | T89F | QOVA | TEXPOQOVA02 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Vedavayas TST Near Pahadi Resturant Rourkela | Vedavayas | 9256 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16958 |  |  | TX4P | QGWT | TEXPOQGWT04 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Jaleshwar TST Main Market Adjacent To Hero Showroom | Jaleshwar | 6947 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16959 |  |  | TWUK | Q2VC | TEXPOQ2VC03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Chandabali TST | Chandabali | 5628 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16960 |  |  | TWUO | Q6T4 | TEXPOQ6T403 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Bhanjanagar TST | Bhanjanagar | 5565 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16961 |  |  | TSZ1 | Q2TG | TEXPOQ2TG03 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Digapahandi TST | Digapahandi | 5675 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16962 |  |  | TKV9 | QDZ0 | TEXPOQDZ001 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Rajagangapur TST | Rajagangapur | 5472 | 2026-05-29 | 2026-05-29 |  | 15 | 2026-06-13 | 2026-06-13 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16963 |  |  | TWVD | Q6V1 | TEXPOQ6V103 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Orissa |  |  | Brajaraj Nagar TST | Brajaraj Nagar | 8468 | 2026-05-30 | 2026-05-30 |  | 15 | 2026-06-14 | 2026-06-14 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSD16964 |  |  | TX76 | NA36 | TEXPANA3601 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | East | SD | Andhra Pradesh |  |  | Palamaner TST | Palamaner | 5336 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-06-08 | 2026-06-08 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16965 |  |  | 9589 | NFU1 | TRNDVNFU101 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Calicut TW Surabhi M | Calicut | 1830 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16966 |  |  | TTD1 | Q9C5 | TEXPVQ9C502 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Balussery TST | Balussery | 6278 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16967 |  |  | TWUH | Q2UZ | TEXPTQ2UZ01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Tamil Nadu |  |  | Sholingur TST | Sholingur | 6089 | 2026-06-03 | 2026-06-03 |  | 15 | 2026-06-18 | 2026-06-18 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16968 |  |  | TAPM | QF5S | TEXPVQF5S01 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Koratty TST | Koratty | 6219 | 2026-05-24 | 2026-05-24 |  | 15 | 2026-06-08 | 2026-06-08 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
TRTRSZ FO16969 |  |  | TLB2 | QGQ0 | TEXPVQGQ002 | B. Fashion & Lifestyle | Trends & Allied Formats | Trends Transformation (Partial) | Amit C | Jitendra Talreja | Nitesh Warhade | Refit | South | SZ FO | Kerala |  |  | Chavakkad TST | Chavakkad | 6954 | 2026-05-31 | 2026-05-31 |  | 15 | 2026-06-15 | 2026-06-15 |  | WIP |  | Cycle-1 FM | [5 empty] | JUNE 26 PLANNED
Formulas:
Actual Finish Date = MASTER[[#This Row],[HOTO Date]]

## Delivery Done Site Type Wise
Delivery Done | EPC Ready Previous FY Carry Forward |  |  |  | EPC Ready Current FY 2026-27 | [5 empty] | GRAND TOTAL
Business Format / Sub Format | NSO | Refit | SCM | TOTAL | NSO | Refit | Dehire | Petro | SCM | TOTAL
Count of Site Name | Column Labels
| EPC Ready Previous FY Carry Forward |  |  | EPC Ready Previous FY Carry Forward Total | EPC Ready |  |  |  |  | EPC Ready Total | Grand Total
Business Format / Sub Format | NSO | Refit | SCM |  | NSO | Refit | Dehire | Petro | SCM
B. Fashion & Lifestyle | 2 |  |  | 2 | 11 | 589 | 10 |  |  | 610 | 612
Trends & Allied Formats (Part A) | 1 |  |  | 1 | 4 | 1 |  |  |  | 5 | 6
Trends 3.0 |  |  |  |  | 1 |  |  |  |  | 1 | 1
Fashion Factory |  |  |  |  | 2 |  |  |  |  | 2 | 2
Trends - Refit | [5 empty] | 1 |  |  |  | 1 | 1
Azorte Conversion |  |  |  |  | 1 |  |  |  |  | 1 | 1
Yousta | 1 |  |  | 1 | [6 empty] | 1
Trends & Allied Formats (Part B) | [6 empty] | 1 |  |  | 1 | 1
F&L - Dehire | [6 empty] | 1 |  |  | 1 | 1
Trends & Allied Formats | 1 |  |  | 1 | 7 | 588 | 9 |  |  | 604 | 605
Trends Footwear |  |  |  |  | 1 |  |  |  |  | 1 | 1
Trends 3.0 |  |  |  |  | 2 |  |  |  |  | 2 | 2
Fashion Factory | 1 |  |  | 1 | 1 |  |  |  |  | 1 | 2
Trends - Refit | [5 empty] | 1 |  |  |  | 1 | 1
Azorte |  |  |  |  | 1 |  |  |  |  | 1 | 1
Azorte Conversion |  |  |  |  | 1 |  |  |  |  | 1 | 1
F&L - Dehire | [6 empty] | 9 |  |  | 9 | 9
Yousta |  |  |  |  | 1 |  |  |  |  | 1 | 1
Trends Transformation (Partial) | [5 empty] | 586 |  |  |  | 586 | 586
Trends Transformation (Full) | [5 empty] | 1 |  |  |  | 1 | 1
C. Grocery | 6 |  |  | 6 | 11 | 18 | 5 |  |  | 34 | 40
Grocery | 6 |  |  | 6 | 10 | 18 | 5 |  |  | 33 | 39
Grocery - Dehire | [6 empty] | 5 |  |  | 5 | 5
Smart | 6 |  |  | 6 | 8 |  |  |  |  | 8 | 14
Smart Point |  |  |  |  | 1 |  |  |  |  | 1 | 1
Smart Bazar - Refit | [5 empty] | 1 |  |  |  | 1 | 1
Go Fresh |  |  |  |  | 1 |  |  |  |  | 1 | 1
Grocery - Refit (Partial) | [5 empty] | 8 |  |  |  | 8 | 8
Grocery - SLP Works | [5 empty] | 9 |  |  |  | 9 | 9
V Retail |  |  |  |  | 1 |  |  |  |  | 1 | 1
Centro Footwear (V Retail) |  |  |  |  | 1 |  |  |  |  | 1 | 1
E. Other Business |  |  |  |  | 3 |  | 4 |  |  | 7 | 7
Other Business |  |  |  |  | 3 |  | 4 |  |  | 7 | 7
7-Eleven |  |  |  |  | 1 |  |  |  |  | 1 | 1
Jio Mart Digital |  |  |  |  | 1 |  |  |  |  | 1 | 1
7-Eleven - Dehire | [6 empty] | 4 |  |  | 4 | 4
Urban Ladder SIS |  |  |  |  | 1 |  |  |  |  | 1 | 1
F. SCM |  |  | 4 | 4 |  |  | 1 |  | 6 | 7 | 11
SCM | [6 empty] | 1 |  | 1 | 2 | 2
SCM - Dehire | [6 empty] | 1 |  |  | 1 | 1
Smart Net - DC | [8 empty] | 1 | 1 | 1
SCM BF |  |  | 4 | 4 |  |  |  |  | 5 | 5 | 9
CPC |  |  | 3 | 3 |  |  |  |  | 1 | 1 | 4
Urban Ladder DC | [8 empty] | 1 | 1 | 1
Value DC |  |  | 1 | 1 |  |  |  |  | 3 | 3 | 4
I. Petro | [7 empty] | 5 |  | 5 | 5
Petro | [7 empty] | 5 |  | 5 | 5
Consumer Pump | [7 empty] | 1 |  | 1 | 1
Terminal Aug | [7 empty] | 4 |  | 4 | 4
J. Jio Business |  |  |  |  | 6 |  |  |  |  | 6 | 6
Jio Business |  |  |  |  | 6 |  |  |  |  | 6 | 6
Jio Mart Digital |  |  |  |  | 6 |  |  |  |  | 6 | 6
A. Consumer Electronics & Jewels | 4 | 2 |  | 6 | 13 | 6 | 2 |  |  | 21 | 27
Jewels & Allied Formats |  |  |  |  | 1 |  |  |  |  | 1 | 1
Jewels SAS |  |  |  |  | 1 |  |  |  |  | 1 | 1
Consumer Electronics | 4 | 2 |  | 6 | 12 | 6 | 2 |  |  | 20 | 26
Digital Stores | 4 |  |  | 4 | 7 |  |  |  |  | 7 | 11
Consumer Electronics - Dehire | [6 empty] | 2 |  |  | 2 | 2
Digital - Refit |  | 2 |  | 2 |  | 6 |  |  |  | 6 | 8
DMS |  |  |  |  | 4 |  |  |  |  | 4 | 4
RESQ |  |  |  |  | 1 |  |  |  |  | 1 | 1
L. Dark Store | 16 |  |  | 16 | 18 |  |  |  |  | 18 | 34
Dark Store | 16 |  |  | 16 | 18 |  |  |  |  | 18 | 34
Dark Store | 16 |  |  | 16 | 18 |  |  |  |  | 18 | 34
M. Brands |  |  |  |  | 5 |  |  |  |  | 5 | 5
Brands |  |  |  |  | 5 |  |  |  |  | 5 | 5
Ed-A-Mamma EBO |  |  |  |  | 5 |  |  |  |  | 5 | 5
Grand Total | 28 | 2 | 4 | 34 | 67 | 613 | 22 | 5 | 6 | 713 | 747

## Delivery BTG Site Type Wise
WIP FY 2026-27
EPC Status (Current Week) | WIP
Count of Site Name | Column Labels
Business Format / Sub Format | NSO | Refit | Dehire | Petro | SCM | Grand Total
B. Fashion & Lifestyle | 9 | 253 | 2 |  |  | 264
Trends & Allied Formats (Part A) | 4 |  |  |  |  | 4
Trends 3.0 | 1 |  |  |  |  | 1
Fashion Factory | 1 |  |  |  |  | 1
Azorte Conversion | 1 |  |  |  |  | 1
Yousta | 1 |  |  |  |  | 1
Trends & Allied Formats | 5 | 253 | 2 |  |  | 260
Trends Footwear | 1 |  |  |  |  | 1
Trends - Refit |  | 2 |  |  |  | 2
Azorte | 1 |  |  |  |  | 1
F&L - Dehire |  |  | 2 |  |  | 2
Yousta | 1 |  |  |  |  | 1
Yousta Conversion | 1 |  |  |  |  | 1
Trends Transformation (Partial) |  | 222 |  |  |  | 222
Trends 4.0 | 1 |  |  |  |  | 1
Trends Transformation (Full) |  | 29 |  |  |  | 29
C. Grocery | 12 | 55 |  |  |  | 67
Grocery | 10 | 55 |  |  |  | 65
FreshPik | 1 |  |  |  |  | 1
Grocery - Refit |  | 5 |  |  |  | 5
Smart | 8 |  |  |  |  | 8
Smart Bazar - Refit |  | 1 |  |  |  | 1
Go Fresh | 1 |  |  |  |  | 1
Grocery - Refit (Partial) |  | 44 |  |  |  | 44
Grocery - SLP Works |  | 5 |  |  |  | 5
V Retail | 2 |  |  |  |  | 2
Centro Footwear (V Retail) | 2 |  |  |  |  | 2
E. Other Business | 1 |  |  |  |  | 1
Other Business | 1 |  |  |  |  | 1
7-Eleven | 1 |  |  |  |  | 1
F. SCM |  |  | 1 |  | 12 | 13
SCM |  |  | 1 |  |  | 1
SCM - Dehire |  |  | 1 |  |  | 1
SCM BF |  |  |  |  | 12 | 12
CPC |  |  |  |  | 2 | 2
F&L DC |  |  |  |  | 2 | 2
Market Place |  |  |  |  | 1 | 1
Urban Ladder DC |  |  |  |  | 1 | 1
Value DC |  |  |  |  | 5 | 5
WH |  |  |  |  | 1 | 1
G. GreenField and Other Large Scale Projects |  |  |  |  | 2 | 2
GreenField |  |  |  |  | 2 | 2
Mall Revamp |  |  |  |  | 2 | 2
I. Petro |  |  |  | 6 |  | 6
Petro |  |  |  | 6 |  | 6
Consumer Pump |  |  |  | 1 |  | 1
Mini Depo - Aug |  |  |  | 3 |  | 3
Terminal Aug |  |  |  | 2 |  | 2
J. Jio Business | 3 |  |  |  |  | 3
Jio Business | 3 |  |  |  |  | 3
Jio Centre | 2 |  |  |  |  | 2
Jio Mart Digital | 1 |  |  |  |  | 1
A. Consumer Electronics & Jewels | 16 | 4 | 2 |  |  | 22
Jewels & Allied Formats | 1 |  |  |  |  | 1
Jewels SAS | 1 |  |  |  |  | 1
Consumer Electronics | 15 | 4 | 2 |  |  | 21
Digital Stores | 12 |  |  |  |  | 12
Compact Digital | 1 |  |  |  |  | 1
Consumer Electronics - Dehire |  |  | 2 |  |  | 2
Digital - Refit |  | 4 |  |  |  | 4
Digital Bismi | 1 |  |  |  |  | 1
DMS | 1 |  |  |  |  | 1
L. Dark Store | 4 |  |  |  |  | 4
Dark Store | 4 |  |  |  |  | 4
Dark Store | 4 |  |  |  |  | 4
Grand Total | 45 | 312 | 5 | 6 | 14 | 382

## Dehire Summary (hidden)
Dehire Summary FY 2025-26 as on 10-06-2026
HOTO STATUS
Dehire Summary FY 2024-25 | Zonal Head | Target Total | EPC Ready | Done | Pending | Dropped | BTG | WIP | Partial WIP | On Hold | YTS | In Pipeline | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Business Issue | ML Received - Design WIP | SDR Done - ML Pending | SDR in Process | Pre Budget Dehire Site
| RT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dehire - Consumer Electronics Target | Zonal Head | Target Total | EPC Ready | Done | Pending | Dropped | BTG | WIP | Partial WIP | On Hold | YTS | In Pipeline | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Business Issue | ML Received - Design WIP | SDR Done - ML Pending | SDR in Process | Pre Budget Dehire Site
| RT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dehire - Jewels Target | Zonal Head | Target Total | EPC Ready | Done | Pending | Dropped | BTG | WIP | Partial WIP | On Hold | YTS | In Pipeline | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Business Issue | ML Received - Design WIP | SDR Done - ML Pending | SDR in Process | Pre Budget Dehire Site
| RT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dehire - F&L Target | Zonal Head | Target Total | EPC Ready | Done | Pending | Dropped | BTG | WIP | Partial WIP | On Hold | YTS | In Pipeline | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Business Issue | ML Received - Design WIP | SDR Done - ML Pending | SDR in Process | Pre Budget Dehire Site
| RT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dehire - Misc Target | Zonal Head | Target Total | EPC Ready | Done | Pending | Dropped | BTG | WIP | Partial WIP | On Hold | YTS | In Pipeline | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Business Issue | ML Received - Design WIP | SDR Done - ML Pending | SDR in Process | Pre Budget Dehire Site
| RT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dehire - SCM Target | Zonal Head | Target Total | EPC Ready | Done | Pending | Dropped | BTG | WIP | Partial WIP | On Hold | YTS | In Pipeline | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Business Issue | ML Received - Design WIP | SDR Done - ML Pending | SDR in Process | Pre Budget Dehire Site
| RT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dehire - Grocery | Zonal Head | Target Total | EPC Ready | Done | Pending | Dropped | BTG | WIP | Partial WIP | On Hold | YTS | In Pipeline | Budget Approved - RFC Awaited | Budget Submitted - Approval Awaited | ML Received - Business Issue | ML Received - Design WIP | SDR Done - ML Pending | SDR in Process | Pre Budget Dehire Site
| RT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| KC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Dead Rent Summary (hidden)
WIP Dead Rent Summary (NSO)
EPC Status (Current Week) | (Multiple Items)
Site Type (Dehire/NSO/Refit) | NSO
Count of Site Name | Column Labels
Grand Total
Zonal Head
Grand Total
Jio Centre - Zion Building Kharghar

## PBI (hidden)
Business Format | Format | Sub Format | AOP | EPC Ready | EPC Ready Previous FY | LAUNCHED | YTL | WIP | Balance
A. Consumer Electronics & Jewels | Consumer Electronics | Digital Stores | 85 | 7 | 4 | 5 | 6 | 12 | 62
A. Consumer Electronics & Jewels | Consumer Electronics | My Jio Store | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Jio Store (SSST) | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Resque ( COCO + COFO+FOFO) | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Digital in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Digital 3K | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Digital Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Digital - Refit | 89 | 6 | 2 | 3 | 5 | 4 | 77
A. Consumer Electronics & Jewels | Consumer Electronics | MINIDX - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Consumer Electronics - Dehire | 10 | 2 | 0 | 2 | 0 | 2 | 6
A. Consumer Electronics & Jewels | Consumer Electronics | Maintenance & Service Location (MSL) | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | ResQ Training Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Training Centre | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | MINI DX | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Digital Bismi | 10 | 0 | 0 | 0 | 0 | 1 | 9
A. Consumer Electronics & Jewels | Consumer Electronics | Digital Bismi - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Consumer Electronics | Compact Digital | 0 | 0 | 0 | 0 | 0 | 1 | -1
A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels SAS | 22 | 1 | 0 | 0 | 1 | 1 | 20
A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels Flagship | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Jewels & Allied Formats | New Jewels 3K | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Jewels & Allied Formats | New Jewels 1K | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels - LFS | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. Consumer Electronics & Jewels | Jewels & Allied Formats | Jewels - Dehire | 12 | 0 | 0 | 0 | 0 | 0 | 12
B. Fashion & Lifestyle | Trends & Allied Formats | Trends | 50 | 0 | 0 | 0 | 0 | 0 | 50
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Woman | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Man | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Junior | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Small Town | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Sarees | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear | 3 | 1 | 0 | 1 | 0 | 1 | 1
B. Fashion & Lifestyle | Trends & Allied Formats | Performax | 1 | 0 | 0 | 0 | 0 | 0 | 1
B. Fashion & Lifestyle | Trends & Allied Formats | Azorte | 12 | 1 | 0 | 1 | 0 | 1 | 10
B. Fashion & Lifestyle | Trends & Allied Formats | Azorte Conversion | 0 | 2 | 0 | 2 | 0 | 1 | -3
B. Fashion & Lifestyle | Trends & Allied Formats | Johnplayer EBO | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Lee Cooper EBO | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Payless | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Kalanikethan / VRK Heritage | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Kalanikethan Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Brand Factory to Fashion Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Central to Centro | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Small Store/Easyday to Footwear | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Small Store/Easyday to Man | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Small Store/Easyday to Woman | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | FBB to Saree | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | FBB to Trends | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | FBB to Fashion Factory | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | FBB to Portico | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | FBB TO Footwear | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | FBB TO Woman | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP EBO | 5 | 0 | 0 | 0 | 0 | 0 | 5
B. Fashion & Lifestyle | Trends & Allied Formats | Portico EBO | 3 | 0 | 0 | 0 | 0 | 0 | 3
B. Fashion & Lifestyle | Trends & Allied Formats | Catwalk | 1 | 0 | 0 | 0 | 0 | 0 | 1
B. Fashion & Lifestyle | Trends & Allied Formats | Catwalk SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Yousta | 5 | 1 | 1 | 1 | 1 | 2 | 1
B. Fashion & Lifestyle | Trends & Allied Formats | Yousta Conversion | 0 | 0 | 0 | 0 | 0 | 1 | -1
B. Fashion & Lifestyle | Trends & Allied Formats | FBB TO Junior | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Centro NSO | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends to Yousta | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | FBB to Yousta | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends 3.0 | 0 | 3 | 0 | 1 | 2 | 1 | -4
B. Fashion & Lifestyle | Trends & Allied Formats | Azorte in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends WIW 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Small Town 3.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory | 18 | 3 | 1 | 1 | 3 | 1 | 13
B. Fashion & Lifestyle | Trends & Allied Formats | Fashion World | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear to Facelift | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Ed-A-Mamma EBO | - | 5 | 0 | 5 | 0 | 0 | #VALUE!
B. Fashion & Lifestyle | Trends & Allied Formats | Swadesh | 1 | 0 | 0 | 0 | 0 | 0 | 1
B. Fashion & Lifestyle | Trends & Allied Formats | Cover Story | 5 | 0 | 0 | 0 | 0 | 0 | 5
B. Fashion & Lifestyle | Trends & Allied Formats | Ancestry | 1 | 0 | 0 | 0 | 0 | 0 | 1
B. Fashion & Lifestyle | Trends & Allied Formats | Cover Story SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Ancestry SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Zivame EBO | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Amante | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Clovia | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Portico SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Footwear SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP in Centro | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP_Azorte SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP_Mens SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP KIDS SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | GAP WOMAN SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Azorte SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Johnplayer SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Payless SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Lee Cooper SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Footwear - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Refit | - | 2 | 0 | 1 | 1 | 2 | #VALUE!
B. Fashion & Lifestyle | Trends & Allied Formats | Trends - Renovation | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | F&L - Dehire | 115 | 10 | 0 | 10 | 0 | 2 | 103
B. Fashion & Lifestyle | Trends & Allied Formats | Fashion Factory NEW Design | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Centro New Design | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Centro FAÇADE Refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | VRK Silks | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Ajio | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | New Independent Ivory Mall Centro | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Kalanikethan New Design | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Kalanikethan Chennai -Old Design | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Centro - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Avantara Façade Replacement Works | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Kids Business | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Ecko SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Performax SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Trends Plus | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Yousta - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | F&L Wholesale Formats | Wholesale Store | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | F&L Wholesale Formats | B2B2C | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | F&L Wholesale Formats | Sambandam Store | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Clovia - POS Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Trends & Allied Formats | Zivame in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Other Fashion & Lifestyle Formats | Rise Hub (Swadesh) | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Other Fashion & Lifestyle Formats | Brands India | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. Fashion & Lifestyle | Other Fashion & Lifestyle Formats | Brands UK | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Smart Point | 0 | 1 | 0 | 1 | 0 | 0 | -1
C. Grocery | Grocery | Smart | 200 | 8 | 6 | 12 | 2 | 8 | 178
C. Grocery | Grocery | Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Signature | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | JAISURYA | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | SKDS - Value Format | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Signature Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Smart point Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Small Store/Easyday to Smart Point | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Small Store/Easyday to Signature Fresh | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Grocery - Refit | 268 | 0 | 0 | 0 | 0 | 5 | 263
C. Grocery | Grocery | Grocery - Refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | CNC to Smart Conversion | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | FreshPik | 25 | 0 | 0 | 0 | 0 | 1 | 24
C. Grocery | Grocery | BWS in Smart Bazar | - | 0 | 0 | 0 | 0 | 0 | #VALUE!
C. Grocery | Grocery | Fresh food in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Sweet in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | SIS in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | FBB to Signature | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | FBB to Smart Point | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | FMCG Manufacturing | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Smart Bazar NSO | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Go Fresh | 10 | 1 | 0 | 0 | 1 | 1 | 8
C. Grocery | Grocery | Grocery Bismi - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Smart 3.O | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Mall Food courts | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | BWS IN SMART | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Smart Bazar - Refit | 0 | 1 | 0 | 0 | 1 | 1 | -2
C. Grocery | Grocery | Smart Bazar Azorte - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Smart Bazar Apparel - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Autonomous Store @ Experience Center | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | New Whole sale store Format | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | BB to Smart | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Green Field Malls with Seamless Stores With Format Allocation | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Misc Toilet Works @ SBZ | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Grocery - Dehire | - | 5 | 0 | 5 | 0 | 0 | #VALUE!
C. Grocery | Grocery | Grocery Bismi | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Smart Point to Bismi | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Women's World @ SBZ | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Lift | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Blushlace | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Blushlace in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Blushlace in Smart | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Blushlace in Trends | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Brand Stores to Blushlace | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Refit - Light Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Refit - Façade modification | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | SMART Remodel | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | BWS - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | Grocery | Blushlace - Dehire | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | V Retail | Centro Footwear (V Retail) | 0 | 1 | 0 | 0 | 1 | 2 | -3
C. Grocery | V Retail | Centro Footwear (V Retail) - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | V Retail | Centro Footwear (V Retail) in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | V Retail | Centro Footwear (V Retail) - Dehire | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Grocery | V Retail | Centro Footwear (V Retail) - The Shoe Store | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | Smart Point Pharma | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | HN OP Pharmacy | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | HN IP Pharmacy | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | Seven Hills | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | Netmed | 75 | 0 | 0 | 0 | 0 | 0 | 75
D. Pharma Format | Pharma Format | Pharma SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | Pharma COCO Store (SP Fix Setup) | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | Pharma-Partition Modi. Work (Refit) | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Pharma Format | Pharma Format | Pharma SKDS - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | 7-Eleven | 100 | 1 | 0 | 1 | 0 | 1 | 98
E. Other Business | Other Business | 7 Eleven in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | 7-Eleven - Dehire | 0 | 4 | 0 | 4 | 0 | 0 | -4
E. Other Business | Other Business | Furniture - Mid Premium Store (UL) | 9 | 0 | 0 | 0 | 0 | 0 | 9
E. Other Business | Other Business | Urban ladder in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Urban Ladder SIS | 0 | 1 | 0 | 1 | 0 | 0 | -1
E. Other Business | Other Business | Furniture - SIS - SimplyWud | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Misc - Dehire | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | TDSC | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Beauty (TIRA) | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Beauty in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Interior and Kitchen Fitouts | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Beauty & Cosmetic EBO | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Beauty & Cosmetic SIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | POS Migration | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. Other Business | Other Business | Misc - Refit | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | Smart Hub - DC | - | 0 | 0 | 0 | 0 | 0 | #VALUE!
F. SCM | SCM | Smart Net - DC | 0 | 1 | 0 | 0 | 1 | 0 | -1
F. SCM | SCM | Milk Basket | 15 | 0 | 0 | 0 | 0 | 0 | 15
F. SCM | SCM | Milk basket in Smart Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | HoReCa | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | Milkbasket in SmartNET | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | Staple HUB | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | SCM - Dehire | 0 | 1 | 0 | 1 | 0 | 1 | -2
F. SCM | SCM | CNC to Metro | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | Metro | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM | Centro to Metro | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | B2B | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | B2C | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | CPC | 0 | 1 | 3 | 0 | 4 | 2 | -6
F. SCM | SCM BF | CNC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Beauty DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Digital DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | F&L DC | 0 | 0 | 0 | 0 | 0 | 2 | -2
F. SCM | SCM BF | Urban Ladder DC | 0 | 1 | 0 | 0 | 1 | 1 | -2
F. SCM | SCM BF | Value DC | 0 | 3 | 1 | 0 | 4 | 5 | -9
F. SCM | SCM BF | Jewels DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Pharma-DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Smart Bazar DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Record Room | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Transport HUB- F&L | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | NDC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Collection centre | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Groceries | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Food DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Market Place | 0 | 0 | 0 | 0 | 0 | 1 | -1
F. SCM | SCM BF | WH Property | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | 3P- Market Place | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | FC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Ecom | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | MSR | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Packhouse | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | WH | 0 | 0 | 0 | 0 | 0 | 1 | -1
F. SCM | SCM BF | Device DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Grocery Bismi DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. SCM | SCM BF | Jio DC | 0 | 0 | 0 | 0 | 0 | 0 | 0
G. GreenField and Other Large Scale Projects | GreenField | Mall Revamp | 0 | 0 | 0 | 0 | 0 | 2 | -2
G. GreenField and Other Large Scale Projects | GreenField | Greenfield | 0 | 0 | 0 | 0 | 0 | 0 | 0
G. GreenField and Other Large Scale Projects | GreenField | Jamnagar Mall - Township | 0 | 0 | 0 | 0 | 0 | 0 | 0
G. GreenField and Other Large Scale Projects | GreenField | Jamnagar Mall - Strip Mall | 0 | 0 | 0 | 0 | 0 | 0 | 0
G. GreenField and Other Large Scale Projects | GreenField | Industrial Plant | 0 | 0 | 0 | 0 | 0 | 0 | 0
H. New Energy Business | New Energy Business | EV Battery Swapping | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Petro | Mini Depo - Aug | 0 | 0 | 0 | 0 | 0 | 3 | -3
I. Petro | Petro | Terminal Aug | 0 | 4 | 0 | 4 | 0 | 2 | -6
I. Petro | Petro | Consumer Pump | 0 | 1 | 0 | 1 | 0 | 1 | -2
I. Petro | FMCG Lab | R&D FMCG Lab | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | AFS Aug | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | AFS New | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | ALDS | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | Driveway | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | Highmast | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | MDU | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | NH Affected | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | NRO | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | PFC | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | R&H-Canopy | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | R&H-Driveway | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | RO Augmentation | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | QwikMart | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | Railway Consumer Depot | 0 | 0 | 0 | 0 | 0 | 0 | 0
I. Petro | Other Petro Projects | RO ReCommissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0
J. Jio Business | Jio Business | Jio Mart - Kirana | 0 | 0 | 0 | 0 | 0 | 0 | 0
J. Jio Business | Jio Business | Jio Mart Digital | 185 | 7 | 0 | 7 | 0 | 1 | 177
J. Jio Business | Jio Business | Jio Point | 0 | 0 | 0 | 0 | 0 | 0 | 0
J. Jio Business | Jio Business | Jio Centre | 8 | 0 | 0 | 0 | 0 | 2 | 6
K. Other Office Infrastructure | Office | Zivame Office | 0 | 0 | 0 | 0 | 0 | 0 | 0
K. Other Office Infrastructure | Office | Admin Office (Corporate Services) | 0 | 0 | 0 | 0 | 0 | 0 | 0
K. Other Office Infrastructure | Office | Cover Story Office | 0 | 0 | 0 | 0 | 0 | 0 | 0
K. Other Office Infrastructure | Office | Office Areas in Malls | 0 | 0 | 0 | 0 | 0 | 0 | 0
K. Other Office Infrastructure | Office | Office at IBC (TDSC+Office+Cafeteria+Design Studio) | 0 | 0 | 0 | 0 | 0 | 0 | 0
K. Other Office Infrastructure | Office | Grocery Office | 0 | 0 | 0 | 0 | 0 | 0 | 0
L. Dark Store | Dark Store | Dark Store | 450 | 18 | 16 | 22 | 12 | 4 | 412

## AOP Calendar (hidden)
Sl. No. | Date | Month | Year | Day | No. | Week No. | Concatenate Month & Week | Month for Plan | Plan | Concatenate Month & Plan
1 | 2022-04-01 | April | 22 | 1 | 1 | Week 1 | April 22 Week 1 | APRIL 22 | PLANNED | APRIL 22 PLANNED
2 | 2022-04-02 | April | 22 | 2 | 1 | Week 1 | April 22 Week 1 | APRIL 22 | PLANNED | APRIL 22 PLANNED
3 | 2022-04-03 | April | 22 | 3 | 1 | Week 1 | April 22 Week 1 | APRIL 22 | PLANNED | APRIL 22 PLANNED
4 | 2022-04-04 | April | 22 | 4 | 1 | Week 1 | April 22 Week 1 | APRIL 22 | PLANNED | APRIL 22 PLANNED
5 | 2022-04-05 | April | 22 | 5 | 1 | Week 1 | April 22 Week 1 | APRIL 22 | PLANNED | APRIL 22 PLANNED
6 | 2022-04-06 | April | 22 | 6 | 1 | Week 1 | April 22 Week 1 | APRIL 22 | PLANNED | APRIL 22 PLANNED
7 | 2022-04-07 | April | 22 | 7 | 1 | Week 1 | April 22 Week 1 | APRIL 22 | PLANNED | APRIL 22 PLANNED
1 | 2022-04-08 | April | 22 | 8 | 2 | Week 2 | April 22 Week 2 | APRIL 22 | PLANNED | APRIL 22 PLANNED
2 | 2022-04-09 | April | 22 | 9 | 2 | Week 2 | April 22 Week 2 | APRIL 22 | PLANNED | APRIL 22 PLANNED
3 | 2022-04-10 | April | 22 | 10 | 2 | Week 2 | April 22 Week 2 | APRIL 22 | PLANNED | APRIL 22 PLANNED
4 | 2022-04-11 | April | 22 | 11 | 2 | Week 2 | April 22 Week 2 | APRIL 22 | PLANNED | APRIL 22 PLANNED
5 | 2022-04-12 | April | 22 | 12 | 2 | Week 2 | April 22 Week 2 | APRIL 22 | PLANNED | APRIL 22 PLANNED
6 | 2022-04-13 | April | 22 | 13 | 2 | Week 2 | April 22 Week 2 | APRIL 22 | PLANNED | APRIL 22 PLANNED
7 | 2022-04-14 | April | 22 | 14 | 2 | Week 2 | April 22 Week 2 | APRIL 22 | PLANNED | APRIL 22 PLANNED
1 | 2022-04-15 | April | 22 | 15 | 3 | Week 3 | April 22 Week 3 | APRIL 22 | PLANNED | APRIL 22 PLANNED
2 | 2022-04-16 | April | 22 | 16 | 3 | Week 3 | April 22 Week 3 | APRIL 22 | PLANNED | APRIL 22 PLANNED
3 | 2022-04-17 | April | 22 | 17 | 3 | Week 3 | April 22 Week 3 | APRIL 22 | PLANNED | APRIL 22 PLANNED
4 | 2022-04-18 | April | 22 | 18 | 3 | Week 3 | April 22 Week 3 | APRIL 22 | PLANNED | APRIL 22 PLANNED
5 | 2022-04-19 | April | 22 | 19 | 3 | Week 3 | April 22 Week 3 | APRIL 22 | PLANNED | APRIL 22 PLANNED
6 | 2022-04-20 | April | 22 | 20 | 3 | Week 3 | April 22 Week 3 | APRIL 22 | PLANNED | APRIL 22 PLANNED
7 | 2022-04-21 | April | 22 | 21 | 3 | Week 3 | April 22 Week 3 | APRIL 22 | PLANNED | APRIL 22 PLANNED
1 | 2022-04-22 | April | 22 | 22 | 4 | Week 4 | April 22 Week 4 | APRIL 22 | PLANNED | APRIL 22 PLANNED
2 | 2022-04-23 | April | 22 | 23 | 4 | Week 4 | April 22 Week 4 | APRIL 22 | PLANNED | APRIL 22 PLANNED
3 | 2022-04-24 | April | 22 | 24 | 4 | Week 4 | April 22 Week 4 | APRIL 22 | PLANNED | APRIL 22 PLANNED
4 | 2022-04-25 | April | 22 | 25 | 4 | Week 4 | April 22 Week 4 | APRIL 22 | PLANNED | APRIL 22 PLANNED
5 | 2022-04-26 | April | 22 | 26 | 4 | Week 4 | April 22 Week 4 | APRIL 22 | PLANNED | APRIL 22 PLANNED
6 | 2022-04-27 | April | 22 | 27 | 4 | Week 4 | April 22 Week 4 | APRIL 22 | PLANNED | APRIL 22 PLANNED
7 | 2022-04-28 | April | 22 | 28 | 4 | Week 4 | April 22 Week 4 | APRIL 22 | PLANNED | APRIL 22 PLANNED
1 | 2022-04-29 | April | 22 | 29 | 5 | Week 5 | April 22 Week 5 | APRIL 22 | PLANNED | APRIL 22 PLANNED
2 | 2022-04-30 | April | 22 | 30 | 5 | Week 5 | April 22 Week 5 | APRIL 22 | PLANNED | APRIL 22 PLANNED
1 | 2022-05-01 | May | 22 | 1 | 1 | Week 1 | May 22 Week 1 | MAY 22 | PLANNED | MAY 22 PLANNED
2 | 2022-05-02 | May | 22 | 2 | 1 | Week 1 | May 22 Week 1 | MAY 22 | PLANNED | MAY 22 PLANNED
3 | 2022-05-03 | May | 22 | 3 | 1 | Week 1 | May 22 Week 1 | MAY 22 | PLANNED | MAY 22 PLANNED
4 | 2022-05-04 | May | 22 | 4 | 1 | Week 1 | May 22 Week 1 | MAY 22 | PLANNED | MAY 22 PLANNED
5 | 2022-05-05 | May | 22 | 5 | 1 | Week 1 | May 22 Week 1 | MAY 22 | PLANNED | MAY 22 PLANNED
6 | 2022-05-06 | May | 22 | 6 | 1 | Week 1 | May 22 Week 1 | MAY 22 | PLANNED | MAY 22 PLANNED
7 | 2022-05-07 | May | 22 | 7 | 1 | Week 1 | May 22 Week 1 | MAY 22 | PLANNED | MAY 22 PLANNED
1 | 2022-05-08 | May | 22 | 8 | 2 | Week 2 | May 22 Week 2 | MAY 22 | PLANNED | MAY 22 PLANNED
2 | 2022-05-09 | May | 22 | 9 | 2 | Week 2 | May 22 Week 2 | MAY 22 | PLANNED | MAY 22 PLANNED
3 | 2022-05-10 | May | 22 | 10 | 2 | Week 2 | May 22 Week 2 | MAY 22 | PLANNED | MAY 22 PLANNED
4 | 2022-05-11 | May | 22 | 11 | 2 | Week 2 | May 22 Week 2 | MAY 22 | PLANNED | MAY 22 PLANNED
5 | 2022-05-12 | May | 22 | 12 | 2 | Week 2 | May 22 Week 2 | MAY 22 | PLANNED | MAY 22 PLANNED
6 | 2022-05-13 | May | 22 | 13 | 2 | Week 2 | May 22 Week 2 | MAY 22 | PLANNED | MAY 22 PLANNED
7 | 2022-05-14 | May | 22 | 14 | 2 | Week 2 | May 22 Week 2 | MAY 22 | PLANNED | MAY 22 PLANNED
1 | 2022-05-15 | May | 22 | 15 | 3 | Week 3 | May 22 Week 3 | MAY 22 | PLANNED | MAY 22 PLANNED
2 | 2022-05-16 | May | 22 | 16 | 3 | Week 3 | May 22 Week 3 | MAY 22 | PLANNED | MAY 22 PLANNED
3 | 2022-05-17 | May | 22 | 17 | 3 | Week 3 | May 22 Week 3 | MAY 22 | PLANNED | MAY 22 PLANNED
4 | 2022-05-18 | May | 22 | 18 | 3 | Week 3 | May 22 Week 3 | MAY 22 | PLANNED | MAY 22 PLANNED
5 | 2022-05-19 | May | 22 | 19 | 3 | Week 3 | May 22 Week 3 | MAY 22 | PLANNED | MAY 22 PLANNED
6 | 2022-05-20 | May | 22 | 20 | 3 | Week 3 | May 22 Week 3 | MAY 22 | PLANNED | MAY 22 PLANNED
7 | 2022-05-21 | May | 22 | 21 | 3 | Week 3 | May 22 Week 3 | MAY 22 | PLANNED | MAY 22 PLANNED
1 | 2022-05-22 | May | 22 | 22 | 4 | Week 4 | May 22 Week 4 | MAY 22 | PLANNED | MAY 22 PLANNED
2 | 2022-05-23 | May | 22 | 23 | 4 | Week 4 | May 22 Week 4 | MAY 22 | PLANNED | MAY 22 PLANNED
3 | 2022-05-24 | May | 22 | 24 | 4 | Week 4 | May 22 Week 4 | MAY 22 | PLANNED | MAY 22 PLANNED
4 | 2022-05-25 | May | 22 | 25 | 4 | Week 4 | May 22 Week 4 | MAY 22 | PLANNED | MAY 22 PLANNED
5 | 2022-05-26 | May | 22 | 26 | 4 | Week 4 | May 22 Week 4 | MAY 22 | PLANNED | MAY 22 PLANNED
6 | 2022-05-27 | May | 22 | 27 | 4 | Week 4 | May 22 Week 4 | MAY 22 | PLANNED | MAY 22 PLANNED
7 | 2022-05-28 | May | 22 | 28 | 4 | Week 4 | May 22 Week 4 | MAY 22 | PLANNED | MAY 22 PLANNED
1 | 2022-05-29 | May | 22 | 29 | 5 | Week 5 | May 22 Week 5 | MAY 22 | PLANNED | MAY 22 PLANNED
2 | 2022-05-30 | May | 22 | 30 | 5 | Week 5 | May 22 Week 5 | MAY 22 | PLANNED | MAY 22 PLANNED
3 | 2022-05-31 | May | 22 | 31 | 5 | Week 5 | May 22 Week 5 | MAY 22 | PLANNED | MAY 22 PLANNED
1 | 2022-06-01 | June | 22 | 1 | 1 | Week 1 | June 22 Week 1 | JUNE 22 | PLANNED | JUNE 22 PLANNED
2 | 2022-06-02 | June | 22 | 2 | 1 | Week 1 | June 22 Week 1 | JUNE 22 | PLANNED | JUNE 22 PLANNED
3 | 2022-06-03 | June | 22 | 3 | 1 | Week 1 | June 22 Week 1 | JUNE 22 | PLANNED | JUNE 22 PLANNED
4 | 2022-06-04 | June | 22 | 4 | 1 | Week 1 | June 22 Week 1 | JUNE 22 | PLANNED | JUNE 22 PLANNED
5 | 2022-06-05 | June | 22 | 5 | 1 | Week 1 | June 22 Week 1 | JUNE 22 | PLANNED | JUNE 22 PLANNED
6 | 2022-06-06 | June | 22 | 6 | 1 | Week 1 | June 22 Week 1 | JUNE 22 | PLANNED | JUNE 22 PLANNED
7 | 2022-06-07 | June | 22 | 7 | 1 | Week 1 | June 22 Week 1 | JUNE 22 | PLANNED | JUNE 22 PLANNED
1 | 2022-06-08 | June | 22 | 8 | 2 | Week 2 | June 22 Week 2 | JUNE 22 | PLANNED | JUNE 22 PLANNED
2 | 2022-06-09 | June | 22 | 9 | 2 | Week 2 | June 22 Week 2 | JUNE 22 | PLANNED | JUNE 22 PLANNED
3 | 2022-06-10 | June | 22 | 10 | 2 | Week 2 | June 22 Week 2 | JUNE 22 | PLANNED | JUNE 22 PLANNED
4 | 2022-06-11 | June | 22 | 11 | 2 | Week 2 | June 22 Week 2 | JUNE 22 | PLANNED | JUNE 22 PLANNED
5 | 2022-06-12 | June | 22 | 12 | 2 | Week 2 | June 22 Week 2 | JUNE 22 | PLANNED | JUNE 22 PLANNED
6 | 2022-06-13 | June | 22 | 13 | 2 | Week 2 | June 22 Week 2 | JUNE 22 | PLANNED | JUNE 22 PLANNED
7 | 2022-06-14 | June | 22 | 14 | 2 | Week 2 | June 22 Week 2 | JUNE 22 | PLANNED | JUNE 22 PLANNED
1 | 2022-06-15 | June | 22 | 15 | 3 | Week 3 | June 22 Week 3 | JUNE 22 | PLANNED | JUNE 22 PLANNED
2 | 2022-06-16 | June | 22 | 16 | 3 | Week 3 | June 22 Week 3 | JUNE 22 | PLANNED | JUNE 22 PLANNED
3 | 2022-06-17 | June | 22 | 17 | 3 | Week 3 | June 22 Week 3 | JUNE 22 | PLANNED | JUNE 22 PLANNED
4 | 2022-06-18 | June | 22 | 18 | 3 | Week 3 | June 22 Week 3 | JUNE 22 | PLANNED | JUNE 22 PLANNED
5 | 2022-06-19 | June | 22 | 19 | 3 | Week 3 | June 22 Week 3 | JUNE 22 | PLANNED | JUNE 22 PLANNED
6 | 2022-06-20 | June | 22 | 20 | 3 | Week 3 | June 22 Week 3 | JUNE 22 | PLANNED | JUNE 22 PLANNED
7 | 2022-06-21 | June | 22 | 21 | 3 | Week 3 | June 22 Week 3 | JUNE 22 | PLANNED | JUNE 22 PLANNED
1 | 2022-06-22 | June | 22 | 22 | 4 | Week 4 | June 22 Week 4 | JUNE 22 | PLANNED | JUNE 22 PLANNED
2 | 2022-06-23 | June | 22 | 23 | 4 | Week 4 | June 22 Week 4 | JUNE 22 | PLANNED | JUNE 22 PLANNED
3 | 2022-06-24 | June | 22 | 24 | 4 | Week 4 | June 22 Week 4 | JUNE 22 | PLANNED | JUNE 22 PLANNED
4 | 2022-06-25 | June | 22 | 25 | 4 | Week 4 | June 22 Week 4 | JUNE 22 | PLANNED | JUNE 22 PLANNED
5 | 2022-06-26 | June | 22 | 26 | 4 | Week 4 | June 22 Week 4 | JUNE 22 | PLANNED | JUNE 22 PLANNED
6 | 2022-06-27 | June | 22 | 27 | 4 | Week 4 | June 22 Week 4 | JUNE 22 | PLANNED | JUNE 22 PLANNED
7 | 2022-06-28 | June | 22 | 28 | 4 | Week 4 | June 22 Week 4 | JUNE 22 | PLANNED | JUNE 22 PLANNED
1 | 2022-06-29 | June | 22 | 29 | 5 | Week 5 | June 22 Week 5 | JUNE 22 | PLANNED | JUNE 22 PLANNED
2 | 2022-06-30 | June | 22 | 30 | 5 | Week 5 | June 22 Week 5 | JUNE 22 | PLANNED | JUNE 22 PLANNED
1 | 2022-07-01 | July | 22 | 1 | 1 | Week 1 | July 22 Week 1 | JULY 22 | PLANNED | JULY 22 PLANNED
2 | 2022-07-02 | July | 22 | 2 | 1 | Week 1 | July 22 Week 1 | JULY 22 | PLANNED | JULY 22 PLANNED
3 | 2022-07-03 | July | 22 | 3 | 1 | Week 1 | July 22 Week 1 | JULY 22 | PLANNED | JULY 22 PLANNED
4 | 2022-07-04 | July | 22 | 4 | 1 | Week 1 | July 22 Week 1 | JULY 22 | PLANNED | JULY 22 PLANNED
5 | 2022-07-05 | July | 22 | 5 | 1 | Week 1 | July 22 Week 1 | JULY 22 | PLANNED | JULY 22 PLANNED
6 | 2022-07-06 | July | 22 | 6 | 1 | Week 1 | July 22 Week 1 | JULY 22 | PLANNED | JULY 22 PLANNED
7 | 2022-07-07 | July | 22 | 7 | 1 | Week 1 | July 22 Week 1 | JULY 22 | PLANNED | JULY 22 PLANNED
1 | 2022-07-08 | July | 22 | 8 | 2 | Week 2 | July 22 Week 2 | JULY 22 | PLANNED | JULY 22 PLANNED
2 | 2022-07-09 | July | 22 | 9 | 2 | Week 2 | July 22 Week 2 | JULY 22 | PLANNED | JULY 22 PLANNED
3 | 2022-07-10 | July | 22 | 10 | 2 | Week 2 | July 22 Week 2 | JULY 22 | PLANNED | JULY 22 PLANNED
4 | 2022-07-11 | July | 22 | 11 | 2 | Week 2 | July 22 Week 2 | JULY 22 | PLANNED | JULY 22 PLANNED
5 | 2022-07-12 | July | 22 | 12 | 2 | Week 2 | July 22 Week 2 | JULY 22 | PLANNED | JULY 22 PLANNED
6 | 2022-07-13 | July | 22 | 13 | 2 | Week 2 | July 22 Week 2 | JULY 22 | PLANNED | JULY 22 PLANNED
7 | 2022-07-14 | July | 22 | 14 | 2 | Week 2 | July 22 Week 2 | JULY 22 | PLANNED | JULY 22 PLANNED
1 | 2022-07-15 | July | 22 | 15 | 3 | Week 3 | July 22 Week 3 | JULY 22 | PLANNED | JULY 22 PLANNED
2 | 2022-07-16 | July | 22 | 16 | 3 | Week 3 | July 22 Week 3 | JULY 22 | PLANNED | JULY 22 PLANNED
3 | 2022-07-17 | July | 22 | 17 | 3 | Week 3 | July 22 Week 3 | JULY 22 | PLANNED | JULY 22 PLANNED
4 | 2022-07-18 | July | 22 | 18 | 3 | Week 3 | July 22 Week 3 | JULY 22 | PLANNED | JULY 22 PLANNED
5 | 2022-07-19 | July | 22 | 19 | 3 | Week 3 | July 22 Week 3 | JULY 22 | PLANNED | JULY 22 PLANNED
6 | 2022-07-20 | July | 22 | 20 | 3 | Week 3 | July 22 Week 3 | JULY 22 | PLANNED | JULY 22 PLANNED
7 | 2022-07-21 | July | 22 | 21 | 3 | Week 3 | July 22 Week 3 | JULY 22 | PLANNED | JULY 22 PLANNED
1 | 2022-07-22 | July | 22 | 22 | 4 | Week 4 | July 22 Week 4 | JULY 22 | PLANNED | JULY 22 PLANNED
2 | 2022-07-23 | July | 22 | 23 | 4 | Week 4 | July 22 Week 4 | JULY 22 | PLANNED | JULY 22 PLANNED
3 | 2022-07-24 | July | 22 | 24 | 4 | Week 4 | July 22 Week 4 | JULY 22 | PLANNED | JULY 22 PLANNED
4 | 2022-07-25 | July | 22 | 25 | 4 | Week 4 | July 22 Week 4 | JULY 22 | PLANNED | JULY 22 PLANNED
5 | 2022-07-26 | July | 22 | 26 | 4 | Week 4 | July 22 Week 4 | JULY 22 | PLANNED | JULY 22 PLANNED
6 | 2022-07-27 | July | 22 | 27 | 4 | Week 4 | July 22 Week 4 | JULY 22 | PLANNED | JULY 22 PLANNED
7 | 2022-07-28 | July | 22 | 28 | 4 | Week 4 | July 22 Week 4 | JULY 22 | PLANNED | JULY 22 PLANNED
1 | 2022-07-29 | July | 22 | 29 | 5 | Week 5 | July 22 Week 5 | JULY 22 | PLANNED | JULY 22 PLANNED
2 | 2022-07-30 | July | 22 | 30 | 5 | Week 5 | July 22 Week 5 | JULY 22 | PLANNED | JULY 22 PLANNED
3 | 2022-07-31 | July | 22 | 31 | 5 | Week 5 | July 22 Week 5 | JULY 22 | PLANNED | JULY 22 PLANNED
1 | 2022-08-01 | August | 22 | 1 | 1 | Week 1 | August 22 Week 1 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
2 | 2022-08-02 | August | 22 | 2 | 1 | Week 1 | August 22 Week 1 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
3 | 2022-08-03 | August | 22 | 3 | 1 | Week 1 | August 22 Week 1 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
4 | 2022-08-04 | August | 22 | 4 | 1 | Week 1 | August 22 Week 1 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
5 | 2022-08-05 | August | 22 | 5 | 1 | Week 1 | August 22 Week 1 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
6 | 2022-08-06 | August | 22 | 6 | 1 | Week 1 | August 22 Week 1 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
7 | 2022-08-07 | August | 22 | 7 | 1 | Week 1 | August 22 Week 1 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
1 | 2022-08-08 | August | 22 | 8 | 2 | Week 2 | August 22 Week 2 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
2 | 2022-08-09 | August | 22 | 9 | 2 | Week 2 | August 22 Week 2 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
3 | 2022-08-10 | August | 22 | 10 | 2 | Week 2 | August 22 Week 2 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
4 | 2022-08-11 | August | 22 | 11 | 2 | Week 2 | August 22 Week 2 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
5 | 2022-08-12 | August | 22 | 12 | 2 | Week 2 | August 22 Week 2 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
6 | 2022-08-13 | August | 22 | 13 | 2 | Week 2 | August 22 Week 2 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
7 | 2022-08-14 | August | 22 | 14 | 2 | Week 2 | August 22 Week 2 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
1 | 2022-08-15 | August | 22 | 15 | 3 | Week 3 | August 22 Week 3 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
2 | 2022-08-16 | August | 22 | 16 | 3 | Week 3 | August 22 Week 3 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
3 | 2022-08-17 | August | 22 | 17 | 3 | Week 3 | August 22 Week 3 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
4 | 2022-08-18 | August | 22 | 18 | 3 | Week 3 | August 22 Week 3 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
5 | 2022-08-19 | August | 22 | 19 | 3 | Week 3 | August 22 Week 3 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
6 | 2022-08-20 | August | 22 | 20 | 3 | Week 3 | August 22 Week 3 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
7 | 2022-08-21 | August | 22 | 21 | 3 | Week 3 | August 22 Week 3 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
1 | 2022-08-22 | August | 22 | 22 | 4 | Week 4 | August 22 Week 4 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
2 | 2022-08-23 | August | 22 | 23 | 4 | Week 4 | August 22 Week 4 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
3 | 2022-08-24 | August | 22 | 24 | 4 | Week 4 | August 22 Week 4 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
4 | 2022-08-25 | August | 22 | 25 | 4 | Week 4 | August 22 Week 4 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
5 | 2022-08-26 | August | 22 | 26 | 4 | Week 4 | August 22 Week 4 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
6 | 2022-08-27 | August | 22 | 27 | 4 | Week 4 | August 22 Week 4 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
7 | 2022-08-28 | August | 22 | 28 | 4 | Week 4 | August 22 Week 4 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
1 | 2022-08-29 | August | 22 | 29 | 5 | Week 5 | August 22 Week 5 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
2 | 2022-08-30 | August | 22 | 30 | 5 | Week 5 | August 22 Week 5 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
3 | 2022-08-31 | August | 22 | 31 | 5 | Week 5 | August 22 Week 5 | AUGUST 22 | PLANNED | AUGUST 22 PLANNED
1 | 2022-09-01 | September | 22 | 1 | 1 | Week 1 | September 22 Week 1 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
2 | 2022-09-02 | September | 22 | 2 | 1 | Week 1 | September 22 Week 1 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
3 | 2022-09-03 | September | 22 | 3 | 1 | Week 1 | September 22 Week 1 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
4 | 2022-09-04 | September | 22 | 4 | 1 | Week 1 | September 22 Week 1 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
5 | 2022-09-05 | September | 22 | 5 | 1 | Week 1 | September 22 Week 1 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
6 | 2022-09-06 | September | 22 | 6 | 1 | Week 1 | September 22 Week 1 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
7 | 2022-09-07 | September | 22 | 7 | 1 | Week 1 | September 22 Week 1 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
1 | 2022-09-08 | September | 22 | 8 | 2 | Week 2 | September 22 Week 2 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
2 | 2022-09-09 | September | 22 | 9 | 2 | Week 2 | September 22 Week 2 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
3 | 2022-09-10 | September | 22 | 10 | 2 | Week 2 | September 22 Week 2 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
4 | 2022-09-11 | September | 22 | 11 | 2 | Week 2 | September 22 Week 2 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
5 | 2022-09-12 | September | 22 | 12 | 2 | Week 2 | September 22 Week 2 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
6 | 2022-09-13 | September | 22 | 13 | 2 | Week 2 | September 22 Week 2 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
7 | 2022-09-14 | September | 22 | 14 | 2 | Week 2 | September 22 Week 2 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
1 | 2022-09-15 | September | 22 | 15 | 3 | Week 3 | September 22 Week 3 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
2 | 2022-09-16 | September | 22 | 16 | 3 | Week 3 | September 22 Week 3 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
3 | 2022-09-17 | September | 22 | 17 | 3 | Week 3 | September 22 Week 3 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
4 | 2022-09-18 | September | 22 | 18 | 3 | Week 3 | September 22 Week 3 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
5 | 2022-09-19 | September | 22 | 19 | 3 | Week 3 | September 22 Week 3 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
6 | 2022-09-20 | September | 22 | 20 | 3 | Week 3 | September 22 Week 3 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
7 | 2022-09-21 | September | 22 | 21 | 3 | Week 3 | September 22 Week 3 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
1 | 2022-09-22 | September | 22 | 22 | 4 | Week 4 | September 22 Week 4 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
2 | 2022-09-23 | September | 22 | 23 | 4 | Week 4 | September 22 Week 4 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
3 | 2022-09-24 | September | 22 | 24 | 4 | Week 4 | September 22 Week 4 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
4 | 2022-09-25 | September | 22 | 25 | 4 | Week 4 | September 22 Week 4 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
5 | 2022-09-26 | September | 22 | 26 | 4 | Week 4 | September 22 Week 4 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
6 | 2022-09-27 | September | 22 | 27 | 4 | Week 4 | September 22 Week 4 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
7 | 2022-09-28 | September | 22 | 28 | 4 | Week 4 | September 22 Week 4 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
1 | 2022-09-29 | September | 22 | 29 | 5 | Week 5 | September 22 Week 5 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
2 | 2022-09-30 | September | 22 | 30 | 5 | Week 5 | September 22 Week 5 | SEPTEMBER 22 | PLANNED | SEPTEMBER 22 PLANNED
1 | 2022-10-01 | October | 22 | 1 | 1 | Week 1 | October 22 Week 1 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
2 | 2022-10-02 | October | 22 | 2 | 1 | Week 1 | October 22 Week 1 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
3 | 2022-10-03 | October | 22 | 3 | 1 | Week 1 | October 22 Week 1 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
4 | 2022-10-04 | October | 22 | 4 | 1 | Week 1 | October 22 Week 1 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
5 | 2022-10-05 | October | 22 | 5 | 1 | Week 1 | October 22 Week 1 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
6 | 2022-10-06 | October | 22 | 6 | 1 | Week 1 | October 22 Week 1 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
7 | 2022-10-07 | October | 22 | 7 | 1 | Week 1 | October 22 Week 1 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
1 | 2022-10-08 | October | 22 | 8 | 2 | Week 2 | October 22 Week 2 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
2 | 2022-10-09 | October | 22 | 9 | 2 | Week 2 | October 22 Week 2 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
3 | 2022-10-10 | October | 22 | 10 | 2 | Week 2 | October 22 Week 2 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
4 | 2022-10-11 | October | 22 | 11 | 2 | Week 2 | October 22 Week 2 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
5 | 2022-10-12 | October | 22 | 12 | 2 | Week 2 | October 22 Week 2 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
6 | 2022-10-13 | October | 22 | 13 | 2 | Week 2 | October 22 Week 2 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
7 | 2022-10-14 | October | 22 | 14 | 2 | Week 2 | October 22 Week 2 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
1 | 2022-10-15 | October | 22 | 15 | 3 | Week 3 | October 22 Week 3 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
2 | 2022-10-16 | October | 22 | 16 | 3 | Week 3 | October 22 Week 3 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
3 | 2022-10-17 | October | 22 | 17 | 3 | Week 3 | October 22 Week 3 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
4 | 2022-10-18 | October | 22 | 18 | 3 | Week 3 | October 22 Week 3 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
5 | 2022-10-19 | October | 22 | 19 | 3 | Week 3 | October 22 Week 3 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
6 | 2022-10-20 | October | 22 | 20 | 3 | Week 3 | October 22 Week 3 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
7 | 2022-10-21 | October | 22 | 21 | 3 | Week 3 | October 22 Week 3 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
1 | 2022-10-22 | October | 22 | 22 | 4 | Week 4 | October 22 Week 4 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
2 | 2022-10-23 | October | 22 | 23 | 4 | Week 4 | October 22 Week 4 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
3 | 2022-10-24 | October | 22 | 24 | 4 | Week 4 | October 22 Week 4 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
4 | 2022-10-25 | October | 22 | 25 | 4 | Week 4 | October 22 Week 4 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
5 | 2022-10-26 | October | 22 | 26 | 4 | Week 4 | October 22 Week 4 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
6 | 2022-10-27 | October | 22 | 27 | 4 | Week 4 | October 22 Week 4 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
7 | 2022-10-28 | October | 22 | 28 | 4 | Week 4 | October 22 Week 4 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
1 | 2022-10-29 | October | 22 | 29 | 5 | Week 5 | October 22 Week 5 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
2 | 2022-10-30 | October | 22 | 30 | 5 | Week 5 | October 22 Week 5 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
3 | 2022-10-31 | October | 22 | 31 | 5 | Week 5 | October 22 Week 5 | OCTOBER 22 | PLANNED | OCTOBER 22 PLANNED
1 | 2022-11-01 | November | 22 | 1 | 1 | Week 1 | November 22 Week 1 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
2 | 2022-11-02 | November | 22 | 2 | 1 | Week 1 | November 22 Week 1 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
3 | 2022-11-03 | November | 22 | 3 | 1 | Week 1 | November 22 Week 1 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
4 | 2022-11-04 | November | 22 | 4 | 1 | Week 1 | November 22 Week 1 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
5 | 2022-11-05 | November | 22 | 5 | 1 | Week 1 | November 22 Week 1 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
6 | 2022-11-06 | November | 22 | 6 | 1 | Week 1 | November 22 Week 1 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
7 | 2022-11-07 | November | 22 | 7 | 1 | Week 1 | November 22 Week 1 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
1 | 2022-11-08 | November | 22 | 8 | 2 | Week 2 | November 22 Week 2 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
2 | 2022-11-09 | November | 22 | 9 | 2 | Week 2 | November 22 Week 2 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
3 | 2022-11-10 | November | 22 | 10 | 2 | Week 2 | November 22 Week 2 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
4 | 2022-11-11 | November | 22 | 11 | 2 | Week 2 | November 22 Week 2 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
5 | 2022-11-12 | November | 22 | 12 | 2 | Week 2 | November 22 Week 2 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
6 | 2022-11-13 | November | 22 | 13 | 2 | Week 2 | November 22 Week 2 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
7 | 2022-11-14 | November | 22 | 14 | 2 | Week 2 | November 22 Week 2 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
1 | 2022-11-15 | November | 22 | 15 | 3 | Week 3 | November 22 Week 3 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
2 | 2022-11-16 | November | 22 | 16 | 3 | Week 3 | November 22 Week 3 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
3 | 2022-11-17 | November | 22 | 17 | 3 | Week 3 | November 22 Week 3 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
4 | 2022-11-18 | November | 22 | 18 | 3 | Week 3 | November 22 Week 3 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
5 | 2022-11-19 | November | 22 | 19 | 3 | Week 3 | November 22 Week 3 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
6 | 2022-11-20 | November | 22 | 20 | 3 | Week 3 | November 22 Week 3 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
7 | 2022-11-21 | November | 22 | 21 | 3 | Week 3 | November 22 Week 3 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
1 | 2022-11-22 | November | 22 | 22 | 4 | Week 4 | November 22 Week 4 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
2 | 2022-11-23 | November | 22 | 23 | 4 | Week 4 | November 22 Week 4 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
3 | 2022-11-24 | November | 22 | 24 | 4 | Week 4 | November 22 Week 4 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
4 | 2022-11-25 | November | 22 | 25 | 4 | Week 4 | November 22 Week 4 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
5 | 2022-11-26 | November | 22 | 26 | 4 | Week 4 | November 22 Week 4 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
6 | 2022-11-27 | November | 22 | 27 | 4 | Week 4 | November 22 Week 4 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
7 | 2022-11-28 | November | 22 | 28 | 4 | Week 4 | November 22 Week 4 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
1 | 2022-11-29 | November | 22 | 29 | 5 | Week 5 | November 22 Week 5 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
2 | 2022-11-30 | November | 22 | 30 | 5 | Week 5 | November 22 Week 5 | NOVEMBER 22 | PLANNED | NOVEMBER 22 PLANNED
1 | 2022-12-01 | December | 22 | 1 | 1 | Week 1 | December 22 Week 1 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
2 | 2022-12-02 | December | 22 | 2 | 1 | Week 1 | December 22 Week 1 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
3 | 2022-12-03 | December | 22 | 3 | 1 | Week 1 | December 22 Week 1 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
4 | 2022-12-04 | December | 22 | 4 | 1 | Week 1 | December 22 Week 1 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
5 | 2022-12-05 | December | 22 | 5 | 1 | Week 1 | December 22 Week 1 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
6 | 2022-12-06 | December | 22 | 6 | 1 | Week 1 | December 22 Week 1 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
7 | 2022-12-07 | December | 22 | 7 | 1 | Week 1 | December 22 Week 1 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
1 | 2022-12-08 | December | 22 | 8 | 2 | Week 2 | December 22 Week 2 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
2 | 2022-12-09 | December | 22 | 9 | 2 | Week 2 | December 22 Week 2 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
3 | 2022-12-10 | December | 22 | 10 | 2 | Week 2 | December 22 Week 2 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
4 | 2022-12-11 | December | 22 | 11 | 2 | Week 2 | December 22 Week 2 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
5 | 2022-12-12 | December | 22 | 12 | 2 | Week 2 | December 22 Week 2 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
6 | 2022-12-13 | December | 22 | 13 | 2 | Week 2 | December 22 Week 2 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
7 | 2022-12-14 | December | 22 | 14 | 2 | Week 2 | December 22 Week 2 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
1 | 2022-12-15 | December | 22 | 15 | 3 | Week 3 | December 22 Week 3 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
2 | 2022-12-16 | December | 22 | 16 | 3 | Week 3 | December 22 Week 3 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
3 | 2022-12-17 | December | 22 | 17 | 3 | Week 3 | December 22 Week 3 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
4 | 2022-12-18 | December | 22 | 18 | 3 | Week 3 | December 22 Week 3 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
5 | 2022-12-19 | December | 22 | 19 | 3 | Week 3 | December 22 Week 3 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
6 | 2022-12-20 | December | 22 | 20 | 3 | Week 3 | December 22 Week 3 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
7 | 2022-12-21 | December | 22 | 21 | 3 | Week 3 | December 22 Week 3 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
1 | 2022-12-22 | December | 22 | 22 | 4 | Week 4 | December 22 Week 4 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
2 | 2022-12-23 | December | 22 | 23 | 4 | Week 4 | December 22 Week 4 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
3 | 2022-12-24 | December | 22 | 24 | 4 | Week 4 | December 22 Week 4 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
4 | 2022-12-25 | December | 22 | 25 | 4 | Week 4 | December 22 Week 4 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
5 | 2022-12-26 | December | 22 | 26 | 4 | Week 4 | December 22 Week 4 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
6 | 2022-12-27 | December | 22 | 27 | 4 | Week 4 | December 22 Week 4 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
7 | 2022-12-28 | December | 22 | 28 | 4 | Week 4 | December 22 Week 4 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
1 | 2022-12-29 | December | 22 | 29 | 5 | Week 5 | December 22 Week 5 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
2 | 2022-12-30 | December | 22 | 30 | 5 | Week 5 | December 22 Week 5 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
3 | 2022-12-31 | December | 22 | 31 | 5 | Week 5 | December 22 Week 5 | DECEMBER 22 | PLANNED | DECEMBER 22 PLANNED
1 | 2023-01-01 | January | 23 | 1 | 1 | Week 1 | January 23 Week 1 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
2 | 2023-01-02 | January | 23 | 2 | 1 | Week 1 | January 23 Week 1 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
3 | 2023-01-03 | January | 23 | 3 | 1 | Week 1 | January 23 Week 1 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
4 | 2023-01-04 | January | 23 | 4 | 1 | Week 1 | January 23 Week 1 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
5 | 2023-01-05 | January | 23 | 5 | 1 | Week 1 | January 23 Week 1 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
6 | 2023-01-06 | January | 23 | 6 | 1 | Week 1 | January 23 Week 1 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
7 | 2023-01-07 | January | 23 | 7 | 1 | Week 1 | January 23 Week 1 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
1 | 2023-01-08 | January | 23 | 8 | 2 | Week 2 | January 23 Week 2 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
2 | 2023-01-09 | January | 23 | 9 | 2 | Week 2 | January 23 Week 2 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
3 | 2023-01-10 | January | 23 | 10 | 2 | Week 2 | January 23 Week 2 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
4 | 2023-01-11 | January | 23 | 11 | 2 | Week 2 | January 23 Week 2 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
5 | 2023-01-12 | January | 23 | 12 | 2 | Week 2 | January 23 Week 2 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
6 | 2023-01-13 | January | 23 | 13 | 2 | Week 2 | January 23 Week 2 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
7 | 2023-01-14 | January | 23 | 14 | 2 | Week 2 | January 23 Week 2 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
1 | 2023-01-15 | January | 23 | 15 | 3 | Week 3 | January 23 Week 3 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
2 | 2023-01-16 | January | 23 | 16 | 3 | Week 3 | January 23 Week 3 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
3 | 2023-01-17 | January | 23 | 17 | 3 | Week 3 | January 23 Week 3 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
4 | 2023-01-18 | January | 23 | 18 | 3 | Week 3 | January 23 Week 3 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
5 | 2023-01-19 | January | 23 | 19 | 3 | Week 3 | January 23 Week 3 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
6 | 2023-01-20 | January | 23 | 20 | 3 | Week 3 | January 23 Week 3 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
7 | 2023-01-21 | January | 23 | 21 | 3 | Week 3 | January 23 Week 3 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
1 | 2023-01-22 | January | 23 | 22 | 4 | Week 4 | January 23 Week 4 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
2 | 2023-01-23 | January | 23 | 23 | 4 | Week 4 | January 23 Week 4 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
3 | 2023-01-24 | January | 23 | 24 | 4 | Week 4 | January 23 Week 4 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
4 | 2023-01-25 | January | 23 | 25 | 4 | Week 4 | January 23 Week 4 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
5 | 2023-01-26 | January | 23 | 26 | 4 | Week 4 | January 23 Week 4 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
6 | 2023-01-27 | January | 23 | 27 | 4 | Week 4 | January 23 Week 4 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
7 | 2023-01-28 | January | 23 | 28 | 4 | Week 4 | January 23 Week 4 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
1 | 2023-01-29 | January | 23 | 29 | 5 | Week 5 | January 23 Week 5 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
2 | 2023-01-30 | January | 23 | 30 | 5 | Week 5 | January 23 Week 5 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
3 | 2023-01-31 | January | 23 | 31 | 5 | Week 5 | January 23 Week 5 | JANUARY 23 | PLANNED | JANUARY 23 PLANNED
1 | 2023-02-01 | February | 23 | 1 | 1 | Week 1 | February 23 Week 1 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
2 | 2023-02-02 | February | 23 | 2 | 1 | Week 1 | February 23 Week 1 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
3 | 2023-02-03 | February | 23 | 3 | 1 | Week 1 | February 23 Week 1 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
4 | 2023-02-04 | February | 23 | 4 | 1 | Week 1 | February 23 Week 1 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
5 | 2023-02-05 | February | 23 | 5 | 1 | Week 1 | February 23 Week 1 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
6 | 2023-02-06 | February | 23 | 6 | 1 | Week 1 | February 23 Week 1 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
7 | 2023-02-07 | February | 23 | 7 | 1 | Week 1 | February 23 Week 1 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
1 | 2023-02-08 | February | 23 | 8 | 2 | Week 2 | February 23 Week 2 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
2 | 2023-02-09 | February | 23 | 9 | 2 | Week 2 | February 23 Week 2 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
3 | 2023-02-10 | February | 23 | 10 | 2 | Week 2 | February 23 Week 2 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
4 | 2023-02-11 | February | 23 | 11 | 2 | Week 2 | February 23 Week 2 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
5 | 2023-02-12 | February | 23 | 12 | 2 | Week 2 | February 23 Week 2 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
6 | 2023-02-13 | February | 23 | 13 | 2 | Week 2 | February 23 Week 2 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
7 | 2023-02-14 | February | 23 | 14 | 2 | Week 2 | February 23 Week 2 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
1 | 2023-02-15 | February | 23 | 15 | 3 | Week 3 | February 23 Week 3 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
2 | 2023-02-16 | February | 23 | 16 | 3 | Week 3 | February 23 Week 3 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
3 | 2023-02-17 | February | 23 | 17 | 3 | Week 3 | February 23 Week 3 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
4 | 2023-02-18 | February | 23 | 18 | 3 | Week 3 | February 23 Week 3 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
5 | 2023-02-19 | February | 23 | 19 | 3 | Week 3 | February 23 Week 3 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
6 | 2023-02-20 | February | 23 | 20 | 3 | Week 3 | February 23 Week 3 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
7 | 2023-02-21 | February | 23 | 21 | 3 | Week 3 | February 23 Week 3 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
1 | 2023-02-22 | February | 23 | 22 | 4 | Week 4 | February 23 Week 4 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
2 | 2023-02-23 | February | 23 | 23 | 4 | Week 4 | February 23 Week 4 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
3 | 2023-02-24 | February | 23 | 24 | 4 | Week 4 | February 23 Week 4 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
4 | 2023-02-25 | February | 23 | 25 | 4 | Week 4 | February 23 Week 4 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
5 | 2023-02-26 | February | 23 | 26 | 4 | Week 4 | February 23 Week 4 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
6 | 2023-02-27 | February | 23 | 27 | 4 | Week 4 | February 23 Week 4 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
7 | 2023-02-28 | February | 23 | 28 | 4 | Week 4 | February 23 Week 4 | FEBRUARY 23 | PLANNED | FEBRUARY 23 PLANNED
1 | 2023-03-01 | March | 23 | 1 | 1 | Week 1 | March 23 Week 1 | MARCH 23 | PLANNED | MARCH 23 PLANNED
2 | 2023-03-02 | March | 23 | 2 | 1 | Week 1 | March 23 Week 1 | MARCH 23 | PLANNED | MARCH 23 PLANNED
3 | 2023-03-03 | March | 23 | 3 | 1 | Week 1 | March 23 Week 1 | MARCH 23 | PLANNED | MARCH 23 PLANNED
4 | 2023-03-04 | March | 23 | 4 | 1 | Week 1 | March 23 Week 1 | MARCH 23 | PLANNED | MARCH 23 PLANNED
5 | 2023-03-05 | March | 23 | 5 | 1 | Week 1 | March 23 Week 1 | MARCH 23 | PLANNED | MARCH 23 PLANNED
6 | 2023-03-06 | March | 23 | 6 | 1 | Week 1 | March 23 Week 1 | MARCH 23 | PLANNED | MARCH 23 PLANNED
7 | 2023-03-07 | March | 23 | 7 | 1 | Week 1 | March 23 Week 1 | MARCH 23 | PLANNED | MARCH 23 PLANNED
1 | 2023-03-08 | March | 23 | 8 | 2 | Week 2 | March 23 Week 2 | MARCH 23 | PLANNED | MARCH 23 PLANNED
2 | 2023-03-09 | March | 23 | 9 | 2 | Week 2 | March 23 Week 2 | MARCH 23 | PLANNED | MARCH 23 PLANNED
3 | 2023-03-10 | March | 23 | 10 | 2 | Week 2 | March 23 Week 2 | MARCH 23 | PLANNED | MARCH 23 PLANNED
4 | 2023-03-11 | March | 23 | 11 | 2 | Week 2 | March 23 Week 2 | MARCH 23 | PLANNED | MARCH 23 PLANNED
5 | 2023-03-12 | March | 23 | 12 | 2 | Week 2 | March 23 Week 2 | MARCH 23 | PLANNED | MARCH 23 PLANNED
6 | 2023-03-13 | March | 23 | 13 | 2 | Week 2 | March 23 Week 2 | MARCH 23 | PLANNED | MARCH 23 PLANNED
7 | 2023-03-14 | March | 23 | 14 | 2 | Week 2 | March 23 Week 2 | MARCH 23 | PLANNED | MARCH 23 PLANNED
1 | 2023-03-15 | March | 23 | 15 | 3 | Week 3 | March 23 Week 3 | MARCH 23 | PLANNED | MARCH 23 PLANNED
2 | 2023-03-16 | March | 23 | 16 | 3 | Week 3 | March 23 Week 3 | MARCH 23 | PLANNED | MARCH 23 PLANNED
3 | 2023-03-17 | March | 23 | 17 | 3 | Week 3 | March 23 Week 3 | MARCH 23 | PLANNED | MARCH 23 PLANNED
4 | 2023-03-18 | March | 23 | 18 | 3 | Week 3 | March 23 Week 3 | MARCH 23 | PLANNED | MARCH 23 PLANNED
5 | 2023-03-19 | March | 23 | 19 | 3 | Week 3 | March 23 Week 3 | MARCH 23 | PLANNED | MARCH 23 PLANNED
6 | 2023-03-20 | March | 23 | 20 | 3 | Week 3 | March 23 Week 3 | MARCH 23 | PLANNED | MARCH 23 PLANNED
7 | 2023-03-21 | March | 23 | 21 | 3 | Week 3 | March 23 Week 3 | MARCH 23 | PLANNED | MARCH 23 PLANNED
1 | 2023-03-22 | March | 23 | 22 | 4 | Week 4 | March 23 Week 4 | MARCH 23 | PLANNED | MARCH 23 PLANNED
2 | 2023-03-23 | March | 23 | 23 | 4 | Week 4 | March 23 Week 4 | MARCH 23 | PLANNED | MARCH 23 PLANNED
3 | 2023-03-24 | March | 23 | 24 | 4 | Week 4 | March 23 Week 4 | MARCH 23 | PLANNED | MARCH 23 PLANNED
4 | 2023-03-25 | March | 23 | 25 | 4 | Week 4 | March 23 Week 4 | MARCH 23 | PLANNED | MARCH 23 PLANNED
5 | 2023-03-26 | March | 23 | 26 | 4 | Week 4 | March 23 Week 4 | MARCH 23 | PLANNED | MARCH 23 PLANNED
6 | 2023-03-27 | March | 23 | 27 | 4 | Week 4 | March 23 Week 4 | MARCH 23 | PLANNED | MARCH 23 PLANNED
7 | 2023-03-28 | March | 23 | 28 | 4 | Week 4 | March 23 Week 4 | MARCH 23 | PLANNED | MARCH 23 PLANNED
1 | 2023-03-29 | March | 23 | 29 | 5 | Week 5 | March 23 Week 5 | MARCH 23 | PLANNED | MARCH 23 PLANNED
2 | 2023-03-30 | March | 23 | 30 | 5 | Week 5 | March 23 Week 5 | MARCH 23 | PLANNED | MARCH 23 PLANNED
3 | 2023-03-31 | March | 23 | 31 | 5 | Week 5 | March 23 Week 5 | MARCH 23 | PLANNED | MARCH 23 PLANNED
1 | 2023-04-01 | April | 23 | 1 | 1 | Week 1 | April 23 Week 1 | APRIL 23 | PLANNED | APRIL 23 PLANNED
2 | 2023-04-02 | April | 23 | 2 | 1 | Week 1 | April 23 Week 1 | APRIL 23 | PLANNED | APRIL 23 PLANNED
3 | 2023-04-03 | April | 23 | 3 | 1 | Week 1 | April 23 Week 1 | APRIL 23 | PLANNED | APRIL 23 PLANNED
4 | 2023-04-04 | April | 23 | 4 | 1 | Week 1 | April 23 Week 1 | APRIL 23 | PLANNED | APRIL 23 PLANNED
5 | 2023-04-05 | April | 23 | 5 | 1 | Week 1 | April 23 Week 1 | APRIL 23 | PLANNED | APRIL 23 PLANNED
6 | 2023-04-06 | April | 23 | 6 | 1 | Week 1 | April 23 Week 1 | APRIL 23 | PLANNED | APRIL 23 PLANNED
7 | 2023-04-07 | April | 23 | 7 | 1 | Week 1 | April 23 Week 1 | APRIL 23 | PLANNED | APRIL 23 PLANNED
1 | 2023-04-08 | April | 23 | 8 | 2 | Week 2 | April 23 Week 2 | APRIL 23 | PLANNED | APRIL 23 PLANNED
2 | 2023-04-09 | April | 23 | 9 | 2 | Week 2 | April 23 Week 2 | APRIL 23 | PLANNED | APRIL 23 PLANNED
3 | 2023-04-10 | April | 23 | 10 | 2 | Week 2 | April 23 Week 2 | APRIL 23 | PLANNED | APRIL 23 PLANNED
4 | 2023-04-11 | April | 23 | 11 | 2 | Week 2 | April 23 Week 2 | APRIL 23 | PLANNED | APRIL 23 PLANNED
5 | 2023-04-12 | April | 23 | 12 | 2 | Week 2 | April 23 Week 2 | APRIL 23 | PLANNED | APRIL 23 PLANNED
6 | 2023-04-13 | April | 23 | 13 | 2 | Week 2 | April 23 Week 2 | APRIL 23 | PLANNED | APRIL 23 PLANNED
7 | 2023-04-14 | April | 23 | 14 | 2 | Week 2 | April 23 Week 2 | APRIL 23 | PLANNED | APRIL 23 PLANNED
1 | 2023-04-15 | April | 23 | 15 | 3 | Week 3 | April 23 Week 3 | APRIL 23 | PLANNED | APRIL 23 PLANNED
2 | 2023-04-16 | April | 23 | 16 | 3 | Week 3 | April 23 Week 3 | APRIL 23 | PLANNED | APRIL 23 PLANNED
3 | 2023-04-17 | April | 23 | 17 | 3 | Week 3 | April 23 Week 3 | APRIL 23 | PLANNED | APRIL 23 PLANNED
4 | 2023-04-18 | April | 23 | 18 | 3 | Week 3 | April 23 Week 3 | APRIL 23 | PLANNED | APRIL 23 PLANNED
5 | 2023-04-19 | April | 23 | 19 | 3 | Week 3 | April 23 Week 3 | APRIL 23 | PLANNED | APRIL 23 PLANNED
6 | 2023-04-20 | April | 23 | 20 | 3 | Week 3 | April 23 Week 3 | APRIL 23 | PLANNED | APRIL 23 PLANNED
7 | 2023-04-21 | April | 23 | 21 | 3 | Week 3 | April 23 Week 3 | APRIL 23 | PLANNED | APRIL 23 PLANNED
1 | 2023-04-22 | April | 23 | 22 | 4 | Week 4 | April 23 Week 4 | APRIL 23 | PLANNED | APRIL 23 PLANNED
2 | 2023-04-23 | April | 23 | 23 | 4 | Week 4 | April 23 Week 4 | APRIL 23 | PLANNED | APRIL 23 PLANNED
3 | 2023-04-24 | April | 23 | 24 | 4 | Week 4 | April 23 Week 4 | APRIL 23 | PLANNED | APRIL 23 PLANNED
4 | 2023-04-25 | April | 23 | 25 | 4 | Week 4 | April 23 Week 4 | APRIL 23 | PLANNED | APRIL 23 PLANNED
5 | 2023-04-26 | April | 23 | 26 | 4 | Week 4 | April 23 Week 4 | APRIL 23 | PLANNED | APRIL 23 PLANNED
6 | 2023-04-27 | April | 23 | 27 | 4 | Week 4 | April 23 Week 4 | APRIL 23 | PLANNED | APRIL 23 PLANNED
7 | 2023-04-28 | April | 23 | 28 | 4 | Week 4 | April 23 Week 4 | APRIL 23 | PLANNED | APRIL 23 PLANNED
1 | 2023-04-29 | April | 23 | 29 | 5 | Week 5 | April 23 Week 5 | APRIL 23 | PLANNED | APRIL 23 PLANNED
2 | 2023-04-30 | April | 23 | 30 | 5 | Week 5 | April 23 Week 5 | APRIL 23 | PLANNED | APRIL 23 PLANNED
1 | 2023-05-01 | May | 23 | 1 | 1 | Week 1 | May 23 Week 1 | MAY 23 | PLANNED | MAY 23 PLANNED
2 | 2023-05-02 | May | 23 | 2 | 1 | Week 1 | May 23 Week 1 | MAY 23 | PLANNED | MAY 23 PLANNED
3 | 2023-05-03 | May | 23 | 3 | 1 | Week 1 | May 23 Week 1 | MAY 23 | PLANNED | MAY 23 PLANNED
4 | 2023-05-04 | May | 23 | 4 | 1 | Week 1 | May 23 Week 1 | MAY 23 | PLANNED | MAY 23 PLANNED
5 | 2023-05-05 | May | 23 | 5 | 1 | Week 1 | May 23 Week 1 | MAY 23 | PLANNED | MAY 23 PLANNED
6 | 2023-05-06 | May | 23 | 6 | 1 | Week 1 | May 23 Week 1 | MAY 23 | PLANNED | MAY 23 PLANNED
7 | 2023-05-07 | May | 23 | 7 | 1 | Week 1 | May 23 Week 1 | MAY 23 | PLANNED | MAY 23 PLANNED
1 | 2023-05-08 | May | 23 | 8 | 2 | Week 2 | May 23 Week 2 | MAY 23 | PLANNED | MAY 23 PLANNED
2 | 2023-05-09 | May | 23 | 9 | 2 | Week 2 | May 23 Week 2 | MAY 23 | PLANNED | MAY 23 PLANNED
3 | 2023-05-10 | May | 23 | 10 | 2 | Week 2 | May 23 Week 2 | MAY 23 | PLANNED | MAY 23 PLANNED
4 | 2023-05-11 | May | 23 | 11 | 2 | Week 2 | May 23 Week 2 | MAY 23 | PLANNED | MAY 23 PLANNED
5 | 2023-05-12 | May | 23 | 12 | 2 | Week 2 | May 23 Week 2 | MAY 23 | PLANNED | MAY 23 PLANNED
6 | 2023-05-13 | May | 23 | 13 | 2 | Week 2 | May 23 Week 2 | MAY 23 | PLANNED | MAY 23 PLANNED
7 | 2023-05-14 | May | 23 | 14 | 2 | Week 2 | May 23 Week 2 | MAY 23 | PLANNED | MAY 23 PLANNED
1 | 2023-05-15 | May | 23 | 15 | 3 | Week 3 | May 23 Week 3 | MAY 23 | PLANNED | MAY 23 PLANNED
2 | 2023-05-16 | May | 23 | 16 | 3 | Week 3 | May 23 Week 3 | MAY 23 | PLANNED | MAY 23 PLANNED
3 | 2023-05-17 | May | 23 | 17 | 3 | Week 3 | May 23 Week 3 | MAY 23 | PLANNED | MAY 23 PLANNED
4 | 2023-05-18 | May | 23 | 18 | 3 | Week 3 | May 23 Week 3 | MAY 23 | PLANNED | MAY 23 PLANNED
5 | 2023-05-19 | May | 23 | 19 | 3 | Week 3 | May 23 Week 3 | MAY 23 | PLANNED | MAY 23 PLANNED
6 | 2023-05-20 | May | 23 | 20 | 3 | Week 3 | May 23 Week 3 | MAY 23 | PLANNED | MAY 23 PLANNED
7 | 2023-05-21 | May | 23 | 21 | 3 | Week 3 | May 23 Week 3 | MAY 23 | PLANNED | MAY 23 PLANNED
1 | 2023-05-22 | May | 23 | 22 | 4 | Week 4 | May 23 Week 4 | MAY 23 | PLANNED | MAY 23 PLANNED
2 | 2023-05-23 | May | 23 | 23 | 4 | Week 4 | May 23 Week 4 | MAY 23 | PLANNED | MAY 23 PLANNED
3 | 2023-05-24 | May | 23 | 24 | 4 | Week 4 | May 23 Week 4 | MAY 23 | PLANNED | MAY 23 PLANNED
4 | 2023-05-25 | May | 23 | 25 | 4 | Week 4 | May 23 Week 4 | MAY 23 | PLANNED | MAY 23 PLANNED
5 | 2023-05-26 | May | 23 | 26 | 4 | Week 4 | May 23 Week 4 | MAY 23 | PLANNED | MAY 23 PLANNED
6 | 2023-05-27 | May | 23 | 27 | 4 | Week 4 | May 23 Week 4 | MAY 23 | PLANNED | MAY 23 PLANNED
7 | 2023-05-28 | May | 23 | 28 | 4 | Week 4 | May 23 Week 4 | MAY 23 | PLANNED | MAY 23 PLANNED
1 | 2023-05-29 | May | 23 | 29 | 5 | Week 5 | May 23 Week 5 | MAY 23 | PLANNED | MAY 23 PLANNED
2 | 2023-05-30 | May | 23 | 30 | 5 | Week 5 | May 23 Week 5 | MAY 23 | PLANNED | MAY 23 PLANNED
3 | 2023-05-31 | May | 23 | 31 | 5 | Week 5 | May 23 Week 5 | MAY 23 | PLANNED | MAY 23 PLANNED
1 | 2023-06-01 | June | 23 | 1 | 1 | Week 1 | June 23 Week 1 | JUNE 23 | PLANNED | JUNE 23 PLANNED
2 | 2023-06-02 | June | 23 | 2 | 1 | Week 1 | June 23 Week 1 | JUNE 23 | PLANNED | JUNE 23 PLANNED
3 | 2023-06-03 | June | 23 | 3 | 1 | Week 1 | June 23 Week 1 | JUNE 23 | PLANNED | JUNE 23 PLANNED
4 | 2023-06-04 | June | 23 | 4 | 1 | Week 1 | June 23 Week 1 | JUNE 23 | PLANNED | JUNE 23 PLANNED
5 | 2023-06-05 | June | 23 | 5 | 1 | Week 1 | June 23 Week 1 | JUNE 23 | PLANNED | JUNE 23 PLANNED
6 | 2023-06-06 | June | 23 | 6 | 1 | Week 1 | June 23 Week 1 | JUNE 23 | PLANNED | JUNE 23 PLANNED
7 | 2023-06-07 | June | 23 | 7 | 1 | Week 1 | June 23 Week 1 | JUNE 23 | PLANNED | JUNE 23 PLANNED
1 | 2023-06-08 | June | 23 | 8 | 2 | Week 2 | June 23 Week 2 | JUNE 23 | PLANNED | JUNE 23 PLANNED
2 | 2023-06-09 | June | 23 | 9 | 2 | Week 2 | June 23 Week 2 | JUNE 23 | PLANNED | JUNE 23 PLANNED
3 | 2023-06-10 | June | 23 | 10 | 2 | Week 2 | June 23 Week 2 | JUNE 23 | PLANNED | JUNE 23 PLANNED
4 | 2023-06-11 | June | 23 | 11 | 2 | Week 2 | June 23 Week 2 | JUNE 23 | PLANNED | JUNE 23 PLANNED
5 | 2023-06-12 | June | 23 | 12 | 2 | Week 2 | June 23 Week 2 | JUNE 23 | PLANNED | JUNE 23 PLANNED
6 | 2023-06-13 | June | 23 | 13 | 2 | Week 2 | June 23 Week 2 | JUNE 23 | PLANNED | JUNE 23 PLANNED
7 | 2023-06-14 | June | 23 | 14 | 2 | Week 2 | June 23 Week 2 | JUNE 23 | PLANNED | JUNE 23 PLANNED
1 | 2023-06-15 | June | 23 | 15 | 3 | Week 3 | June 23 Week 3 | JUNE 23 | PLANNED | JUNE 23 PLANNED
2 | 2023-06-16 | June | 23 | 16 | 3 | Week 3 | June 23 Week 3 | JUNE 23 | PLANNED | JUNE 23 PLANNED
3 | 2023-06-17 | June | 23 | 17 | 3 | Week 3 | June 23 Week 3 | JUNE 23 | PLANNED | JUNE 23 PLANNED
4 | 2023-06-18 | June | 23 | 18 | 3 | Week 3 | June 23 Week 3 | JUNE 23 | PLANNED | JUNE 23 PLANNED
5 | 2023-06-19 | June | 23 | 19 | 3 | Week 3 | June 23 Week 3 | JUNE 23 | PLANNED | JUNE 23 PLANNED
6 | 2023-06-20 | June | 23 | 20 | 3 | Week 3 | June 23 Week 3 | JUNE 23 | PLANNED | JUNE 23 PLANNED
7 | 2023-06-21 | June | 23 | 21 | 3 | Week 3 | June 23 Week 3 | JUNE 23 | PLANNED | JUNE 23 PLANNED
1 | 2023-06-22 | June | 23 | 22 | 4 | Week 4 | June 23 Week 4 | JUNE 23 | PLANNED | JUNE 23 PLANNED
2 | 2023-06-23 | June | 23 | 23 | 4 | Week 4 | June 23 Week 4 | JUNE 23 | PLANNED | JUNE 23 PLANNED
3 | 2023-06-24 | June | 23 | 24 | 4 | Week 4 | June 23 Week 4 | JUNE 23 | PLANNED | JUNE 23 PLANNED
4 | 2023-06-25 | June | 23 | 25 | 4 | Week 4 | June 23 Week 4 | JUNE 23 | PLANNED | JUNE 23 PLANNED
5 | 2023-06-26 | June | 23 | 26 | 4 | Week 4 | June 23 Week 4 | JUNE 23 | PLANNED | JUNE 23 PLANNED
6 | 2023-06-27 | June | 23 | 27 | 4 | Week 4 | June 23 Week 4 | JUNE 23 | PLANNED | JUNE 23 PLANNED
7 | 2023-06-28 | June | 23 | 28 | 4 | Week 4 | June 23 Week 4 | JUNE 23 | PLANNED | JUNE 23 PLANNED
1 | 2023-06-29 | June | 23 | 29 | 5 | Week 5 | June 23 Week 5 | JUNE 23 | PLANNED | JUNE 23 PLANNED
2 | 2023-06-30 | June | 23 | 30 | 5 | Week 5 | June 23 Week 5 | JUNE 23 | PLANNED | JUNE 23 PLANNED
1 | 2023-07-01 | July | 23 | 1 | 1 | Week 1 | July 23 Week 1 | JULY 23 | PLANNED | JULY 23 PLANNED
2 | 2023-07-02 | July | 23 | 2 | 1 | Week 1 | July 23 Week 1 | JULY 23 | PLANNED | JULY 23 PLANNED
3 | 2023-07-03 | July | 23 | 3 | 1 | Week 1 | July 23 Week 1 | JULY 23 | PLANNED | JULY 23 PLANNED
4 | 2023-07-04 | July | 23 | 4 | 1 | Week 1 | July 23 Week 1 | JULY 23 | PLANNED | JULY 23 PLANNED
5 | 2023-07-05 | July | 23 | 5 | 1 | Week 1 | July 23 Week 1 | JULY 23 | PLANNED | JULY 23 PLANNED
6 | 2023-07-06 | July | 23 | 6 | 1 | Week 1 | July 23 Week 1 | JULY 23 | PLANNED | JULY 23 PLANNED
7 | 2023-07-07 | July | 23 | 7 | 1 | Week 1 | July 23 Week 1 | JULY 23 | PLANNED | JULY 23 PLANNED
1 | 2023-07-08 | July | 23 | 8 | 2 | Week 2 | July 23 Week 2 | JULY 23 | PLANNED | JULY 23 PLANNED
2 | 2023-07-09 | July | 23 | 9 | 2 | Week 2 | July 23 Week 2 | JULY 23 | PLANNED | JULY 23 PLANNED
3 | 2023-07-10 | July | 23 | 10 | 2 | Week 2 | July 23 Week 2 | JULY 23 | PLANNED | JULY 23 PLANNED
4 | 2023-07-11 | July | 23 | 11 | 2 | Week 2 | July 23 Week 2 | JULY 23 | PLANNED | JULY 23 PLANNED
5 | 2023-07-12 | July | 23 | 12 | 2 | Week 2 | July 23 Week 2 | JULY 23 | PLANNED | JULY 23 PLANNED
6 | 2023-07-13 | July | 23 | 13 | 2 | Week 2 | July 23 Week 2 | JULY 23 | PLANNED | JULY 23 PLANNED
7 | 2023-07-14 | July | 23 | 14 | 2 | Week 2 | July 23 Week 2 | JULY 23 | PLANNED | JULY 23 PLANNED
1 | 2023-07-15 | July | 23 | 15 | 3 | Week 3 | July 23 Week 3 | JULY 23 | PLANNED | JULY 23 PLANNED
2 | 2023-07-16 | July | 23 | 16 | 3 | Week 3 | July 23 Week 3 | JULY 23 | PLANNED | JULY 23 PLANNED
3 | 2023-07-17 | July | 23 | 17 | 3 | Week 3 | July 23 Week 3 | JULY 23 | PLANNED | JULY 23 PLANNED
4 | 2023-07-18 | July | 23 | 18 | 3 | Week 3 | July 23 Week 3 | JULY 23 | PLANNED | JULY 23 PLANNED
5 | 2023-07-19 | July | 23 | 19 | 3 | Week 3 | July 23 Week 3 | JULY 23 | PLANNED | JULY 23 PLANNED
6 | 2023-07-20 | July | 23 | 20 | 3 | Week 3 | July 23 Week 3 | JULY 23 | PLANNED | JULY 23 PLANNED
7 | 2023-07-21 | July | 23 | 21 | 3 | Week 3 | July 23 Week 3 | JULY 23 | PLANNED | JULY 23 PLANNED
1 | 2023-07-22 | July | 23 | 22 | 4 | Week 4 | July 23 Week 4 | JULY 23 | PLANNED | JULY 23 PLANNED
2 | 2023-07-23 | July | 23 | 23 | 4 | Week 4 | July 23 Week 4 | JULY 23 | PLANNED | JULY 23 PLANNED
3 | 2023-07-24 | July | 23 | 24 | 4 | Week 4 | July 23 Week 4 | JULY 23 | PLANNED | JULY 23 PLANNED
4 | 2023-07-25 | July | 23 | 25 | 4 | Week 4 | July 23 Week 4 | JULY 23 | PLANNED | JULY 23 PLANNED
5 | 2023-07-26 | July | 23 | 26 | 4 | Week 4 | July 23 Week 4 | JULY 23 | PLANNED | JULY 23 PLANNED
6 | 2023-07-27 | July | 23 | 27 | 4 | Week 4 | July 23 Week 4 | JULY 23 | PLANNED | JULY 23 PLANNED
7 | 2023-07-28 | July | 23 | 28 | 4 | Week 4 | July 23 Week 4 | JULY 23 | PLANNED | JULY 23 PLANNED
1 | 2023-07-29 | July | 23 | 29 | 5 | Week 5 | July 23 Week 5 | JULY 23 | PLANNED | JULY 23 PLANNED
2 | 2023-07-30 | July | 23 | 30 | 5 | Week 5 | July 23 Week 5 | JULY 23 | PLANNED | JULY 23 PLANNED
3 | 2023-07-31 | July | 23 | 31 | 5 | Week 5 | July 23 Week 5 | JULY 23 | PLANNED | JULY 23 PLANNED
1 | 2023-08-01 | August | 23 | 1 | 1 | Week 1 | August 23 Week 1 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
2 | 2023-08-02 | August | 23 | 2 | 1 | Week 1 | August 23 Week 1 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
3 | 2023-08-03 | August | 23 | 3 | 1 | Week 1 | August 23 Week 1 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
4 | 2023-08-04 | August | 23 | 4 | 1 | Week 1 | August 23 Week 1 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
5 | 2023-08-05 | August | 23 | 5 | 1 | Week 1 | August 23 Week 1 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
6 | 2023-08-06 | August | 23 | 6 | 1 | Week 1 | August 23 Week 1 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
7 | 2023-08-07 | August | 23 | 7 | 1 | Week 1 | August 23 Week 1 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
1 | 2023-08-08 | August | 23 | 8 | 2 | Week 2 | August 23 Week 2 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
2 | 2023-08-09 | August | 23 | 9 | 2 | Week 2 | August 23 Week 2 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
3 | 2023-08-10 | August | 23 | 10 | 2 | Week 2 | August 23 Week 2 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
4 | 2023-08-11 | August | 23 | 11 | 2 | Week 2 | August 23 Week 2 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
5 | 2023-08-12 | August | 23 | 12 | 2 | Week 2 | August 23 Week 2 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
6 | 2023-08-13 | August | 23 | 13 | 2 | Week 2 | August 23 Week 2 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
7 | 2023-08-14 | August | 23 | 14 | 2 | Week 2 | August 23 Week 2 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
1 | 2023-08-15 | August | 23 | 15 | 3 | Week 3 | August 23 Week 3 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
2 | 2023-08-16 | August | 23 | 16 | 3 | Week 3 | August 23 Week 3 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
3 | 2023-08-17 | August | 23 | 17 | 3 | Week 3 | August 23 Week 3 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
4 | 2023-08-18 | August | 23 | 18 | 3 | Week 3 | August 23 Week 3 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
5 | 2023-08-19 | August | 23 | 19 | 3 | Week 3 | August 23 Week 3 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
6 | 2023-08-20 | August | 23 | 20 | 3 | Week 3 | August 23 Week 3 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
7 | 2023-08-21 | August | 23 | 21 | 3 | Week 3 | August 23 Week 3 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
1 | 2023-08-22 | August | 23 | 22 | 4 | Week 4 | August 23 Week 4 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
2 | 2023-08-23 | August | 23 | 23 | 4 | Week 4 | August 23 Week 4 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
3 | 2023-08-24 | August | 23 | 24 | 4 | Week 4 | August 23 Week 4 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
4 | 2023-08-25 | August | 23 | 25 | 4 | Week 4 | August 23 Week 4 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
5 | 2023-08-26 | August | 23 | 26 | 4 | Week 4 | August 23 Week 4 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
6 | 2023-08-27 | August | 23 | 27 | 4 | Week 4 | August 23 Week 4 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
7 | 2023-08-28 | August | 23 | 28 | 4 | Week 4 | August 23 Week 4 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
1 | 2023-08-29 | August | 23 | 29 | 5 | Week 5 | August 23 Week 5 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
2 | 2023-08-30 | August | 23 | 30 | 5 | Week 5 | August 23 Week 5 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
3 | 2023-08-31 | August | 23 | 31 | 5 | Week 5 | August 23 Week 5 | AUGUST 23 | PLANNED | AUGUST 23 PLANNED
1 | 2023-09-01 | September | 23 | 1 | 1 | Week 1 | September 23 Week 1 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
2 | 2023-09-02 | September | 23 | 2 | 1 | Week 1 | September 23 Week 1 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
3 | 2023-09-03 | September | 23 | 3 | 1 | Week 1 | September 23 Week 1 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
4 | 2023-09-04 | September | 23 | 4 | 1 | Week 1 | September 23 Week 1 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
5 | 2023-09-05 | September | 23 | 5 | 1 | Week 1 | September 23 Week 1 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
6 | 2023-09-06 | September | 23 | 6 | 1 | Week 1 | September 23 Week 1 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
7 | 2023-09-07 | September | 23 | 7 | 1 | Week 1 | September 23 Week 1 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
1 | 2023-09-08 | September | 23 | 8 | 2 | Week 2 | September 23 Week 2 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
2 | 2023-09-09 | September | 23 | 9 | 2 | Week 2 | September 23 Week 2 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
3 | 2023-09-10 | September | 23 | 10 | 2 | Week 2 | September 23 Week 2 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
4 | 2023-09-11 | September | 23 | 11 | 2 | Week 2 | September 23 Week 2 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
5 | 2023-09-12 | September | 23 | 12 | 2 | Week 2 | September 23 Week 2 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
6 | 2023-09-13 | September | 23 | 13 | 2 | Week 2 | September 23 Week 2 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
7 | 2023-09-14 | September | 23 | 14 | 2 | Week 2 | September 23 Week 2 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
1 | 2023-09-15 | September | 23 | 15 | 3 | Week 3 | September 23 Week 3 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
2 | 2023-09-16 | September | 23 | 16 | 3 | Week 3 | September 23 Week 3 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
3 | 2023-09-17 | September | 23 | 17 | 3 | Week 3 | September 23 Week 3 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
4 | 2023-09-18 | September | 23 | 18 | 3 | Week 3 | September 23 Week 3 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
5 | 2023-09-19 | September | 23 | 19 | 3 | Week 3 | September 23 Week 3 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
6 | 2023-09-20 | September | 23 | 20 | 3 | Week 3 | September 23 Week 3 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
7 | 2023-09-21 | September | 23 | 21 | 3 | Week 3 | September 23 Week 3 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
1 | 2023-09-22 | September | 23 | 22 | 4 | Week 4 | September 23 Week 4 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
2 | 2023-09-23 | September | 23 | 23 | 4 | Week 4 | September 23 Week 4 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
3 | 2023-09-24 | September | 23 | 24 | 4 | Week 4 | September 23 Week 4 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
4 | 2023-09-25 | September | 23 | 25 | 4 | Week 4 | September 23 Week 4 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
5 | 2023-09-26 | September | 23 | 26 | 4 | Week 4 | September 23 Week 4 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
6 | 2023-09-27 | September | 23 | 27 | 4 | Week 4 | September 23 Week 4 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
7 | 2023-09-28 | September | 23 | 28 | 4 | Week 4 | September 23 Week 4 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
1 | 2023-09-29 | September | 23 | 29 | 5 | Week 5 | September 23 Week 5 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
2 | 2023-09-30 | September | 23 | 30 | 5 | Week 5 | September 23 Week 5 | SEPTEMBER 23 | PLANNED | SEPTEMBER 23 PLANNED
1 | 2023-10-01 | October | 23 | 1 | 1 | Week 1 | October 23 Week 1 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
2 | 2023-10-02 | October | 23 | 2 | 1 | Week 1 | October 23 Week 1 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
3 | 2023-10-03 | October | 23 | 3 | 1 | Week 1 | October 23 Week 1 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
4 | 2023-10-04 | October | 23 | 4 | 1 | Week 1 | October 23 Week 1 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
5 | 2023-10-05 | October | 23 | 5 | 1 | Week 1 | October 23 Week 1 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
6 | 2023-10-06 | October | 23 | 6 | 1 | Week 1 | October 23 Week 1 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
7 | 2023-10-07 | October | 23 | 7 | 1 | Week 1 | October 23 Week 1 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
1 | 2023-10-08 | October | 23 | 8 | 2 | Week 2 | October 23 Week 2 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
2 | 2023-10-09 | October | 23 | 9 | 2 | Week 2 | October 23 Week 2 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
3 | 2023-10-10 | October | 23 | 10 | 2 | Week 2 | October 23 Week 2 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
4 | 2023-10-11 | October | 23 | 11 | 2 | Week 2 | October 23 Week 2 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
5 | 2023-10-12 | October | 23 | 12 | 2 | Week 2 | October 23 Week 2 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
6 | 2023-10-13 | October | 23 | 13 | 2 | Week 2 | October 23 Week 2 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
7 | 2023-10-14 | October | 23 | 14 | 2 | Week 2 | October 23 Week 2 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
1 | 2023-10-15 | October | 23 | 15 | 3 | Week 3 | October 23 Week 3 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
2 | 2023-10-16 | October | 23 | 16 | 3 | Week 3 | October 23 Week 3 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
3 | 2023-10-17 | October | 23 | 17 | 3 | Week 3 | October 23 Week 3 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
4 | 2023-10-18 | October | 23 | 18 | 3 | Week 3 | October 23 Week 3 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
5 | 2023-10-19 | October | 23 | 19 | 3 | Week 3 | October 23 Week 3 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
6 | 2023-10-20 | October | 23 | 20 | 3 | Week 3 | October 23 Week 3 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
7 | 2023-10-21 | October | 23 | 21 | 3 | Week 3 | October 23 Week 3 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
1 | 2023-10-22 | October | 23 | 22 | 4 | Week 4 | October 23 Week 4 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
2 | 2023-10-23 | October | 23 | 23 | 4 | Week 4 | October 23 Week 4 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
3 | 2023-10-24 | October | 23 | 24 | 4 | Week 4 | October 23 Week 4 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
4 | 2023-10-25 | October | 23 | 25 | 4 | Week 4 | October 23 Week 4 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
5 | 2023-10-26 | October | 23 | 26 | 4 | Week 4 | October 23 Week 4 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
6 | 2023-10-27 | October | 23 | 27 | 4 | Week 4 | October 23 Week 4 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
7 | 2023-10-28 | October | 23 | 28 | 4 | Week 4 | October 23 Week 4 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
1 | 2023-10-29 | October | 23 | 29 | 5 | Week 5 | October 23 Week 5 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
2 | 2023-10-30 | October | 23 | 30 | 5 | Week 5 | October 23 Week 5 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
3 | 2023-10-31 | October | 23 | 31 | 5 | Week 5 | October 23 Week 5 | OCTOBER 23 | PLANNED | OCTOBER 23 PLANNED
1 | 2023-11-01 | November | 23 | 1 | 1 | Week 1 | November 23 Week 1 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
2 | 2023-11-02 | November | 23 | 2 | 1 | Week 1 | November 23 Week 1 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
3 | 2023-11-03 | November | 23 | 3 | 1 | Week 1 | November 23 Week 1 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
4 | 2023-11-04 | November | 23 | 4 | 1 | Week 1 | November 23 Week 1 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
5 | 2023-11-05 | November | 23 | 5 | 1 | Week 1 | November 23 Week 1 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
6 | 2023-11-06 | November | 23 | 6 | 1 | Week 1 | November 23 Week 1 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
7 | 2023-11-07 | November | 23 | 7 | 1 | Week 1 | November 23 Week 1 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
1 | 2023-11-08 | November | 23 | 8 | 2 | Week 2 | November 23 Week 2 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
2 | 2023-11-09 | November | 23 | 9 | 2 | Week 2 | November 23 Week 2 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
3 | 2023-11-10 | November | 23 | 10 | 2 | Week 2 | November 23 Week 2 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
4 | 2023-11-11 | November | 23 | 11 | 2 | Week 2 | November 23 Week 2 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
5 | 2023-11-12 | November | 23 | 12 | 2 | Week 2 | November 23 Week 2 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
6 | 2023-11-13 | November | 23 | 13 | 2 | Week 2 | November 23 Week 2 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
7 | 2023-11-14 | November | 23 | 14 | 2 | Week 2 | November 23 Week 2 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
1 | 2023-11-15 | November | 23 | 15 | 3 | Week 3 | November 23 Week 3 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
2 | 2023-11-16 | November | 23 | 16 | 3 | Week 3 | November 23 Week 3 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
3 | 2023-11-17 | November | 23 | 17 | 3 | Week 3 | November 23 Week 3 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
4 | 2023-11-18 | November | 23 | 18 | 3 | Week 3 | November 23 Week 3 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
5 | 2023-11-19 | November | 23 | 19 | 3 | Week 3 | November 23 Week 3 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
6 | 2023-11-20 | November | 23 | 20 | 3 | Week 3 | November 23 Week 3 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
7 | 2023-11-21 | November | 23 | 21 | 3 | Week 3 | November 23 Week 3 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
1 | 2023-11-22 | November | 23 | 22 | 4 | Week 4 | November 23 Week 4 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
2 | 2023-11-23 | November | 23 | 23 | 4 | Week 4 | November 23 Week 4 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
3 | 2023-11-24 | November | 23 | 24 | 4 | Week 4 | November 23 Week 4 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
4 | 2023-11-25 | November | 23 | 25 | 4 | Week 4 | November 23 Week 4 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
5 | 2023-11-26 | November | 23 | 26 | 4 | Week 4 | November 23 Week 4 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
6 | 2023-11-27 | November | 23 | 27 | 4 | Week 4 | November 23 Week 4 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
7 | 2023-11-28 | November | 23 | 28 | 4 | Week 4 | November 23 Week 4 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
1 | 2023-11-29 | November | 23 | 29 | 5 | Week 5 | November 23 Week 5 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
2 | 2023-11-30 | November | 23 | 30 | 5 | Week 5 | November 23 Week 5 | NOVEMBER 23 | PLANNED | NOVEMBER 23 PLANNED
1 | 2023-12-01 | December | 23 | 1 | 1 | Week 1 | December 23 Week 1 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
2 | 2023-12-02 | December | 23 | 2 | 1 | Week 1 | December 23 Week 1 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
3 | 2023-12-03 | December | 23 | 3 | 1 | Week 1 | December 23 Week 1 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
4 | 2023-12-04 | December | 23 | 4 | 1 | Week 1 | December 23 Week 1 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
5 | 2023-12-05 | December | 23 | 5 | 1 | Week 1 | December 23 Week 1 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
6 | 2023-12-06 | December | 23 | 6 | 1 | Week 1 | December 23 Week 1 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
7 | 2023-12-07 | December | 23 | 7 | 1 | Week 1 | December 23 Week 1 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
1 | 2023-12-08 | December | 23 | 8 | 2 | Week 2 | December 23 Week 2 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
2 | 2023-12-09 | December | 23 | 9 | 2 | Week 2 | December 23 Week 2 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
3 | 2023-12-10 | December | 23 | 10 | 2 | Week 2 | December 23 Week 2 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
4 | 2023-12-11 | December | 23 | 11 | 2 | Week 2 | December 23 Week 2 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
5 | 2023-12-12 | December | 23 | 12 | 2 | Week 2 | December 23 Week 2 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
6 | 2023-12-13 | December | 23 | 13 | 2 | Week 2 | December 23 Week 2 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
7 | 2023-12-14 | December | 23 | 14 | 2 | Week 2 | December 23 Week 2 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
1 | 2023-12-15 | December | 23 | 15 | 3 | Week 3 | December 23 Week 3 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
2 | 2023-12-16 | December | 23 | 16 | 3 | Week 3 | December 23 Week 3 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
3 | 2023-12-17 | December | 23 | 17 | 3 | Week 3 | December 23 Week 3 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
4 | 2023-12-18 | December | 23 | 18 | 3 | Week 3 | December 23 Week 3 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
5 | 2023-12-19 | December | 23 | 19 | 3 | Week 3 | December 23 Week 3 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
6 | 2023-12-20 | December | 23 | 20 | 3 | Week 3 | December 23 Week 3 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
7 | 2023-12-21 | December | 23 | 21 | 3 | Week 3 | December 23 Week 3 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
1 | 2023-12-22 | December | 23 | 22 | 4 | Week 4 | December 23 Week 4 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
2 | 2023-12-23 | December | 23 | 23 | 4 | Week 4 | December 23 Week 4 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
3 | 2023-12-24 | December | 23 | 24 | 4 | Week 4 | December 23 Week 4 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
4 | 2023-12-25 | December | 23 | 25 | 4 | Week 4 | December 23 Week 4 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
5 | 2023-12-26 | December | 23 | 26 | 4 | Week 4 | December 23 Week 4 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
6 | 2023-12-27 | December | 23 | 27 | 4 | Week 4 | December 23 Week 4 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
7 | 2023-12-28 | December | 23 | 28 | 4 | Week 4 | December 23 Week 4 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
1 | 2023-12-29 | December | 23 | 29 | 5 | Week 5 | December 23 Week 5 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
2 | 2023-12-30 | December | 23 | 30 | 5 | Week 5 | December 23 Week 5 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
3 | 2023-12-31 | December | 23 | 31 | 5 | Week 5 | December 23 Week 5 | DECEMBER 23 | PLANNED | DECEMBER 23 PLANNED
1 | 2024-01-01 | January | 24 | 1 | 1 | Week 1 | January 24 Week 1 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
2 | 2024-01-02 | January | 24 | 2 | 1 | Week 1 | January 24 Week 1 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
3 | 2024-01-03 | January | 24 | 3 | 1 | Week 1 | January 24 Week 1 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
4 | 2024-01-04 | January | 24 | 4 | 1 | Week 1 | January 24 Week 1 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
5 | 2024-01-05 | January | 24 | 5 | 1 | Week 1 | January 24 Week 1 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
6 | 2024-01-06 | January | 24 | 6 | 1 | Week 1 | January 24 Week 1 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
7 | 2024-01-07 | January | 24 | 7 | 1 | Week 1 | January 24 Week 1 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
1 | 2024-01-08 | January | 24 | 8 | 2 | Week 2 | January 24 Week 2 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
2 | 2024-01-09 | January | 24 | 9 | 2 | Week 2 | January 24 Week 2 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
3 | 2024-01-10 | January | 24 | 10 | 2 | Week 2 | January 24 Week 2 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
4 | 2024-01-11 | January | 24 | 11 | 2 | Week 2 | January 24 Week 2 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
5 | 2024-01-12 | January | 24 | 12 | 2 | Week 2 | January 24 Week 2 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
6 | 2024-01-13 | January | 24 | 13 | 2 | Week 2 | January 24 Week 2 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
7 | 2024-01-14 | January | 24 | 14 | 2 | Week 2 | January 24 Week 2 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
1 | 2024-01-15 | January | 24 | 15 | 3 | Week 3 | January 24 Week 3 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
2 | 2024-01-16 | January | 24 | 16 | 3 | Week 3 | January 24 Week 3 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
3 | 2024-01-17 | January | 24 | 17 | 3 | Week 3 | January 24 Week 3 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
4 | 2024-01-18 | January | 24 | 18 | 3 | Week 3 | January 24 Week 3 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
5 | 2024-01-19 | January | 24 | 19 | 3 | Week 3 | January 24 Week 3 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
6 | 2024-01-20 | January | 24 | 20 | 3 | Week 3 | January 24 Week 3 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
7 | 2024-01-21 | January | 24 | 21 | 3 | Week 3 | January 24 Week 3 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
1 | 2024-01-22 | January | 24 | 22 | 4 | Week 4 | January 24 Week 4 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
2 | 2024-01-23 | January | 24 | 23 | 4 | Week 4 | January 24 Week 4 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
3 | 2024-01-24 | January | 24 | 24 | 4 | Week 4 | January 24 Week 4 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
4 | 2024-01-25 | January | 24 | 25 | 4 | Week 4 | January 24 Week 4 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
5 | 2024-01-26 | January | 24 | 26 | 4 | Week 4 | January 24 Week 4 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
6 | 2024-01-27 | January | 24 | 27 | 4 | Week 4 | January 24 Week 4 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
7 | 2024-01-28 | January | 24 | 28 | 4 | Week 4 | January 24 Week 4 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
1 | 2024-01-29 | January | 24 | 29 | 5 | Week 5 | January 24 Week 5 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
2 | 2024-01-30 | January | 24 | 30 | 5 | Week 5 | January 24 Week 5 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
3 | 2024-01-31 | January | 24 | 31 | 5 | Week 5 | January 24 Week 5 | JANUARY 24 | PLANNED | JANUARY 24 PLANNED
1 | 2024-02-01 | February | 24 | 1 | 1 | Week 1 | February 24 Week 1 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
2 | 2024-02-02 | February | 24 | 2 | 1 | Week 1 | February 24 Week 1 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
3 | 2024-02-03 | February | 24 | 3 | 1 | Week 1 | February 24 Week 1 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
4 | 2024-02-04 | February | 24 | 4 | 1 | Week 1 | February 24 Week 1 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
5 | 2024-02-05 | February | 24 | 5 | 1 | Week 1 | February 24 Week 1 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
6 | 2024-02-06 | February | 24 | 6 | 1 | Week 1 | February 24 Week 1 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
7 | 2024-02-07 | February | 24 | 7 | 1 | Week 1 | February 24 Week 1 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
1 | 2024-02-08 | February | 24 | 8 | 2 | Week 2 | February 24 Week 2 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
2 | 2024-02-09 | February | 24 | 9 | 2 | Week 2 | February 24 Week 2 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
3 | 2024-02-10 | February | 24 | 10 | 2 | Week 2 | February 24 Week 2 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
4 | 2024-02-11 | February | 24 | 11 | 2 | Week 2 | February 24 Week 2 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
5 | 2024-02-12 | February | 24 | 12 | 2 | Week 2 | February 24 Week 2 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
6 | 2024-02-13 | February | 24 | 13 | 2 | Week 2 | February 24 Week 2 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
7 | 2024-02-14 | February | 24 | 14 | 2 | Week 2 | February 24 Week 2 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
1 | 2024-02-15 | February | 24 | 15 | 3 | Week 3 | February 24 Week 3 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
2 | 2024-02-16 | February | 24 | 16 | 3 | Week 3 | February 24 Week 3 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
3 | 2024-02-17 | February | 24 | 17 | 3 | Week 3 | February 24 Week 3 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
4 | 2024-02-18 | February | 24 | 18 | 3 | Week 3 | February 24 Week 3 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
5 | 2024-02-19 | February | 24 | 19 | 3 | Week 3 | February 24 Week 3 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
6 | 2024-02-20 | February | 24 | 20 | 3 | Week 3 | February 24 Week 3 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
7 | 2024-02-21 | February | 24 | 21 | 3 | Week 3 | February 24 Week 3 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
1 | 2024-02-22 | February | 24 | 22 | 4 | Week 4 | February 24 Week 4 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
2 | 2024-02-23 | February | 24 | 23 | 4 | Week 4 | February 24 Week 4 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
3 | 2024-02-24 | February | 24 | 24 | 4 | Week 4 | February 24 Week 4 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
4 | 2024-02-25 | February | 24 | 25 | 4 | Week 4 | February 24 Week 4 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
5 | 2024-02-26 | February | 24 | 26 | 4 | Week 4 | February 24 Week 4 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
6 | 2024-02-27 | February | 24 | 27 | 4 | Week 4 | February 24 Week 4 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
7 | 2024-02-28 | February | 24 | 28 | 4 | Week 4 | February 24 Week 4 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
1 | 2024-02-29 | February | 24 | 29 | 5 | Week 5 | February 24 Week 5 | FEBRUARY 24 | PLANNED | FEBRUARY 24 PLANNED
1 | 2024-03-01 | March | 24 | 1 | 1 | Week 1 | March 24 Week 1 | MARCH 24 | PLANNED | MARCH 24 PLANNED
2 | 2024-03-02 | March | 24 | 2 | 1 | Week 1 | March 24 Week 1 | MARCH 24 | PLANNED | MARCH 24 PLANNED
3 | 2024-03-03 | March | 24 | 3 | 1 | Week 1 | March 24 Week 1 | MARCH 24 | PLANNED | MARCH 24 PLANNED
4 | 2024-03-04 | March | 24 | 4 | 1 | Week 1 | March 24 Week 1 | MARCH 24 | PLANNED | MARCH 24 PLANNED
5 | 2024-03-05 | March | 24 | 5 | 1 | Week 1 | March 24 Week 1 | MARCH 24 | PLANNED | MARCH 24 PLANNED
6 | 2024-03-06 | March | 24 | 6 | 1 | Week 1 | March 24 Week 1 | MARCH 24 | PLANNED | MARCH 24 PLANNED
7 | 2024-03-07 | March | 24 | 7 | 1 | Week 1 | March 24 Week 1 | MARCH 24 | PLANNED | MARCH 24 PLANNED
1 | 2024-03-08 | March | 24 | 8 | 2 | Week 2 | March 24 Week 2 | MARCH 24 | PLANNED | MARCH 24 PLANNED
2 | 2024-03-09 | March | 24 | 9 | 2 | Week 2 | March 24 Week 2 | MARCH 24 | PLANNED | MARCH 24 PLANNED
3 | 2024-03-10 | March | 24 | 10 | 2 | Week 2 | March 24 Week 2 | MARCH 24 | PLANNED | MARCH 24 PLANNED
4 | 2024-03-11 | March | 24 | 11 | 2 | Week 2 | March 24 Week 2 | MARCH 24 | PLANNED | MARCH 24 PLANNED
5 | 2024-03-12 | March | 24 | 12 | 2 | Week 2 | March 24 Week 2 | MARCH 24 | PLANNED | MARCH 24 PLANNED
6 | 2024-03-13 | March | 24 | 13 | 2 | Week 2 | March 24 Week 2 | MARCH 24 | PLANNED | MARCH 24 PLANNED
7 | 2024-03-14 | March | 24 | 14 | 2 | Week 2 | March 24 Week 2 | MARCH 24 | PLANNED | MARCH 24 PLANNED
1 | 2024-03-15 | March | 24 | 15 | 3 | Week 3 | March 24 Week 3 | MARCH 24 | PLANNED | MARCH 24 PLANNED
2 | 2024-03-16 | March | 24 | 16 | 3 | Week 3 | March 24 Week 3 | MARCH 24 | PLANNED | MARCH 24 PLANNED
3 | 2024-03-17 | March | 24 | 17 | 3 | Week 3 | March 24 Week 3 | MARCH 24 | PLANNED | MARCH 24 PLANNED
4 | 2024-03-18 | March | 24 | 18 | 3 | Week 3 | March 24 Week 3 | MARCH 24 | PLANNED | MARCH 24 PLANNED
5 | 2024-03-19 | March | 24 | 19 | 3 | Week 3 | March 24 Week 3 | MARCH 24 | PLANNED | MARCH 24 PLANNED
6 | 2024-03-20 | March | 24 | 20 | 3 | Week 3 | March 24 Week 3 | MARCH 24 | PLANNED | MARCH 24 PLANNED
7 | 2024-03-21 | March | 24 | 21 | 3 | Week 3 | March 24 Week 3 | MARCH 24 | PLANNED | MARCH 24 PLANNED
1 | 2024-03-22 | March | 24 | 22 | 4 | Week 4 | March 24 Week 4 | MARCH 24 | PLANNED | MARCH 24 PLANNED
2 | 2024-03-23 | March | 24 | 23 | 4 | Week 4 | March 24 Week 4 | MARCH 24 | PLANNED | MARCH 24 PLANNED
3 | 2024-03-24 | March | 24 | 24 | 4 | Week 4 | March 24 Week 4 | MARCH 24 | PLANNED | MARCH 24 PLANNED
4 | 2024-03-25 | March | 24 | 25 | 4 | Week 4 | March 24 Week 4 | MARCH 24 | PLANNED | MARCH 24 PLANNED
5 | 2024-03-26 | March | 24 | 26 | 4 | Week 4 | March 24 Week 4 | MARCH 24 | PLANNED | MARCH 24 PLANNED
6 | 2024-03-27 | March | 24 | 27 | 4 | Week 4 | March 24 Week 4 | MARCH 24 | PLANNED | MARCH 24 PLANNED
7 | 2024-03-28 | March | 24 | 28 | 4 | Week 4 | March 24 Week 4 | MARCH 24 | PLANNED | MARCH 24 PLANNED
1 | 2024-03-29 | March | 24 | 29 | 5 | Week 5 | March 24 Week 5 | MARCH 24 | PLANNED | MARCH 24 PLANNED
2 | 2024-03-30 | March | 24 | 30 | 5 | Week 5 | March 24 Week 5 | MARCH 24 | PLANNED | MARCH 24 PLANNED
3 | 2024-03-31 | March | 24 | 31 | 5 | Week 5 | March 24 Week 5 | MARCH 24 | PLANNED | MARCH 24 PLANNED
1 | 2024-04-01 | April | 24 | 1 | 1 | Week 1 | April 24 Week 1 | APRIL 24 | PLANNED | APRIL 24 PLANNED
2 | 2024-04-02 | April | 24 | 2 | 1 | Week 1 | April 24 Week 1 | APRIL 24 | PLANNED | APRIL 24 PLANNED
3 | 2024-04-03 | April | 24 | 3 | 1 | Week 1 | April 24 Week 1 | APRIL 24 | PLANNED | APRIL 24 PLANNED
4 | 2024-04-04 | April | 24 | 4 | 1 | Week 1 | April 24 Week 1 | APRIL 24 | PLANNED | APRIL 24 PLANNED
5 | 2024-04-05 | April | 24 | 5 | 1 | Week 1 | April 24 Week 1 | APRIL 24 | PLANNED | APRIL 24 PLANNED
6 | 2024-04-06 | April | 24 | 6 | 1 | Week 1 | April 24 Week 1 | APRIL 24 | PLANNED | APRIL 24 PLANNED
7 | 2024-04-07 | April | 24 | 7 | 1 | Week 1 | April 24 Week 1 | APRIL 24 | PLANNED | APRIL 24 PLANNED
1 | 2024-04-08 | April | 24 | 8 | 2 | Week 2 | April 24 Week 2 | APRIL 24 | PLANNED | APRIL 24 PLANNED
2 | 2024-04-09 | April | 24 | 9 | 2 | Week 2 | April 24 Week 2 | APRIL 24 | PLANNED | APRIL 24 PLANNED
3 | 2024-04-10 | April | 24 | 10 | 2 | Week 2 | April 24 Week 2 | APRIL 24 | PLANNED | APRIL 24 PLANNED
4 | 2024-04-11 | April | 24 | 11 | 2 | Week 2 | April 24 Week 2 | APRIL 24 | PLANNED | APRIL 24 PLANNED
5 | 2024-04-12 | April | 24 | 12 | 2 | Week 2 | April 24 Week 2 | APRIL 24 | PLANNED | APRIL 24 PLANNED
6 | 2024-04-13 | April | 24 | 13 | 2 | Week 2 | April 24 Week 2 | APRIL 24 | PLANNED | APRIL 24 PLANNED
7 | 2024-04-14 | April | 24 | 14 | 2 | Week 2 | April 24 Week 2 | APRIL 24 | PLANNED | APRIL 24 PLANNED
1 | 2024-04-15 | April | 24 | 15 | 3 | Week 3 | April 24 Week 3 | APRIL 24 | PLANNED | APRIL 24 PLANNED
2 | 2024-04-16 | April | 24 | 16 | 3 | Week 3 | April 24 Week 3 | APRIL 24 | PLANNED | APRIL 24 PLANNED
3 | 2024-04-17 | April | 24 | 17 | 3 | Week 3 | April 24 Week 3 | APRIL 24 | PLANNED | APRIL 24 PLANNED
4 | 2024-04-18 | April | 24 | 18 | 3 | Week 3 | April 24 Week 3 | APRIL 24 | PLANNED | APRIL 24 PLANNED
5 | 2024-04-19 | April | 24 | 19 | 3 | Week 3 | April 24 Week 3 | APRIL 24 | PLANNED | APRIL 24 PLANNED
6 | 2024-04-20 | April | 24 | 20 | 3 | Week 3 | April 24 Week 3 | APRIL 24 | PLANNED | APRIL 24 PLANNED
7 | 2024-04-21 | April | 24 | 21 | 3 | Week 3 | April 24 Week 3 | APRIL 24 | PLANNED | APRIL 24 PLANNED
1 | 2024-04-22 | April | 24 | 22 | 4 | Week 4 | April 24 Week 4 | APRIL 24 | PLANNED | APRIL 24 PLANNED
2 | 2024-04-23 | April | 24 | 23 | 4 | Week 4 | April 24 Week 4 | APRIL 24 | PLANNED | APRIL 24 PLANNED
3 | 2024-04-24 | April | 24 | 24 | 4 | Week 4 | April 24 Week 4 | APRIL 24 | PLANNED | APRIL 24 PLANNED
4 | 2024-04-25 | April | 24 | 25 | 4 | Week 4 | April 24 Week 4 | APRIL 24 | PLANNED | APRIL 24 PLANNED
5 | 2024-04-26 | April | 24 | 26 | 4 | Week 4 | April 24 Week 4 | APRIL 24 | PLANNED | APRIL 24 PLANNED
6 | 2024-04-27 | April | 24 | 27 | 4 | Week 4 | April 24 Week 4 | APRIL 24 | PLANNED | APRIL 24 PLANNED
7 | 2024-04-28 | April | 24 | 28 | 4 | Week 4 | April 24 Week 4 | APRIL 24 | PLANNED | APRIL 24 PLANNED
1 | 2024-04-29 | April | 24 | 29 | 5 | Week 5 | April 24 Week 5 | APRIL 24 | PLANNED | APRIL 24 PLANNED
2 | 2024-04-30 | April | 24 | 30 | 5 | Week 5 | April 24 Week 5 | APRIL 24 | PLANNED | APRIL 24 PLANNED
1 | 2024-05-01 | May | 24 | 1 | 1 | Week 1 | May 24 Week 1 | MAY 24 | PLANNED | MAY 24 PLANNED
2 | 2024-05-02 | May | 24 | 2 | 1 | Week 1 | May 24 Week 1 | MAY 24 | PLANNED | MAY 24 PLANNED
3 | 2024-05-03 | May | 24 | 3 | 1 | Week 1 | May 24 Week 1 | MAY 24 | PLANNED | MAY 24 PLANNED
4 | 2024-05-04 | May | 24 | 4 | 1 | Week 1 | May 24 Week 1 | MAY 24 | PLANNED | MAY 24 PLANNED
5 | 2024-05-05 | May | 24 | 5 | 1 | Week 1 | May 24 Week 1 | MAY 24 | PLANNED | MAY 24 PLANNED
6 | 2024-05-06 | May | 24 | 6 | 1 | Week 1 | May 24 Week 1 | MAY 24 | PLANNED | MAY 24 PLANNED
7 | 2024-05-07 | May | 24 | 7 | 1 | Week 1 | May 24 Week 1 | MAY 24 | PLANNED | MAY 24 PLANNED
1 | 2024-05-08 | May | 24 | 8 | 2 | Week 2 | May 24 Week 2 | MAY 24 | PLANNED | MAY 24 PLANNED
2 | 2024-05-09 | May | 24 | 9 | 2 | Week 2 | May 24 Week 2 | MAY 24 | PLANNED | MAY 24 PLANNED
3 | 2024-05-10 | May | 24 | 10 | 2 | Week 2 | May 24 Week 2 | MAY 24 | PLANNED | MAY 24 PLANNED
4 | 2024-05-11 | May | 24 | 11 | 2 | Week 2 | May 24 Week 2 | MAY 24 | PLANNED | MAY 24 PLANNED
5 | 2024-05-12 | May | 24 | 12 | 2 | Week 2 | May 24 Week 2 | MAY 24 | PLANNED | MAY 24 PLANNED
6 | 2024-05-13 | May | 24 | 13 | 2 | Week 2 | May 24 Week 2 | MAY 24 | PLANNED | MAY 24 PLANNED
7 | 2024-05-14 | May | 24 | 14 | 2 | Week 2 | May 24 Week 2 | MAY 24 | PLANNED | MAY 24 PLANNED
1 | 2024-05-15 | May | 24 | 15 | 3 | Week 3 | May 24 Week 3 | MAY 24 | PLANNED | MAY 24 PLANNED
2 | 2024-05-16 | May | 24 | 16 | 3 | Week 3 | May 24 Week 3 | MAY 24 | PLANNED | MAY 24 PLANNED
3 | 2024-05-17 | May | 24 | 17 | 3 | Week 3 | May 24 Week 3 | MAY 24 | PLANNED | MAY 24 PLANNED
4 | 2024-05-18 | May | 24 | 18 | 3 | Week 3 | May 24 Week 3 | MAY 24 | PLANNED | MAY 24 PLANNED
5 | 2024-05-19 | May | 24 | 19 | 3 | Week 3 | May 24 Week 3 | MAY 24 | PLANNED | MAY 24 PLANNED
6 | 2024-05-20 | May | 24 | 20 | 3 | Week 3 | May 24 Week 3 | MAY 24 | PLANNED | MAY 24 PLANNED
7 | 2024-05-21 | May | 24 | 21 | 3 | Week 3 | May 24 Week 3 | MAY 24 | PLANNED | MAY 24 PLANNED
1 | 2024-05-22 | May | 24 | 22 | 4 | Week 4 | May 24 Week 4 | MAY 24 | PLANNED | MAY 24 PLANNED
2 | 2024-05-23 | May | 24 | 23 | 4 | Week 4 | May 24 Week 4 | MAY 24 | PLANNED | MAY 24 PLANNED
3 | 2024-05-24 | May | 24 | 24 | 4 | Week 4 | May 24 Week 4 | MAY 24 | PLANNED | MAY 24 PLANNED
4 | 2024-05-25 | May | 24 | 25 | 4 | Week 4 | May 24 Week 4 | MAY 24 | PLANNED | MAY 24 PLANNED
5 | 2024-05-26 | May | 24 | 26 | 4 | Week 4 | May 24 Week 4 | MAY 24 | PLANNED | MAY 24 PLANNED
6 | 2024-05-27 | May | 24 | 27 | 4 | Week 4 | May 24 Week 4 | MAY 24 | PLANNED | MAY 24 PLANNED
7 | 2024-05-28 | May | 24 | 28 | 4 | Week 4 | May 24 Week 4 | MAY 24 | PLANNED | MAY 24 PLANNED
1 | 2024-05-29 | May | 24 | 29 | 5 | Week 5 | May 24 Week 5 | MAY 24 | PLANNED | MAY 24 PLANNED
2 | 2024-05-30 | May | 24 | 30 | 5 | Week 5 | May 24 Week 5 | MAY 24 | PLANNED | MAY 24 PLANNED
3 | 2024-05-31 | May | 24 | 31 | 5 | Week 5 | May 24 Week 5 | MAY 24 | PLANNED | MAY 24 PLANNED
1 | 2024-06-01 | June | 24 | 1 | 1 | Week 1 | June 24 Week 1 | JUNE 24 | PLANNED | JUNE 24 PLANNED
2 | 2024-06-02 | June | 24 | 2 | 1 | Week 1 | June 24 Week 1 | JUNE 24 | PLANNED | JUNE 24 PLANNED
3 | 2024-06-03 | June | 24 | 3 | 1 | Week 1 | June 24 Week 1 | JUNE 24 | PLANNED | JUNE 24 PLANNED
4 | 2024-06-04 | June | 24 | 4 | 1 | Week 1 | June 24 Week 1 | JUNE 24 | PLANNED | JUNE 24 PLANNED
5 | 2024-06-05 | June | 24 | 5 | 1 | Week 1 | June 24 Week 1 | JUNE 24 | PLANNED | JUNE 24 PLANNED
6 | 2024-06-06 | June | 24 | 6 | 1 | Week 1 | June 24 Week 1 | JUNE 24 | PLANNED | JUNE 24 PLANNED
7 | 2024-06-07 | June | 24 | 7 | 1 | Week 1 | June 24 Week 1 | JUNE 24 | PLANNED | JUNE 24 PLANNED
1 | 2024-06-08 | June | 24 | 8 | 2 | Week 2 | June 24 Week 2 | JUNE 24 | PLANNED | JUNE 24 PLANNED
2 | 2024-06-09 | June | 24 | 9 | 2 | Week 2 | June 24 Week 2 | JUNE 24 | PLANNED | JUNE 24 PLANNED
3 | 2024-06-10 | June | 24 | 10 | 2 | Week 2 | June 24 Week 2 | JUNE 24 | PLANNED | JUNE 24 PLANNED
4 | 2024-06-11 | June | 24 | 11 | 2 | Week 2 | June 24 Week 2 | JUNE 24 | PLANNED | JUNE 24 PLANNED
5 | 2024-06-12 | June | 24 | 12 | 2 | Week 2 | June 24 Week 2 | JUNE 24 | PLANNED | JUNE 24 PLANNED
6 | 2024-06-13 | June | 24 | 13 | 2 | Week 2 | June 24 Week 2 | JUNE 24 | PLANNED | JUNE 24 PLANNED
7 | 2024-06-14 | June | 24 | 14 | 2 | Week 2 | June 24 Week 2 | JUNE 24 | PLANNED | JUNE 24 PLANNED
1 | 2024-06-15 | June | 24 | 15 | 3 | Week 3 | June 24 Week 3 | JUNE 24 | PLANNED | JUNE 24 PLANNED
2 | 2024-06-16 | June | 24 | 16 | 3 | Week 3 | June 24 Week 3 | JUNE 24 | PLANNED | JUNE 24 PLANNED
3 | 2024-06-17 | June | 24 | 17 | 3 | Week 3 | June 24 Week 3 | JUNE 24 | PLANNED | JUNE 24 PLANNED
4 | 2024-06-18 | June | 24 | 18 | 3 | Week 3 | June 24 Week 3 | JUNE 24 | PLANNED | JUNE 24 PLANNED
5 | 2024-06-19 | June | 24 | 19 | 3 | Week 3 | June 24 Week 3 | JUNE 24 | PLANNED | JUNE 24 PLANNED
6 | 2024-06-20 | June | 24 | 20 | 3 | Week 3 | June 24 Week 3 | JUNE 24 | PLANNED | JUNE 24 PLANNED
7 | 2024-06-21 | June | 24 | 21 | 3 | Week 3 | June 24 Week 3 | JUNE 24 | PLANNED | JUNE 24 PLANNED
1 | 2024-06-22 | June | 24 | 22 | 4 | Week 4 | June 24 Week 4 | JUNE 24 | PLANNED | JUNE 24 PLANNED
2 | 2024-06-23 | June | 24 | 23 | 4 | Week 4 | June 24 Week 4 | JUNE 24 | PLANNED | JUNE 24 PLANNED
3 | 2024-06-24 | June | 24 | 24 | 4 | Week 4 | June 24 Week 4 | JUNE 24 | PLANNED | JUNE 24 PLANNED
4 | 2024-06-25 | June | 24 | 25 | 4 | Week 4 | June 24 Week 4 | JUNE 24 | PLANNED | JUNE 24 PLANNED
5 | 2024-06-26 | June | 24 | 26 | 4 | Week 4 | June 24 Week 4 | JUNE 24 | PLANNED | JUNE 24 PLANNED
6 | 2024-06-27 | June | 24 | 27 | 4 | Week 4 | June 24 Week 4 | JUNE 24 | PLANNED | JUNE 24 PLANNED
7 | 2024-06-28 | June | 24 | 28 | 4 | Week 4 | June 24 Week 4 | JUNE 24 | PLANNED | JUNE 24 PLANNED
1 | 2024-06-29 | June | 24 | 29 | 5 | Week 5 | June 24 Week 5 | JUNE 24 | PLANNED | JUNE 24 PLANNED
2 | 2024-06-30 | June | 24 | 30 | 5 | Week 5 | June 24 Week 5 | JUNE 24 | PLANNED | JUNE 24 PLANNED
1 | 2024-07-01 | July | 24 | 1 | 1 | Week 1 | July 24 Week 1 | JULY 24 | PLANNED | JULY 24 PLANNED
2 | 2024-07-02 | July | 24 | 2 | 1 | Week 1 | July 24 Week 1 | JULY 24 | PLANNED | JULY 24 PLANNED
3 | 2024-07-03 | July | 24 | 3 | 1 | Week 1 | July 24 Week 1 | JULY 24 | PLANNED | JULY 24 PLANNED
4 | 2024-07-04 | July | 24 | 4 | 1 | Week 1 | July 24 Week 1 | JULY 24 | PLANNED | JULY 24 PLANNED
5 | 2024-07-05 | July | 24 | 5 | 1 | Week 1 | July 24 Week 1 | JULY 24 | PLANNED | JULY 24 PLANNED
6 | 2024-07-06 | July | 24 | 6 | 1 | Week 1 | July 24 Week 1 | JULY 24 | PLANNED | JULY 24 PLANNED
7 | 2024-07-07 | July | 24 | 7 | 1 | Week 1 | July 24 Week 1 | JULY 24 | PLANNED | JULY 24 PLANNED
1 | 2024-07-08 | July | 24 | 8 | 2 | Week 2 | July 24 Week 2 | JULY 24 | PLANNED | JULY 24 PLANNED
2 | 2024-07-09 | July | 24 | 9 | 2 | Week 2 | July 24 Week 2 | JULY 24 | PLANNED | JULY 24 PLANNED
3 | 2024-07-10 | July | 24 | 10 | 2 | Week 2 | July 24 Week 2 | JULY 24 | PLANNED | JULY 24 PLANNED
4 | 2024-07-11 | July | 24 | 11 | 2 | Week 2 | July 24 Week 2 | JULY 24 | PLANNED | JULY 24 PLANNED
5 | 2024-07-12 | July | 24 | 12 | 2 | Week 2 | July 24 Week 2 | JULY 24 | PLANNED | JULY 24 PLANNED
6 | 2024-07-13 | July | 24 | 13 | 2 | Week 2 | July 24 Week 2 | JULY 24 | PLANNED | JULY 24 PLANNED
7 | 2024-07-14 | July | 24 | 14 | 2 | Week 2 | July 24 Week 2 | JULY 24 | PLANNED | JULY 24 PLANNED
1 | 2024-07-15 | July | 24 | 15 | 3 | Week 3 | July 24 Week 3 | JULY 24 | PLANNED | JULY 24 PLANNED
2 | 2024-07-16 | July | 24 | 16 | 3 | Week 3 | July 24 Week 3 | JULY 24 | PLANNED | JULY 24 PLANNED
3 | 2024-07-17 | July | 24 | 17 | 3 | Week 3 | July 24 Week 3 | JULY 24 | PLANNED | JULY 24 PLANNED
4 | 2024-07-18 | July | 24 | 18 | 3 | Week 3 | July 24 Week 3 | JULY 24 | PLANNED | JULY 24 PLANNED
5 | 2024-07-19 | July | 24 | 19 | 3 | Week 3 | July 24 Week 3 | JULY 24 | PLANNED | JULY 24 PLANNED
6 | 2024-07-20 | July | 24 | 20 | 3 | Week 3 | July 24 Week 3 | JULY 24 | PLANNED | JULY 24 PLANNED
7 | 2024-07-21 | July | 24 | 21 | 3 | Week 3 | July 24 Week 3 | JULY 24 | PLANNED | JULY 24 PLANNED
1 | 2024-07-22 | July | 24 | 22 | 4 | Week 4 | July 24 Week 4 | JULY 24 | PLANNED | JULY 24 PLANNED
2 | 2024-07-23 | July | 24 | 23 | 4 | Week 4 | July 24 Week 4 | JULY 24 | PLANNED | JULY 24 PLANNED
3 | 2024-07-24 | July | 24 | 24 | 4 | Week 4 | July 24 Week 4 | JULY 24 | PLANNED | JULY 24 PLANNED
4 | 2024-07-25 | July | 24 | 25 | 4 | Week 4 | July 24 Week 4 | JULY 24 | PLANNED | JULY 24 PLANNED
5 | 2024-07-26 | July | 24 | 26 | 4 | Week 4 | July 24 Week 4 | JULY 24 | PLANNED | JULY 24 PLANNED
6 | 2024-07-27 | July | 24 | 27 | 4 | Week 4 | July 24 Week 4 | JULY 24 | PLANNED | JULY 24 PLANNED
7 | 2024-07-28 | July | 24 | 28 | 4 | Week 4 | July 24 Week 4 | JULY 24 | PLANNED | JULY 24 PLANNED
1 | 2024-07-29 | July | 24 | 29 | 5 | Week 5 | July 24 Week 5 | JULY 24 | PLANNED | JULY 24 PLANNED
2 | 2024-07-30 | July | 24 | 30 | 5 | Week 5 | July 24 Week 5 | JULY 24 | PLANNED | JULY 24 PLANNED
3 | 2024-07-31 | July | 24 | 31 | 5 | Week 5 | July 24 Week 5 | JULY 24 | PLANNED | JULY 24 PLANNED
1 | 2024-08-01 | August | 24 | 1 | 1 | Week 1 | August 24 Week 1 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
2 | 2024-08-02 | August | 24 | 2 | 1 | Week 1 | August 24 Week 1 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
3 | 2024-08-03 | August | 24 | 3 | 1 | Week 1 | August 24 Week 1 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
4 | 2024-08-04 | August | 24 | 4 | 1 | Week 1 | August 24 Week 1 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
5 | 2024-08-05 | August | 24 | 5 | 1 | Week 1 | August 24 Week 1 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
6 | 2024-08-06 | August | 24 | 6 | 1 | Week 1 | August 24 Week 1 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
7 | 2024-08-07 | August | 24 | 7 | 1 | Week 1 | August 24 Week 1 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
1 | 2024-08-08 | August | 24 | 8 | 2 | Week 2 | August 24 Week 2 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
2 | 2024-08-09 | August | 24 | 9 | 2 | Week 2 | August 24 Week 2 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
3 | 2024-08-10 | August | 24 | 10 | 2 | Week 2 | August 24 Week 2 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
4 | 2024-08-11 | August | 24 | 11 | 2 | Week 2 | August 24 Week 2 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
5 | 2024-08-12 | August | 24 | 12 | 2 | Week 2 | August 24 Week 2 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
6 | 2024-08-13 | August | 24 | 13 | 2 | Week 2 | August 24 Week 2 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
7 | 2024-08-14 | August | 24 | 14 | 2 | Week 2 | August 24 Week 2 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
1 | 2024-08-15 | August | 24 | 15 | 3 | Week 3 | August 24 Week 3 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
2 | 2024-08-16 | August | 24 | 16 | 3 | Week 3 | August 24 Week 3 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
3 | 2024-08-17 | August | 24 | 17 | 3 | Week 3 | August 24 Week 3 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
4 | 2024-08-18 | August | 24 | 18 | 3 | Week 3 | August 24 Week 3 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
5 | 2024-08-19 | August | 24 | 19 | 3 | Week 3 | August 24 Week 3 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
6 | 2024-08-20 | August | 24 | 20 | 3 | Week 3 | August 24 Week 3 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
7 | 2024-08-21 | August | 24 | 21 | 3 | Week 3 | August 24 Week 3 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
1 | 2024-08-22 | August | 24 | 22 | 4 | Week 4 | August 24 Week 4 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
2 | 2024-08-23 | August | 24 | 23 | 4 | Week 4 | August 24 Week 4 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
3 | 2024-08-24 | August | 24 | 24 | 4 | Week 4 | August 24 Week 4 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
4 | 2024-08-25 | August | 24 | 25 | 4 | Week 4 | August 24 Week 4 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
5 | 2024-08-26 | August | 24 | 26 | 4 | Week 4 | August 24 Week 4 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
6 | 2024-08-27 | August | 24 | 27 | 4 | Week 4 | August 24 Week 4 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
7 | 2024-08-28 | August | 24 | 28 | 4 | Week 4 | August 24 Week 4 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
1 | 2024-08-29 | August | 24 | 29 | 5 | Week 5 | August 24 Week 5 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
2 | 2024-08-30 | August | 24 | 30 | 5 | Week 5 | August 24 Week 5 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
3 | 2024-08-31 | August | 24 | 31 | 5 | Week 5 | August 24 Week 5 | AUGUST 24 | PLANNED | AUGUST 24 PLANNED
1 | 2024-09-01 | September | 24 | 1 | 1 | Week 1 | September 24 Week 1 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
2 | 2024-09-02 | September | 24 | 2 | 1 | Week 1 | September 24 Week 1 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
3 | 2024-09-03 | September | 24 | 3 | 1 | Week 1 | September 24 Week 1 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
4 | 2024-09-04 | September | 24 | 4 | 1 | Week 1 | September 24 Week 1 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
5 | 2024-09-05 | September | 24 | 5 | 1 | Week 1 | September 24 Week 1 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
6 | 2024-09-06 | September | 24 | 6 | 1 | Week 1 | September 24 Week 1 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
7 | 2024-09-07 | September | 24 | 7 | 1 | Week 1 | September 24 Week 1 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
1 | 2024-09-08 | September | 24 | 8 | 2 | Week 2 | September 24 Week 2 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
2 | 2024-09-09 | September | 24 | 9 | 2 | Week 2 | September 24 Week 2 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
3 | 2024-09-10 | September | 24 | 10 | 2 | Week 2 | September 24 Week 2 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
4 | 2024-09-11 | September | 24 | 11 | 2 | Week 2 | September 24 Week 2 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
5 | 2024-09-12 | September | 24 | 12 | 2 | Week 2 | September 24 Week 2 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
6 | 2024-09-13 | September | 24 | 13 | 2 | Week 2 | September 24 Week 2 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
7 | 2024-09-14 | September | 24 | 14 | 2 | Week 2 | September 24 Week 2 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
1 | 2024-09-15 | September | 24 | 15 | 3 | Week 3 | September 24 Week 3 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
2 | 2024-09-16 | September | 24 | 16 | 3 | Week 3 | September 24 Week 3 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
3 | 2024-09-17 | September | 24 | 17 | 3 | Week 3 | September 24 Week 3 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
4 | 2024-09-18 | September | 24 | 18 | 3 | Week 3 | September 24 Week 3 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
5 | 2024-09-19 | September | 24 | 19 | 3 | Week 3 | September 24 Week 3 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
6 | 2024-09-20 | September | 24 | 20 | 3 | Week 3 | September 24 Week 3 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
7 | 2024-09-21 | September | 24 | 21 | 3 | Week 3 | September 24 Week 3 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
1 | 2024-09-22 | September | 24 | 22 | 4 | Week 4 | September 24 Week 4 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
2 | 2024-09-23 | September | 24 | 23 | 4 | Week 4 | September 24 Week 4 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
3 | 2024-09-24 | September | 24 | 24 | 4 | Week 4 | September 24 Week 4 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
4 | 2024-09-25 | September | 24 | 25 | 4 | Week 4 | September 24 Week 4 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
5 | 2024-09-26 | September | 24 | 26 | 4 | Week 4 | September 24 Week 4 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
6 | 2024-09-27 | September | 24 | 27 | 4 | Week 4 | September 24 Week 4 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
7 | 2024-09-28 | September | 24 | 28 | 4 | Week 4 | September 24 Week 4 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
1 | 2024-09-29 | September | 24 | 29 | 5 | Week 5 | September 24 Week 5 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
2 | 2024-09-30 | September | 24 | 30 | 5 | Week 5 | September 24 Week 5 | SEPTEMBER 24 | PLANNED | SEPTEMBER 24 PLANNED
1 | 2024-10-01 | October | 24 | 1 | 1 | Week 1 | October 24 Week 1 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
2 | 2024-10-02 | October | 24 | 2 | 1 | Week 1 | October 24 Week 1 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
3 | 2024-10-03 | October | 24 | 3 | 1 | Week 1 | October 24 Week 1 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
4 | 2024-10-04 | October | 24 | 4 | 1 | Week 1 | October 24 Week 1 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
5 | 2024-10-05 | October | 24 | 5 | 1 | Week 1 | October 24 Week 1 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
6 | 2024-10-06 | October | 24 | 6 | 1 | Week 1 | October 24 Week 1 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
7 | 2024-10-07 | October | 24 | 7 | 1 | Week 1 | October 24 Week 1 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
1 | 2024-10-08 | October | 24 | 8 | 2 | Week 2 | October 24 Week 2 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
2 | 2024-10-09 | October | 24 | 9 | 2 | Week 2 | October 24 Week 2 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
3 | 2024-10-10 | October | 24 | 10 | 2 | Week 2 | October 24 Week 2 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
4 | 2024-10-11 | October | 24 | 11 | 2 | Week 2 | October 24 Week 2 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
5 | 2024-10-12 | October | 24 | 12 | 2 | Week 2 | October 24 Week 2 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
6 | 2024-10-13 | October | 24 | 13 | 2 | Week 2 | October 24 Week 2 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
7 | 2024-10-14 | October | 24 | 14 | 2 | Week 2 | October 24 Week 2 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
1 | 2024-10-15 | October | 24 | 15 | 3 | Week 3 | October 24 Week 3 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
2 | 2024-10-16 | October | 24 | 16 | 3 | Week 3 | October 24 Week 3 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
3 | 2024-10-17 | October | 24 | 17 | 3 | Week 3 | October 24 Week 3 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
4 | 2024-10-18 | October | 24 | 18 | 3 | Week 3 | October 24 Week 3 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
5 | 2024-10-19 | October | 24 | 19 | 3 | Week 3 | October 24 Week 3 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
6 | 2024-10-20 | October | 24 | 20 | 3 | Week 3 | October 24 Week 3 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
7 | 2024-10-21 | October | 24 | 21 | 3 | Week 3 | October 24 Week 3 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
1 | 2024-10-22 | October | 24 | 22 | 4 | Week 4 | October 24 Week 4 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
2 | 2024-10-23 | October | 24 | 23 | 4 | Week 4 | October 24 Week 4 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
3 | 2024-10-24 | October | 24 | 24 | 4 | Week 4 | October 24 Week 4 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
4 | 2024-10-25 | October | 24 | 25 | 4 | Week 4 | October 24 Week 4 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
5 | 2024-10-26 | October | 24 | 26 | 4 | Week 4 | October 24 Week 4 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
6 | 2024-10-27 | October | 24 | 27 | 4 | Week 4 | October 24 Week 4 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
7 | 2024-10-28 | October | 24 | 28 | 4 | Week 4 | October 24 Week 4 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
1 | 2024-10-29 | October | 24 | 29 | 5 | Week 5 | October 24 Week 5 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
2 | 2024-10-30 | October | 24 | 30 | 5 | Week 5 | October 24 Week 5 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
3 | 2024-10-31 | October | 24 | 31 | 5 | Week 5 | October 24 Week 5 | OCTOBER 24 | PLANNED | OCTOBER 24 PLANNED
1 | 2024-11-01 | November | 24 | 1 | 1 | Week 1 | November 24 Week 1 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
2 | 2024-11-02 | November | 24 | 2 | 1 | Week 1 | November 24 Week 1 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
3 | 2024-11-03 | November | 24 | 3 | 1 | Week 1 | November 24 Week 1 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
4 | 2024-11-04 | November | 24 | 4 | 1 | Week 1 | November 24 Week 1 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
5 | 2024-11-05 | November | 24 | 5 | 1 | Week 1 | November 24 Week 1 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
6 | 2024-11-06 | November | 24 | 6 | 1 | Week 1 | November 24 Week 1 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
7 | 2024-11-07 | November | 24 | 7 | 1 | Week 1 | November 24 Week 1 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
1 | 2024-11-08 | November | 24 | 8 | 2 | Week 2 | November 24 Week 2 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
2 | 2024-11-09 | November | 24 | 9 | 2 | Week 2 | November 24 Week 2 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
3 | 2024-11-10 | November | 24 | 10 | 2 | Week 2 | November 24 Week 2 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
4 | 2024-11-11 | November | 24 | 11 | 2 | Week 2 | November 24 Week 2 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
5 | 2024-11-12 | November | 24 | 12 | 2 | Week 2 | November 24 Week 2 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
6 | 2024-11-13 | November | 24 | 13 | 2 | Week 2 | November 24 Week 2 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
7 | 2024-11-14 | November | 24 | 14 | 2 | Week 2 | November 24 Week 2 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
1 | 2024-11-15 | November | 24 | 15 | 3 | Week 3 | November 24 Week 3 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
2 | 2024-11-16 | November | 24 | 16 | 3 | Week 3 | November 24 Week 3 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
3 | 2024-11-17 | November | 24 | 17 | 3 | Week 3 | November 24 Week 3 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
4 | 2024-11-18 | November | 24 | 18 | 3 | Week 3 | November 24 Week 3 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
5 | 2024-11-19 | November | 24 | 19 | 3 | Week 3 | November 24 Week 3 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
6 | 2024-11-20 | November | 24 | 20 | 3 | Week 3 | November 24 Week 3 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
7 | 2024-11-21 | November | 24 | 21 | 3 | Week 3 | November 24 Week 3 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
1 | 2024-11-22 | November | 24 | 22 | 4 | Week 4 | November 24 Week 4 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
2 | 2024-11-23 | November | 24 | 23 | 4 | Week 4 | November 24 Week 4 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
3 | 2024-11-24 | November | 24 | 24 | 4 | Week 4 | November 24 Week 4 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
4 | 2024-11-25 | November | 24 | 25 | 4 | Week 4 | November 24 Week 4 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
5 | 2024-11-26 | November | 24 | 26 | 4 | Week 4 | November 24 Week 4 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
6 | 2024-11-27 | November | 24 | 27 | 4 | Week 4 | November 24 Week 4 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
7 | 2024-11-28 | November | 24 | 28 | 4 | Week 4 | November 24 Week 4 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
1 | 2024-11-29 | November | 24 | 29 | 5 | Week 5 | November 24 Week 5 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
2 | 2024-11-30 | November | 24 | 30 | 5 | Week 5 | November 24 Week 5 | NOVEMBER 24 | PLANNED | NOVEMBER 24 PLANNED
1 | 2024-12-01 | December | 24 | 1 | 1 | Week 1 | December 24 Week 1 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
2 | 2024-12-02 | December | 24 | 2 | 1 | Week 1 | December 24 Week 1 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
3 | 2024-12-03 | December | 24 | 3 | 1 | Week 1 | December 24 Week 1 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
4 | 2024-12-04 | December | 24 | 4 | 1 | Week 1 | December 24 Week 1 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
5 | 2024-12-05 | December | 24 | 5 | 1 | Week 1 | December 24 Week 1 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
6 | 2024-12-06 | December | 24 | 6 | 1 | Week 1 | December 24 Week 1 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
7 | 2024-12-07 | December | 24 | 7 | 1 | Week 1 | December 24 Week 1 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
1 | 2024-12-08 | December | 24 | 8 | 2 | Week 2 | December 24 Week 2 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
2 | 2024-12-09 | December | 24 | 9 | 2 | Week 2 | December 24 Week 2 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
3 | 2024-12-10 | December | 24 | 10 | 2 | Week 2 | December 24 Week 2 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
4 | 2024-12-11 | December | 24 | 11 | 2 | Week 2 | December 24 Week 2 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
5 | 2024-12-12 | December | 24 | 12 | 2 | Week 2 | December 24 Week 2 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
6 | 2024-12-13 | December | 24 | 13 | 2 | Week 2 | December 24 Week 2 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
7 | 2024-12-14 | December | 24 | 14 | 2 | Week 2 | December 24 Week 2 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
1 | 2024-12-15 | December | 24 | 15 | 3 | Week 3 | December 24 Week 3 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
2 | 2024-12-16 | December | 24 | 16 | 3 | Week 3 | December 24 Week 3 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
3 | 2024-12-17 | December | 24 | 17 | 3 | Week 3 | December 24 Week 3 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
4 | 2024-12-18 | December | 24 | 18 | 3 | Week 3 | December 24 Week 3 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
5 | 2024-12-19 | December | 24 | 19 | 3 | Week 3 | December 24 Week 3 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
6 | 2024-12-20 | December | 24 | 20 | 3 | Week 3 | December 24 Week 3 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
7 | 2024-12-21 | December | 24 | 21 | 3 | Week 3 | December 24 Week 3 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
1 | 2024-12-22 | December | 24 | 22 | 4 | Week 4 | December 24 Week 4 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
2 | 2024-12-23 | December | 24 | 23 | 4 | Week 4 | December 24 Week 4 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
3 | 2024-12-24 | December | 24 | 24 | 4 | Week 4 | December 24 Week 4 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
4 | 2024-12-25 | December | 24 | 25 | 4 | Week 4 | December 24 Week 4 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
5 | 2024-12-26 | December | 24 | 26 | 4 | Week 4 | December 24 Week 4 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
6 | 2024-12-27 | December | 24 | 27 | 4 | Week 4 | December 24 Week 4 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
7 | 2024-12-28 | December | 24 | 28 | 4 | Week 4 | December 24 Week 4 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
1 | 2024-12-29 | December | 24 | 29 | 5 | Week 5 | December 24 Week 5 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
2 | 2024-12-30 | December | 24 | 30 | 5 | Week 5 | December 24 Week 5 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
3 | 2024-12-31 | December | 24 | 31 | 5 | Week 5 | December 24 Week 5 | DECEMBER 24 | PLANNED | DECEMBER 24 PLANNED
1 | 2025-01-01 | January | 25 | 1 | 1 | Week 1 | January 25 Week 1 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
2 | 2025-01-02 | January | 25 | 2 | 1 | Week 1 | January 25 Week 1 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
3 | 2025-01-03 | January | 25 | 3 | 1 | Week 1 | January 25 Week 1 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
4 | 2025-01-04 | January | 25 | 4 | 1 | Week 1 | January 25 Week 1 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
5 | 2025-01-05 | January | 25 | 5 | 1 | Week 1 | January 25 Week 1 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
6 | 2025-01-06 | January | 25 | 6 | 1 | Week 1 | January 25 Week 1 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
7 | 2025-01-07 | January | 25 | 7 | 1 | Week 1 | January 25 Week 1 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
1 | 2025-01-08 | January | 25 | 8 | 2 | Week 2 | January 25 Week 2 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
2 | 2025-01-09 | January | 25 | 9 | 2 | Week 2 | January 25 Week 2 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
3 | 2025-01-10 | January | 25 | 10 | 2 | Week 2 | January 25 Week 2 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
4 | 2025-01-11 | January | 25 | 11 | 2 | Week 2 | January 25 Week 2 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
5 | 2025-01-12 | January | 25 | 12 | 2 | Week 2 | January 25 Week 2 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
6 | 2025-01-13 | January | 25 | 13 | 2 | Week 2 | January 25 Week 2 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
7 | 2025-01-14 | January | 25 | 14 | 2 | Week 2 | January 25 Week 2 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
1 | 2025-01-15 | January | 25 | 15 | 3 | Week 3 | January 25 Week 3 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
2 | 2025-01-16 | January | 25 | 16 | 3 | Week 3 | January 25 Week 3 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
3 | 2025-01-17 | January | 25 | 17 | 3 | Week 3 | January 25 Week 3 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
4 | 2025-01-18 | January | 25 | 18 | 3 | Week 3 | January 25 Week 3 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
5 | 2025-01-19 | January | 25 | 19 | 3 | Week 3 | January 25 Week 3 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
6 | 2025-01-20 | January | 25 | 20 | 3 | Week 3 | January 25 Week 3 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
7 | 2025-01-21 | January | 25 | 21 | 3 | Week 3 | January 25 Week 3 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
1 | 2025-01-22 | January | 25 | 22 | 4 | Week 4 | January 25 Week 4 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
2 | 2025-01-23 | January | 25 | 23 | 4 | Week 4 | January 25 Week 4 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
3 | 2025-01-24 | January | 25 | 24 | 4 | Week 4 | January 25 Week 4 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
4 | 2025-01-25 | January | 25 | 25 | 4 | Week 4 | January 25 Week 4 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
5 | 2025-01-26 | January | 25 | 26 | 4 | Week 4 | January 25 Week 4 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
6 | 2025-01-27 | January | 25 | 27 | 4 | Week 4 | January 25 Week 4 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
7 | 2025-01-28 | January | 25 | 28 | 4 | Week 4 | January 25 Week 4 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
1 | 2025-01-29 | January | 25 | 29 | 5 | Week 5 | January 25 Week 5 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
2 | 2025-01-30 | January | 25 | 30 | 5 | Week 5 | January 25 Week 5 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
3 | 2025-01-31 | January | 25 | 31 | 5 | Week 5 | January 25 Week 5 | JANUARY 25 | PLANNED | JANUARY 25 PLANNED
1 | 2025-02-01 | February | 25 | 1 | 1 | Week 1 | February 25 Week 1 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
2 | 2025-02-02 | February | 25 | 2 | 1 | Week 1 | February 25 Week 1 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
3 | 2025-02-03 | February | 25 | 3 | 1 | Week 1 | February 25 Week 1 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
4 | 2025-02-04 | February | 25 | 4 | 1 | Week 1 | February 25 Week 1 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
5 | 2025-02-05 | February | 25 | 5 | 1 | Week 1 | February 25 Week 1 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
6 | 2025-02-06 | February | 25 | 6 | 1 | Week 1 | February 25 Week 1 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
7 | 2025-02-07 | February | 25 | 7 | 1 | Week 1 | February 25 Week 1 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
1 | 2025-02-08 | February | 25 | 8 | 2 | Week 2 | February 25 Week 2 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
2 | 2025-02-09 | February | 25 | 9 | 2 | Week 2 | February 25 Week 2 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
3 | 2025-02-10 | February | 25 | 10 | 2 | Week 2 | February 25 Week 2 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
4 | 2025-02-11 | February | 25 | 11 | 2 | Week 2 | February 25 Week 2 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
5 | 2025-02-12 | February | 25 | 12 | 2 | Week 2 | February 25 Week 2 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
6 | 2025-02-13 | February | 25 | 13 | 2 | Week 2 | February 25 Week 2 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
7 | 2025-02-14 | February | 25 | 14 | 2 | Week 2 | February 25 Week 2 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
1 | 2025-02-15 | February | 25 | 15 | 3 | Week 3 | February 25 Week 3 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
2 | 2025-02-16 | February | 25 | 16 | 3 | Week 3 | February 25 Week 3 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
3 | 2025-02-17 | February | 25 | 17 | 3 | Week 3 | February 25 Week 3 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
4 | 2025-02-18 | February | 25 | 18 | 3 | Week 3 | February 25 Week 3 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
5 | 2025-02-19 | February | 25 | 19 | 3 | Week 3 | February 25 Week 3 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
6 | 2025-02-20 | February | 25 | 20 | 3 | Week 3 | February 25 Week 3 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
7 | 2025-02-21 | February | 25 | 21 | 3 | Week 3 | February 25 Week 3 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
1 | 2025-02-22 | February | 25 | 22 | 4 | Week 4 | February 25 Week 4 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
2 | 2025-02-23 | February | 25 | 23 | 4 | Week 4 | February 25 Week 4 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
3 | 2025-02-24 | February | 25 | 24 | 4 | Week 4 | February 25 Week 4 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
4 | 2025-02-25 | February | 25 | 25 | 4 | Week 4 | February 25 Week 4 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
5 | 2025-02-26 | February | 25 | 26 | 4 | Week 4 | February 25 Week 4 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
6 | 2025-02-27 | February | 25 | 27 | 4 | Week 4 | February 25 Week 4 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
7 | 2025-02-28 | February | 25 | 28 | 4 | Week 4 | February 25 Week 4 | FEBRUARY 25 | PLANNED | FEBRUARY 25 PLANNED
1 | 2025-03-01 | March | 25 | 1 | 1 | Week 1 | March 25 Week 1 | MARCH 25 | PLANNED | MARCH 25 PLANNED
2 | 2025-03-02 | March | 25 | 2 | 1 | Week 1 | March 25 Week 1 | MARCH 25 | PLANNED | MARCH 25 PLANNED
3 | 2025-03-03 | March | 25 | 3 | 1 | Week 1 | March 25 Week 1 | MARCH 25 | PLANNED | MARCH 25 PLANNED
4 | 2025-03-04 | March | 25 | 4 | 1 | Week 1 | March 25 Week 1 | MARCH 25 | PLANNED | MARCH 25 PLANNED
5 | 2025-03-05 | March | 25 | 5 | 1 | Week 1 | March 25 Week 1 | MARCH 25 | PLANNED | MARCH 25 PLANNED
6 | 2025-03-06 | March | 25 | 6 | 1 | Week 1 | March 25 Week 1 | MARCH 25 | PLANNED | MARCH 25 PLANNED
7 | 2025-03-07 | March | 25 | 7 | 1 | Week 1 | March 25 Week 1 | MARCH 25 | PLANNED | MARCH 25 PLANNED
1 | 2025-03-08 | March | 25 | 8 | 2 | Week 2 | March 25 Week 2 | MARCH 25 | PLANNED | MARCH 25 PLANNED
2 | 2025-03-09 | March | 25 | 9 | 2 | Week 2 | March 25 Week 2 | MARCH 25 | PLANNED | MARCH 25 PLANNED
3 | 2025-03-10 | March | 25 | 10 | 2 | Week 2 | March 25 Week 2 | MARCH 25 | PLANNED | MARCH 25 PLANNED
4 | 2025-03-11 | March | 25 | 11 | 2 | Week 2 | March 25 Week 2 | MARCH 25 | PLANNED | MARCH 25 PLANNED
5 | 2025-03-12 | March | 25 | 12 | 2 | Week 2 | March 25 Week 2 | MARCH 25 | PLANNED | MARCH 25 PLANNED
6 | 2025-03-13 | March | 25 | 13 | 2 | Week 2 | March 25 Week 2 | MARCH 25 | PLANNED | MARCH 25 PLANNED
7 | 2025-03-14 | March | 25 | 14 | 2 | Week 2 | March 25 Week 2 | MARCH 25 | PLANNED | MARCH 25 PLANNED
1 | 2025-03-15 | March | 25 | 15 | 3 | Week 3 | March 25 Week 3 | MARCH 25 | PLANNED | MARCH 25 PLANNED
2 | 2025-03-16 | March | 25 | 16 | 3 | Week 3 | March 25 Week 3 | MARCH 25 | PLANNED | MARCH 25 PLANNED
3 | 2025-03-17 | March | 25 | 17 | 3 | Week 3 | March 25 Week 3 | MARCH 25 | PLANNED | MARCH 25 PLANNED
4 | 2025-03-18 | March | 25 | 18 | 3 | Week 3 | March 25 Week 3 | MARCH 25 | PLANNED | MARCH 25 PLANNED
5 | 2025-03-19 | March | 25 | 19 | 3 | Week 3 | March 25 Week 3 | MARCH 25 | PLANNED | MARCH 25 PLANNED
6 | 2025-03-20 | March | 25 | 20 | 3 | Week 3 | March 25 Week 3 | MARCH 25 | PLANNED | MARCH 25 PLANNED
7 | 2025-03-21 | March | 25 | 21 | 3 | Week 3 | March 25 Week 3 | MARCH 25 | PLANNED | MARCH 25 PLANNED
1 | 2025-03-22 | March | 25 | 22 | 4 | Week 4 | March 25 Week 4 | MARCH 25 | PLANNED | MARCH 25 PLANNED
2 | 2025-03-23 | March | 25 | 23 | 4 | Week 4 | March 25 Week 4 | MARCH 25 | PLANNED | MARCH 25 PLANNED
3 | 2025-03-24 | March | 25 | 24 | 4 | Week 4 | March 25 Week 4 | MARCH 25 | PLANNED | MARCH 25 PLANNED
4 | 2025-03-25 | March | 25 | 25 | 4 | Week 4 | March 25 Week 4 | MARCH 25 | PLANNED | MARCH 25 PLANNED
5 | 2025-03-26 | March | 25 | 26 | 4 | Week 4 | March 25 Week 4 | MARCH 25 | PLANNED | MARCH 25 PLANNED
6 | 2025-03-27 | March | 25 | 27 | 4 | Week 4 | March 25 Week 4 | MARCH 25 | PLANNED | MARCH 25 PLANNED
7 | 2025-03-28 | March | 25 | 28 | 4 | Week 4 | March 25 Week 4 | MARCH 25 | PLANNED | MARCH 25 PLANNED
1 | 2025-03-29 | March | 25 | 29 | 5 | Week 5 | March 25 Week 5 | MARCH 25 | PLANNED | MARCH 25 PLANNED
2 | 2025-03-30 | March | 25 | 30 | 5 | Week 5 | March 25 Week 5 | MARCH 25 | PLANNED | MARCH 25 PLANNED
3 | 2025-03-31 | March | 25 | 31 | 5 | Week 5 | March 25 Week 5 | MARCH 25 | PLANNED | MARCH 25 PLANNED
1 | 2025-04-01 | April | 25 | 1 | 1 | Week 1 | April 25 Week 1 | APRIL 25 | PLANNED | APRIL 25 PLANNED
2 | 2025-04-02 | April | 25 | 2 | 1 | Week 1 | April 25 Week 1 | APRIL 25 | PLANNED | APRIL 25 PLANNED
3 | 2025-04-03 | April | 25 | 3 | 1 | Week 1 | April 25 Week 1 | APRIL 25 | PLANNED | APRIL 25 PLANNED
4 | 2025-04-04 | April | 25 | 4 | 1 | Week 1 | April 25 Week 1 | APRIL 25 | PLANNED | APRIL 25 PLANNED
5 | 2025-04-05 | April | 25 | 5 | 1 | Week 1 | April 25 Week 1 | APRIL 25 | PLANNED | APRIL 25 PLANNED
6 | 2025-04-06 | April | 25 | 6 | 1 | Week 1 | April 25 Week 1 | APRIL 25 | PLANNED | APRIL 25 PLANNED
7 | 2025-04-07 | April | 25 | 7 | 1 | Week 1 | April 25 Week 1 | APRIL 25 | PLANNED | APRIL 25 PLANNED
1 | 2025-04-08 | April | 25 | 8 | 2 | Week 2 | April 25 Week 2 | APRIL 25 | PLANNED | APRIL 25 PLANNED
2 | 2025-04-09 | April | 25 | 9 | 2 | Week 2 | April 25 Week 2 | APRIL 25 | PLANNED | APRIL 25 PLANNED
3 | 2025-04-10 | April | 25 | 10 | 2 | Week 2 | April 25 Week 2 | APRIL 25 | PLANNED | APRIL 25 PLANNED
4 | 2025-04-11 | April | 25 | 11 | 2 | Week 2 | April 25 Week 2 | APRIL 25 | PLANNED | APRIL 25 PLANNED
5 | 2025-04-12 | April | 25 | 12 | 2 | Week 2 | April 25 Week 2 | APRIL 25 | PLANNED | APRIL 25 PLANNED
6 | 2025-04-13 | April | 25 | 13 | 2 | Week 2 | April 25 Week 2 | APRIL 25 | PLANNED | APRIL 25 PLANNED
7 | 2025-04-14 | April | 25 | 14 | 2 | Week 2 | April 25 Week 2 | APRIL 25 | PLANNED | APRIL 25 PLANNED
1 | 2025-04-15 | April | 25 | 15 | 3 | Week 3 | April 25 Week 3 | APRIL 25 | PLANNED | APRIL 25 PLANNED
2 | 2025-04-16 | April | 25 | 16 | 3 | Week 3 | April 25 Week 3 | APRIL 25 | PLANNED | APRIL 25 PLANNED
3 | 2025-04-17 | April | 25 | 17 | 3 | Week 3 | April 25 Week 3 | APRIL 25 | PLANNED | APRIL 25 PLANNED
4 | 2025-04-18 | April | 25 | 18 | 3 | Week 3 | April 25 Week 3 | APRIL 25 | PLANNED | APRIL 25 PLANNED
5 | 2025-04-19 | April | 25 | 19 | 3 | Week 3 | April 25 Week 3 | APRIL 25 | PLANNED | APRIL 25 PLANNED
6 | 2025-04-20 | April | 25 | 20 | 3 | Week 3 | April 25 Week 3 | APRIL 25 | PLANNED | APRIL 25 PLANNED
7 | 2025-04-21 | April | 25 | 21 | 3 | Week 3 | April 25 Week 3 | APRIL 25 | PLANNED | APRIL 25 PLANNED
1 | 2025-04-22 | April | 25 | 22 | 4 | Week 4 | April 25 Week 4 | APRIL 25 | PLANNED | APRIL 25 PLANNED
2 | 2025-04-23 | April | 25 | 23 | 4 | Week 4 | April 25 Week 4 | APRIL 25 | PLANNED | APRIL 25 PLANNED
3 | 2025-04-24 | April | 25 | 24 | 4 | Week 4 | April 25 Week 4 | APRIL 25 | PLANNED | APRIL 25 PLANNED
4 | 2025-04-25 | April | 25 | 25 | 4 | Week 4 | April 25 Week 4 | APRIL 25 | PLANNED | APRIL 25 PLANNED
5 | 2025-04-26 | April | 25 | 26 | 4 | Week 4 | April 25 Week 4 | APRIL 25 | PLANNED | APRIL 25 PLANNED
6 | 2025-04-27 | April | 25 | 27 | 4 | Week 4 | April 25 Week 4 | APRIL 25 | PLANNED | APRIL 25 PLANNED
7 | 2025-04-28 | April | 25 | 28 | 4 | Week 4 | April 25 Week 4 | APRIL 25 | PLANNED | APRIL 25 PLANNED
1 | 2025-04-29 | April | 25 | 29 | 5 | Week 5 | April 25 Week 5 | APRIL 25 | PLANNED | APRIL 25 PLANNED
2 | 2025-04-30 | April | 25 | 30 | 5 | Week 5 | April 25 Week 5 | APRIL 25 | PLANNED | APRIL 25 PLANNED
1 | 2025-05-01 | May | 25 | 1 | 1 | Week 1 | May 25 Week 1 | MAY 25 | PLANNED | MAY 25 PLANNED
2 | 2025-05-02 | May | 25 | 2 | 1 | Week 1 | May 25 Week 1 | MAY 25 | PLANNED | MAY 25 PLANNED
3 | 2025-05-03 | May | 25 | 3 | 1 | Week 1 | May 25 Week 1 | MAY 25 | PLANNED | MAY 25 PLANNED
4 | 2025-05-04 | May | 25 | 4 | 1 | Week 1 | May 25 Week 1 | MAY 25 | PLANNED | MAY 25 PLANNED
5 | 2025-05-05 | May | 25 | 5 | 1 | Week 1 | May 25 Week 1 | MAY 25 | PLANNED | MAY 25 PLANNED
6 | 2025-05-06 | May | 25 | 6 | 1 | Week 1 | May 25 Week 1 | MAY 25 | PLANNED | MAY 25 PLANNED
7 | 2025-05-07 | May | 25 | 7 | 1 | Week 1 | May 25 Week 1 | MAY 25 | PLANNED | MAY 25 PLANNED
1 | 2025-05-08 | May | 25 | 8 | 2 | Week 2 | May 25 Week 2 | MAY 25 | PLANNED | MAY 25 PLANNED
2 | 2025-05-09 | May | 25 | 9 | 2 | Week 2 | May 25 Week 2 | MAY 25 | PLANNED | MAY 25 PLANNED
3 | 2025-05-10 | May | 25 | 10 | 2 | Week 2 | May 25 Week 2 | MAY 25 | PLANNED | MAY 25 PLANNED
4 | 2025-05-11 | May | 25 | 11 | 2 | Week 2 | May 25 Week 2 | MAY 25 | PLANNED | MAY 25 PLANNED
5 | 2025-05-12 | May | 25 | 12 | 2 | Week 2 | May 25 Week 2 | MAY 25 | PLANNED | MAY 25 PLANNED
6 | 2025-05-13 | May | 25 | 13 | 2 | Week 2 | May 25 Week 2 | MAY 25 | PLANNED | MAY 25 PLANNED
7 | 2025-05-14 | May | 25 | 14 | 2 | Week 2 | May 25 Week 2 | MAY 25 | PLANNED | MAY 25 PLANNED
1 | 2025-05-15 | May | 25 | 15 | 3 | Week 3 | May 25 Week 3 | MAY 25 | PLANNED | MAY 25 PLANNED
2 | 2025-05-16 | May | 25 | 16 | 3 | Week 3 | May 25 Week 3 | MAY 25 | PLANNED | MAY 25 PLANNED
3 | 2025-05-17 | May | 25 | 17 | 3 | Week 3 | May 25 Week 3 | MAY 25 | PLANNED | MAY 25 PLANNED
4 | 2025-05-18 | May | 25 | 18 | 3 | Week 3 | May 25 Week 3 | MAY 25 | PLANNED | MAY 25 PLANNED
5 | 2025-05-19 | May | 25 | 19 | 3 | Week 3 | May 25 Week 3 | MAY 25 | PLANNED | MAY 25 PLANNED
6 | 2025-05-20 | May | 25 | 20 | 3 | Week 3 | May 25 Week 3 | MAY 25 | PLANNED | MAY 25 PLANNED
7 | 2025-05-21 | May | 25 | 21 | 3 | Week 3 | May 25 Week 3 | MAY 25 | PLANNED | MAY 25 PLANNED
1 | 2025-05-22 | May | 25 | 22 | 4 | Week 4 | May 25 Week 4 | MAY 25 | PLANNED | MAY 25 PLANNED
2 | 2025-05-23 | May | 25 | 23 | 4 | Week 4 | May 25 Week 4 | MAY 25 | PLANNED | MAY 25 PLANNED
3 | 2025-05-24 | May | 25 | 24 | 4 | Week 4 | May 25 Week 4 | MAY 25 | PLANNED | MAY 25 PLANNED
4 | 2025-05-25 | May | 25 | 25 | 4 | Week 4 | May 25 Week 4 | MAY 25 | PLANNED | MAY 25 PLANNED
5 | 2025-05-26 | May | 25 | 26 | 4 | Week 4 | May 25 Week 4 | MAY 25 | PLANNED | MAY 25 PLANNED
6 | 2025-05-27 | May | 25 | 27 | 4 | Week 4 | May 25 Week 4 | MAY 25 | PLANNED | MAY 25 PLANNED
7 | 2025-05-28 | May | 25 | 28 | 4 | Week 4 | May 25 Week 4 | MAY 25 | PLANNED | MAY 25 PLANNED
1 | 2025-05-29 | May | 25 | 29 | 5 | Week 5 | May 25 Week 5 | MAY 25 | PLANNED | MAY 25 PLANNED
2 | 2025-05-30 | May | 25 | 30 | 5 | Week 5 | May 25 Week 5 | MAY 25 | PLANNED | MAY 25 PLANNED
3 | 2025-05-31 | May | 25 | 31 | 5 | Week 5 | May 25 Week 5 | MAY 25 | PLANNED | MAY 25 PLANNED
1 | 2025-06-01 | June | 25 | 1 | 1 | Week 1 | June 25 Week 1 | JUNE 25 | PLANNED | JUNE 25 PLANNED
2 | 2025-06-02 | June | 25 | 2 | 1 | Week 1 | June 25 Week 1 | JUNE 25 | PLANNED | JUNE 25 PLANNED
3 | 2025-06-03 | June | 25 | 3 | 1 | Week 1 | June 25 Week 1 | JUNE 25 | PLANNED | JUNE 25 PLANNED
4 | 2025-06-04 | June | 25 | 4 | 1 | Week 1 | June 25 Week 1 | JUNE 25 | PLANNED | JUNE 25 PLANNED
5 | 2025-06-05 | June | 25 | 5 | 1 | Week 1 | June 25 Week 1 | JUNE 25 | PLANNED | JUNE 25 PLANNED
6 | 2025-06-06 | June | 25 | 6 | 1 | Week 1 | June 25 Week 1 | JUNE 25 | PLANNED | JUNE 25 PLANNED
7 | 2025-06-07 | June | 25 | 7 | 1 | Week 1 | June 25 Week 1 | JUNE 25 | PLANNED | JUNE 25 PLANNED
1 | 2025-06-08 | June | 25 | 8 | 2 | Week 2 | June 25 Week 2 | JUNE 25 | PLANNED | JUNE 25 PLANNED
2 | 2025-06-09 | June | 25 | 9 | 2 | Week 2 | June 25 Week 2 | JUNE 25 | PLANNED | JUNE 25 PLANNED
3 | 2025-06-10 | June | 25 | 10 | 2 | Week 2 | June 25 Week 2 | JUNE 25 | PLANNED | JUNE 25 PLANNED
4 | 2025-06-11 | June | 25 | 11 | 2 | Week 2 | June 25 Week 2 | JUNE 25 | PLANNED | JUNE 25 PLANNED
5 | 2025-06-12 | June | 25 | 12 | 2 | Week 2 | June 25 Week 2 | JUNE 25 | PLANNED | JUNE 25 PLANNED
6 | 2025-06-13 | June | 25 | 13 | 2 | Week 2 | June 25 Week 2 | JUNE 25 | PLANNED | JUNE 25 PLANNED
7 | 2025-06-14 | June | 25 | 14 | 2 | Week 2 | June 25 Week 2 | JUNE 25 | PLANNED | JUNE 25 PLANNED
1 | 2025-06-15 | June | 25 | 15 | 3 | Week 3 | June 25 Week 3 | JUNE 25 | PLANNED | JUNE 25 PLANNED
2 | 2025-06-16 | June | 25 | 16 | 3 | Week 3 | June 25 Week 3 | JUNE 25 | PLANNED | JUNE 25 PLANNED
3 | 2025-06-17 | June | 25 | 17 | 3 | Week 3 | June 25 Week 3 | JUNE 25 | PLANNED | JUNE 25 PLANNED
4 | 2025-06-18 | June | 25 | 18 | 3 | Week 3 | June 25 Week 3 | JUNE 25 | PLANNED | JUNE 25 PLANNED
5 | 2025-06-19 | June | 25 | 19 | 3 | Week 3 | June 25 Week 3 | JUNE 25 | PLANNED | JUNE 25 PLANNED
6 | 2025-06-20 | June | 25 | 20 | 3 | Week 3 | June 25 Week 3 | JUNE 25 | PLANNED | JUNE 25 PLANNED
7 | 2025-06-21 | June | 25 | 21 | 3 | Week 3 | June 25 Week 3 | JUNE 25 | PLANNED | JUNE 25 PLANNED
1 | 2025-06-22 | June | 25 | 22 | 4 | Week 4 | June 25 Week 4 | JUNE 25 | PLANNED | JUNE 25 PLANNED
2 | 2025-06-23 | June | 25 | 23 | 4 | Week 4 | June 25 Week 4 | JUNE 25 | PLANNED | JUNE 25 PLANNED
3 | 2025-06-24 | June | 25 | 24 | 4 | Week 4 | June 25 Week 4 | JUNE 25 | PLANNED | JUNE 25 PLANNED
4 | 2025-06-25 | June | 25 | 25 | 4 | Week 4 | June 25 Week 4 | JUNE 25 | PLANNED | JUNE 25 PLANNED
5 | 2025-06-26 | June | 25 | 26 | 4 | Week 4 | June 25 Week 4 | JUNE 25 | PLANNED | JUNE 25 PLANNED
6 | 2025-06-27 | June | 25 | 27 | 4 | Week 4 | June 25 Week 4 | JUNE 25 | PLANNED | JUNE 25 PLANNED
7 | 2025-06-28 | June | 25 | 28 | 4 | Week 4 | June 25 Week 4 | JUNE 25 | PLANNED | JUNE 25 PLANNED
1 | 2025-06-29 | June | 25 | 29 | 5 | Week 5 | June 25 Week 5 | JUNE 25 | PLANNED | JUNE 25 PLANNED
2 | 2025-06-30 | June | 25 | 30 | 5 | Week 5 | June 25 Week 5 | JUNE 25 | PLANNED | JUNE 25 PLANNED
1 | 2025-07-01 | July | 25 | 1 | 1 | Week 1 | July 25 Week 1 | JULY 25 | PLANNED | JULY 25 PLANNED
2 | 2025-07-02 | July | 25 | 2 | 1 | Week 1 | July 25 Week 1 | JULY 25 | PLANNED | JULY 25 PLANNED
3 | 2025-07-03 | July | 25 | 3 | 1 | Week 1 | July 25 Week 1 | JULY 25 | PLANNED | JULY 25 PLANNED
4 | 2025-07-04 | July | 25 | 4 | 1 | Week 1 | July 25 Week 1 | JULY 25 | PLANNED | JULY 25 PLANNED
5 | 2025-07-05 | July | 25 | 5 | 1 | Week 1 | July 25 Week 1 | JULY 25 | PLANNED | JULY 25 PLANNED
6 | 2025-07-06 | July | 25 | 6 | 1 | Week 1 | July 25 Week 1 | JULY 25 | PLANNED | JULY 25 PLANNED
7 | 2025-07-07 | July | 25 | 7 | 1 | Week 1 | July 25 Week 1 | JULY 25 | PLANNED | JULY 25 PLANNED
1 | 2025-07-08 | July | 25 | 8 | 2 | Week 2 | July 25 Week 2 | JULY 25 | PLANNED | JULY 25 PLANNED
2 | 2025-07-09 | July | 25 | 9 | 2 | Week 2 | July 25 Week 2 | JULY 25 | PLANNED | JULY 25 PLANNED
3 | 2025-07-10 | July | 25 | 10 | 2 | Week 2 | July 25 Week 2 | JULY 25 | PLANNED | JULY 25 PLANNED
4 | 2025-07-11 | July | 25 | 11 | 2 | Week 2 | July 25 Week 2 | JULY 25 | PLANNED | JULY 25 PLANNED
5 | 2025-07-12 | July | 25 | 12 | 2 | Week 2 | July 25 Week 2 | JULY 25 | PLANNED | JULY 25 PLANNED
6 | 2025-07-13 | July | 25 | 13 | 2 | Week 2 | July 25 Week 2 | JULY 25 | PLANNED | JULY 25 PLANNED
7 | 2025-07-14 | July | 25 | 14 | 2 | Week 2 | July 25 Week 2 | JULY 25 | PLANNED | JULY 25 PLANNED
1 | 2025-07-15 | July | 25 | 15 | 3 | Week 3 | July 25 Week 3 | JULY 25 | PLANNED | JULY 25 PLANNED
2 | 2025-07-16 | July | 25 | 16 | 3 | Week 3 | July 25 Week 3 | JULY 25 | PLANNED | JULY 25 PLANNED
3 | 2025-07-17 | July | 25 | 17 | 3 | Week 3 | July 25 Week 3 | JULY 25 | PLANNED | JULY 25 PLANNED
4 | 2025-07-18 | July | 25 | 18 | 3 | Week 3 | July 25 Week 3 | JULY 25 | PLANNED | JULY 25 PLANNED
5 | 2025-07-19 | July | 25 | 19 | 3 | Week 3 | July 25 Week 3 | JULY 25 | PLANNED | JULY 25 PLANNED
6 | 2025-07-20 | July | 25 | 20 | 3 | Week 3 | July 25 Week 3 | JULY 25 | PLANNED | JULY 25 PLANNED
7 | 2025-07-21 | July | 25 | 21 | 3 | Week 3 | July 25 Week 3 | JULY 25 | PLANNED | JULY 25 PLANNED
1 | 2025-07-22 | July | 25 | 22 | 4 | Week 4 | July 25 Week 4 | JULY 25 | PLANNED | JULY 25 PLANNED
2 | 2025-07-23 | July | 25 | 23 | 4 | Week 4 | July 25 Week 4 | JULY 25 | PLANNED | JULY 25 PLANNED
3 | 2025-07-24 | July | 25 | 24 | 4 | Week 4 | July 25 Week 4 | JULY 25 | PLANNED | JULY 25 PLANNED
4 | 2025-07-25 | July | 25 | 25 | 4 | Week 4 | July 25 Week 4 | JULY 25 | PLANNED | JULY 25 PLANNED
5 | 2025-07-26 | July | 25 | 26 | 4 | Week 4 | July 25 Week 4 | JULY 25 | PLANNED | JULY 25 PLANNED
6 | 2025-07-27 | July | 25 | 27 | 4 | Week 4 | July 25 Week 4 | JULY 25 | PLANNED | JULY 25 PLANNED
7 | 2025-07-28 | July | 25 | 28 | 4 | Week 4 | July 25 Week 4 | JULY 25 | PLANNED | JULY 25 PLANNED
1 | 2025-07-29 | July | 25 | 29 | 5 | Week 5 | July 25 Week 5 | JULY 25 | PLANNED | JULY 25 PLANNED
2 | 2025-07-30 | July | 25 | 30 | 5 | Week 5 | July 25 Week 5 | JULY 25 | PLANNED | JULY 25 PLANNED
3 | 2025-07-31 | July | 25 | 31 | 5 | Week 5 | July 25 Week 5 | JULY 25 | PLANNED | JULY 25 PLANNED
1 | 2025-08-01 | August | 25 | 1 | 1 | Week 1 | August 25 Week 1 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
2 | 2025-08-02 | August | 25 | 2 | 1 | Week 1 | August 25 Week 1 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
3 | 2025-08-03 | August | 25 | 3 | 1 | Week 1 | August 25 Week 1 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
4 | 2025-08-04 | August | 25 | 4 | 1 | Week 1 | August 25 Week 1 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
5 | 2025-08-05 | August | 25 | 5 | 1 | Week 1 | August 25 Week 1 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
6 | 2025-08-06 | August | 25 | 6 | 1 | Week 1 | August 25 Week 1 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
7 | 2025-08-07 | August | 25 | 7 | 1 | Week 1 | August 25 Week 1 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
1 | 2025-08-08 | August | 25 | 8 | 2 | Week 2 | August 25 Week 2 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
2 | 2025-08-09 | August | 25 | 9 | 2 | Week 2 | August 25 Week 2 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
3 | 2025-08-10 | August | 25 | 10 | 2 | Week 2 | August 25 Week 2 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
4 | 2025-08-11 | August | 25 | 11 | 2 | Week 2 | August 25 Week 2 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
5 | 2025-08-12 | August | 25 | 12 | 2 | Week 2 | August 25 Week 2 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
6 | 2025-08-13 | August | 25 | 13 | 2 | Week 2 | August 25 Week 2 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
7 | 2025-08-14 | August | 25 | 14 | 2 | Week 2 | August 25 Week 2 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
1 | 2025-08-15 | August | 25 | 15 | 3 | Week 3 | August 25 Week 3 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
2 | 2025-08-16 | August | 25 | 16 | 3 | Week 3 | August 25 Week 3 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
3 | 2025-08-17 | August | 25 | 17 | 3 | Week 3 | August 25 Week 3 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
4 | 2025-08-18 | August | 25 | 18 | 3 | Week 3 | August 25 Week 3 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
5 | 2025-08-19 | August | 25 | 19 | 3 | Week 3 | August 25 Week 3 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
6 | 2025-08-20 | August | 25 | 20 | 3 | Week 3 | August 25 Week 3 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
7 | 2025-08-21 | August | 25 | 21 | 3 | Week 3 | August 25 Week 3 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
1 | 2025-08-22 | August | 25 | 22 | 4 | Week 4 | August 25 Week 4 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
2 | 2025-08-23 | August | 25 | 23 | 4 | Week 4 | August 25 Week 4 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
3 | 2025-08-24 | August | 25 | 24 | 4 | Week 4 | August 25 Week 4 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
4 | 2025-08-25 | August | 25 | 25 | 4 | Week 4 | August 25 Week 4 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
5 | 2025-08-26 | August | 25 | 26 | 4 | Week 4 | August 25 Week 4 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
6 | 2025-08-27 | August | 25 | 27 | 4 | Week 4 | August 25 Week 4 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
7 | 2025-08-28 | August | 25 | 28 | 4 | Week 4 | August 25 Week 4 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
1 | 2025-08-29 | August | 25 | 29 | 5 | Week 5 | August 25 Week 5 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
2 | 2025-08-30 | August | 25 | 30 | 5 | Week 5 | August 25 Week 5 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
3 | 2025-08-31 | August | 25 | 31 | 5 | Week 5 | August 25 Week 5 | AUGUST 25 | PLANNED | AUGUST 25 PLANNED
1 | 2025-09-01 | September | 25 | 1 | 1 | Week 1 | September 25 Week 1 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
2 | 2025-09-02 | September | 25 | 2 | 1 | Week 1 | September 25 Week 1 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
3 | 2025-09-03 | September | 25 | 3 | 1 | Week 1 | September 25 Week 1 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
4 | 2025-09-04 | September | 25 | 4 | 1 | Week 1 | September 25 Week 1 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
5 | 2025-09-05 | September | 25 | 5 | 1 | Week 1 | September 25 Week 1 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
6 | 2025-09-06 | September | 25 | 6 | 1 | Week 1 | September 25 Week 1 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
7 | 2025-09-07 | September | 25 | 7 | 1 | Week 1 | September 25 Week 1 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
1 | 2025-09-08 | September | 25 | 8 | 2 | Week 2 | September 25 Week 2 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
2 | 2025-09-09 | September | 25 | 9 | 2 | Week 2 | September 25 Week 2 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
3 | 2025-09-10 | September | 25 | 10 | 2 | Week 2 | September 25 Week 2 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
4 | 2025-09-11 | September | 25 | 11 | 2 | Week 2 | September 25 Week 2 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
5 | 2025-09-12 | September | 25 | 12 | 2 | Week 2 | September 25 Week 2 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
6 | 2025-09-13 | September | 25 | 13 | 2 | Week 2 | September 25 Week 2 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
7 | 2025-09-14 | September | 25 | 14 | 2 | Week 2 | September 25 Week 2 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
1 | 2025-09-15 | September | 25 | 15 | 3 | Week 3 | September 25 Week 3 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
2 | 2025-09-16 | September | 25 | 16 | 3 | Week 3 | September 25 Week 3 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
3 | 2025-09-17 | September | 25 | 17 | 3 | Week 3 | September 25 Week 3 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
4 | 2025-09-18 | September | 25 | 18 | 3 | Week 3 | September 25 Week 3 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
5 | 2025-09-19 | September | 25 | 19 | 3 | Week 3 | September 25 Week 3 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
6 | 2025-09-20 | September | 25 | 20 | 3 | Week 3 | September 25 Week 3 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
7 | 2025-09-21 | September | 25 | 21 | 3 | Week 3 | September 25 Week 3 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
1 | 2025-09-22 | September | 25 | 22 | 4 | Week 4 | September 25 Week 4 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
2 | 2025-09-23 | September | 25 | 23 | 4 | Week 4 | September 25 Week 4 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
3 | 2025-09-24 | September | 25 | 24 | 4 | Week 4 | September 25 Week 4 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
4 | 2025-09-25 | September | 25 | 25 | 4 | Week 4 | September 25 Week 4 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
5 | 2025-09-26 | September | 25 | 26 | 4 | Week 4 | September 25 Week 4 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
6 | 2025-09-27 | September | 25 | 27 | 4 | Week 4 | September 25 Week 4 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
7 | 2025-09-28 | September | 25 | 28 | 4 | Week 4 | September 25 Week 4 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
1 | 2025-09-29 | September | 25 | 29 | 5 | Week 5 | September 25 Week 5 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
2 | 2025-09-30 | September | 25 | 30 | 5 | Week 5 | September 25 Week 5 | SEPTEMBER 25 | PLANNED | SEPTEMBER 25 PLANNED
1 | 2025-10-01 | October | 25 | 1 | 1 | Week 1 | October 25 Week 1 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
2 | 2025-10-02 | October | 25 | 2 | 1 | Week 1 | October 25 Week 1 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
3 | 2025-10-03 | October | 25 | 3 | 1 | Week 1 | October 25 Week 1 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
4 | 2025-10-04 | October | 25 | 4 | 1 | Week 1 | October 25 Week 1 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
5 | 2025-10-05 | October | 25 | 5 | 1 | Week 1 | October 25 Week 1 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
6 | 2025-10-06 | October | 25 | 6 | 1 | Week 1 | October 25 Week 1 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
7 | 2025-10-07 | October | 25 | 7 | 1 | Week 1 | October 25 Week 1 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
1 | 2025-10-08 | October | 25 | 8 | 2 | Week 2 | October 25 Week 2 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
2 | 2025-10-09 | October | 25 | 9 | 2 | Week 2 | October 25 Week 2 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
3 | 2025-10-10 | October | 25 | 10 | 2 | Week 2 | October 25 Week 2 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
4 | 2025-10-11 | October | 25 | 11 | 2 | Week 2 | October 25 Week 2 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
5 | 2025-10-12 | October | 25 | 12 | 2 | Week 2 | October 25 Week 2 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
6 | 2025-10-13 | October | 25 | 13 | 2 | Week 2 | October 25 Week 2 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
7 | 2025-10-14 | October | 25 | 14 | 2 | Week 2 | October 25 Week 2 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
1 | 2025-10-15 | October | 25 | 15 | 3 | Week 3 | October 25 Week 3 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
2 | 2025-10-16 | October | 25 | 16 | 3 | Week 3 | October 25 Week 3 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
3 | 2025-10-17 | October | 25 | 17 | 3 | Week 3 | October 25 Week 3 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
4 | 2025-10-18 | October | 25 | 18 | 3 | Week 3 | October 25 Week 3 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
5 | 2025-10-19 | October | 25 | 19 | 3 | Week 3 | October 25 Week 3 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
6 | 2025-10-20 | October | 25 | 20 | 3 | Week 3 | October 25 Week 3 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
7 | 2025-10-21 | October | 25 | 21 | 3 | Week 3 | October 25 Week 3 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
1 | 2025-10-22 | October | 25 | 22 | 4 | Week 4 | October 25 Week 4 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
2 | 2025-10-23 | October | 25 | 23 | 4 | Week 4 | October 25 Week 4 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
3 | 2025-10-24 | October | 25 | 24 | 4 | Week 4 | October 25 Week 4 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
4 | 2025-10-25 | October | 25 | 25 | 4 | Week 4 | October 25 Week 4 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
5 | 2025-10-26 | October | 25 | 26 | 4 | Week 4 | October 25 Week 4 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
6 | 2025-10-27 | October | 25 | 27 | 4 | Week 4 | October 25 Week 4 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
7 | 2025-10-28 | October | 25 | 28 | 4 | Week 4 | October 25 Week 4 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
1 | 2025-10-29 | October | 25 | 29 | 5 | Week 5 | October 25 Week 5 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
2 | 2025-10-30 | October | 25 | 30 | 5 | Week 5 | October 25 Week 5 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
3 | 2025-10-31 | October | 25 | 31 | 5 | Week 5 | October 25 Week 5 | OCTOBER 25 | PLANNED | OCTOBER 25 PLANNED
1 | 2025-11-01 | November | 25 | 1 | 1 | Week 1 | November 25 Week 1 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
2 | 2025-11-02 | November | 25 | 2 | 1 | Week 1 | November 25 Week 1 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
3 | 2025-11-03 | November | 25 | 3 | 1 | Week 1 | November 25 Week 1 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
4 | 2025-11-04 | November | 25 | 4 | 1 | Week 1 | November 25 Week 1 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
5 | 2025-11-05 | November | 25 | 5 | 1 | Week 1 | November 25 Week 1 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
6 | 2025-11-06 | November | 25 | 6 | 1 | Week 1 | November 25 Week 1 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
7 | 2025-11-07 | November | 25 | 7 | 1 | Week 1 | November 25 Week 1 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
1 | 2025-11-08 | November | 25 | 8 | 2 | Week 2 | November 25 Week 2 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
2 | 2025-11-09 | November | 25 | 9 | 2 | Week 2 | November 25 Week 2 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
3 | 2025-11-10 | November | 25 | 10 | 2 | Week 2 | November 25 Week 2 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
4 | 2025-11-11 | November | 25 | 11 | 2 | Week 2 | November 25 Week 2 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
5 | 2025-11-12 | November | 25 | 12 | 2 | Week 2 | November 25 Week 2 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
6 | 2025-11-13 | November | 25 | 13 | 2 | Week 2 | November 25 Week 2 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
7 | 2025-11-14 | November | 25 | 14 | 2 | Week 2 | November 25 Week 2 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
1 | 2025-11-15 | November | 25 | 15 | 3 | Week 3 | November 25 Week 3 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
2 | 2025-11-16 | November | 25 | 16 | 3 | Week 3 | November 25 Week 3 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
3 | 2025-11-17 | November | 25 | 17 | 3 | Week 3 | November 25 Week 3 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
4 | 2025-11-18 | November | 25 | 18 | 3 | Week 3 | November 25 Week 3 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
5 | 2025-11-19 | November | 25 | 19 | 3 | Week 3 | November 25 Week 3 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
6 | 2025-11-20 | November | 25 | 20 | 3 | Week 3 | November 25 Week 3 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
7 | 2025-11-21 | November | 25 | 21 | 3 | Week 3 | November 25 Week 3 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
1 | 2025-11-22 | November | 25 | 22 | 4 | Week 4 | November 25 Week 4 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
2 | 2025-11-23 | November | 25 | 23 | 4 | Week 4 | November 25 Week 4 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
3 | 2025-11-24 | November | 25 | 24 | 4 | Week 4 | November 25 Week 4 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
4 | 2025-11-25 | November | 25 | 25 | 4 | Week 4 | November 25 Week 4 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
5 | 2025-11-26 | November | 25 | 26 | 4 | Week 4 | November 25 Week 4 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
6 | 2025-11-27 | November | 25 | 27 | 4 | Week 4 | November 25 Week 4 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
7 | 2025-11-28 | November | 25 | 28 | 4 | Week 4 | November 25 Week 4 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
1 | 2025-11-29 | November | 25 | 29 | 5 | Week 5 | November 25 Week 5 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
2 | 2025-11-30 | November | 25 | 30 | 5 | Week 5 | November 25 Week 5 | NOVEMBER 25 | PLANNED | NOVEMBER 25 PLANNED
1 | 2025-12-01 | December | 25 | 1 | 1 | Week 1 | December 25 Week 1 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
2 | 2025-12-02 | December | 25 | 2 | 1 | Week 1 | December 25 Week 1 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
3 | 2025-12-03 | December | 25 | 3 | 1 | Week 1 | December 25 Week 1 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
4 | 2025-12-04 | December | 25 | 4 | 1 | Week 1 | December 25 Week 1 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
5 | 2025-12-05 | December | 25 | 5 | 1 | Week 1 | December 25 Week 1 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
6 | 2025-12-06 | December | 25 | 6 | 1 | Week 1 | December 25 Week 1 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
7 | 2025-12-07 | December | 25 | 7 | 1 | Week 1 | December 25 Week 1 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
1 | 2025-12-08 | December | 25 | 8 | 2 | Week 2 | December 25 Week 2 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
2 | 2025-12-09 | December | 25 | 9 | 2 | Week 2 | December 25 Week 2 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
3 | 2025-12-10 | December | 25 | 10 | 2 | Week 2 | December 25 Week 2 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
4 | 2025-12-11 | December | 25 | 11 | 2 | Week 2 | December 25 Week 2 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
5 | 2025-12-12 | December | 25 | 12 | 2 | Week 2 | December 25 Week 2 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
6 | 2025-12-13 | December | 25 | 13 | 2 | Week 2 | December 25 Week 2 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
7 | 2025-12-14 | December | 25 | 14 | 2 | Week 2 | December 25 Week 2 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
1 | 2025-12-15 | December | 25 | 15 | 3 | Week 3 | December 25 Week 3 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
2 | 2025-12-16 | December | 25 | 16 | 3 | Week 3 | December 25 Week 3 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
3 | 2025-12-17 | December | 25 | 17 | 3 | Week 3 | December 25 Week 3 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
4 | 2025-12-18 | December | 25 | 18 | 3 | Week 3 | December 25 Week 3 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
5 | 2025-12-19 | December | 25 | 19 | 3 | Week 3 | December 25 Week 3 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
6 | 2025-12-20 | December | 25 | 20 | 3 | Week 3 | December 25 Week 3 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
7 | 2025-12-21 | December | 25 | 21 | 3 | Week 3 | December 25 Week 3 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
1 | 2025-12-22 | December | 25 | 22 | 4 | Week 4 | December 25 Week 4 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
2 | 2025-12-23 | December | 25 | 23 | 4 | Week 4 | December 25 Week 4 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
3 | 2025-12-24 | December | 25 | 24 | 4 | Week 4 | December 25 Week 4 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
4 | 2025-12-25 | December | 25 | 25 | 4 | Week 4 | December 25 Week 4 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
5 | 2025-12-26 | December | 25 | 26 | 4 | Week 4 | December 25 Week 4 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
6 | 2025-12-27 | December | 25 | 27 | 4 | Week 4 | December 25 Week 4 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
7 | 2025-12-28 | December | 25 | 28 | 4 | Week 4 | December 25 Week 4 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
1 | 2025-12-29 | December | 25 | 29 | 5 | Week 5 | December 25 Week 5 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
2 | 2025-12-30 | December | 25 | 30 | 5 | Week 5 | December 25 Week 5 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
3 | 2025-12-31 | December | 25 | 31 | 5 | Week 5 | December 25 Week 5 | DECEMBER 25 | PLANNED | DECEMBER 25 PLANNED
1 | 2026-01-01 | January | 26 | 1 | 1 | Week 1 | January 26 Week 1 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
2 | 2026-01-02 | January | 26 | 2 | 1 | Week 1 | January 26 Week 1 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
3 | 2026-01-03 | January | 26 | 3 | 1 | Week 1 | January 26 Week 1 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
4 | 2026-01-04 | January | 26 | 4 | 1 | Week 1 | January 26 Week 1 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
5 | 2026-01-05 | January | 26 | 5 | 1 | Week 1 | January 26 Week 1 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
6 | 2026-01-06 | January | 26 | 6 | 1 | Week 1 | January 26 Week 1 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
7 | 2026-01-07 | January | 26 | 7 | 1 | Week 1 | January 26 Week 1 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
1 | 2026-01-08 | January | 26 | 8 | 2 | Week 2 | January 26 Week 2 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
2 | 2026-01-09 | January | 26 | 9 | 2 | Week 2 | January 26 Week 2 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
3 | 2026-01-10 | January | 26 | 10 | 2 | Week 2 | January 26 Week 2 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
4 | 2026-01-11 | January | 26 | 11 | 2 | Week 2 | January 26 Week 2 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
5 | 2026-01-12 | January | 26 | 12 | 2 | Week 2 | January 26 Week 2 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
6 | 2026-01-13 | January | 26 | 13 | 2 | Week 2 | January 26 Week 2 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
7 | 2026-01-14 | January | 26 | 14 | 2 | Week 2 | January 26 Week 2 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
1 | 2026-01-15 | January | 26 | 15 | 3 | Week 3 | January 26 Week 3 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
2 | 2026-01-16 | January | 26 | 16 | 3 | Week 3 | January 26 Week 3 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
3 | 2026-01-17 | January | 26 | 17 | 3 | Week 3 | January 26 Week 3 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
4 | 2026-01-18 | January | 26 | 18 | 3 | Week 3 | January 26 Week 3 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
5 | 2026-01-19 | January | 26 | 19 | 3 | Week 3 | January 26 Week 3 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
6 | 2026-01-20 | January | 26 | 20 | 3 | Week 3 | January 26 Week 3 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
7 | 2026-01-21 | January | 26 | 21 | 3 | Week 3 | January 26 Week 3 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
1 | 2026-01-22 | January | 26 | 22 | 4 | Week 4 | January 26 Week 4 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
2 | 2026-01-23 | January | 26 | 23 | 4 | Week 4 | January 26 Week 4 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
3 | 2026-01-24 | January | 26 | 24 | 4 | Week 4 | January 26 Week 4 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
4 | 2026-01-25 | January | 26 | 25 | 4 | Week 4 | January 26 Week 4 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
5 | 2026-01-26 | January | 26 | 26 | 4 | Week 4 | January 26 Week 4 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
6 | 2026-01-27 | January | 26 | 27 | 4 | Week 4 | January 26 Week 4 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
7 | 2026-01-28 | January | 26 | 28 | 4 | Week 4 | January 26 Week 4 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
1 | 2026-01-29 | January | 26 | 29 | 5 | Week 5 | January 26 Week 5 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
2 | 2026-01-30 | January | 26 | 30 | 5 | Week 5 | January 26 Week 5 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
3 | 2026-01-31 | January | 26 | 31 | 5 | Week 5 | January 26 Week 5 | JANUARY 26 | PLANNED | JANUARY 26 PLANNED
1 | 2026-02-01 | February | 26 | 1 | 1 | Week 1 | February 26 Week 1 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
2 | 2026-02-02 | February | 26 | 2 | 1 | Week 1 | February 26 Week 1 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
3 | 2026-02-03 | February | 26 | 3 | 1 | Week 1 | February 26 Week 1 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
4 | 2026-02-04 | February | 26 | 4 | 1 | Week 1 | February 26 Week 1 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
5 | 2026-02-05 | February | 26 | 5 | 1 | Week 1 | February 26 Week 1 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
6 | 2026-02-06 | February | 26 | 6 | 1 | Week 1 | February 26 Week 1 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
7 | 2026-02-07 | February | 26 | 7 | 1 | Week 1 | February 26 Week 1 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
1 | 2026-02-08 | February | 26 | 8 | 2 | Week 2 | February 26 Week 2 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
2 | 2026-02-09 | February | 26 | 9 | 2 | Week 2 | February 26 Week 2 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
3 | 2026-02-10 | February | 26 | 10 | 2 | Week 2 | February 26 Week 2 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
4 | 2026-02-11 | February | 26 | 11 | 2 | Week 2 | February 26 Week 2 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
5 | 2026-02-12 | February | 26 | 12 | 2 | Week 2 | February 26 Week 2 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
6 | 2026-02-13 | February | 26 | 13 | 2 | Week 2 | February 26 Week 2 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
7 | 2026-02-14 | February | 26 | 14 | 2 | Week 2 | February 26 Week 2 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
1 | 2026-02-15 | February | 26 | 15 | 3 | Week 3 | February 26 Week 3 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
2 | 2026-02-16 | February | 26 | 16 | 3 | Week 3 | February 26 Week 3 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
3 | 2026-02-17 | February | 26 | 17 | 3 | Week 3 | February 26 Week 3 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
4 | 2026-02-18 | February | 26 | 18 | 3 | Week 3 | February 26 Week 3 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
5 | 2026-02-19 | February | 26 | 19 | 3 | Week 3 | February 26 Week 3 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
6 | 2026-02-20 | February | 26 | 20 | 3 | Week 3 | February 26 Week 3 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
7 | 2026-02-21 | February | 26 | 21 | 3 | Week 3 | February 26 Week 3 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
1 | 2026-02-22 | February | 26 | 22 | 4 | Week 4 | February 26 Week 4 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
2 | 2026-02-23 | February | 26 | 23 | 4 | Week 4 | February 26 Week 4 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
3 | 2026-02-24 | February | 26 | 24 | 4 | Week 4 | February 26 Week 4 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
4 | 2026-02-25 | February | 26 | 25 | 4 | Week 4 | February 26 Week 4 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
5 | 2026-02-26 | February | 26 | 26 | 4 | Week 4 | February 26 Week 4 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
6 | 2026-02-27 | February | 26 | 27 | 4 | Week 4 | February 26 Week 4 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
7 | 2026-02-28 | February | 26 | 28 | 4 | Week 4 | February 26 Week 4 | FEBRUARY 26 | PLANNED | FEBRUARY 26 PLANNED
1 | 2026-03-01 | March | 26 | 1 | 1 | Week 1 | March 26 Week 1 | MARCH 26 | PLANNED | MARCH 26 PLANNED
2 | 2026-03-02 | March | 26 | 2 | 1 | Week 1 | March 26 Week 1 | MARCH 26 | PLANNED | MARCH 26 PLANNED
3 | 2026-03-03 | March | 26 | 3 | 1 | Week 1 | March 26 Week 1 | MARCH 26 | PLANNED | MARCH 26 PLANNED
4 | 2026-03-04 | March | 26 | 4 | 1 | Week 1 | March 26 Week 1 | MARCH 26 | PLANNED | MARCH 26 PLANNED
5 | 2026-03-05 | March | 26 | 5 | 1 | Week 1 | March 26 Week 1 | MARCH 26 | PLANNED | MARCH 26 PLANNED
6 | 2026-03-06 | March | 26 | 6 | 1 | Week 1 | March 26 Week 1 | MARCH 26 | PLANNED | MARCH 26 PLANNED
7 | 2026-03-07 | March | 26 | 7 | 1 | Week 1 | March 26 Week 1 | MARCH 26 | PLANNED | MARCH 26 PLANNED
1 | 2026-03-08 | March | 26 | 8 | 2 | Week 2 | March 26 Week 2 | MARCH 26 | PLANNED | MARCH 26 PLANNED
2 | 2026-03-09 | March | 26 | 9 | 2 | Week 2 | March 26 Week 2 | MARCH 26 | PLANNED | MARCH 26 PLANNED
3 | 2026-03-10 | March | 26 | 10 | 2 | Week 2 | March 26 Week 2 | MARCH 26 | PLANNED | MARCH 26 PLANNED
4 | 2026-03-11 | March | 26 | 11 | 2 | Week 2 | March 26 Week 2 | MARCH 26 | PLANNED | MARCH 26 PLANNED
5 | 2026-03-12 | March | 26 | 12 | 2 | Week 2 | March 26 Week 2 | MARCH 26 | PLANNED | MARCH 26 PLANNED
6 | 2026-03-13 | March | 26 | 13 | 2 | Week 2 | March 26 Week 2 | MARCH 26 | PLANNED | MARCH 26 PLANNED
7 | 2026-03-14 | March | 26 | 14 | 2 | Week 2 | March 26 Week 2 | MARCH 26 | PLANNED | MARCH 26 PLANNED
1 | 2026-03-15 | March | 26 | 15 | 3 | Week 3 | March 26 Week 3 | MARCH 26 | PLANNED | MARCH 26 PLANNED
2 | 2026-03-16 | March | 26 | 16 | 3 | Week 3 | March 26 Week 3 | MARCH 26 | PLANNED | MARCH 26 PLANNED
3 | 2026-03-17 | March | 26 | 17 | 3 | Week 3 | March 26 Week 3 | MARCH 26 | PLANNED | MARCH 26 PLANNED
4 | 2026-03-18 | March | 26 | 18 | 3 | Week 3 | March 26 Week 3 | MARCH 26 | PLANNED | MARCH 26 PLANNED
5 | 2026-03-19 | March | 26 | 19 | 3 | Week 3 | March 26 Week 3 | MARCH 26 | PLANNED | MARCH 26 PLANNED
6 | 2026-03-20 | March | 26 | 20 | 3 | Week 3 | March 26 Week 3 | MARCH 26 | PLANNED | MARCH 26 PLANNED
7 | 2026-03-21 | March | 26 | 21 | 3 | Week 3 | March 26 Week 3 | MARCH 26 | PLANNED | MARCH 26 PLANNED
1 | 2026-03-22 | March | 26 | 22 | 4 | Week 4 | March 26 Week 4 | MARCH 26 | PLANNED | MARCH 26 PLANNED
2 | 2026-03-23 | March | 26 | 23 | 4 | Week 4 | March 26 Week 4 | MARCH 26 | PLANNED | MARCH 26 PLANNED
3 | 2026-03-24 | March | 26 | 24 | 4 | Week 4 | March 26 Week 4 | MARCH 26 | PLANNED | MARCH 26 PLANNED
4 | 2026-03-25 | March | 26 | 25 | 4 | Week 4 | March 26 Week 4 | MARCH 26 | PLANNED | MARCH 26 PLANNED
5 | 2026-03-26 | March | 26 | 26 | 4 | Week 4 | March 26 Week 4 | MARCH 26 | PLANNED | MARCH 26 PLANNED
6 | 2026-03-27 | March | 26 | 27 | 4 | Week 4 | March 26 Week 4 | MARCH 26 | PLANNED | MARCH 26 PLANNED
7 | 2026-03-28 | March | 26 | 28 | 4 | Week 4 | March 26 Week 4 | MARCH 26 | PLANNED | MARCH 26 PLANNED
1 | 2026-03-29 | March | 26 | 29 | 5 | Week 5 | March 26 Week 5 | MARCH 26 | PLANNED | MARCH 26 PLANNED
2 | 2026-03-30 | March | 26 | 30 | 5 | Week 5 | March 26 Week 5 | MARCH 26 | PLANNED | MARCH 26 PLANNED
3 | 2026-03-31 | March | 26 | 31 | 5 | Week 5 | March 26 Week 5 | MARCH 26 | PLANNED | MARCH 26 PLANNED
1 | 2026-04-01 | April | 26 | 1 | 1 | Week 1 | April 26 Week 1 | APRIL 26 | PLANNED | APRIL 26 PLANNED
2 | 2026-04-02 | April | 26 | 2 | 1 | Week 1 | April 26 Week 1 | APRIL 26 | PLANNED | APRIL 26 PLANNED
3 | 2026-04-03 | April | 26 | 3 | 1 | Week 1 | April 26 Week 1 | APRIL 26 | PLANNED | APRIL 26 PLANNED
4 | 2026-04-04 | April | 26 | 4 | 1 | Week 1 | April 26 Week 1 | APRIL 26 | PLANNED | APRIL 26 PLANNED
5 | 2026-04-05 | April | 26 | 5 | 1 | Week 1 | April 26 Week 1 | APRIL 26 | PLANNED | APRIL 26 PLANNED
6 | 2026-04-06 | April | 26 | 6 | 1 | Week 1 | April 26 Week 1 | APRIL 26 | PLANNED | APRIL 26 PLANNED
7 | 2026-04-07 | April | 26 | 7 | 1 | Week 1 | April 26 Week 1 | APRIL 26 | PLANNED | APRIL 26 PLANNED
1 | 2026-04-08 | April | 26 | 8 | 2 | Week 2 | April 26 Week 2 | APRIL 26 | PLANNED | APRIL 26 PLANNED
2 | 2026-04-09 | April | 26 | 9 | 2 | Week 2 | April 26 Week 2 | APRIL 26 | PLANNED | APRIL 26 PLANNED
3 | 2026-04-10 | April | 26 | 10 | 2 | Week 2 | April 26 Week 2 | APRIL 26 | PLANNED | APRIL 26 PLANNED
4 | 2026-04-11 | April | 26 | 11 | 2 | Week 2 | April 26 Week 2 | APRIL 26 | PLANNED | APRIL 26 PLANNED
5 | 2026-04-12 | April | 26 | 12 | 2 | Week 2 | April 26 Week 2 | APRIL 26 | PLANNED | APRIL 26 PLANNED
6 | 2026-04-13 | April | 26 | 13 | 2 | Week 2 | April 26 Week 2 | APRIL 26 | PLANNED | APRIL 26 PLANNED
7 | 2026-04-14 | April | 26 | 14 | 2 | Week 2 | April 26 Week 2 | APRIL 26 | PLANNED | APRIL 26 PLANNED
1 | 2026-04-15 | April | 26 | 15 | 3 | Week 3 | April 26 Week 3 | APRIL 26 | PLANNED | APRIL 26 PLANNED
2 | 2026-04-16 | April | 26 | 16 | 3 | Week 3 | April 26 Week 3 | APRIL 26 | PLANNED | APRIL 26 PLANNED
3 | 2026-04-17 | April | 26 | 17 | 3 | Week 3 | April 26 Week 3 | APRIL 26 | PLANNED | APRIL 26 PLANNED
4 | 2026-04-18 | April | 26 | 18 | 3 | Week 3 | April 26 Week 3 | APRIL 26 | PLANNED | APRIL 26 PLANNED
5 | 2026-04-19 | April | 26 | 19 | 3 | Week 3 | April 26 Week 3 | APRIL 26 | PLANNED | APRIL 26 PLANNED
6 | 2026-04-20 | April | 26 | 20 | 3 | Week 3 | April 26 Week 3 | APRIL 26 | PLANNED | APRIL 26 PLANNED
7 | 2026-04-21 | April | 26 | 21 | 3 | Week 3 | April 26 Week 3 | APRIL 26 | PLANNED | APRIL 26 PLANNED
1 | 2026-04-22 | April | 26 | 22 | 4 | Week 4 | April 26 Week 4 | APRIL 26 | PLANNED | APRIL 26 PLANNED
2 | 2026-04-23 | April | 26 | 23 | 4 | Week 4 | April 26 Week 4 | APRIL 26 | PLANNED | APRIL 26 PLANNED
3 | 2026-04-24 | April | 26 | 24 | 4 | Week 4 | April 26 Week 4 | APRIL 26 | PLANNED | APRIL 26 PLANNED
4 | 2026-04-25 | April | 26 | 25 | 4 | Week 4 | April 26 Week 4 | APRIL 26 | PLANNED | APRIL 26 PLANNED
5 | 2026-04-26 | April | 26 | 26 | 4 | Week 4 | April 26 Week 4 | APRIL 26 | PLANNED | APRIL 26 PLANNED
6 | 2026-04-27 | April | 26 | 27 | 4 | Week 4 | April 26 Week 4 | APRIL 26 | PLANNED | APRIL 26 PLANNED
7 | 2026-04-28 | April | 26 | 28 | 4 | Week 4 | April 26 Week 4 | APRIL 26 | PLANNED | APRIL 26 PLANNED
1 | 2026-04-29 | April | 26 | 29 | 5 | Week 5 | April 26 Week 5 | APRIL 26 | PLANNED | APRIL 26 PLANNED
2 | 2026-04-30 | April | 26 | 30 | 5 | Week 5 | April 26 Week 5 | APRIL 26 | PLANNED | APRIL 26 PLANNED
1 | 2026-05-01 | May | 26 | 1 | 1 | Week 1 | May 26 Week 1 | MAY 26 | PLANNED | MAY 26 PLANNED
2 | 2026-05-02 | May | 26 | 2 | 1 | Week 1 | May 26 Week 1 | MAY 26 | PLANNED | MAY 26 PLANNED
3 | 2026-05-03 | May | 26 | 3 | 1 | Week 1 | May 26 Week 1 | MAY 26 | PLANNED | MAY 26 PLANNED
4 | 2026-05-04 | May | 26 | 4 | 1 | Week 1 | May 26 Week 1 | MAY 26 | PLANNED | MAY 26 PLANNED
5 | 2026-05-05 | May | 26 | 5 | 1 | Week 1 | May 26 Week 1 | MAY 26 | PLANNED | MAY 26 PLANNED
6 | 2026-05-06 | May | 26 | 6 | 1 | Week 1 | May 26 Week 1 | MAY 26 | PLANNED | MAY 26 PLANNED
7 | 2026-05-07 | May | 26 | 7 | 1 | Week 1 | May 26 Week 1 | MAY 26 | PLANNED | MAY 26 PLANNED
1 | 2026-05-08 | May | 26 | 8 | 2 | Week 2 | May 26 Week 2 | MAY 26 | PLANNED | MAY 26 PLANNED
2 | 2026-05-09 | May | 26 | 9 | 2 | Week 2 | May 26 Week 2 | MAY 26 | PLANNED | MAY 26 PLANNED
3 | 2026-05-10 | May | 26 | 10 | 2 | Week 2 | May 26 Week 2 | MAY 26 | PLANNED | MAY 26 PLANNED
4 | 2026-05-11 | May | 26 | 11 | 2 | Week 2 | May 26 Week 2 | MAY 26 | PLANNED | MAY 26 PLANNED
5 | 2026-05-12 | May | 26 | 12 | 2 | Week 2 | May 26 Week 2 | MAY 26 | PLANNED | MAY 26 PLANNED
6 | 2026-05-13 | May | 26 | 13 | 2 | Week 2 | May 26 Week 2 | MAY 26 | PLANNED | MAY 26 PLANNED
7 | 2026-05-14 | May | 26 | 14 | 2 | Week 2 | May 26 Week 2 | MAY 26 | PLANNED | MAY 26 PLANNED
1 | 2026-05-15 | May | 26 | 15 | 3 | Week 3 | May 26 Week 3 | MAY 26 | PLANNED | MAY 26 PLANNED
2 | 2026-05-16 | May | 26 | 16 | 3 | Week 3 | May 26 Week 3 | MAY 26 | PLANNED | MAY 26 PLANNED
3 | 2026-05-17 | May | 26 | 17 | 3 | Week 3 | May 26 Week 3 | MAY 26 | PLANNED | MAY 26 PLANNED
4 | 2026-05-18 | May | 26 | 18 | 3 | Week 3 | May 26 Week 3 | MAY 26 | PLANNED | MAY 26 PLANNED
5 | 2026-05-19 | May | 26 | 19 | 3 | Week 3 | May 26 Week 3 | MAY 26 | PLANNED | MAY 26 PLANNED
6 | 2026-05-20 | May | 26 | 20 | 3 | Week 3 | May 26 Week 3 | MAY 26 | PLANNED | MAY 26 PLANNED
7 | 2026-05-21 | May | 26 | 21 | 3 | Week 3 | May 26 Week 3 | MAY 26 | PLANNED | MAY 26 PLANNED
1 | 2026-05-22 | May | 26 | 22 | 4 | Week 4 | May 26 Week 4 | MAY 26 | PLANNED | MAY 26 PLANNED
2 | 2026-05-23 | May | 26 | 23 | 4 | Week 4 | May 26 Week 4 | MAY 26 | PLANNED | MAY 26 PLANNED
3 | 2026-05-24 | May | 26 | 24 | 4 | Week 4 | May 26 Week 4 | MAY 26 | PLANNED | MAY 26 PLANNED
4 | 2026-05-25 | May | 26 | 25 | 4 | Week 4 | May 26 Week 4 | MAY 26 | PLANNED | MAY 26 PLANNED
5 | 2026-05-26 | May | 26 | 26 | 4 | Week 4 | May 26 Week 4 | MAY 26 | PLANNED | MAY 26 PLANNED
6 | 2026-05-27 | May | 26 | 27 | 4 | Week 4 | May 26 Week 4 | MAY 26 | PLANNED | MAY 26 PLANNED
7 | 2026-05-28 | May | 26 | 28 | 4 | Week 4 | May 26 Week 4 | MAY 26 | PLANNED | MAY 26 PLANNED
1 | 2026-05-29 | May | 26 | 29 | 5 | Week 5 | May 26 Week 5 | MAY 26 | PLANNED | MAY 26 PLANNED
2 | 2026-05-30 | May | 26 | 30 | 5 | Week 5 | May 26 Week 5 | MAY 26 | PLANNED | MAY 26 PLANNED
3 | 2026-05-31 | May | 26 | 31 | 5 | Week 5 | May 26 Week 5 | MAY 26 | PLANNED | MAY 26 PLANNED
1 | 2026-06-01 | June | 26 | 1 | 1 | Week 1 | June 26 Week 1 | JUNE 26 | PLANNED | JUNE 26 PLANNED
2 | 2026-06-02 | June | 26 | 2 | 1 | Week 1 | June 26 Week 1 | JUNE 26 | PLANNED | JUNE 26 PLANNED
3 | 2026-06-03 | June | 26 | 3 | 1 | Week 1 | June 26 Week 1 | JUNE 26 | PLANNED | JUNE 26 PLANNED
4 | 2026-06-04 | June | 26 | 4 | 1 | Week 1 | June 26 Week 1 | JUNE 26 | PLANNED | JUNE 26 PLANNED
5 | 2026-06-05 | June | 26 | 5 | 1 | Week 1 | June 26 Week 1 | JUNE 26 | PLANNED | JUNE 26 PLANNED
6 | 2026-06-06 | June | 26 | 6 | 1 | Week 1 | June 26 Week 1 | JUNE 26 | PLANNED | JUNE 26 PLANNED
7 | 2026-06-07 | June | 26 | 7 | 1 | Week 1 | June 26 Week 1 | JUNE 26 | PLANNED | JUNE 26 PLANNED
1 | 2026-06-08 | June | 26 | 8 | 2 | Week 2 | June 26 Week 2 | JUNE 26 | PLANNED | JUNE 26 PLANNED
2 | 2026-06-09 | June | 26 | 9 | 2 | Week 2 | June 26 Week 2 | JUNE 26 | PLANNED | JUNE 26 PLANNED
3 | 2026-06-10 | June | 26 | 10 | 2 | Week 2 | June 26 Week 2 | JUNE 26 | PLANNED | JUNE 26 PLANNED
4 | 2026-06-11 | June | 26 | 11 | 2 | Week 2 | June 26 Week 2 | JUNE 26 | PLANNED | JUNE 26 PLANNED
5 | 2026-06-12 | June | 26 | 12 | 2 | Week 2 | June 26 Week 2 | JUNE 26 | PLANNED | JUNE 26 PLANNED
6 | 2026-06-13 | June | 26 | 13 | 2 | Week 2 | June 26 Week 2 | JUNE 26 | PLANNED | JUNE 26 PLANNED
7 | 2026-06-14 | June | 26 | 14 | 2 | Week 2 | June 26 Week 2 | JUNE 26 | PLANNED | JUNE 26 PLANNED
1 | 2026-06-15 | June | 26 | 15 | 3 | Week 3 | June 26 Week 3 | JUNE 26 | PLANNED | JUNE 26 PLANNED
2 | 2026-06-16 | June | 26 | 16 | 3 | Week 3 | June 26 Week 3 | JUNE 26 | PLANNED | JUNE 26 PLANNED
3 | 2026-06-17 | June | 26 | 17 | 3 | Week 3 | June 26 Week 3 | JUNE 26 | PLANNED | JUNE 26 PLANNED
4 | 2026-06-18 | June | 26 | 18 | 3 | Week 3 | June 26 Week 3 | JUNE 26 | PLANNED | JUNE 26 PLANNED
5 | 2026-06-19 | June | 26 | 19 | 3 | Week 3 | June 26 Week 3 | JUNE 26 | PLANNED | JUNE 26 PLANNED
6 | 2026-06-20 | June | 26 | 20 | 3 | Week 3 | June 26 Week 3 | JUNE 26 | PLANNED | JUNE 26 PLANNED
7 | 2026-06-21 | June | 26 | 21 | 3 | Week 3 | June 26 Week 3 | JUNE 26 | PLANNED | JUNE 26 PLANNED
1 | 2026-06-22 | June | 26 | 22 | 4 | Week 4 | June 26 Week 4 | JUNE 26 | PLANNED | JUNE 26 PLANNED
2 | 2026-06-23 | June | 26 | 23 | 4 | Week 4 | June 26 Week 4 | JUNE 26 | PLANNED | JUNE 26 PLANNED
3 | 2026-06-24 | June | 26 | 24 | 4 | Week 4 | June 26 Week 4 | JUNE 26 | PLANNED | JUNE 26 PLANNED
4 | 2026-06-25 | June | 26 | 25 | 4 | Week 4 | June 26 Week 4 | JUNE 26 | PLANNED | JUNE 26 PLANNED
5 | 2026-06-26 | June | 26 | 26 | 4 | Week 4 | June 26 Week 4 | JUNE 26 | PLANNED | JUNE 26 PLANNED
6 | 2026-06-27 | June | 26 | 27 | 4 | Week 4 | June 26 Week 4 | JUNE 26 | PLANNED | JUNE 26 PLANNED
7 | 2026-06-28 | June | 26 | 28 | 4 | Week 4 | June 26 Week 4 | JUNE 26 | PLANNED | JUNE 26 PLANNED
1 | 2026-06-29 | June | 26 | 29 | 5 | Week 5 | June 26 Week 5 | JUNE 26 | PLANNED | JUNE 26 PLANNED
2 | 2026-06-30 | June | 26 | 30 | 5 | Week 5 | June 26 Week 5 | JUNE 26 | PLANNED | JUNE 26 PLANNED
1 | 2026-07-01 | July | 26 | 1 | 1 | Week 1 | July 26 Week 1 | JULY 26 | PLANNED | JULY 26 PLANNED
2 | 2026-07-02 | July | 26 | 2 | 1 | Week 1 | July 26 Week 1 | JULY 26 | PLANNED | JULY 26 PLANNED
3 | 2026-07-03 | July | 26 | 3 | 1 | Week 1 | July 26 Week 1 | JULY 26 | PLANNED | JULY 26 PLANNED
4 | 2026-07-04 | July | 26 | 4 | 1 | Week 1 | July 26 Week 1 | JULY 26 | PLANNED | JULY 26 PLANNED
5 | 2026-07-05 | July | 26 | 5 | 1 | Week 1 | July 26 Week 1 | JULY 26 | PLANNED | JULY 26 PLANNED
6 | 2026-07-06 | July | 26 | 6 | 1 | Week 1 | July 26 Week 1 | JULY 26 | PLANNED | JULY 26 PLANNED
7 | 2026-07-07 | July | 26 | 7 | 1 | Week 1 | July 26 Week 1 | JULY 26 | PLANNED | JULY 26 PLANNED
1 | 2026-07-08 | July | 26 | 8 | 2 | Week 2 | July 26 Week 2 | JULY 26 | PLANNED | JULY 26 PLANNED
2 | 2026-07-09 | July | 26 | 9 | 2 | Week 2 | July 26 Week 2 | JULY 26 | PLANNED | JULY 26 PLANNED
3 | 2026-07-10 | July | 26 | 10 | 2 | Week 2 | July 26 Week 2 | JULY 26 | PLANNED | JULY 26 PLANNED
4 | 2026-07-11 | July | 26 | 11 | 2 | Week 2 | July 26 Week 2 | JULY 26 | PLANNED | JULY 26 PLANNED
5 | 2026-07-12 | July | 26 | 12 | 2 | Week 2 | July 26 Week 2 | JULY 26 | PLANNED | JULY 26 PLANNED
6 | 2026-07-13 | July | 26 | 13 | 2 | Week 2 | July 26 Week 2 | JULY 26 | PLANNED | JULY 26 PLANNED
7 | 2026-07-14 | July | 26 | 14 | 2 | Week 2 | July 26 Week 2 | JULY 26 | PLANNED | JULY 26 PLANNED
1 | 2026-07-15 | July | 26 | 15 | 3 | Week 3 | July 26 Week 3 | JULY 26 | PLANNED | JULY 26 PLANNED
2 | 2026-07-16 | July | 26 | 16 | 3 | Week 3 | July 26 Week 3 | JULY 26 | PLANNED | JULY 26 PLANNED
3 | 2026-07-17 | July | 26 | 17 | 3 | Week 3 | July 26 Week 3 | JULY 26 | PLANNED | JULY 26 PLANNED
4 | 2026-07-18 | July | 26 | 18 | 3 | Week 3 | July 26 Week 3 | JULY 26 | PLANNED | JULY 26 PLANNED
5 | 2026-07-19 | July | 26 | 19 | 3 | Week 3 | July 26 Week 3 | JULY 26 | PLANNED | JULY 26 PLANNED
6 | 2026-07-20 | July | 26 | 20 | 3 | Week 3 | July 26 Week 3 | JULY 26 | PLANNED | JULY 26 PLANNED
7 | 2026-07-21 | July | 26 | 21 | 3 | Week 3 | July 26 Week 3 | JULY 26 | PLANNED | JULY 26 PLANNED
1 | 2026-07-22 | July | 26 | 22 | 4 | Week 4 | July 26 Week 4 | JULY 26 | PLANNED | JULY 26 PLANNED
2 | 2026-07-23 | July | 26 | 23 | 4 | Week 4 | July 26 Week 4 | JULY 26 | PLANNED | JULY 26 PLANNED
3 | 2026-07-24 | July | 26 | 24 | 4 | Week 4 | July 26 Week 4 | JULY 26 | PLANNED | JULY 26 PLANNED
4 | 2026-07-25 | July | 26 | 25 | 4 | Week 4 | July 26 Week 4 | JULY 26 | PLANNED | JULY 26 PLANNED
5 | 2026-07-26 | July | 26 | 26 | 4 | Week 4 | July 26 Week 4 | JULY 26 | PLANNED | JULY 26 PLANNED
6 | 2026-07-27 | July | 26 | 27 | 4 | Week 4 | July 26 Week 4 | JULY 26 | PLANNED | JULY 26 PLANNED
7 | 2026-07-28 | July | 26 | 28 | 4 | Week 4 | July 26 Week 4 | JULY 26 | PLANNED | JULY 26 PLANNED
1 | 2026-07-29 | July | 26 | 29 | 5 | Week 5 | July 26 Week 5 | JULY 26 | PLANNED | JULY 26 PLANNED
2 | 2026-07-30 | July | 26 | 30 | 5 | Week 5 | July 26 Week 5 | JULY 26 | PLANNED | JULY 26 PLANNED
3 | 2026-07-31 | July | 26 | 31 | 5 | Week 5 | July 26 Week 5 | JULY 26 | PLANNED | JULY 26 PLANNED
1 | 2026-08-01 | August | 26 | 1 | 1 | Week 1 | August 26 Week 1 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
2 | 2026-08-02 | August | 26 | 2 | 1 | Week 1 | August 26 Week 1 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
3 | 2026-08-03 | August | 26 | 3 | 1 | Week 1 | August 26 Week 1 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
4 | 2026-08-04 | August | 26 | 4 | 1 | Week 1 | August 26 Week 1 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
5 | 2026-08-05 | August | 26 | 5 | 1 | Week 1 | August 26 Week 1 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
6 | 2026-08-06 | August | 26 | 6 | 1 | Week 1 | August 26 Week 1 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
7 | 2026-08-07 | August | 26 | 7 | 1 | Week 1 | August 26 Week 1 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
1 | 2026-08-08 | August | 26 | 8 | 2 | Week 2 | August 26 Week 2 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
2 | 2026-08-09 | August | 26 | 9 | 2 | Week 2 | August 26 Week 2 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
3 | 2026-08-10 | August | 26 | 10 | 2 | Week 2 | August 26 Week 2 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
4 | 2026-08-11 | August | 26 | 11 | 2 | Week 2 | August 26 Week 2 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
5 | 2026-08-12 | August | 26 | 12 | 2 | Week 2 | August 26 Week 2 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
6 | 2026-08-13 | August | 26 | 13 | 2 | Week 2 | August 26 Week 2 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
7 | 2026-08-14 | August | 26 | 14 | 2 | Week 2 | August 26 Week 2 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
1 | 2026-08-15 | August | 26 | 15 | 3 | Week 3 | August 26 Week 3 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
2 | 2026-08-16 | August | 26 | 16 | 3 | Week 3 | August 26 Week 3 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
3 | 2026-08-17 | August | 26 | 17 | 3 | Week 3 | August 26 Week 3 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
4 | 2026-08-18 | August | 26 | 18 | 3 | Week 3 | August 26 Week 3 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
5 | 2026-08-19 | August | 26 | 19 | 3 | Week 3 | August 26 Week 3 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
6 | 2026-08-20 | August | 26 | 20 | 3 | Week 3 | August 26 Week 3 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
7 | 2026-08-21 | August | 26 | 21 | 3 | Week 3 | August 26 Week 3 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
1 | 2026-08-22 | August | 26 | 22 | 4 | Week 4 | August 26 Week 4 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
2 | 2026-08-23 | August | 26 | 23 | 4 | Week 4 | August 26 Week 4 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
3 | 2026-08-24 | August | 26 | 24 | 4 | Week 4 | August 26 Week 4 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
4 | 2026-08-25 | August | 26 | 25 | 4 | Week 4 | August 26 Week 4 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
5 | 2026-08-26 | August | 26 | 26 | 4 | Week 4 | August 26 Week 4 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
6 | 2026-08-27 | August | 26 | 27 | 4 | Week 4 | August 26 Week 4 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
7 | 2026-08-28 | August | 26 | 28 | 4 | Week 4 | August 26 Week 4 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
1 | 2026-08-29 | August | 26 | 29 | 5 | Week 5 | August 26 Week 5 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
2 | 2026-08-30 | August | 26 | 30 | 5 | Week 5 | August 26 Week 5 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
3 | 2026-08-31 | August | 26 | 31 | 5 | Week 5 | August 26 Week 5 | AUGUST 26 | PLANNED | AUGUST 26 PLANNED
1 | 2026-09-01 | September | 26 | 1 | 1 | Week 1 | September 26 Week 1 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
2 | 2026-09-02 | September | 26 | 2 | 1 | Week 1 | September 26 Week 1 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
3 | 2026-09-03 | September | 26 | 3 | 1 | Week 1 | September 26 Week 1 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
4 | 2026-09-04 | September | 26 | 4 | 1 | Week 1 | September 26 Week 1 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
5 | 2026-09-05 | September | 26 | 5 | 1 | Week 1 | September 26 Week 1 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
6 | 2026-09-06 | September | 26 | 6 | 1 | Week 1 | September 26 Week 1 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
7 | 2026-09-07 | September | 26 | 7 | 1 | Week 1 | September 26 Week 1 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
1 | 2026-09-08 | September | 26 | 8 | 2 | Week 2 | September 26 Week 2 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
2 | 2026-09-09 | September | 26 | 9 | 2 | Week 2 | September 26 Week 2 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
3 | 2026-09-10 | September | 26 | 10 | 2 | Week 2 | September 26 Week 2 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
4 | 2026-09-11 | September | 26 | 11 | 2 | Week 2 | September 26 Week 2 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
5 | 2026-09-12 | September | 26 | 12 | 2 | Week 2 | September 26 Week 2 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
6 | 2026-09-13 | September | 26 | 13 | 2 | Week 2 | September 26 Week 2 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
7 | 2026-09-14 | September | 26 | 14 | 2 | Week 2 | September 26 Week 2 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
1 | 2026-09-15 | September | 26 | 15 | 3 | Week 3 | September 26 Week 3 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
2 | 2026-09-16 | September | 26 | 16 | 3 | Week 3 | September 26 Week 3 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
3 | 2026-09-17 | September | 26 | 17 | 3 | Week 3 | September 26 Week 3 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
4 | 2026-09-18 | September | 26 | 18 | 3 | Week 3 | September 26 Week 3 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
5 | 2026-09-19 | September | 26 | 19 | 3 | Week 3 | September 26 Week 3 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
6 | 2026-09-20 | September | 26 | 20 | 3 | Week 3 | September 26 Week 3 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
7 | 2026-09-21 | September | 26 | 21 | 3 | Week 3 | September 26 Week 3 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
1 | 2026-09-22 | September | 26 | 22 | 4 | Week 4 | September 26 Week 4 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
2 | 2026-09-23 | September | 26 | 23 | 4 | Week 4 | September 26 Week 4 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
3 | 2026-09-24 | September | 26 | 24 | 4 | Week 4 | September 26 Week 4 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
4 | 2026-09-25 | September | 26 | 25 | 4 | Week 4 | September 26 Week 4 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
5 | 2026-09-26 | September | 26 | 26 | 4 | Week 4 | September 26 Week 4 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
6 | 2026-09-27 | September | 26 | 27 | 4 | Week 4 | September 26 Week 4 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
7 | 2026-09-28 | September | 26 | 28 | 4 | Week 4 | September 26 Week 4 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
1 | 2026-09-29 | September | 26 | 29 | 5 | Week 5 | September 26 Week 5 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
2 | 2026-09-30 | September | 26 | 30 | 5 | Week 5 | September 26 Week 5 | SEPTEMBER 26 | PLANNED | SEPTEMBER 26 PLANNED
1 | 2026-10-01 | October | 26 | 1 | 1 | Week 1 | October 26 Week 1 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
2 | 2026-10-02 | October | 26 | 2 | 1 | Week 1 | October 26 Week 1 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
3 | 2026-10-03 | October | 26 | 3 | 1 | Week 1 | October 26 Week 1 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
4 | 2026-10-04 | October | 26 | 4 | 1 | Week 1 | October 26 Week 1 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
5 | 2026-10-05 | October | 26 | 5 | 1 | Week 1 | October 26 Week 1 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
6 | 2026-10-06 | October | 26 | 6 | 1 | Week 1 | October 26 Week 1 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
7 | 2026-10-07 | October | 26 | 7 | 1 | Week 1 | October 26 Week 1 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
1 | 2026-10-08 | October | 26 | 8 | 2 | Week 2 | October 26 Week 2 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
2 | 2026-10-09 | October | 26 | 9 | 2 | Week 2 | October 26 Week 2 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
3 | 2026-10-10 | October | 26 | 10 | 2 | Week 2 | October 26 Week 2 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
4 | 2026-10-11 | October | 26 | 11 | 2 | Week 2 | October 26 Week 2 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
5 | 2026-10-12 | October | 26 | 12 | 2 | Week 2 | October 26 Week 2 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
6 | 2026-10-13 | October | 26 | 13 | 2 | Week 2 | October 26 Week 2 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
7 | 2026-10-14 | October | 26 | 14 | 2 | Week 2 | October 26 Week 2 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
1 | 2026-10-15 | October | 26 | 15 | 3 | Week 3 | October 26 Week 3 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
2 | 2026-10-16 | October | 26 | 16 | 3 | Week 3 | October 26 Week 3 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
3 | 2026-10-17 | October | 26 | 17 | 3 | Week 3 | October 26 Week 3 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
4 | 2026-10-18 | October | 26 | 18 | 3 | Week 3 | October 26 Week 3 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
5 | 2026-10-19 | October | 26 | 19 | 3 | Week 3 | October 26 Week 3 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
6 | 2026-10-20 | October | 26 | 20 | 3 | Week 3 | October 26 Week 3 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
7 | 2026-10-21 | October | 26 | 21 | 3 | Week 3 | October 26 Week 3 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
1 | 2026-10-22 | October | 26 | 22 | 4 | Week 4 | October 26 Week 4 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
2 | 2026-10-23 | October | 26 | 23 | 4 | Week 4 | October 26 Week 4 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
3 | 2026-10-24 | October | 26 | 24 | 4 | Week 4 | October 26 Week 4 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
4 | 2026-10-25 | October | 26 | 25 | 4 | Week 4 | October 26 Week 4 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
5 | 2026-10-26 | October | 26 | 26 | 4 | Week 4 | October 26 Week 4 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
6 | 2026-10-27 | October | 26 | 27 | 4 | Week 4 | October 26 Week 4 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
7 | 2026-10-28 | October | 26 | 28 | 4 | Week 4 | October 26 Week 4 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
1 | 2026-10-29 | October | 26 | 29 | 5 | Week 5 | October 26 Week 5 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
2 | 2026-10-30 | October | 26 | 30 | 5 | Week 5 | October 26 Week 5 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
3 | 2026-10-31 | October | 26 | 31 | 5 | Week 5 | October 26 Week 5 | OCTOBER 26 | PLANNED | OCTOBER 26 PLANNED
1 | 2026-11-01 | November | 26 | 1 | 1 | Week 1 | November 26 Week 1 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
2 | 2026-11-02 | November | 26 | 2 | 1 | Week 1 | November 26 Week 1 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
3 | 2026-11-03 | November | 26 | 3 | 1 | Week 1 | November 26 Week 1 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
4 | 2026-11-04 | November | 26 | 4 | 1 | Week 1 | November 26 Week 1 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
5 | 2026-11-05 | November | 26 | 5 | 1 | Week 1 | November 26 Week 1 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
6 | 2026-11-06 | November | 26 | 6 | 1 | Week 1 | November 26 Week 1 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
7 | 2026-11-07 | November | 26 | 7 | 1 | Week 1 | November 26 Week 1 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
1 | 2026-11-08 | November | 26 | 8 | 2 | Week 2 | November 26 Week 2 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
2 | 2026-11-09 | November | 26 | 9 | 2 | Week 2 | November 26 Week 2 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
3 | 2026-11-10 | November | 26 | 10 | 2 | Week 2 | November 26 Week 2 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
4 | 2026-11-11 | November | 26 | 11 | 2 | Week 2 | November 26 Week 2 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
5 | 2026-11-12 | November | 26 | 12 | 2 | Week 2 | November 26 Week 2 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
6 | 2026-11-13 | November | 26 | 13 | 2 | Week 2 | November 26 Week 2 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
7 | 2026-11-14 | November | 26 | 14 | 2 | Week 2 | November 26 Week 2 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
1 | 2026-11-15 | November | 26 | 15 | 3 | Week 3 | November 26 Week 3 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
2 | 2026-11-16 | November | 26 | 16 | 3 | Week 3 | November 26 Week 3 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
3 | 2026-11-17 | November | 26 | 17 | 3 | Week 3 | November 26 Week 3 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
4 | 2026-11-18 | November | 26 | 18 | 3 | Week 3 | November 26 Week 3 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
5 | 2026-11-19 | November | 26 | 19 | 3 | Week 3 | November 26 Week 3 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
6 | 2026-11-20 | November | 26 | 20 | 3 | Week 3 | November 26 Week 3 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
7 | 2026-11-21 | November | 26 | 21 | 3 | Week 3 | November 26 Week 3 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
1 | 2026-11-22 | November | 26 | 22 | 4 | Week 4 | November 26 Week 4 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
2 | 2026-11-23 | November | 26 | 23 | 4 | Week 4 | November 26 Week 4 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
3 | 2026-11-24 | November | 26 | 24 | 4 | Week 4 | November 26 Week 4 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
4 | 2026-11-25 | November | 26 | 25 | 4 | Week 4 | November 26 Week 4 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
5 | 2026-11-26 | November | 26 | 26 | 4 | Week 4 | November 26 Week 4 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
6 | 2026-11-27 | November | 26 | 27 | 4 | Week 4 | November 26 Week 4 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
7 | 2026-11-28 | November | 26 | 28 | 4 | Week 4 | November 26 Week 4 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
1 | 2026-11-29 | November | 26 | 29 | 5 | Week 5 | November 26 Week 5 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
2 | 2026-11-30 | November | 26 | 30 | 5 | Week 5 | November 26 Week 5 | NOVEMBER 26 | PLANNED | NOVEMBER 26 PLANNED
1 | 2026-12-01 | December | 26 | 1 | 1 | Week 1 | December 26 Week 1 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
2 | 2026-12-02 | December | 26 | 2 | 1 | Week 1 | December 26 Week 1 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
3 | 2026-12-03 | December | 26 | 3 | 1 | Week 1 | December 26 Week 1 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
4 | 2026-12-04 | December | 26 | 4 | 1 | Week 1 | December 26 Week 1 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
5 | 2026-12-05 | December | 26 | 5 | 1 | Week 1 | December 26 Week 1 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
6 | 2026-12-06 | December | 26 | 6 | 1 | Week 1 | December 26 Week 1 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
7 | 2026-12-07 | December | 26 | 7 | 1 | Week 1 | December 26 Week 1 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
1 | 2026-12-08 | December | 26 | 8 | 2 | Week 2 | December 26 Week 2 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
2 | 2026-12-09 | December | 26 | 9 | 2 | Week 2 | December 26 Week 2 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
3 | 2026-12-10 | December | 26 | 10 | 2 | Week 2 | December 26 Week 2 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
4 | 2026-12-11 | December | 26 | 11 | 2 | Week 2 | December 26 Week 2 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
5 | 2026-12-12 | December | 26 | 12 | 2 | Week 2 | December 26 Week 2 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
6 | 2026-12-13 | December | 26 | 13 | 2 | Week 2 | December 26 Week 2 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
7 | 2026-12-14 | December | 26 | 14 | 2 | Week 2 | December 26 Week 2 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
1 | 2026-12-15 | December | 26 | 15 | 3 | Week 3 | December 26 Week 3 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
2 | 2026-12-16 | December | 26 | 16 | 3 | Week 3 | December 26 Week 3 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
3 | 2026-12-17 | December | 26 | 17 | 3 | Week 3 | December 26 Week 3 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
4 | 2026-12-18 | December | 26 | 18 | 3 | Week 3 | December 26 Week 3 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
5 | 2026-12-19 | December | 26 | 19 | 3 | Week 3 | December 26 Week 3 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
6 | 2026-12-20 | December | 26 | 20 | 3 | Week 3 | December 26 Week 3 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
7 | 2026-12-21 | December | 26 | 21 | 3 | Week 3 | December 26 Week 3 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
1 | 2026-12-22 | December | 26 | 22 | 4 | Week 4 | December 26 Week 4 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
2 | 2026-12-23 | December | 26 | 23 | 4 | Week 4 | December 26 Week 4 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
3 | 2026-12-24 | December | 26 | 24 | 4 | Week 4 | December 26 Week 4 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
4 | 2026-12-25 | December | 26 | 25 | 4 | Week 4 | December 26 Week 4 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
5 | 2026-12-26 | December | 26 | 26 | 4 | Week 4 | December 26 Week 4 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
6 | 2026-12-27 | December | 26 | 27 | 4 | Week 4 | December 26 Week 4 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
7 | 2026-12-28 | December | 26 | 28 | 4 | Week 4 | December 26 Week 4 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
1 | 2026-12-29 | December | 26 | 29 | 5 | Week 5 | December 26 Week 5 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
2 | 2026-12-30 | December | 26 | 30 | 5 | Week 5 | December 26 Week 5 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
3 | 2026-12-31 | December | 26 | 31 | 5 | Week 5 | December 26 Week 5 | DECEMBER 26 | PLANNED | DECEMBER 26 PLANNED
1 | 2027-01-01 | January | 27 | 1 | 1 | Week 1 | January 27 Week 1 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
2 | 2027-01-02 | January | 27 | 2 | 1 | Week 1 | January 27 Week 1 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
3 | 2027-01-03 | January | 27 | 3 | 1 | Week 1 | January 27 Week 1 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
4 | 2027-01-04 | January | 27 | 4 | 1 | Week 1 | January 27 Week 1 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
5 | 2027-01-05 | January | 27 | 5 | 1 | Week 1 | January 27 Week 1 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
6 | 2027-01-06 | January | 27 | 6 | 1 | Week 1 | January 27 Week 1 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
7 | 2027-01-07 | January | 27 | 7 | 1 | Week 1 | January 27 Week 1 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
1 | 2027-01-08 | January | 27 | 8 | 2 | Week 2 | January 27 Week 2 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
2 | 2027-01-09 | January | 27 | 9 | 2 | Week 2 | January 27 Week 2 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
3 | 2027-01-10 | January | 27 | 10 | 2 | Week 2 | January 27 Week 2 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
4 | 2027-01-11 | January | 27 | 11 | 2 | Week 2 | January 27 Week 2 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
5 | 2027-01-12 | January | 27 | 12 | 2 | Week 2 | January 27 Week 2 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
6 | 2027-01-13 | January | 27 | 13 | 2 | Week 2 | January 27 Week 2 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
7 | 2027-01-14 | January | 27 | 14 | 2 | Week 2 | January 27 Week 2 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
1 | 2027-01-15 | January | 27 | 15 | 3 | Week 3 | January 27 Week 3 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
2 | 2027-01-16 | January | 27 | 16 | 3 | Week 3 | January 27 Week 3 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
3 | 2027-01-17 | January | 27 | 17 | 3 | Week 3 | January 27 Week 3 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
4 | 2027-01-18 | January | 27 | 18 | 3 | Week 3 | January 27 Week 3 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
5 | 2027-01-19 | January | 27 | 19 | 3 | Week 3 | January 27 Week 3 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
6 | 2027-01-20 | January | 27 | 20 | 3 | Week 3 | January 27 Week 3 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
7 | 2027-01-21 | January | 27 | 21 | 3 | Week 3 | January 27 Week 3 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
1 | 2027-01-22 | January | 27 | 22 | 4 | Week 4 | January 27 Week 4 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
2 | 2027-01-23 | January | 27 | 23 | 4 | Week 4 | January 27 Week 4 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
3 | 2027-01-24 | January | 27 | 24 | 4 | Week 4 | January 27 Week 4 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
4 | 2027-01-25 | January | 27 | 25 | 4 | Week 4 | January 27 Week 4 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
5 | 2027-01-26 | January | 27 | 26 | 4 | Week 4 | January 27 Week 4 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
6 | 2027-01-27 | January | 27 | 27 | 4 | Week 4 | January 27 Week 4 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
7 | 2027-01-28 | January | 27 | 28 | 4 | Week 4 | January 27 Week 4 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
1 | 2027-01-29 | January | 27 | 29 | 5 | Week 5 | January 27 Week 5 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
2 | 2027-01-30 | January | 27 | 30 | 5 | Week 5 | January 27 Week 5 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
3 | 2027-01-31 | January | 27 | 31 | 5 | Week 5 | January 27 Week 5 | JANUARY 27 | PLANNED | JANUARY 27 PLANNED
1 | 2027-02-01 | February | 27 | 1 | 1 | Week 1 | February 27 Week 1 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
2 | 2027-02-02 | February | 27 | 2 | 1 | Week 1 | February 27 Week 1 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
3 | 2027-02-03 | February | 27 | 3 | 1 | Week 1 | February 27 Week 1 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
4 | 2027-02-04 | February | 27 | 4 | 1 | Week 1 | February 27 Week 1 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
5 | 2027-02-05 | February | 27 | 5 | 1 | Week 1 | February 27 Week 1 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
6 | 2027-02-06 | February | 27 | 6 | 1 | Week 1 | February 27 Week 1 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
7 | 2027-02-07 | February | 27 | 7 | 1 | Week 1 | February 27 Week 1 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
1 | 2027-02-08 | February | 27 | 8 | 2 | Week 2 | February 27 Week 2 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
2 | 2027-02-09 | February | 27 | 9 | 2 | Week 2 | February 27 Week 2 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
3 | 2027-02-10 | February | 27 | 10 | 2 | Week 2 | February 27 Week 2 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
4 | 2027-02-11 | February | 27 | 11 | 2 | Week 2 | February 27 Week 2 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
5 | 2027-02-12 | February | 27 | 12 | 2 | Week 2 | February 27 Week 2 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
6 | 2027-02-13 | February | 27 | 13 | 2 | Week 2 | February 27 Week 2 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
7 | 2027-02-14 | February | 27 | 14 | 2 | Week 2 | February 27 Week 2 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
1 | 2027-02-15 | February | 27 | 15 | 3 | Week 3 | February 27 Week 3 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
2 | 2027-02-16 | February | 27 | 16 | 3 | Week 3 | February 27 Week 3 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
3 | 2027-02-17 | February | 27 | 17 | 3 | Week 3 | February 27 Week 3 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
4 | 2027-02-18 | February | 27 | 18 | 3 | Week 3 | February 27 Week 3 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
5 | 2027-02-19 | February | 27 | 19 | 3 | Week 3 | February 27 Week 3 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
6 | 2027-02-20 | February | 27 | 20 | 3 | Week 3 | February 27 Week 3 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
7 | 2027-02-21 | February | 27 | 21 | 3 | Week 3 | February 27 Week 3 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
1 | 2027-02-22 | February | 27 | 22 | 4 | Week 4 | February 27 Week 4 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
2 | 2027-02-23 | February | 27 | 23 | 4 | Week 4 | February 27 Week 4 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
3 | 2027-02-24 | February | 27 | 24 | 4 | Week 4 | February 27 Week 4 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
4 | 2027-02-25 | February | 27 | 25 | 4 | Week 4 | February 27 Week 4 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
5 | 2027-02-26 | February | 27 | 26 | 4 | Week 4 | February 27 Week 4 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
6 | 2027-02-27 | February | 27 | 27 | 4 | Week 4 | February 27 Week 4 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
7 | 2027-02-28 | February | 27 | 28 | 4 | Week 4 | February 27 Week 4 | FEBRUARY 27 | PLANNED | FEBRUARY 27 PLANNED
1 | 2027-03-01 | March | 27 | 1 | 1 | Week 1 | March 27 Week 1 | MARCH 27 | PLANNED | MARCH 27 PLANNED
2 | 2027-03-02 | March | 27 | 2 | 1 | Week 1 | March 27 Week 1 | MARCH 27 | PLANNED | MARCH 27 PLANNED
3 | 2027-03-03 | March | 27 | 3 | 1 | Week 1 | March 27 Week 1 | MARCH 27 | PLANNED | MARCH 27 PLANNED
4 | 2027-03-04 | March | 27 | 4 | 1 | Week 1 | March 27 Week 1 | MARCH 27 | PLANNED | MARCH 27 PLANNED
5 | 2027-03-05 | March | 27 | 5 | 1 | Week 1 | March 27 Week 1 | MARCH 27 | PLANNED | MARCH 27 PLANNED
6 | 2027-03-06 | March | 27 | 6 | 1 | Week 1 | March 27 Week 1 | MARCH 27 | PLANNED | MARCH 27 PLANNED
7 | 2027-03-07 | March | 27 | 7 | 1 | Week 1 | March 27 Week 1 | MARCH 27 | PLANNED | MARCH 27 PLANNED
1 | 2027-03-08 | March | 27 | 8 | 2 | Week 2 | March 27 Week 2 | MARCH 27 | PLANNED | MARCH 27 PLANNED
2 | 2027-03-09 | March | 27 | 9 | 2 | Week 2 | March 27 Week 2 | MARCH 27 | PLANNED | MARCH 27 PLANNED
3 | 2027-03-10 | March | 27 | 10 | 2 | Week 2 | March 27 Week 2 | MARCH 27 | PLANNED | MARCH 27 PLANNED
4 | 2027-03-11 | March | 27 | 11 | 2 | Week 2 | March 27 Week 2 | MARCH 27 | PLANNED | MARCH 27 PLANNED
5 | 2027-03-12 | March | 27 | 12 | 2 | Week 2 | March 27 Week 2 | MARCH 27 | PLANNED | MARCH 27 PLANNED
6 | 2027-03-13 | March | 27 | 13 | 2 | Week 2 | March 27 Week 2 | MARCH 27 | PLANNED | MARCH 27 PLANNED
7 | 2027-03-14 | March | 27 | 14 | 2 | Week 2 | March 27 Week 2 | MARCH 27 | PLANNED | MARCH 27 PLANNED
1 | 2027-03-15 | March | 27 | 15 | 3 | Week 3 | March 27 Week 3 | MARCH 27 | PLANNED | MARCH 27 PLANNED
2 | 2027-03-16 | March | 27 | 16 | 3 | Week 3 | March 27 Week 3 | MARCH 27 | PLANNED | MARCH 27 PLANNED
3 | 2027-03-17 | March | 27 | 17 | 3 | Week 3 | March 27 Week 3 | MARCH 27 | PLANNED | MARCH 27 PLANNED
4 | 2027-03-18 | March | 27 | 18 | 3 | Week 3 | March 27 Week 3 | MARCH 27 | PLANNED | MARCH 27 PLANNED
5 | 2027-03-19 | March | 27 | 19 | 3 | Week 3 | March 27 Week 3 | MARCH 27 | PLANNED | MARCH 27 PLANNED
6 | 2027-03-20 | March | 27 | 20 | 3 | Week 3 | March 27 Week 3 | MARCH 27 | PLANNED | MARCH 27 PLANNED
7 | 2027-03-21 | March | 27 | 21 | 3 | Week 3 | March 27 Week 3 | MARCH 27 | PLANNED | MARCH 27 PLANNED
1 | 2027-03-22 | March | 27 | 22 | 4 | Week 4 | March 27 Week 4 | MARCH 27 | PLANNED | MARCH 27 PLANNED
2 | 2027-03-23 | March | 27 | 23 | 4 | Week 4 | March 27 Week 4 | MARCH 27 | PLANNED | MARCH 27 PLANNED
3 | 2027-03-24 | March | 27 | 24 | 4 | Week 4 | March 27 Week 4 | MARCH 27 | PLANNED | MARCH 27 PLANNED
4 | 2027-03-25 | March | 27 | 25 | 4 | Week 4 | March 27 Week 4 | MARCH 27 | PLANNED | MARCH 27 PLANNED
5 | 2027-03-26 | March | 27 | 26 | 4 | Week 4 | March 27 Week 4 | MARCH 27 | PLANNED | MARCH 27 PLANNED
6 | 2027-03-27 | March | 27 | 27 | 4 | Week 4 | March 27 Week 4 | MARCH 27 | PLANNED | MARCH 27 PLANNED
7 | 2027-03-28 | March | 27 | 28 | 4 | Week 4 | March 27 Week 4 | MARCH 27 | PLANNED | MARCH 27 PLANNED
1 | 2027-03-29 | March | 27 | 29 | 5 | Week 5 | March 27 Week 5 | MARCH 27 | PLANNED | MARCH 27 PLANNED
2 | 2027-03-30 | March | 27 | 30 | 5 | Week 5 | March 27 Week 5 | MARCH 27 | PLANNED | MARCH 27 PLANNED
3 | 2027-03-31 | March | 27 | 31 | 5 | Week 5 | March 27 Week 5 | MARCH 27 | PLANNED | MARCH 27 PLANNED
1 | 2027-04-01 | April | 27 | 1 | 1 | Week 1 | April 27 Week 1 | APRIL 27 | PLANNED | APRIL 27 PLANNED
2 | 2027-04-02 | April | 27 | 2 | 1 | Week 1 | April 27 Week 1 | APRIL 27 | PLANNED | APRIL 27 PLANNED
3 | 2027-04-03 | April | 27 | 3 | 1 | Week 1 | April 27 Week 1 | APRIL 27 | PLANNED | APRIL 27 PLANNED
4 | 2027-04-04 | April | 27 | 4 | 1 | Week 1 | April 27 Week 1 | APRIL 27 | PLANNED | APRIL 27 PLANNED
5 | 2027-04-05 | April | 27 | 5 | 1 | Week 1 | April 27 Week 1 | APRIL 27 | PLANNED | APRIL 27 PLANNED
6 | 2027-04-06 | April | 27 | 6 | 1 | Week 1 | April 27 Week 1 | APRIL 27 | PLANNED | APRIL 27 PLANNED
7 | 2027-04-07 | April | 27 | 7 | 1 | Week 1 | April 27 Week 1 | APRIL 27 | PLANNED | APRIL 27 PLANNED
1 | 2027-04-08 | April | 27 | 8 | 2 | Week 2 | April 27 Week 2 | APRIL 27 | PLANNED | APRIL 27 PLANNED
2 | 2027-04-09 | April | 27 | 9 | 2 | Week 2 | April 27 Week 2 | APRIL 27 | PLANNED | APRIL 27 PLANNED
3 | 2027-04-10 | April | 27 | 10 | 2 | Week 2 | April 27 Week 2 | APRIL 27 | PLANNED | APRIL 27 PLANNED
4 | 2027-04-11 | April | 27 | 11 | 2 | Week 2 | April 27 Week 2 | APRIL 27 | PLANNED | APRIL 27 PLANNED
5 | 2027-04-12 | April | 27 | 12 | 2 | Week 2 | April 27 Week 2 | APRIL 27 | PLANNED | APRIL 27 PLANNED
6 | 2027-04-13 | April | 27 | 13 | 2 | Week 2 | April 27 Week 2 | APRIL 27 | PLANNED | APRIL 27 PLANNED
7 | 2027-04-14 | April | 27 | 14 | 2 | Week 2 | April 27 Week 2 | APRIL 27 | PLANNED | APRIL 27 PLANNED
1 | 2027-04-15 | April | 27 | 15 | 3 | Week 3 | April 27 Week 3 | APRIL 27 | PLANNED | APRIL 27 PLANNED
2 | 2027-04-16 | April | 27 | 16 | 3 | Week 3 | April 27 Week 3 | APRIL 27 | PLANNED | APRIL 27 PLANNED
3 | 2027-04-17 | April | 27 | 17 | 3 | Week 3 | April 27 Week 3 | APRIL 27 | PLANNED | APRIL 27 PLANNED
4 | 2027-04-18 | April | 27 | 18 | 3 | Week 3 | April 27 Week 3 | APRIL 27 | PLANNED | APRIL 27 PLANNED
5 | 2027-04-19 | April | 27 | 19 | 3 | Week 3 | April 27 Week 3 | APRIL 27 | PLANNED | APRIL 27 PLANNED
6 | 2027-04-20 | April | 27 | 20 | 3 | Week 3 | April 27 Week 3 | APRIL 27 | PLANNED | APRIL 27 PLANNED
7 | 2027-04-21 | April | 27 | 21 | 3 | Week 3 | April 27 Week 3 | APRIL 27 | PLANNED | APRIL 27 PLANNED
1 | 2027-04-22 | April | 27 | 22 | 4 | Week 4 | April 27 Week 4 | APRIL 27 | PLANNED | APRIL 27 PLANNED
2 | 2027-04-23 | April | 27 | 23 | 4 | Week 4 | April 27 Week 4 | APRIL 27 | PLANNED | APRIL 27 PLANNED
3 | 2027-04-24 | April | 27 | 24 | 4 | Week 4 | April 27 Week 4 | APRIL 27 | PLANNED | APRIL 27 PLANNED
4 | 2027-04-25 | April | 27 | 25 | 4 | Week 4 | April 27 Week 4 | APRIL 27 | PLANNED | APRIL 27 PLANNED
5 | 2027-04-26 | April | 27 | 26 | 4 | Week 4 | April 27 Week 4 | APRIL 27 | PLANNED | APRIL 27 PLANNED
6 | 2027-04-27 | April | 27 | 27 | 4 | Week 4 | April 27 Week 4 | APRIL 27 | PLANNED | APRIL 27 PLANNED
7 | 2027-04-28 | April | 27 | 28 | 4 | Week 4 | April 27 Week 4 | APRIL 27 | PLANNED | APRIL 27 PLANNED
1 | 2027-04-29 | April | 27 | 29 | 5 | Week 5 | April 27 Week 5 | APRIL 27 | PLANNED | APRIL 27 PLANNED
2 | 2027-04-30 | April | 27 | 30 | 5 | Week 5 | April 27 Week 5 | APRIL 27 | PLANNED | APRIL 27 PLANNED
1 | 2027-05-01 | May | 27 | 1 | 1 | Week 1 | May 27 Week 1 | MAY 27 | PLANNED | MAY 27 PLANNED
2 | 2027-05-02 | May | 27 | 2 | 1 | Week 1 | May 27 Week 1 | MAY 27 | PLANNED | MAY 27 PLANNED
3 | 2027-05-03 | May | 27 | 3 | 1 | Week 1 | May 27 Week 1 | MAY 27 | PLANNED | MAY 27 PLANNED
4 | 2027-05-04 | May | 27 | 4 | 1 | Week 1 | May 27 Week 1 | MAY 27 | PLANNED | MAY 27 PLANNED
5 | 2027-05-05 | May | 27 | 5 | 1 | Week 1 | May 27 Week 1 | MAY 27 | PLANNED | MAY 27 PLANNED
6 | 2027-05-06 | May | 27 | 6 | 1 | Week 1 | May 27 Week 1 | MAY 27 | PLANNED | MAY 27 PLANNED
7 | 2027-05-07 | May | 27 | 7 | 1 | Week 1 | May 27 Week 1 | MAY 27 | PLANNED | MAY 27 PLANNED
1 | 2027-05-08 | May | 27 | 8 | 2 | Week 2 | May 27 Week 2 | MAY 27 | PLANNED | MAY 27 PLANNED
2 | 2027-05-09 | May | 27 | 9 | 2 | Week 2 | May 27 Week 2 | MAY 27 | PLANNED | MAY 27 PLANNED
3 | 2027-05-10 | May | 27 | 10 | 2 | Week 2 | May 27 Week 2 | MAY 27 | PLANNED | MAY 27 PLANNED
4 | 2027-05-11 | May | 27 | 11 | 2 | Week 2 | May 27 Week 2 | MAY 27 | PLANNED | MAY 27 PLANNED
5 | 2027-05-12 | May | 27 | 12 | 2 | Week 2 | May 27 Week 2 | MAY 27 | PLANNED | MAY 27 PLANNED
6 | 2027-05-13 | May | 27 | 13 | 2 | Week 2 | May 27 Week 2 | MAY 27 | PLANNED | MAY 27 PLANNED
7 | 2027-05-14 | May | 27 | 14 | 2 | Week 2 | May 27 Week 2 | MAY 27 | PLANNED | MAY 27 PLANNED
1 | 2027-05-15 | May | 27 | 15 | 3 | Week 3 | May 27 Week 3 | MAY 27 | PLANNED | MAY 27 PLANNED
2 | 2027-05-16 | May | 27 | 16 | 3 | Week 3 | May 27 Week 3 | MAY 27 | PLANNED | MAY 27 PLANNED
3 | 2027-05-17 | May | 27 | 17 | 3 | Week 3 | May 27 Week 3 | MAY 27 | PLANNED | MAY 27 PLANNED
4 | 2027-05-18 | May | 27 | 18 | 3 | Week 3 | May 27 Week 3 | MAY 27 | PLANNED | MAY 27 PLANNED
5 | 2027-05-19 | May | 27 | 19 | 3 | Week 3 | May 27 Week 3 | MAY 27 | PLANNED | MAY 27 PLANNED
6 | 2027-05-20 | May | 27 | 20 | 3 | Week 3 | May 27 Week 3 | MAY 27 | PLANNED | MAY 27 PLANNED
7 | 2027-05-21 | May | 27 | 21 | 3 | Week 3 | May 27 Week 3 | MAY 27 | PLANNED | MAY 27 PLANNED
1 | 2027-05-22 | May | 27 | 22 | 4 | Week 4 | May 27 Week 4 | MAY 27 | PLANNED | MAY 27 PLANNED
2 | 2027-05-23 | May | 27 | 23 | 4 | Week 4 | May 27 Week 4 | MAY 27 | PLANNED | MAY 27 PLANNED
3 | 2027-05-24 | May | 27 | 24 | 4 | Week 4 | May 27 Week 4 | MAY 27 | PLANNED | MAY 27 PLANNED
4 | 2027-05-25 | May | 27 | 25 | 4 | Week 4 | May 27 Week 4 | MAY 27 | PLANNED | MAY 27 PLANNED
5 | 2027-05-26 | May | 27 | 26 | 4 | Week 4 | May 27 Week 4 | MAY 27 | PLANNED | MAY 27 PLANNED
6 | 2027-05-27 | May | 27 | 27 | 4 | Week 4 | May 27 Week 4 | MAY 27 | PLANNED | MAY 27 PLANNED
7 | 2027-05-28 | May | 27 | 28 | 4 | Week 4 | May 27 Week 4 | MAY 27 | PLANNED | MAY 27 PLANNED
1 | 2027-05-29 | May | 27 | 29 | 5 | Week 5 | May 27 Week 5 | MAY 27 | PLANNED | MAY 27 PLANNED
2 | 2027-05-30 | May | 27 | 30 | 5 | Week 5 | May 27 Week 5 | MAY 27 | PLANNED | MAY 27 PLANNED
3 | 2027-05-31 | May | 27 | 31 | 5 | Week 5 | May 27 Week 5 | MAY 27 | PLANNED | MAY 27 PLANNED
1 | 2027-06-01 | June | 27 | 1 | 1 | Week 1 | June 27 Week 1 | JUNE 27 | PLANNED | JUNE 27 PLANNED
2 | 2027-06-02 | June | 27 | 2 | 1 | Week 1 | June 27 Week 1 | JUNE 27 | PLANNED | JUNE 27 PLANNED
3 | 2027-06-03 | June | 27 | 3 | 1 | Week 1 | June 27 Week 1 | JUNE 27 | PLANNED | JUNE 27 PLANNED
4 | 2027-06-04 | June | 27 | 4 | 1 | Week 1 | June 27 Week 1 | JUNE 27 | PLANNED | JUNE 27 PLANNED
5 | 2027-06-05 | June | 27 | 5 | 1 | Week 1 | June 27 Week 1 | JUNE 27 | PLANNED | JUNE 27 PLANNED
6 | 2027-06-06 | June | 27 | 6 | 1 | Week 1 | June 27 Week 1 | JUNE 27 | PLANNED | JUNE 27 PLANNED
7 | 2027-06-07 | June | 27 | 7 | 1 | Week 1 | June 27 Week 1 | JUNE 27 | PLANNED | JUNE 27 PLANNED
1 | 2027-06-08 | June | 27 | 8 | 2 | Week 2 | June 27 Week 2 | JUNE 27 | PLANNED | JUNE 27 PLANNED
2 | 2027-06-09 | June | 27 | 9 | 2 | Week 2 | June 27 Week 2 | JUNE 27 | PLANNED | JUNE 27 PLANNED
3 | 2027-06-10 | June | 27 | 10 | 2 | Week 2 | June 27 Week 2 | JUNE 27 | PLANNED | JUNE 27 PLANNED
4 | 2027-06-11 | June | 27 | 11 | 2 | Week 2 | June 27 Week 2 | JUNE 27 | PLANNED | JUNE 27 PLANNED
5 | 2027-06-12 | June | 27 | 12 | 2 | Week 2 | June 27 Week 2 | JUNE 27 | PLANNED | JUNE 27 PLANNED
6 | 2027-06-13 | June | 27 | 13 | 2 | Week 2 | June 27 Week 2 | JUNE 27 | PLANNED | JUNE 27 PLANNED
7 | 2027-06-14 | June | 27 | 14 | 2 | Week 2 | June 27 Week 2 | JUNE 27 | PLANNED | JUNE 27 PLANNED
1 | 2027-06-15 | June | 27 | 15 | 3 | Week 3 | June 27 Week 3 | JUNE 27 | PLANNED | JUNE 27 PLANNED
2 | 2027-06-16 | June | 27 | 16 | 3 | Week 3 | June 27 Week 3 | JUNE 27 | PLANNED | JUNE 27 PLANNED
3 | 2027-06-17 | June | 27 | 17 | 3 | Week 3 | June 27 Week 3 | JUNE 27 | PLANNED | JUNE 27 PLANNED
4 | 2027-06-18 | June | 27 | 18 | 3 | Week 3 | June 27 Week 3 | JUNE 27 | PLANNED | JUNE 27 PLANNED
5 | 2027-06-19 | June | 27 | 19 | 3 | Week 3 | June 27 Week 3 | JUNE 27 | PLANNED | JUNE 27 PLANNED
6 | 2027-06-20 | June | 27 | 20 | 3 | Week 3 | June 27 Week 3 | JUNE 27 | PLANNED | JUNE 27 PLANNED
7 | 2027-06-21 | June | 27 | 21 | 3 | Week 3 | June 27 Week 3 | JUNE 27 | PLANNED | JUNE 27 PLANNED
1 | 2027-06-22 | June | 27 | 22 | 4 | Week 4 | June 27 Week 4 | JUNE 27 | PLANNED | JUNE 27 PLANNED
2 | 2027-06-23 | June | 27 | 23 | 4 | Week 4 | June 27 Week 4 | JUNE 27 | PLANNED | JUNE 27 PLANNED
3 | 2027-06-24 | June | 27 | 24 | 4 | Week 4 | June 27 Week 4 | JUNE 27 | PLANNED | JUNE 27 PLANNED
4 | 2027-06-25 | June | 27 | 25 | 4 | Week 4 | June 27 Week 4 | JUNE 27 | PLANNED | JUNE 27 PLANNED
5 | 2027-06-26 | June | 27 | 26 | 4 | Week 4 | June 27 Week 4 | JUNE 27 | PLANNED | JUNE 27 PLANNED
6 | 2027-06-27 | June | 27 | 27 | 4 | Week 4 | June 27 Week 4 | JUNE 27 | PLANNED | JUNE 27 PLANNED
7 | 2027-06-28 | June | 27 | 28 | 4 | Week 4 | June 27 Week 4 | JUNE 27 | PLANNED | JUNE 27 PLANNED
1 | 2027-06-29 | June | 27 | 29 | 5 | Week 5 | June 27 Week 5 | JUNE 27 | PLANNED | JUNE 27 PLANNED
2 | 2027-06-30 | June | 27 | 30 | 5 | Week 5 | June 27 Week 5 | JUNE 27 | PLANNED | JUNE 27 PLANNED
1 | 2027-07-01 | July | 27 | 1 | 1 | Week 1 | July 27 Week 1 | JULY 27 | PLANNED | JULY 27 PLANNED
2 | 2027-07-02 | July | 27 | 2 | 1 | Week 1 | July 27 Week 1 | JULY 27 | PLANNED | JULY 27 PLANNED
3 | 2027-07-03 | July | 27 | 3 | 1 | Week 1 | July 27 Week 1 | JULY 27 | PLANNED | JULY 27 PLANNED
4 | 2027-07-04 | July | 27 | 4 | 1 | Week 1 | July 27 Week 1 | JULY 27 | PLANNED | JULY 27 PLANNED
5 | 2027-07-05 | July | 27 | 5 | 1 | Week 1 | July 27 Week 1 | JULY 27 | PLANNED | JULY 27 PLANNED
6 | 2027-07-06 | July | 27 | 6 | 1 | Week 1 | July 27 Week 1 | JULY 27 | PLANNED | JULY 27 PLANNED
7 | 2027-07-07 | July | 27 | 7 | 1 | Week 1 | July 27 Week 1 | JULY 27 | PLANNED | JULY 27 PLANNED
1 | 2027-07-08 | July | 27 | 8 | 2 | Week 2 | July 27 Week 2 | JULY 27 | PLANNED | JULY 27 PLANNED
2 | 2027-07-09 | July | 27 | 9 | 2 | Week 2 | July 27 Week 2 | JULY 27 | PLANNED | JULY 27 PLANNED
3 | 2027-07-10 | July | 27 | 10 | 2 | Week 2 | July 27 Week 2 | JULY 27 | PLANNED | JULY 27 PLANNED
4 | 2027-07-11 | July | 27 | 11 | 2 | Week 2 | July 27 Week 2 | JULY 27 | PLANNED | JULY 27 PLANNED
5 | 2027-07-12 | July | 27 | 12 | 2 | Week 2 | July 27 Week 2 | JULY 27 | PLANNED | JULY 27 PLANNED
6 | 2027-07-13 | July | 27 | 13 | 2 | Week 2 | July 27 Week 2 | JULY 27 | PLANNED | JULY 27 PLANNED
7 | 2027-07-14 | July | 27 | 14 | 2 | Week 2 | July 27 Week 2 | JULY 27 | PLANNED | JULY 27 PLANNED
1 | 2027-07-15 | July | 27 | 15 | 3 | Week 3 | July 27 Week 3 | JULY 27 | PLANNED | JULY 27 PLANNED
2 | 2027-07-16 | July | 27 | 16 | 3 | Week 3 | July 27 Week 3 | JULY 27 | PLANNED | JULY 27 PLANNED
3 | 2027-07-17 | July | 27 | 17 | 3 | Week 3 | July 27 Week 3 | JULY 27 | PLANNED | JULY 27 PLANNED
4 | 2027-07-18 | July | 27 | 18 | 3 | Week 3 | July 27 Week 3 | JULY 27 | PLANNED | JULY 27 PLANNED
5 | 2027-07-19 | July | 27 | 19 | 3 | Week 3 | July 27 Week 3 | JULY 27 | PLANNED | JULY 27 PLANNED
6 | 2027-07-20 | July | 27 | 20 | 3 | Week 3 | July 27 Week 3 | JULY 27 | PLANNED | JULY 27 PLANNED
7 | 2027-07-21 | July | 27 | 21 | 3 | Week 3 | July 27 Week 3 | JULY 27 | PLANNED | JULY 27 PLANNED
1 | 2027-07-22 | July | 27 | 22 | 4 | Week 4 | July 27 Week 4 | JULY 27 | PLANNED | JULY 27 PLANNED
2 | 2027-07-23 | July | 27 | 23 | 4 | Week 4 | July 27 Week 4 | JULY 27 | PLANNED | JULY 27 PLANNED
3 | 2027-07-24 | July | 27 | 24 | 4 | Week 4 | July 27 Week 4 | JULY 27 | PLANNED | JULY 27 PLANNED
4 | 2027-07-25 | July | 27 | 25 | 4 | Week 4 | July 27 Week 4 | JULY 27 | PLANNED | JULY 27 PLANNED
5 | 2027-07-26 | July | 27 | 26 | 4 | Week 4 | July 27 Week 4 | JULY 27 | PLANNED | JULY 27 PLANNED
6 | 2027-07-27 | July | 27 | 27 | 4 | Week 4 | July 27 Week 4 | JULY 27 | PLANNED | JULY 27 PLANNED
7 | 2027-07-28 | July | 27 | 28 | 4 | Week 4 | July 27 Week 4 | JULY 27 | PLANNED | JULY 27 PLANNED
1 | 2027-07-29 | July | 27 | 29 | 5 | Week 5 | July 27 Week 5 | JULY 27 | PLANNED | JULY 27 PLANNED
2 | 2027-07-30 | July | 27 | 30 | 5 | Week 5 | July 27 Week 5 | JULY 27 | PLANNED | JULY 27 PLANNED
3 | 2027-07-31 | July | 27 | 31 | 5 | Week 5 | July 27 Week 5 | JULY 27 | PLANNED | JULY 27 PLANNED
1 | 2027-08-01 | August | 27 | 1 | 1 | Week 1 | August 27 Week 1 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
2 | 2027-08-02 | August | 27 | 2 | 1 | Week 1 | August 27 Week 1 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
3 | 2027-08-03 | August | 27 | 3 | 1 | Week 1 | August 27 Week 1 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
4 | 2027-08-04 | August | 27 | 4 | 1 | Week 1 | August 27 Week 1 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
5 | 2027-08-05 | August | 27 | 5 | 1 | Week 1 | August 27 Week 1 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
6 | 2027-08-06 | August | 27 | 6 | 1 | Week 1 | August 27 Week 1 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
7 | 2027-08-07 | August | 27 | 7 | 1 | Week 1 | August 27 Week 1 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
1 | 2027-08-08 | August | 27 | 8 | 2 | Week 2 | August 27 Week 2 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
2 | 2027-08-09 | August | 27 | 9 | 2 | Week 2 | August 27 Week 2 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
3 | 2027-08-10 | August | 27 | 10 | 2 | Week 2 | August 27 Week 2 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
4 | 2027-08-11 | August | 27 | 11 | 2 | Week 2 | August 27 Week 2 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
5 | 2027-08-12 | August | 27 | 12 | 2 | Week 2 | August 27 Week 2 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
6 | 2027-08-13 | August | 27 | 13 | 2 | Week 2 | August 27 Week 2 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
7 | 2027-08-14 | August | 27 | 14 | 2 | Week 2 | August 27 Week 2 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
1 | 2027-08-15 | August | 27 | 15 | 3 | Week 3 | August 27 Week 3 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
2 | 2027-08-16 | August | 27 | 16 | 3 | Week 3 | August 27 Week 3 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
3 | 2027-08-17 | August | 27 | 17 | 3 | Week 3 | August 27 Week 3 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
4 | 2027-08-18 | August | 27 | 18 | 3 | Week 3 | August 27 Week 3 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
5 | 2027-08-19 | August | 27 | 19 | 3 | Week 3 | August 27 Week 3 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
6 | 2027-08-20 | August | 27 | 20 | 3 | Week 3 | August 27 Week 3 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
7 | 2027-08-21 | August | 27 | 21 | 3 | Week 3 | August 27 Week 3 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
1 | 2027-08-22 | August | 27 | 22 | 4 | Week 4 | August 27 Week 4 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
2 | 2027-08-23 | August | 27 | 23 | 4 | Week 4 | August 27 Week 4 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
3 | 2027-08-24 | August | 27 | 24 | 4 | Week 4 | August 27 Week 4 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
4 | 2027-08-25 | August | 27 | 25 | 4 | Week 4 | August 27 Week 4 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
5 | 2027-08-26 | August | 27 | 26 | 4 | Week 4 | August 27 Week 4 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
6 | 2027-08-27 | August | 27 | 27 | 4 | Week 4 | August 27 Week 4 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
7 | 2027-08-28 | August | 27 | 28 | 4 | Week 4 | August 27 Week 4 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
1 | 2027-08-29 | August | 27 | 29 | 5 | Week 5 | August 27 Week 5 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
2 | 2027-08-30 | August | 27 | 30 | 5 | Week 5 | August 27 Week 5 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
3 | 2027-08-31 | August | 27 | 31 | 5 | Week 5 | August 27 Week 5 | AUGUST 27 | PLANNED | AUGUST 27 PLANNED
1 | 2027-09-01 | September | 27 | 1 | 1 | Week 1 | September 27 Week 1 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
2 | 2027-09-02 | September | 27 | 2 | 1 | Week 1 | September 27 Week 1 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
3 | 2027-09-03 | September | 27 | 3 | 1 | Week 1 | September 27 Week 1 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
4 | 2027-09-04 | September | 27 | 4 | 1 | Week 1 | September 27 Week 1 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
5 | 2027-09-05 | September | 27 | 5 | 1 | Week 1 | September 27 Week 1 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
6 | 2027-09-06 | September | 27 | 6 | 1 | Week 1 | September 27 Week 1 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
7 | 2027-09-07 | September | 27 | 7 | 1 | Week 1 | September 27 Week 1 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
1 | 2027-09-08 | September | 27 | 8 | 2 | Week 2 | September 27 Week 2 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
2 | 2027-09-09 | September | 27 | 9 | 2 | Week 2 | September 27 Week 2 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
3 | 2027-09-10 | September | 27 | 10 | 2 | Week 2 | September 27 Week 2 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
4 | 2027-09-11 | September | 27 | 11 | 2 | Week 2 | September 27 Week 2 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
5 | 2027-09-12 | September | 27 | 12 | 2 | Week 2 | September 27 Week 2 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
6 | 2027-09-13 | September | 27 | 13 | 2 | Week 2 | September 27 Week 2 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
7 | 2027-09-14 | September | 27 | 14 | 2 | Week 2 | September 27 Week 2 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
1 | 2027-09-15 | September | 27 | 15 | 3 | Week 3 | September 27 Week 3 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
2 | 2027-09-16 | September | 27 | 16 | 3 | Week 3 | September 27 Week 3 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
3 | 2027-09-17 | September | 27 | 17 | 3 | Week 3 | September 27 Week 3 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
4 | 2027-09-18 | September | 27 | 18 | 3 | Week 3 | September 27 Week 3 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
5 | 2027-09-19 | September | 27 | 19 | 3 | Week 3 | September 27 Week 3 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
6 | 2027-09-20 | September | 27 | 20 | 3 | Week 3 | September 27 Week 3 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
7 | 2027-09-21 | September | 27 | 21 | 3 | Week 3 | September 27 Week 3 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
1 | 2027-09-22 | September | 27 | 22 | 4 | Week 4 | September 27 Week 4 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
2 | 2027-09-23 | September | 27 | 23 | 4 | Week 4 | September 27 Week 4 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
3 | 2027-09-24 | September | 27 | 24 | 4 | Week 4 | September 27 Week 4 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
4 | 2027-09-25 | September | 27 | 25 | 4 | Week 4 | September 27 Week 4 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
5 | 2027-09-26 | September | 27 | 26 | 4 | Week 4 | September 27 Week 4 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
6 | 2027-09-27 | September | 27 | 27 | 4 | Week 4 | September 27 Week 4 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
7 | 2027-09-28 | September | 27 | 28 | 4 | Week 4 | September 27 Week 4 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
1 | 2027-09-29 | September | 27 | 29 | 5 | Week 5 | September 27 Week 5 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
2 | 2027-09-30 | September | 27 | 30 | 5 | Week 5 | September 27 Week 5 | SEPTEMBER 27 | PLANNED | SEPTEMBER 27 PLANNED
1 | 2027-10-01 | October | 27 | 1 | 1 | Week 1 | October 27 Week 1 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
2 | 2027-10-02 | October | 27 | 2 | 1 | Week 1 | October 27 Week 1 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
3 | 2027-10-03 | October | 27 | 3 | 1 | Week 1 | October 27 Week 1 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
4 | 2027-10-04 | October | 27 | 4 | 1 | Week 1 | October 27 Week 1 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
5 | 2027-10-05 | October | 27 | 5 | 1 | Week 1 | October 27 Week 1 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
6 | 2027-10-06 | October | 27 | 6 | 1 | Week 1 | October 27 Week 1 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
7 | 2027-10-07 | October | 27 | 7 | 1 | Week 1 | October 27 Week 1 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
1 | 2027-10-08 | October | 27 | 8 | 2 | Week 2 | October 27 Week 2 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
2 | 2027-10-09 | October | 27 | 9 | 2 | Week 2 | October 27 Week 2 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
3 | 2027-10-10 | October | 27 | 10 | 2 | Week 2 | October 27 Week 2 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
4 | 2027-10-11 | October | 27 | 11 | 2 | Week 2 | October 27 Week 2 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
5 | 2027-10-12 | October | 27 | 12 | 2 | Week 2 | October 27 Week 2 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
6 | 2027-10-13 | October | 27 | 13 | 2 | Week 2 | October 27 Week 2 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
7 | 2027-10-14 | October | 27 | 14 | 2 | Week 2 | October 27 Week 2 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
1 | 2027-10-15 | October | 27 | 15 | 3 | Week 3 | October 27 Week 3 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
2 | 2027-10-16 | October | 27 | 16 | 3 | Week 3 | October 27 Week 3 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
3 | 2027-10-17 | October | 27 | 17 | 3 | Week 3 | October 27 Week 3 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
4 | 2027-10-18 | October | 27 | 18 | 3 | Week 3 | October 27 Week 3 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
5 | 2027-10-19 | October | 27 | 19 | 3 | Week 3 | October 27 Week 3 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
6 | 2027-10-20 | October | 27 | 20 | 3 | Week 3 | October 27 Week 3 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
7 | 2027-10-21 | October | 27 | 21 | 3 | Week 3 | October 27 Week 3 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
1 | 2027-10-22 | October | 27 | 22 | 4 | Week 4 | October 27 Week 4 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
2 | 2027-10-23 | October | 27 | 23 | 4 | Week 4 | October 27 Week 4 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
3 | 2027-10-24 | October | 27 | 24 | 4 | Week 4 | October 27 Week 4 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
4 | 2027-10-25 | October | 27 | 25 | 4 | Week 4 | October 27 Week 4 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
5 | 2027-10-26 | October | 27 | 26 | 4 | Week 4 | October 27 Week 4 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
6 | 2027-10-27 | October | 27 | 27 | 4 | Week 4 | October 27 Week 4 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
7 | 2027-10-28 | October | 27 | 28 | 4 | Week 4 | October 27 Week 4 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
1 | 2027-10-29 | October | 27 | 29 | 5 | Week 5 | October 27 Week 5 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
2 | 2027-10-30 | October | 27 | 30 | 5 | Week 5 | October 27 Week 5 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
3 | 2027-10-31 | October | 27 | 31 | 5 | Week 5 | October 27 Week 5 | OCTOBER 27 | PLANNED | OCTOBER 27 PLANNED
1 | 2027-11-01 | November | 27 | 1 | 1 | Week 1 | November 27 Week 1 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
2 | 2027-11-02 | November | 27 | 2 | 1 | Week 1 | November 27 Week 1 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
3 | 2027-11-03 | November | 27 | 3 | 1 | Week 1 | November 27 Week 1 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
4 | 2027-11-04 | November | 27 | 4 | 1 | Week 1 | November 27 Week 1 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
5 | 2027-11-05 | November | 27 | 5 | 1 | Week 1 | November 27 Week 1 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
6 | 2027-11-06 | November | 27 | 6 | 1 | Week 1 | November 27 Week 1 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
7 | 2027-11-07 | November | 27 | 7 | 1 | Week 1 | November 27 Week 1 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
1 | 2027-11-08 | November | 27 | 8 | 2 | Week 2 | November 27 Week 2 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
2 | 2027-11-09 | November | 27 | 9 | 2 | Week 2 | November 27 Week 2 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
3 | 2027-11-10 | November | 27 | 10 | 2 | Week 2 | November 27 Week 2 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
4 | 2027-11-11 | November | 27 | 11 | 2 | Week 2 | November 27 Week 2 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
5 | 2027-11-12 | November | 27 | 12 | 2 | Week 2 | November 27 Week 2 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
6 | 2027-11-13 | November | 27 | 13 | 2 | Week 2 | November 27 Week 2 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
7 | 2027-11-14 | November | 27 | 14 | 2 | Week 2 | November 27 Week 2 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
1 | 2027-11-15 | November | 27 | 15 | 3 | Week 3 | November 27 Week 3 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
2 | 2027-11-16 | November | 27 | 16 | 3 | Week 3 | November 27 Week 3 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
3 | 2027-11-17 | November | 27 | 17 | 3 | Week 3 | November 27 Week 3 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
4 | 2027-11-18 | November | 27 | 18 | 3 | Week 3 | November 27 Week 3 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
5 | 2027-11-19 | November | 27 | 19 | 3 | Week 3 | November 27 Week 3 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
6 | 2027-11-20 | November | 27 | 20 | 3 | Week 3 | November 27 Week 3 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
7 | 2027-11-21 | November | 27 | 21 | 3 | Week 3 | November 27 Week 3 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
1 | 2027-11-22 | November | 27 | 22 | 4 | Week 4 | November 27 Week 4 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
2 | 2027-11-23 | November | 27 | 23 | 4 | Week 4 | November 27 Week 4 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
3 | 2027-11-24 | November | 27 | 24 | 4 | Week 4 | November 27 Week 4 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
4 | 2027-11-25 | November | 27 | 25 | 4 | Week 4 | November 27 Week 4 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
5 | 2027-11-26 | November | 27 | 26 | 4 | Week 4 | November 27 Week 4 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
6 | 2027-11-27 | November | 27 | 27 | 4 | Week 4 | November 27 Week 4 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
7 | 2027-11-28 | November | 27 | 28 | 4 | Week 4 | November 27 Week 4 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
1 | 2027-11-29 | November | 27 | 29 | 5 | Week 5 | November 27 Week 5 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
2 | 2027-11-30 | November | 27 | 30 | 5 | Week 5 | November 27 Week 5 | NOVEMBER 27 | PLANNED | NOVEMBER 27 PLANNED
1 | 2027-12-01 | December | 27 | 1 | 1 | Week 1 | December 27 Week 1 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
2 | 2027-12-02 | December | 27 | 2 | 1 | Week 1 | December 27 Week 1 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
3 | 2027-12-03 | December | 27 | 3 | 1 | Week 1 | December 27 Week 1 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
4 | 2027-12-04 | December | 27 | 4 | 1 | Week 1 | December 27 Week 1 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
5 | 2027-12-05 | December | 27 | 5 | 1 | Week 1 | December 27 Week 1 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
6 | 2027-12-06 | December | 27 | 6 | 1 | Week 1 | December 27 Week 1 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
7 | 2027-12-07 | December | 27 | 7 | 1 | Week 1 | December 27 Week 1 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
1 | 2027-12-08 | December | 27 | 8 | 2 | Week 2 | December 27 Week 2 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
2 | 2027-12-09 | December | 27 | 9 | 2 | Week 2 | December 27 Week 2 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
3 | 2027-12-10 | December | 27 | 10 | 2 | Week 2 | December 27 Week 2 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
4 | 2027-12-11 | December | 27 | 11 | 2 | Week 2 | December 27 Week 2 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
5 | 2027-12-12 | December | 27 | 12 | 2 | Week 2 | December 27 Week 2 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
6 | 2027-12-13 | December | 27 | 13 | 2 | Week 2 | December 27 Week 2 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
7 | 2027-12-14 | December | 27 | 14 | 2 | Week 2 | December 27 Week 2 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
1 | 2027-12-15 | December | 27 | 15 | 3 | Week 3 | December 27 Week 3 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
2 | 2027-12-16 | December | 27 | 16 | 3 | Week 3 | December 27 Week 3 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
3 | 2027-12-17 | December | 27 | 17 | 3 | Week 3 | December 27 Week 3 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
4 | 2027-12-18 | December | 27 | 18 | 3 | Week 3 | December 27 Week 3 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
5 | 2027-12-19 | December | 27 | 19 | 3 | Week 3 | December 27 Week 3 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
6 | 2027-12-20 | December | 27 | 20 | 3 | Week 3 | December 27 Week 3 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
7 | 2027-12-21 | December | 27 | 21 | 3 | Week 3 | December 27 Week 3 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
1 | 2027-12-22 | December | 27 | 22 | 4 | Week 4 | December 27 Week 4 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
2 | 2027-12-23 | December | 27 | 23 | 4 | Week 4 | December 27 Week 4 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
3 | 2027-12-24 | December | 27 | 24 | 4 | Week 4 | December 27 Week 4 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
4 | 2027-12-25 | December | 27 | 25 | 4 | Week 4 | December 27 Week 4 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
5 | 2027-12-26 | December | 27 | 26 | 4 | Week 4 | December 27 Week 4 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
6 | 2027-12-27 | December | 27 | 27 | 4 | Week 4 | December 27 Week 4 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
7 | 2027-12-28 | December | 27 | 28 | 4 | Week 4 | December 27 Week 4 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
1 | 2027-12-29 | December | 27 | 29 | 5 | Week 5 | December 27 Week 5 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
2 | 2027-12-30 | December | 27 | 30 | 5 | Week 5 | December 27 Week 5 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
3 | 2027-12-31 | December | 27 | 31 | 5 | Week 5 | December 27 Week 5 | DECEMBER 27 | PLANNED | DECEMBER 27 PLANNED
1 | 2028-01-01 | January | 28 | 1 | 1 | Week 1 | January 28 Week 1 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
2 | 2028-01-02 | January | 28 | 2 | 1 | Week 1 | January 28 Week 1 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
3 | 2028-01-03 | January | 28 | 3 | 1 | Week 1 | January 28 Week 1 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
4 | 2028-01-04 | January | 28 | 4 | 1 | Week 1 | January 28 Week 1 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
5 | 2028-01-05 | January | 28 | 5 | 1 | Week 1 | January 28 Week 1 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
6 | 2028-01-06 | January | 28 | 6 | 1 | Week 1 | January 28 Week 1 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
7 | 2028-01-07 | January | 28 | 7 | 1 | Week 1 | January 28 Week 1 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
1 | 2028-01-08 | January | 28 | 8 | 2 | Week 2 | January 28 Week 2 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
2 | 2028-01-09 | January | 28 | 9 | 2 | Week 2 | January 28 Week 2 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
3 | 2028-01-10 | January | 28 | 10 | 2 | Week 2 | January 28 Week 2 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
4 | 2028-01-11 | January | 28 | 11 | 2 | Week 2 | January 28 Week 2 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
5 | 2028-01-12 | January | 28 | 12 | 2 | Week 2 | January 28 Week 2 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
6 | 2028-01-13 | January | 28 | 13 | 2 | Week 2 | January 28 Week 2 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
7 | 2028-01-14 | January | 28 | 14 | 2 | Week 2 | January 28 Week 2 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
1 | 2028-01-15 | January | 28 | 15 | 3 | Week 3 | January 28 Week 3 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
2 | 2028-01-16 | January | 28 | 16 | 3 | Week 3 | January 28 Week 3 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
3 | 2028-01-17 | January | 28 | 17 | 3 | Week 3 | January 28 Week 3 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
4 | 2028-01-18 | January | 28 | 18 | 3 | Week 3 | January 28 Week 3 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
5 | 2028-01-19 | January | 28 | 19 | 3 | Week 3 | January 28 Week 3 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
6 | 2028-01-20 | January | 28 | 20 | 3 | Week 3 | January 28 Week 3 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
7 | 2028-01-21 | January | 28 | 21 | 3 | Week 3 | January 28 Week 3 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
1 | 2028-01-22 | January | 28 | 22 | 4 | Week 4 | January 28 Week 4 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
2 | 2028-01-23 | January | 28 | 23 | 4 | Week 4 | January 28 Week 4 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
3 | 2028-01-24 | January | 28 | 24 | 4 | Week 4 | January 28 Week 4 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
4 | 2028-01-25 | January | 28 | 25 | 4 | Week 4 | January 28 Week 4 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
5 | 2028-01-26 | January | 28 | 26 | 4 | Week 4 | January 28 Week 4 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
6 | 2028-01-27 | January | 28 | 27 | 4 | Week 4 | January 28 Week 4 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
7 | 2028-01-28 | January | 28 | 28 | 4 | Week 4 | January 28 Week 4 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
1 | 2028-01-29 | January | 28 | 29 | 5 | Week 5 | January 28 Week 5 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
2 | 2028-01-30 | January | 28 | 30 | 5 | Week 5 | January 28 Week 5 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
3 | 2028-01-31 | January | 28 | 31 | 5 | Week 5 | January 28 Week 5 | JANUARY 28 | PLANNED | JANUARY 28 PLANNED
1 | 2028-02-01 | February | 28 | 1 | 1 | Week 1 | February 28 Week 1 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
2 | 2028-02-02 | February | 28 | 2 | 1 | Week 1 | February 28 Week 1 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
3 | 2028-02-03 | February | 28 | 3 | 1 | Week 1 | February 28 Week 1 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
4 | 2028-02-04 | February | 28 | 4 | 1 | Week 1 | February 28 Week 1 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
5 | 2028-02-05 | February | 28 | 5 | 1 | Week 1 | February 28 Week 1 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
6 | 2028-02-06 | February | 28 | 6 | 1 | Week 1 | February 28 Week 1 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
7 | 2028-02-07 | February | 28 | 7 | 1 | Week 1 | February 28 Week 1 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
1 | 2028-02-08 | February | 28 | 8 | 2 | Week 2 | February 28 Week 2 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
2 | 2028-02-09 | February | 28 | 9 | 2 | Week 2 | February 28 Week 2 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
3 | 2028-02-10 | February | 28 | 10 | 2 | Week 2 | February 28 Week 2 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
4 | 2028-02-11 | February | 28 | 11 | 2 | Week 2 | February 28 Week 2 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
5 | 2028-02-12 | February | 28 | 12 | 2 | Week 2 | February 28 Week 2 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
6 | 2028-02-13 | February | 28 | 13 | 2 | Week 2 | February 28 Week 2 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
7 | 2028-02-14 | February | 28 | 14 | 2 | Week 2 | February 28 Week 2 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
1 | 2028-02-15 | February | 28 | 15 | 3 | Week 3 | February 28 Week 3 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
2 | 2028-02-16 | February | 28 | 16 | 3 | Week 3 | February 28 Week 3 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
3 | 2028-02-17 | February | 28 | 17 | 3 | Week 3 | February 28 Week 3 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
4 | 2028-02-18 | February | 28 | 18 | 3 | Week 3 | February 28 Week 3 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
5 | 2028-02-19 | February | 28 | 19 | 3 | Week 3 | February 28 Week 3 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
6 | 2028-02-20 | February | 28 | 20 | 3 | Week 3 | February 28 Week 3 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
7 | 2028-02-21 | February | 28 | 21 | 3 | Week 3 | February 28 Week 3 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
1 | 2028-02-22 | February | 28 | 22 | 4 | Week 4 | February 28 Week 4 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
2 | 2028-02-23 | February | 28 | 23 | 4 | Week 4 | February 28 Week 4 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
3 | 2028-02-24 | February | 28 | 24 | 4 | Week 4 | February 28 Week 4 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
4 | 2028-02-25 | February | 28 | 25 | 4 | Week 4 | February 28 Week 4 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
5 | 2028-02-26 | February | 28 | 26 | 4 | Week 4 | February 28 Week 4 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
6 | 2028-02-27 | February | 28 | 27 | 4 | Week 4 | February 28 Week 4 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
7 | 2028-02-28 | February | 28 | 28 | 4 | Week 4 | February 28 Week 4 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
1 | 2028-02-29 | February | 28 | 29 | 5 | Week 5 | February 28 Week 5 | FEBRUARY 28 | PLANNED | FEBRUARY 28 PLANNED
1 | 2028-03-01 | March | 28 | 1 | 1 | Week 1 | March 28 Week 1 | MARCH 28 | PLANNED | MARCH 28 PLANNED
2 | 2028-03-02 | March | 28 | 2 | 1 | Week 1 | March 28 Week 1 | MARCH 28 | PLANNED | MARCH 28 PLANNED
3 | 2028-03-03 | March | 28 | 3 | 1 | Week 1 | March 28 Week 1 | MARCH 28 | PLANNED | MARCH 28 PLANNED
4 | 2028-03-04 | March | 28 | 4 | 1 | Week 1 | March 28 Week 1 | MARCH 28 | PLANNED | MARCH 28 PLANNED
5 | 2028-03-05 | March | 28 | 5 | 1 | Week 1 | March 28 Week 1 | MARCH 28 | PLANNED | MARCH 28 PLANNED
6 | 2028-03-06 | March | 28 | 6 | 1 | Week 1 | March 28 Week 1 | MARCH 28 | PLANNED | MARCH 28 PLANNED
7 | 2028-03-07 | March | 28 | 7 | 1 | Week 1 | March 28 Week 1 | MARCH 28 | PLANNED | MARCH 28 PLANNED
1 | 2028-03-08 | March | 28 | 8 | 2 | Week 2 | March 28 Week 2 | MARCH 28 | PLANNED | MARCH 28 PLANNED
2 | 2028-03-09 | March | 28 | 9 | 2 | Week 2 | March 28 Week 2 | MARCH 28 | PLANNED | MARCH 28 PLANNED
3 | 2028-03-10 | March | 28 | 10 | 2 | Week 2 | March 28 Week 2 | MARCH 28 | PLANNED | MARCH 28 PLANNED
4 | 2028-03-11 | March | 28 | 11 | 2 | Week 2 | March 28 Week 2 | MARCH 28 | PLANNED | MARCH 28 PLANNED
5 | 2028-03-12 | March | 28 | 12 | 2 | Week 2 | March 28 Week 2 | MARCH 28 | PLANNED | MARCH 28 PLANNED
6 | 2028-03-13 | March | 28 | 13 | 2 | Week 2 | March 28 Week 2 | MARCH 28 | PLANNED | MARCH 28 PLANNED
7 | 2028-03-14 | March | 28 | 14 | 2 | Week 2 | March 28 Week 2 | MARCH 28 | PLANNED | MARCH 28 PLANNED
1 | 2028-03-15 | March | 28 | 15 | 3 | Week 3 | March 28 Week 3 | MARCH 28 | PLANNED | MARCH 28 PLANNED
2 | 2028-03-16 | March | 28 | 16 | 3 | Week 3 | March 28 Week 3 | MARCH 28 | PLANNED | MARCH 28 PLANNED
3 | 2028-03-17 | March | 28 | 17 | 3 | Week 3 | March 28 Week 3 | MARCH 28 | PLANNED | MARCH 28 PLANNED
4 | 2028-03-18 | March | 28 | 18 | 3 | Week 3 | March 28 Week 3 | MARCH 28 | PLANNED | MARCH 28 PLANNED
5 | 2028-03-19 | March | 28 | 19 | 3 | Week 3 | March 28 Week 3 | MARCH 28 | PLANNED | MARCH 28 PLANNED
6 | 2028-03-20 | March | 28 | 20 | 3 | Week 3 | March 28 Week 3 | MARCH 28 | PLANNED | MARCH 28 PLANNED
7 | 2028-03-21 | March | 28 | 21 | 3 | Week 3 | March 28 Week 3 | MARCH 28 | PLANNED | MARCH 28 PLANNED
1 | 2028-03-22 | March | 28 | 22 | 4 | Week 4 | March 28 Week 4 | MARCH 28 | PLANNED | MARCH 28 PLANNED
2 | 2028-03-23 | March | 28 | 23 | 4 | Week 4 | March 28 Week 4 | MARCH 28 | PLANNED | MARCH 28 PLANNED
3 | 2028-03-24 | March | 28 | 24 | 4 | Week 4 | March 28 Week 4 | MARCH 28 | PLANNED | MARCH 28 PLANNED
4 | 2028-03-25 | March | 28 | 25 | 4 | Week 4 | March 28 Week 4 | MARCH 28 | PLANNED | MARCH 28 PLANNED
5 | 2028-03-26 | March | 28 | 26 | 4 | Week 4 | March 28 Week 4 | MARCH 28 | PLANNED | MARCH 28 PLANNED
6 | 2028-03-27 | March | 28 | 27 | 4 | Week 4 | March 28 Week 4 | MARCH 28 | PLANNED | MARCH 28 PLANNED
7 | 2028-03-28 | March | 28 | 28 | 4 | Week 4 | March 28 Week 4 | MARCH 28 | PLANNED | MARCH 28 PLANNED
1 | 2028-03-29 | March | 28 | 29 | 5 | Week 5 | March 28 Week 5 | MARCH 28 | PLANNED | MARCH 28 PLANNED
2 | 2028-03-30 | March | 28 | 30 | 5 | Week 5 | March 28 Week 5 | MARCH 28 | PLANNED | MARCH 28 PLANNED
3 | 2028-03-31 | March | 28 | 31 | 5 | Week 5 | March 28 Week 5 | MARCH 28 | PLANNED | MARCH 28 PLANNED
1 | 2028-04-01 | April | 28 | 1 | 1 | Week 1 | April 28 Week 1 | APRIL 28 | PLANNED | APRIL 28 PLANNED
2 | 2028-04-02 | April | 28 | 2 | 1 | Week 1 | April 28 Week 1 | APRIL 28 | PLANNED | APRIL 28 PLANNED
3 | 2028-04-03 | April | 28 | 3 | 1 | Week 1 | April 28 Week 1 | APRIL 28 | PLANNED | APRIL 28 PLANNED
4 | 2028-04-04 | April | 28 | 4 | 1 | Week 1 | April 28 Week 1 | APRIL 28 | PLANNED | APRIL 28 PLANNED
5 | 2028-04-05 | April | 28 | 5 | 1 | Week 1 | April 28 Week 1 | APRIL 28 | PLANNED | APRIL 28 PLANNED
6 | 2028-04-06 | April | 28 | 6 | 1 | Week 1 | April 28 Week 1 | APRIL 28 | PLANNED | APRIL 28 PLANNED
7 | 2028-04-07 | April | 28 | 7 | 1 | Week 1 | April 28 Week 1 | APRIL 28 | PLANNED | APRIL 28 PLANNED
1 | 2028-04-08 | April | 28 | 8 | 2 | Week 2 | April 28 Week 2 | APRIL 28 | PLANNED | APRIL 28 PLANNED
2 | 2028-04-09 | April | 28 | 9 | 2 | Week 2 | April 28 Week 2 | APRIL 28 | PLANNED | APRIL 28 PLANNED
3 | 2028-04-10 | April | 28 | 10 | 2 | Week 2 | April 28 Week 2 | APRIL 28 | PLANNED | APRIL 28 PLANNED
4 | 2028-04-11 | April | 28 | 11 | 2 | Week 2 | April 28 Week 2 | APRIL 28 | PLANNED | APRIL 28 PLANNED
5 | 2028-04-12 | April | 28 | 12 | 2 | Week 2 | April 28 Week 2 | APRIL 28 | PLANNED | APRIL 28 PLANNED
6 | 2028-04-13 | April | 28 | 13 | 2 | Week 2 | April 28 Week 2 | APRIL 28 | PLANNED | APRIL 28 PLANNED
7 | 2028-04-14 | April | 28 | 14 | 2 | Week 2 | April 28 Week 2 | APRIL 28 | PLANNED | APRIL 28 PLANNED
1 | 2028-04-15 | April | 28 | 15 | 3 | Week 3 | April 28 Week 3 | APRIL 28 | PLANNED | APRIL 28 PLANNED
2 | 2028-04-16 | April | 28 | 16 | 3 | Week 3 | April 28 Week 3 | APRIL 28 | PLANNED | APRIL 28 PLANNED
3 | 2028-04-17 | April | 28 | 17 | 3 | Week 3 | April 28 Week 3 | APRIL 28 | PLANNED | APRIL 28 PLANNED
4 | 2028-04-18 | April | 28 | 18 | 3 | Week 3 | April 28 Week 3 | APRIL 28 | PLANNED | APRIL 28 PLANNED
5 | 2028-04-19 | April | 28 | 19 | 3 | Week 3 | April 28 Week 3 | APRIL 28 | PLANNED | APRIL 28 PLANNED
6 | 2028-04-20 | April | 28 | 20 | 3 | Week 3 | April 28 Week 3 | APRIL 28 | PLANNED | APRIL 28 PLANNED
7 | 2028-04-21 | April | 28 | 21 | 3 | Week 3 | April 28 Week 3 | APRIL 28 | PLANNED | APRIL 28 PLANNED
1 | 2028-04-22 | April | 28 | 22 | 4 | Week 4 | April 28 Week 4 | APRIL 28 | PLANNED | APRIL 28 PLANNED
2 | 2028-04-23 | April | 28 | 23 | 4 | Week 4 | April 28 Week 4 | APRIL 28 | PLANNED | APRIL 28 PLANNED
3 | 2028-04-24 | April | 28 | 24 | 4 | Week 4 | April 28 Week 4 | APRIL 28 | PLANNED | APRIL 28 PLANNED
4 | 2028-04-25 | April | 28 | 25 | 4 | Week 4 | April 28 Week 4 | APRIL 28 | PLANNED | APRIL 28 PLANNED
5 | 2028-04-26 | April | 28 | 26 | 4 | Week 4 | April 28 Week 4 | APRIL 28 | PLANNED | APRIL 28 PLANNED
6 | 2028-04-27 | April | 28 | 27 | 4 | Week 4 | April 28 Week 4 | APRIL 28 | PLANNED | APRIL 28 PLANNED
7 | 2028-04-28 | April | 28 | 28 | 4 | Week 4 | April 28 Week 4 | APRIL 28 | PLANNED | APRIL 28 PLANNED
1 | 2028-04-29 | April | 28 | 29 | 5 | Week 5 | April 28 Week 5 | APRIL 28 | PLANNED | APRIL 28 PLANNED
2 | 2028-04-30 | April | 28 | 30 | 5 | Week 5 | April 28 Week 5 | APRIL 28 | PLANNED | APRIL 28 PLANNED
1 | 2028-05-01 | May | 28 | 1 | 1 | Week 1 | May 28 Week 1 | MAY 28 | PLANNED | MAY 28 PLANNED
2 | 2028-05-02 | May | 28 | 2 | 1 | Week 1 | May 28 Week 1 | MAY 28 | PLANNED | MAY 28 PLANNED
3 | 2028-05-03 | May | 28 | 3 | 1 | Week 1 | May 28 Week 1 | MAY 28 | PLANNED | MAY 28 PLANNED
4 | 2028-05-04 | May | 28 | 4 | 1 | Week 1 | May 28 Week 1 | MAY 28 | PLANNED | MAY 28 PLANNED
5 | 2028-05-05 | May | 28 | 5 | 1 | Week 1 | May 28 Week 1 | MAY 28 | PLANNED | MAY 28 PLANNED
6 | 2028-05-06 | May | 28 | 6 | 1 | Week 1 | May 28 Week 1 | MAY 28 | PLANNED | MAY 28 PLANNED
7 | 2028-05-07 | May | 28 | 7 | 1 | Week 1 | May 28 Week 1 | MAY 28 | PLANNED | MAY 28 PLANNED
1 | 2028-05-08 | May | 28 | 8 | 2 | Week 2 | May 28 Week 2 | MAY 28 | PLANNED | MAY 28 PLANNED
2 | 2028-05-09 | May | 28 | 9 | 2 | Week 2 | May 28 Week 2 | MAY 28 | PLANNED | MAY 28 PLANNED
3 | 2028-05-10 | May | 28 | 10 | 2 | Week 2 | May 28 Week 2 | MAY 28 | PLANNED | MAY 28 PLANNED
4 | 2028-05-11 | May | 28 | 11 | 2 | Week 2 | May 28 Week 2 | MAY 28 | PLANNED | MAY 28 PLANNED
5 | 2028-05-12 | May | 28 | 12 | 2 | Week 2 | May 28 Week 2 | MAY 28 | PLANNED | MAY 28 PLANNED
6 | 2028-05-13 | May | 28 | 13 | 2 | Week 2 | May 28 Week 2 | MAY 28 | PLANNED | MAY 28 PLANNED
7 | 2028-05-14 | May | 28 | 14 | 2 | Week 2 | May 28 Week 2 | MAY 28 | PLANNED | MAY 28 PLANNED
1 | 2028-05-15 | May | 28 | 15 | 3 | Week 3 | May 28 Week 3 | MAY 28 | PLANNED | MAY 28 PLANNED
2 | 2028-05-16 | May | 28 | 16 | 3 | Week 3 | May 28 Week 3 | MAY 28 | PLANNED | MAY 28 PLANNED
3 | 2028-05-17 | May | 28 | 17 | 3 | Week 3 | May 28 Week 3 | MAY 28 | PLANNED | MAY 28 PLANNED
4 | 2028-05-18 | May | 28 | 18 | 3 | Week 3 | May 28 Week 3 | MAY 28 | PLANNED | MAY 28 PLANNED
5 | 2028-05-19 | May | 28 | 19 | 3 | Week 3 | May 28 Week 3 | MAY 28 | PLANNED | MAY 28 PLANNED
6 | 2028-05-20 | May | 28 | 20 | 3 | Week 3 | May 28 Week 3 | MAY 28 | PLANNED | MAY 28 PLANNED
7 | 2028-05-21 | May | 28 | 21 | 3 | Week 3 | May 28 Week 3 | MAY 28 | PLANNED | MAY 28 PLANNED
1 | 2028-05-22 | May | 28 | 22 | 4 | Week 4 | May 28 Week 4 | MAY 28 | PLANNED | MAY 28 PLANNED
2 | 2028-05-23 | May | 28 | 23 | 4 | Week 4 | May 28 Week 4 | MAY 28 | PLANNED | MAY 28 PLANNED
3 | 2028-05-24 | May | 28 | 24 | 4 | Week 4 | May 28 Week 4 | MAY 28 | PLANNED | MAY 28 PLANNED
4 | 2028-05-25 | May | 28 | 25 | 4 | Week 4 | May 28 Week 4 | MAY 28 | PLANNED | MAY 28 PLANNED
5 | 2028-05-26 | May | 28 | 26 | 4 | Week 4 | May 28 Week 4 | MAY 28 | PLANNED | MAY 28 PLANNED
6 | 2028-05-27 | May | 28 | 27 | 4 | Week 4 | May 28 Week 4 | MAY 28 | PLANNED | MAY 28 PLANNED
7 | 2028-05-28 | May | 28 | 28 | 4 | Week 4 | May 28 Week 4 | MAY 28 | PLANNED | MAY 28 PLANNED
1 | 2028-05-29 | May | 28 | 29 | 5 | Week 5 | May 28 Week 5 | MAY 28 | PLANNED | MAY 28 PLANNED
2 | 2028-05-30 | May | 28 | 30 | 5 | Week 5 | May 28 Week 5 | MAY 28 | PLANNED | MAY 28 PLANNED
3 | 2028-05-31 | May | 28 | 31 | 5 | Week 5 | May 28 Week 5 | MAY 28 | PLANNED | MAY 28 PLANNED
1 | 2028-06-01 | June | 28 | 1 | 1 | Week 1 | June 28 Week 1 | JUNE 28 | PLANNED | JUNE 28 PLANNED
2 | 2028-06-02 | June | 28 | 2 | 1 | Week 1 | June 28 Week 1 | JUNE 28 | PLANNED | JUNE 28 PLANNED
3 | 2028-06-03 | June | 28 | 3 | 1 | Week 1 | June 28 Week 1 | JUNE 28 | PLANNED | JUNE 28 PLANNED
4 | 2028-06-04 | June | 28 | 4 | 1 | Week 1 | June 28 Week 1 | JUNE 28 | PLANNED | JUNE 28 PLANNED
5 | 2028-06-05 | June | 28 | 5 | 1 | Week 1 | June 28 Week 1 | JUNE 28 | PLANNED | JUNE 28 PLANNED
6 | 2028-06-06 | June | 28 | 6 | 1 | Week 1 | June 28 Week 1 | JUNE 28 | PLANNED | JUNE 28 PLANNED
7 | 2028-06-07 | June | 28 | 7 | 1 | Week 1 | June 28 Week 1 | JUNE 28 | PLANNED | JUNE 28 PLANNED
1 | 2028-06-08 | June | 28 | 8 | 2 | Week 2 | June 28 Week 2 | JUNE 28 | PLANNED | JUNE 28 PLANNED
2 | 2028-06-09 | June | 28 | 9 | 2 | Week 2 | June 28 Week 2 | JUNE 28 | PLANNED | JUNE 28 PLANNED
3 | 2028-06-10 | June | 28 | 10 | 2 | Week 2 | June 28 Week 2 | JUNE 28 | PLANNED | JUNE 28 PLANNED
4 | 2028-06-11 | June | 28 | 11 | 2 | Week 2 | June 28 Week 2 | JUNE 28 | PLANNED | JUNE 28 PLANNED
5 | 2028-06-12 | June | 28 | 12 | 2 | Week 2 | June 28 Week 2 | JUNE 28 | PLANNED | JUNE 28 PLANNED
6 | 2028-06-13 | June | 28 | 13 | 2 | Week 2 | June 28 Week 2 | JUNE 28 | PLANNED | JUNE 28 PLANNED
7 | 2028-06-14 | June | 28 | 14 | 2 | Week 2 | June 28 Week 2 | JUNE 28 | PLANNED | JUNE 28 PLANNED
1 | 2028-06-15 | June | 28 | 15 | 3 | Week 3 | June 28 Week 3 | JUNE 28 | PLANNED | JUNE 28 PLANNED
2 | 2028-06-16 | June | 28 | 16 | 3 | Week 3 | June 28 Week 3 | JUNE 28 | PLANNED | JUNE 28 PLANNED
3 | 2028-06-17 | June | 28 | 17 | 3 | Week 3 | June 28 Week 3 | JUNE 28 | PLANNED | JUNE 28 PLANNED
4 | 2028-06-18 | June | 28 | 18 | 3 | Week 3 | June 28 Week 3 | JUNE 28 | PLANNED | JUNE 28 PLANNED
5 | 2028-06-19 | June | 28 | 19 | 3 | Week 3 | June 28 Week 3 | JUNE 28 | PLANNED | JUNE 28 PLANNED
6 | 2028-06-20 | June | 28 | 20 | 3 | Week 3 | June 28 Week 3 | JUNE 28 | PLANNED | JUNE 28 PLANNED
7 | 2028-06-21 | June | 28 | 21 | 3 | Week 3 | June 28 Week 3 | JUNE 28 | PLANNED | JUNE 28 PLANNED
1 | 2028-06-22 | June | 28 | 22 | 4 | Week 4 | June 28 Week 4 | JUNE 28 | PLANNED | JUNE 28 PLANNED
2 | 2028-06-23 | June | 28 | 23 | 4 | Week 4 | June 28 Week 4 | JUNE 28 | PLANNED | JUNE 28 PLANNED
3 | 2028-06-24 | June | 28 | 24 | 4 | Week 4 | June 28 Week 4 | JUNE 28 | PLANNED | JUNE 28 PLANNED
4 | 2028-06-25 | June | 28 | 25 | 4 | Week 4 | June 28 Week 4 | JUNE 28 | PLANNED | JUNE 28 PLANNED
5 | 2028-06-26 | June | 28 | 26 | 4 | Week 4 | June 28 Week 4 | JUNE 28 | PLANNED | JUNE 28 PLANNED
6 | 2028-06-27 | June | 28 | 27 | 4 | Week 4 | June 28 Week 4 | JUNE 28 | PLANNED | JUNE 28 PLANNED
7 | 2028-06-28 | June | 28 | 28 | 4 | Week 4 | June 28 Week 4 | JUNE 28 | PLANNED | JUNE 28 PLANNED
1 | 2028-06-29 | June | 28 | 29 | 5 | Week 5 | June 28 Week 5 | JUNE 28 | PLANNED | JUNE 28 PLANNED
2 | 2028-06-30 | June | 28 | 30 | 5 | Week 5 | June 28 Week 5 | JUNE 28 | PLANNED | JUNE 28 PLANNED
1 | 2028-07-01 | July | 28 | 1 | 1 | Week 1 | July 28 Week 1 | JULY 28 | PLANNED | JULY 28 PLANNED
2 | 2028-07-02 | July | 28 | 2 | 1 | Week 1 | July 28 Week 1 | JULY 28 | PLANNED | JULY 28 PLANNED
3 | 2028-07-03 | July | 28 | 3 | 1 | Week 1 | July 28 Week 1 | JULY 28 | PLANNED | JULY 28 PLANNED
4 | 2028-07-04 | July | 28 | 4 | 1 | Week 1 | July 28 Week 1 | JULY 28 | PLANNED | JULY 28 PLANNED
5 | 2028-07-05 | July | 28 | 5 | 1 | Week 1 | July 28 Week 1 | JULY 28 | PLANNED | JULY 28 PLANNED
6 | 2028-07-06 | July | 28 | 6 | 1 | Week 1 | July 28 Week 1 | JULY 28 | PLANNED | JULY 28 PLANNED
7 | 2028-07-07 | July | 28 | 7 | 1 | Week 1 | July 28 Week 1 | JULY 28 | PLANNED | JULY 28 PLANNED
1 | 2028-07-08 | July | 28 | 8 | 2 | Week 2 | July 28 Week 2 | JULY 28 | PLANNED | JULY 28 PLANNED
2 | 2028-07-09 | July | 28 | 9 | 2 | Week 2 | July 28 Week 2 | JULY 28 | PLANNED | JULY 28 PLANNED
3 | 2028-07-10 | July | 28 | 10 | 2 | Week 2 | July 28 Week 2 | JULY 28 | PLANNED | JULY 28 PLANNED
4 | 2028-07-11 | July | 28 | 11 | 2 | Week 2 | July 28 Week 2 | JULY 28 | PLANNED | JULY 28 PLANNED
5 | 2028-07-12 | July | 28 | 12 | 2 | Week 2 | July 28 Week 2 | JULY 28 | PLANNED | JULY 28 PLANNED
6 | 2028-07-13 | July | 28 | 13 | 2 | Week 2 | July 28 Week 2 | JULY 28 | PLANNED | JULY 28 PLANNED
7 | 2028-07-14 | July | 28 | 14 | 2 | Week 2 | July 28 Week 2 | JULY 28 | PLANNED | JULY 28 PLANNED
1 | 2028-07-15 | July | 28 | 15 | 3 | Week 3 | July 28 Week 3 | JULY 28 | PLANNED | JULY 28 PLANNED
2 | 2028-07-16 | July | 28 | 16 | 3 | Week 3 | July 28 Week 3 | JULY 28 | PLANNED | JULY 28 PLANNED
3 | 2028-07-17 | July | 28 | 17 | 3 | Week 3 | July 28 Week 3 | JULY 28 | PLANNED | JULY 28 PLANNED
4 | 2028-07-18 | July | 28 | 18 | 3 | Week 3 | July 28 Week 3 | JULY 28 | PLANNED | JULY 28 PLANNED
5 | 2028-07-19 | July | 28 | 19 | 3 | Week 3 | July 28 Week 3 | JULY 28 | PLANNED | JULY 28 PLANNED
6 | 2028-07-20 | July | 28 | 20 | 3 | Week 3 | July 28 Week 3 | JULY 28 | PLANNED | JULY 28 PLANNED
7 | 2028-07-21 | July | 28 | 21 | 3 | Week 3 | July 28 Week 3 | JULY 28 | PLANNED | JULY 28 PLANNED
1 | 2028-07-22 | July | 28 | 22 | 4 | Week 4 | July 28 Week 4 | JULY 28 | PLANNED | JULY 28 PLANNED
2 | 2028-07-23 | July | 28 | 23 | 4 | Week 4 | July 28 Week 4 | JULY 28 | PLANNED | JULY 28 PLANNED
3 | 2028-07-24 | July | 28 | 24 | 4 | Week 4 | July 28 Week 4 | JULY 28 | PLANNED | JULY 28 PLANNED
4 | 2028-07-25 | July | 28 | 25 | 4 | Week 4 | July 28 Week 4 | JULY 28 | PLANNED | JULY 28 PLANNED
5 | 2028-07-26 | July | 28 | 26 | 4 | Week 4 | July 28 Week 4 | JULY 28 | PLANNED | JULY 28 PLANNED
6 | 2028-07-27 | July | 28 | 27 | 4 | Week 4 | July 28 Week 4 | JULY 28 | PLANNED | JULY 28 PLANNED
7 | 2028-07-28 | July | 28 | 28 | 4 | Week 4 | July 28 Week 4 | JULY 28 | PLANNED | JULY 28 PLANNED
1 | 2028-07-29 | July | 28 | 29 | 5 | Week 5 | July 28 Week 5 | JULY 28 | PLANNED | JULY 28 PLANNED
2 | 2028-07-30 | July | 28 | 30 | 5 | Week 5 | July 28 Week 5 | JULY 28 | PLANNED | JULY 28 PLANNED
3 | 2028-07-31 | July | 28 | 31 | 5 | Week 5 | July 28 Week 5 | JULY 28 | PLANNED | JULY 28 PLANNED
1 | 2028-08-01 | August | 28 | 1 | 1 | Week 1 | August 28 Week 1 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
2 | 2028-08-02 | August | 28 | 2 | 1 | Week 1 | August 28 Week 1 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
3 | 2028-08-03 | August | 28 | 3 | 1 | Week 1 | August 28 Week 1 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
4 | 2028-08-04 | August | 28 | 4 | 1 | Week 1 | August 28 Week 1 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
5 | 2028-08-05 | August | 28 | 5 | 1 | Week 1 | August 28 Week 1 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
6 | 2028-08-06 | August | 28 | 6 | 1 | Week 1 | August 28 Week 1 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
7 | 2028-08-07 | August | 28 | 7 | 1 | Week 1 | August 28 Week 1 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
1 | 2028-08-08 | August | 28 | 8 | 2 | Week 2 | August 28 Week 2 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
2 | 2028-08-09 | August | 28 | 9 | 2 | Week 2 | August 28 Week 2 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
3 | 2028-08-10 | August | 28 | 10 | 2 | Week 2 | August 28 Week 2 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
4 | 2028-08-11 | August | 28 | 11 | 2 | Week 2 | August 28 Week 2 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
5 | 2028-08-12 | August | 28 | 12 | 2 | Week 2 | August 28 Week 2 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
6 | 2028-08-13 | August | 28 | 13 | 2 | Week 2 | August 28 Week 2 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
7 | 2028-08-14 | August | 28 | 14 | 2 | Week 2 | August 28 Week 2 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
1 | 2028-08-15 | August | 28 | 15 | 3 | Week 3 | August 28 Week 3 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
2 | 2028-08-16 | August | 28 | 16 | 3 | Week 3 | August 28 Week 3 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
3 | 2028-08-17 | August | 28 | 17 | 3 | Week 3 | August 28 Week 3 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
4 | 2028-08-18 | August | 28 | 18 | 3 | Week 3 | August 28 Week 3 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
5 | 2028-08-19 | August | 28 | 19 | 3 | Week 3 | August 28 Week 3 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
6 | 2028-08-20 | August | 28 | 20 | 3 | Week 3 | August 28 Week 3 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
7 | 2028-08-21 | August | 28 | 21 | 3 | Week 3 | August 28 Week 3 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
1 | 2028-08-22 | August | 28 | 22 | 4 | Week 4 | August 28 Week 4 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
2 | 2028-08-23 | August | 28 | 23 | 4 | Week 4 | August 28 Week 4 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
3 | 2028-08-24 | August | 28 | 24 | 4 | Week 4 | August 28 Week 4 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
4 | 2028-08-25 | August | 28 | 25 | 4 | Week 4 | August 28 Week 4 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
5 | 2028-08-26 | August | 28 | 26 | 4 | Week 4 | August 28 Week 4 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
6 | 2028-08-27 | August | 28 | 27 | 4 | Week 4 | August 28 Week 4 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
7 | 2028-08-28 | August | 28 | 28 | 4 | Week 4 | August 28 Week 4 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
1 | 2028-08-29 | August | 28 | 29 | 5 | Week 5 | August 28 Week 5 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
2 | 2028-08-30 | August | 28 | 30 | 5 | Week 5 | August 28 Week 5 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
3 | 2028-08-31 | August | 28 | 31 | 5 | Week 5 | August 28 Week 5 | AUGUST 28 | PLANNED | AUGUST 28 PLANNED
1 | 2028-09-01 | September | 28 | 1 | 1 | Week 1 | September 28 Week 1 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
2 | 2028-09-02 | September | 28 | 2 | 1 | Week 1 | September 28 Week 1 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
3 | 2028-09-03 | September | 28 | 3 | 1 | Week 1 | September 28 Week 1 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
4 | 2028-09-04 | September | 28 | 4 | 1 | Week 1 | September 28 Week 1 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
5 | 2028-09-05 | September | 28 | 5 | 1 | Week 1 | September 28 Week 1 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
6 | 2028-09-06 | September | 28 | 6 | 1 | Week 1 | September 28 Week 1 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
7 | 2028-09-07 | September | 28 | 7 | 1 | Week 1 | September 28 Week 1 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
1 | 2028-09-08 | September | 28 | 8 | 2 | Week 2 | September 28 Week 2 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
2 | 2028-09-09 | September | 28 | 9 | 2 | Week 2 | September 28 Week 2 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
3 | 2028-09-10 | September | 28 | 10 | 2 | Week 2 | September 28 Week 2 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
4 | 2028-09-11 | September | 28 | 11 | 2 | Week 2 | September 28 Week 2 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
5 | 2028-09-12 | September | 28 | 12 | 2 | Week 2 | September 28 Week 2 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
6 | 2028-09-13 | September | 28 | 13 | 2 | Week 2 | September 28 Week 2 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
7 | 2028-09-14 | September | 28 | 14 | 2 | Week 2 | September 28 Week 2 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
1 | 2028-09-15 | September | 28 | 15 | 3 | Week 3 | September 28 Week 3 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
2 | 2028-09-16 | September | 28 | 16 | 3 | Week 3 | September 28 Week 3 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
3 | 2028-09-17 | September | 28 | 17 | 3 | Week 3 | September 28 Week 3 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
4 | 2028-09-18 | September | 28 | 18 | 3 | Week 3 | September 28 Week 3 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
5 | 2028-09-19 | September | 28 | 19 | 3 | Week 3 | September 28 Week 3 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
6 | 2028-09-20 | September | 28 | 20 | 3 | Week 3 | September 28 Week 3 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
7 | 2028-09-21 | September | 28 | 21 | 3 | Week 3 | September 28 Week 3 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
1 | 2028-09-22 | September | 28 | 22 | 4 | Week 4 | September 28 Week 4 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
2 | 2028-09-23 | September | 28 | 23 | 4 | Week 4 | September 28 Week 4 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
3 | 2028-09-24 | September | 28 | 24 | 4 | Week 4 | September 28 Week 4 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
4 | 2028-09-25 | September | 28 | 25 | 4 | Week 4 | September 28 Week 4 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
5 | 2028-09-26 | September | 28 | 26 | 4 | Week 4 | September 28 Week 4 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
6 | 2028-09-27 | September | 28 | 27 | 4 | Week 4 | September 28 Week 4 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
7 | 2028-09-28 | September | 28 | 28 | 4 | Week 4 | September 28 Week 4 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
1 | 2028-09-29 | September | 28 | 29 | 5 | Week 5 | September 28 Week 5 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
2 | 2028-09-30 | September | 28 | 30 | 5 | Week 5 | September 28 Week 5 | SEPTEMBER 28 | PLANNED | SEPTEMBER 28 PLANNED
1 | 2028-10-01 | October | 28 | 1 | 1 | Week 1 | October 28 Week 1 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
2 | 2028-10-02 | October | 28 | 2 | 1 | Week 1 | October 28 Week 1 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
3 | 2028-10-03 | October | 28 | 3 | 1 | Week 1 | October 28 Week 1 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
4 | 2028-10-04 | October | 28 | 4 | 1 | Week 1 | October 28 Week 1 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
5 | 2028-10-05 | October | 28 | 5 | 1 | Week 1 | October 28 Week 1 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
6 | 2028-10-06 | October | 28 | 6 | 1 | Week 1 | October 28 Week 1 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
7 | 2028-10-07 | October | 28 | 7 | 1 | Week 1 | October 28 Week 1 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
1 | 2028-10-08 | October | 28 | 8 | 2 | Week 2 | October 28 Week 2 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
2 | 2028-10-09 | October | 28 | 9 | 2 | Week 2 | October 28 Week 2 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
3 | 2028-10-10 | October | 28 | 10 | 2 | Week 2 | October 28 Week 2 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
4 | 2028-10-11 | October | 28 | 11 | 2 | Week 2 | October 28 Week 2 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
5 | 2028-10-12 | October | 28 | 12 | 2 | Week 2 | October 28 Week 2 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
6 | 2028-10-13 | October | 28 | 13 | 2 | Week 2 | October 28 Week 2 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
7 | 2028-10-14 | October | 28 | 14 | 2 | Week 2 | October 28 Week 2 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
1 | 2028-10-15 | October | 28 | 15 | 3 | Week 3 | October 28 Week 3 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
2 | 2028-10-16 | October | 28 | 16 | 3 | Week 3 | October 28 Week 3 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
3 | 2028-10-17 | October | 28 | 17 | 3 | Week 3 | October 28 Week 3 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
4 | 2028-10-18 | October | 28 | 18 | 3 | Week 3 | October 28 Week 3 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
5 | 2028-10-19 | October | 28 | 19 | 3 | Week 3 | October 28 Week 3 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
6 | 2028-10-20 | October | 28 | 20 | 3 | Week 3 | October 28 Week 3 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
7 | 2028-10-21 | October | 28 | 21 | 3 | Week 3 | October 28 Week 3 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
1 | 2028-10-22 | October | 28 | 22 | 4 | Week 4 | October 28 Week 4 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
2 | 2028-10-23 | October | 28 | 23 | 4 | Week 4 | October 28 Week 4 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
3 | 2028-10-24 | October | 28 | 24 | 4 | Week 4 | October 28 Week 4 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
4 | 2028-10-25 | October | 28 | 25 | 4 | Week 4 | October 28 Week 4 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
5 | 2028-10-26 | October | 28 | 26 | 4 | Week 4 | October 28 Week 4 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
6 | 2028-10-27 | October | 28 | 27 | 4 | Week 4 | October 28 Week 4 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
7 | 2028-10-28 | October | 28 | 28 | 4 | Week 4 | October 28 Week 4 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
1 | 2028-10-29 | October | 28 | 29 | 5 | Week 5 | October 28 Week 5 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
2 | 2028-10-30 | October | 28 | 30 | 5 | Week 5 | October 28 Week 5 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
3 | 2028-10-31 | October | 28 | 31 | 5 | Week 5 | October 28 Week 5 | OCTOBER 28 | PLANNED | OCTOBER 28 PLANNED
1 | 2028-11-01 | November | 28 | 1 | 1 | Week 1 | November 28 Week 1 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
2 | 2028-11-02 | November | 28 | 2 | 1 | Week 1 | November 28 Week 1 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
3 | 2028-11-03 | November | 28 | 3 | 1 | Week 1 | November 28 Week 1 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
4 | 2028-11-04 | November | 28 | 4 | 1 | Week 1 | November 28 Week 1 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
5 | 2028-11-05 | November | 28 | 5 | 1 | Week 1 | November 28 Week 1 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
6 | 2028-11-06 | November | 28 | 6 | 1 | Week 1 | November 28 Week 1 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
7 | 2028-11-07 | November | 28 | 7 | 1 | Week 1 | November 28 Week 1 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
1 | 2028-11-08 | November | 28 | 8 | 2 | Week 2 | November 28 Week 2 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
2 | 2028-11-09 | November | 28 | 9 | 2 | Week 2 | November 28 Week 2 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
3 | 2028-11-10 | November | 28 | 10 | 2 | Week 2 | November 28 Week 2 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
4 | 2028-11-11 | November | 28 | 11 | 2 | Week 2 | November 28 Week 2 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
5 | 2028-11-12 | November | 28 | 12 | 2 | Week 2 | November 28 Week 2 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
6 | 2028-11-13 | November | 28 | 13 | 2 | Week 2 | November 28 Week 2 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
7 | 2028-11-14 | November | 28 | 14 | 2 | Week 2 | November 28 Week 2 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
1 | 2028-11-15 | November | 28 | 15 | 3 | Week 3 | November 28 Week 3 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
2 | 2028-11-16 | November | 28 | 16 | 3 | Week 3 | November 28 Week 3 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
3 | 2028-11-17 | November | 28 | 17 | 3 | Week 3 | November 28 Week 3 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
4 | 2028-11-18 | November | 28 | 18 | 3 | Week 3 | November 28 Week 3 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
5 | 2028-11-19 | November | 28 | 19 | 3 | Week 3 | November 28 Week 3 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
6 | 2028-11-20 | November | 28 | 20 | 3 | Week 3 | November 28 Week 3 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
7 | 2028-11-21 | November | 28 | 21 | 3 | Week 3 | November 28 Week 3 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
1 | 2028-11-22 | November | 28 | 22 | 4 | Week 4 | November 28 Week 4 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
2 | 2028-11-23 | November | 28 | 23 | 4 | Week 4 | November 28 Week 4 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
3 | 2028-11-24 | November | 28 | 24 | 4 | Week 4 | November 28 Week 4 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
4 | 2028-11-25 | November | 28 | 25 | 4 | Week 4 | November 28 Week 4 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
5 | 2028-11-26 | November | 28 | 26 | 4 | Week 4 | November 28 Week 4 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
6 | 2028-11-27 | November | 28 | 27 | 4 | Week 4 | November 28 Week 4 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
7 | 2028-11-28 | November | 28 | 28 | 4 | Week 4 | November 28 Week 4 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
1 | 2028-11-29 | November | 28 | 29 | 5 | Week 5 | November 28 Week 5 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
2 | 2028-11-30 | November | 28 | 30 | 5 | Week 5 | November 28 Week 5 | NOVEMBER 28 | PLANNED | NOVEMBER 28 PLANNED
1 | 2028-12-01 | December | 28 | 1 | 1 | Week 1 | December 28 Week 1 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
2 | 2028-12-02 | December | 28 | 2 | 1 | Week 1 | December 28 Week 1 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
3 | 2028-12-03 | December | 28 | 3 | 1 | Week 1 | December 28 Week 1 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
4 | 2028-12-04 | December | 28 | 4 | 1 | Week 1 | December 28 Week 1 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
5 | 2028-12-05 | December | 28 | 5 | 1 | Week 1 | December 28 Week 1 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
6 | 2028-12-06 | December | 28 | 6 | 1 | Week 1 | December 28 Week 1 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
7 | 2028-12-07 | December | 28 | 7 | 1 | Week 1 | December 28 Week 1 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
1 | 2028-12-08 | December | 28 | 8 | 2 | Week 2 | December 28 Week 2 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
2 | 2028-12-09 | December | 28 | 9 | 2 | Week 2 | December 28 Week 2 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
3 | 2028-12-10 | December | 28 | 10 | 2 | Week 2 | December 28 Week 2 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
4 | 2028-12-11 | December | 28 | 11 | 2 | Week 2 | December 28 Week 2 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
5 | 2028-12-12 | December | 28 | 12 | 2 | Week 2 | December 28 Week 2 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
6 | 2028-12-13 | December | 28 | 13 | 2 | Week 2 | December 28 Week 2 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
7 | 2028-12-14 | December | 28 | 14 | 2 | Week 2 | December 28 Week 2 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
1 | 2028-12-15 | December | 28 | 15 | 3 | Week 3 | December 28 Week 3 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
2 | 2028-12-16 | December | 28 | 16 | 3 | Week 3 | December 28 Week 3 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
3 | 2028-12-17 | December | 28 | 17 | 3 | Week 3 | December 28 Week 3 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
4 | 2028-12-18 | December | 28 | 18 | 3 | Week 3 | December 28 Week 3 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
5 | 2028-12-19 | December | 28 | 19 | 3 | Week 3 | December 28 Week 3 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
6 | 2028-12-20 | December | 28 | 20 | 3 | Week 3 | December 28 Week 3 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
7 | 2028-12-21 | December | 28 | 21 | 3 | Week 3 | December 28 Week 3 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
1 | 2028-12-22 | December | 28 | 22 | 4 | Week 4 | December 28 Week 4 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
2 | 2028-12-23 | December | 28 | 23 | 4 | Week 4 | December 28 Week 4 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
3 | 2028-12-24 | December | 28 | 24 | 4 | Week 4 | December 28 Week 4 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
4 | 2028-12-25 | December | 28 | 25 | 4 | Week 4 | December 28 Week 4 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
5 | 2028-12-26 | December | 28 | 26 | 4 | Week 4 | December 28 Week 4 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
6 | 2028-12-27 | December | 28 | 27 | 4 | Week 4 | December 28 Week 4 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
7 | 2028-12-28 | December | 28 | 28 | 4 | Week 4 | December 28 Week 4 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
1 | 2028-12-29 | December | 28 | 29 | 5 | Week 5 | December 28 Week 5 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
2 | 2028-12-30 | December | 28 | 30 | 5 | Week 5 | December 28 Week 5 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
3 | 2028-12-31 | December | 28 | 31 | 5 | Week 5 | December 28 Week 5 | DECEMBER 28 | PLANNED | DECEMBER 28 PLANNED
1 | 2029-01-01 | January | 29 | 1 | 1 | Week 1 | January 29 Week 1 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
2 | 2029-01-02 | January | 29 | 2 | 1 | Week 1 | January 29 Week 1 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
3 | 2029-01-03 | January | 29 | 3 | 1 | Week 1 | January 29 Week 1 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
4 | 2029-01-04 | January | 29 | 4 | 1 | Week 1 | January 29 Week 1 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
5 | 2029-01-05 | January | 29 | 5 | 1 | Week 1 | January 29 Week 1 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
6 | 2029-01-06 | January | 29 | 6 | 1 | Week 1 | January 29 Week 1 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
7 | 2029-01-07 | January | 29 | 7 | 1 | Week 1 | January 29 Week 1 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
1 | 2029-01-08 | January | 29 | 8 | 2 | Week 2 | January 29 Week 2 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
2 | 2029-01-09 | January | 29 | 9 | 2 | Week 2 | January 29 Week 2 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
3 | 2029-01-10 | January | 29 | 10 | 2 | Week 2 | January 29 Week 2 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
4 | 2029-01-11 | January | 29 | 11 | 2 | Week 2 | January 29 Week 2 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
5 | 2029-01-12 | January | 29 | 12 | 2 | Week 2 | January 29 Week 2 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
6 | 2029-01-13 | January | 29 | 13 | 2 | Week 2 | January 29 Week 2 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
7 | 2029-01-14 | January | 29 | 14 | 2 | Week 2 | January 29 Week 2 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
1 | 2029-01-15 | January | 29 | 15 | 3 | Week 3 | January 29 Week 3 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
2 | 2029-01-16 | January | 29 | 16 | 3 | Week 3 | January 29 Week 3 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
3 | 2029-01-17 | January | 29 | 17 | 3 | Week 3 | January 29 Week 3 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
4 | 2029-01-18 | January | 29 | 18 | 3 | Week 3 | January 29 Week 3 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
5 | 2029-01-19 | January | 29 | 19 | 3 | Week 3 | January 29 Week 3 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
6 | 2029-01-20 | January | 29 | 20 | 3 | Week 3 | January 29 Week 3 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
7 | 2029-01-21 | January | 29 | 21 | 3 | Week 3 | January 29 Week 3 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
1 | 2029-01-22 | January | 29 | 22 | 4 | Week 4 | January 29 Week 4 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
2 | 2029-01-23 | January | 29 | 23 | 4 | Week 4 | January 29 Week 4 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
3 | 2029-01-24 | January | 29 | 24 | 4 | Week 4 | January 29 Week 4 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
4 | 2029-01-25 | January | 29 | 25 | 4 | Week 4 | January 29 Week 4 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
5 | 2029-01-26 | January | 29 | 26 | 4 | Week 4 | January 29 Week 4 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
6 | 2029-01-27 | January | 29 | 27 | 4 | Week 4 | January 29 Week 4 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
7 | 2029-01-28 | January | 29 | 28 | 4 | Week 4 | January 29 Week 4 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
1 | 2029-01-29 | January | 29 | 29 | 5 | Week 5 | January 29 Week 5 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
2 | 2029-01-30 | January | 29 | 30 | 5 | Week 5 | January 29 Week 5 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
3 | 2029-01-31 | January | 29 | 31 | 5 | Week 5 | January 29 Week 5 | JANUARY 29 | PLANNED | JANUARY 29 PLANNED
1 | 2029-02-01 | February | 29 | 1 | 1 | Week 1 | February 29 Week 1 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
2 | 2029-02-02 | February | 29 | 2 | 1 | Week 1 | February 29 Week 1 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
3 | 2029-02-03 | February | 29 | 3 | 1 | Week 1 | February 29 Week 1 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
4 | 2029-02-04 | February | 29 | 4 | 1 | Week 1 | February 29 Week 1 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
5 | 2029-02-05 | February | 29 | 5 | 1 | Week 1 | February 29 Week 1 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
6 | 2029-02-06 | February | 29 | 6 | 1 | Week 1 | February 29 Week 1 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
7 | 2029-02-07 | February | 29 | 7 | 1 | Week 1 | February 29 Week 1 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
1 | 2029-02-08 | February | 29 | 8 | 2 | Week 2 | February 29 Week 2 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
2 | 2029-02-09 | February | 29 | 9 | 2 | Week 2 | February 29 Week 2 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
3 | 2029-02-10 | February | 29 | 10 | 2 | Week 2 | February 29 Week 2 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
4 | 2029-02-11 | February | 29 | 11 | 2 | Week 2 | February 29 Week 2 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
5 | 2029-02-12 | February | 29 | 12 | 2 | Week 2 | February 29 Week 2 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
6 | 2029-02-13 | February | 29 | 13 | 2 | Week 2 | February 29 Week 2 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
7 | 2029-02-14 | February | 29 | 14 | 2 | Week 2 | February 29 Week 2 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
1 | 2029-02-15 | February | 29 | 15 | 3 | Week 3 | February 29 Week 3 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
2 | 2029-02-16 | February | 29 | 16 | 3 | Week 3 | February 29 Week 3 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
3 | 2029-02-17 | February | 29 | 17 | 3 | Week 3 | February 29 Week 3 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
4 | 2029-02-18 | February | 29 | 18 | 3 | Week 3 | February 29 Week 3 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
5 | 2029-02-19 | February | 29 | 19 | 3 | Week 3 | February 29 Week 3 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
6 | 2029-02-20 | February | 29 | 20 | 3 | Week 3 | February 29 Week 3 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
7 | 2029-02-21 | February | 29 | 21 | 3 | Week 3 | February 29 Week 3 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
1 | 2029-02-22 | February | 29 | 22 | 4 | Week 4 | February 29 Week 4 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
2 | 2029-02-23 | February | 29 | 23 | 4 | Week 4 | February 29 Week 4 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
3 | 2029-02-24 | February | 29 | 24 | 4 | Week 4 | February 29 Week 4 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
4 | 2029-02-25 | February | 29 | 25 | 4 | Week 4 | February 29 Week 4 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
5 | 2029-02-26 | February | 29 | 26 | 4 | Week 4 | February 29 Week 4 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
6 | 2029-02-27 | February | 29 | 27 | 4 | Week 4 | February 29 Week 4 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
7 | 2029-02-28 | February | 29 | 28 | 4 | Week 4 | February 29 Week 4 | FEBRUARY 29 | PLANNED | FEBRUARY 29 PLANNED
1 | 2029-03-01 | March | 29 | 1 | 1 | Week 1 | March 29 Week 1 | MARCH 29 | PLANNED | MARCH 29 PLANNED
2 | 2029-03-02 | March | 29 | 2 | 1 | Week 1 | March 29 Week 1 | MARCH 29 | PLANNED | MARCH 29 PLANNED
3 | 2029-03-03 | March | 29 | 3 | 1 | Week 1 | March 29 Week 1 | MARCH 29 | PLANNED | MARCH 29 PLANNED
4 | 2029-03-04 | March | 29 | 4 | 1 | Week 1 | March 29 Week 1 | MARCH 29 | PLANNED | MARCH 29 PLANNED
5 | 2029-03-05 | March | 29 | 5 | 1 | Week 1 | March 29 Week 1 | MARCH 29 | PLANNED | MARCH 29 PLANNED
6 | 2029-03-06 | March | 29 | 6 | 1 | Week 1 | March 29 Week 1 | MARCH 29 | PLANNED | MARCH 29 PLANNED
7 | 2029-03-07 | March | 29 | 7 | 1 | Week 1 | March 29 Week 1 | MARCH 29 | PLANNED | MARCH 29 PLANNED
1 | 2029-03-08 | March | 29 | 8 | 2 | Week 2 | March 29 Week 2 | MARCH 29 | PLANNED | MARCH 29 PLANNED
2 | 2029-03-09 | March | 29 | 9 | 2 | Week 2 | March 29 Week 2 | MARCH 29 | PLANNED | MARCH 29 PLANNED
3 | 2029-03-10 | March | 29 | 10 | 2 | Week 2 | March 29 Week 2 | MARCH 29 | PLANNED | MARCH 29 PLANNED
4 | 2029-03-11 | March | 29 | 11 | 2 | Week 2 | March 29 Week 2 | MARCH 29 | PLANNED | MARCH 29 PLANNED
5 | 2029-03-12 | March | 29 | 12 | 2 | Week 2 | March 29 Week 2 | MARCH 29 | PLANNED | MARCH 29 PLANNED
6 | 2029-03-13 | March | 29 | 13 | 2 | Week 2 | March 29 Week 2 | MARCH 29 | PLANNED | MARCH 29 PLANNED
7 | 2029-03-14 | March | 29 | 14 | 2 | Week 2 | March 29 Week 2 | MARCH 29 | PLANNED | MARCH 29 PLANNED
1 | 2029-03-15 | March | 29 | 15 | 3 | Week 3 | March 29 Week 3 | MARCH 29 | PLANNED | MARCH 29 PLANNED
2 | 2029-03-16 | March | 29 | 16 | 3 | Week 3 | March 29 Week 3 | MARCH 29 | PLANNED | MARCH 29 PLANNED
3 | 2029-03-17 | March | 29 | 17 | 3 | Week 3 | March 29 Week 3 | MARCH 29 | PLANNED | MARCH 29 PLANNED
4 | 2029-03-18 | March | 29 | 18 | 3 | Week 3 | March 29 Week 3 | MARCH 29 | PLANNED | MARCH 29 PLANNED
5 | 2029-03-19 | March | 29 | 19 | 3 | Week 3 | March 29 Week 3 | MARCH 29 | PLANNED | MARCH 29 PLANNED
6 | 2029-03-20 | March | 29 | 20 | 3 | Week 3 | March 29 Week 3 | MARCH 29 | PLANNED | MARCH 29 PLANNED
7 | 2029-03-21 | March | 29 | 21 | 3 | Week 3 | March 29 Week 3 | MARCH 29 | PLANNED | MARCH 29 PLANNED
1 | 2029-03-22 | March | 29 | 22 | 4 | Week 4 | March 29 Week 4 | MARCH 29 | PLANNED | MARCH 29 PLANNED
2 | 2029-03-23 | March | 29 | 23 | 4 | Week 4 | March 29 Week 4 | MARCH 29 | PLANNED | MARCH 29 PLANNED
3 | 2029-03-24 | March | 29 | 24 | 4 | Week 4 | March 29 Week 4 | MARCH 29 | PLANNED | MARCH 29 PLANNED
4 | 2029-03-25 | March | 29 | 25 | 4 | Week 4 | March 29 Week 4 | MARCH 29 | PLANNED | MARCH 29 PLANNED
5 | 2029-03-26 | March | 29 | 26 | 4 | Week 4 | March 29 Week 4 | MARCH 29 | PLANNED | MARCH 29 PLANNED
6 | 2029-03-27 | March | 29 | 27 | 4 | Week 4 | March 29 Week 4 | MARCH 29 | PLANNED | MARCH 29 PLANNED
7 | 2029-03-28 | March | 29 | 28 | 4 | Week 4 | March 29 Week 4 | MARCH 29 | PLANNED | MARCH 29 PLANNED
1 | 2029-03-29 | March | 29 | 29 | 5 | Week 5 | March 29 Week 5 | MARCH 29 | PLANNED | MARCH 29 PLANNED
2 | 2029-03-30 | March | 29 | 30 | 5 | Week 5 | March 29 Week 5 | MARCH 29 | PLANNED | MARCH 29 PLANNED
3 | 2029-03-31 | March | 29 | 31 | 5 | Week 5 | March 29 Week 5 | MARCH 29 | PLANNED | MARCH 29 PLANNED
1 | 2029-04-01 | April | 29 | 1 | 1 | Week 1 | April 29 Week 1 | APRIL 29 | PLANNED | APRIL 29 PLANNED
2 | 2029-04-02 | April | 29 | 2 | 1 | Week 1 | April 29 Week 1 | APRIL 29 | PLANNED | APRIL 29 PLANNED
3 | 2029-04-03 | April | 29 | 3 | 1 | Week 1 | April 29 Week 1 | APRIL 29 | PLANNED | APRIL 29 PLANNED
4 | 2029-04-04 | April | 29 | 4 | 1 | Week 1 | April 29 Week 1 | APRIL 29 | PLANNED | APRIL 29 PLANNED
5 | 2029-04-05 | April | 29 | 5 | 1 | Week 1 | April 29 Week 1 | APRIL 29 | PLANNED | APRIL 29 PLANNED
6 | 2029-04-06 | April | 29 | 6 | 1 | Week 1 | April 29 Week 1 | APRIL 29 | PLANNED | APRIL 29 PLANNED
7 | 2029-04-07 | April | 29 | 7 | 1 | Week 1 | April 29 Week 1 | APRIL 29 | PLANNED | APRIL 29 PLANNED
1 | 2029-04-08 | April | 29 | 8 | 2 | Week 2 | April 29 Week 2 | APRIL 29 | PLANNED | APRIL 29 PLANNED
2 | 2029-04-09 | April | 29 | 9 | 2 | Week 2 | April 29 Week 2 | APRIL 29 | PLANNED | APRIL 29 PLANNED
3 | 2029-04-10 | April | 29 | 10 | 2 | Week 2 | April 29 Week 2 | APRIL 29 | PLANNED | APRIL 29 PLANNED
4 | 2029-04-11 | April | 29 | 11 | 2 | Week 2 | April 29 Week 2 | APRIL 29 | PLANNED | APRIL 29 PLANNED
5 | 2029-04-12 | April | 29 | 12 | 2 | Week 2 | April 29 Week 2 | APRIL 29 | PLANNED | APRIL 29 PLANNED
6 | 2029-04-13 | April | 29 | 13 | 2 | Week 2 | April 29 Week 2 | APRIL 29 | PLANNED | APRIL 29 PLANNED
7 | 2029-04-14 | April | 29 | 14 | 2 | Week 2 | April 29 Week 2 | APRIL 29 | PLANNED | APRIL 29 PLANNED
1 | 2029-04-15 | April | 29 | 15 | 3 | Week 3 | April 29 Week 3 | APRIL 29 | PLANNED | APRIL 29 PLANNED
2 | 2029-04-16 | April | 29 | 16 | 3 | Week 3 | April 29 Week 3 | APRIL 29 | PLANNED | APRIL 29 PLANNED
3 | 2029-04-17 | April | 29 | 17 | 3 | Week 3 | April 29 Week 3 | APRIL 29 | PLANNED | APRIL 29 PLANNED
4 | 2029-04-18 | April | 29 | 18 | 3 | Week 3 | April 29 Week 3 | APRIL 29 | PLANNED | APRIL 29 PLANNED
5 | 2029-04-19 | April | 29 | 19 | 3 | Week 3 | April 29 Week 3 | APRIL 29 | PLANNED | APRIL 29 PLANNED
6 | 2029-04-20 | April | 29 | 20 | 3 | Week 3 | April 29 Week 3 | APRIL 29 | PLANNED | APRIL 29 PLANNED
7 | 2029-04-21 | April | 29 | 21 | 3 | Week 3 | April 29 Week 3 | APRIL 29 | PLANNED | APRIL 29 PLANNED
1 | 2029-04-22 | April | 29 | 22 | 4 | Week 4 | April 29 Week 4 | APRIL 29 | PLANNED | APRIL 29 PLANNED
2 | 2029-04-23 | April | 29 | 23 | 4 | Week 4 | April 29 Week 4 | APRIL 29 | PLANNED | APRIL 29 PLANNED
3 | 2029-04-24 | April | 29 | 24 | 4 | Week 4 | April 29 Week 4 | APRIL 29 | PLANNED | APRIL 29 PLANNED
4 | 2029-04-25 | April | 29 | 25 | 4 | Week 4 | April 29 Week 4 | APRIL 29 | PLANNED | APRIL 29 PLANNED
5 | 2029-04-26 | April | 29 | 26 | 4 | Week 4 | April 29 Week 4 | APRIL 29 | PLANNED | APRIL 29 PLANNED
6 | 2029-04-27 | April | 29 | 27 | 4 | Week 4 | April 29 Week 4 | APRIL 29 | PLANNED | APRIL 29 PLANNED
7 | 2029-04-28 | April | 29 | 28 | 4 | Week 4 | April 29 Week 4 | APRIL 29 | PLANNED | APRIL 29 PLANNED
1 | 2029-04-29 | April | 29 | 29 | 5 | Week 5 | April 29 Week 5 | APRIL 29 | PLANNED | APRIL 29 PLANNED
2 | 2029-04-30 | April | 29 | 30 | 5 | Week 5 | April 29 Week 5 | APRIL 29 | PLANNED | APRIL 29 PLANNED
1 | 2029-05-01 | May | 29 | 1 | 1 | Week 1 | May 29 Week 1 | MAY 29 | PLANNED | MAY 29 PLANNED
2 | 2029-05-02 | May | 29 | 2 | 1 | Week 1 | May 29 Week 1 | MAY 29 | PLANNED | MAY 29 PLANNED
3 | 2029-05-03 | May | 29 | 3 | 1 | Week 1 | May 29 Week 1 | MAY 29 | PLANNED | MAY 29 PLANNED
4 | 2029-05-04 | May | 29 | 4 | 1 | Week 1 | May 29 Week 1 | MAY 29 | PLANNED | MAY 29 PLANNED
5 | 2029-05-05 | May | 29 | 5 | 1 | Week 1 | May 29 Week 1 | MAY 29 | PLANNED | MAY 29 PLANNED
6 | 2029-05-06 | May | 29 | 6 | 1 | Week 1 | May 29 Week 1 | MAY 29 | PLANNED | MAY 29 PLANNED
7 | 2029-05-07 | May | 29 | 7 | 1 | Week 1 | May 29 Week 1 | MAY 29 | PLANNED | MAY 29 PLANNED
1 | 2029-05-08 | May | 29 | 8 | 2 | Week 2 | May 29 Week 2 | MAY 29 | PLANNED | MAY 29 PLANNED
2 | 2029-05-09 | May | 29 | 9 | 2 | Week 2 | May 29 Week 2 | MAY 29 | PLANNED | MAY 29 PLANNED
3 | 2029-05-10 | May | 29 | 10 | 2 | Week 2 | May 29 Week 2 | MAY 29 | PLANNED | MAY 29 PLANNED
4 | 2029-05-11 | May | 29 | 11 | 2 | Week 2 | May 29 Week 2 | MAY 29 | PLANNED | MAY 29 PLANNED
5 | 2029-05-12 | May | 29 | 12 | 2 | Week 2 | May 29 Week 2 | MAY 29 | PLANNED | MAY 29 PLANNED
6 | 2029-05-13 | May | 29 | 13 | 2 | Week 2 | May 29 Week 2 | MAY 29 | PLANNED | MAY 29 PLANNED
7 | 2029-05-14 | May | 29 | 14 | 2 | Week 2 | May 29 Week 2 | MAY 29 | PLANNED | MAY 29 PLANNED
1 | 2029-05-15 | May | 29 | 15 | 3 | Week 3 | May 29 Week 3 | MAY 29 | PLANNED | MAY 29 PLANNED
2 | 2029-05-16 | May | 29 | 16 | 3 | Week 3 | May 29 Week 3 | MAY 29 | PLANNED | MAY 29 PLANNED
3 | 2029-05-17 | May | 29 | 17 | 3 | Week 3 | May 29 Week 3 | MAY 29 | PLANNED | MAY 29 PLANNED
4 | 2029-05-18 | May | 29 | 18 | 3 | Week 3 | May 29 Week 3 | MAY 29 | PLANNED | MAY 29 PLANNED
5 | 2029-05-19 | May | 29 | 19 | 3 | Week 3 | May 29 Week 3 | MAY 29 | PLANNED | MAY 29 PLANNED
6 | 2029-05-20 | May | 29 | 20 | 3 | Week 3 | May 29 Week 3 | MAY 29 | PLANNED | MAY 29 PLANNED
7 | 2029-05-21 | May | 29 | 21 | 3 | Week 3 | May 29 Week 3 | MAY 29 | PLANNED | MAY 29 PLANNED
1 | 2029-05-22 | May | 29 | 22 | 4 | Week 4 | May 29 Week 4 | MAY 29 | PLANNED | MAY 29 PLANNED
2 | 2029-05-23 | May | 29 | 23 | 4 | Week 4 | May 29 Week 4 | MAY 29 | PLANNED | MAY 29 PLANNED
3 | 2029-05-24 | May | 29 | 24 | 4 | Week 4 | May 29 Week 4 | MAY 29 | PLANNED | MAY 29 PLANNED
4 | 2029-05-25 | May | 29 | 25 | 4 | Week 4 | May 29 Week 4 | MAY 29 | PLANNED | MAY 29 PLANNED
5 | 2029-05-26 | May | 29 | 26 | 4 | Week 4 | May 29 Week 4 | MAY 29 | PLANNED | MAY 29 PLANNED
6 | 2029-05-27 | May | 29 | 27 | 4 | Week 4 | May 29 Week 4 | MAY 29 | PLANNED | MAY 29 PLANNED
7 | 2029-05-28 | May | 29 | 28 | 4 | Week 4 | May 29 Week 4 | MAY 29 | PLANNED | MAY 29 PLANNED
1 | 2029-05-29 | May | 29 | 29 | 5 | Week 5 | May 29 Week 5 | MAY 29 | PLANNED | MAY 29 PLANNED
2 | 2029-05-30 | May | 29 | 30 | 5 | Week 5 | May 29 Week 5 | MAY 29 | PLANNED | MAY 29 PLANNED
3 | 2029-05-31 | May | 29 | 31 | 5 | Week 5 | May 29 Week 5 | MAY 29 | PLANNED | MAY 29 PLANNED
1 | 2029-06-01 | June | 29 | 1 | 1 | Week 1 | June 29 Week 1 | JUNE 29 | PLANNED | JUNE 29 PLANNED
2 | 2029-06-02 | June | 29 | 2 | 1 | Week 1 | June 29 Week 1 | JUNE 29 | PLANNED | JUNE 29 PLANNED
3 | 2029-06-03 | June | 29 | 3 | 1 | Week 1 | June 29 Week 1 | JUNE 29 | PLANNED | JUNE 29 PLANNED
4 | 2029-06-04 | June | 29 | 4 | 1 | Week 1 | June 29 Week 1 | JUNE 29 | PLANNED | JUNE 29 PLANNED
5 | 2029-06-05 | June | 29 | 5 | 1 | Week 1 | June 29 Week 1 | JUNE 29 | PLANNED | JUNE 29 PLANNED
6 | 2029-06-06 | June | 29 | 6 | 1 | Week 1 | June 29 Week 1 | JUNE 29 | PLANNED | JUNE 29 PLANNED
7 | 2029-06-07 | June | 29 | 7 | 1 | Week 1 | June 29 Week 1 | JUNE 29 | PLANNED | JUNE 29 PLANNED
1 | 2029-06-08 | June | 29 | 8 | 2 | Week 2 | June 29 Week 2 | JUNE 29 | PLANNED | JUNE 29 PLANNED
2 | 2029-06-09 | June | 29 | 9 | 2 | Week 2 | June 29 Week 2 | JUNE 29 | PLANNED | JUNE 29 PLANNED
3 | 2029-06-10 | June | 29 | 10 | 2 | Week 2 | June 29 Week 2 | JUNE 29 | PLANNED | JUNE 29 PLANNED
4 | 2029-06-11 | June | 29 | 11 | 2 | Week 2 | June 29 Week 2 | JUNE 29 | PLANNED | JUNE 29 PLANNED
5 | 2029-06-12 | June | 29 | 12 | 2 | Week 2 | June 29 Week 2 | JUNE 29 | PLANNED | JUNE 29 PLANNED
6 | 2029-06-13 | June | 29 | 13 | 2 | Week 2 | June 29 Week 2 | JUNE 29 | PLANNED | JUNE 29 PLANNED
7 | 2029-06-14 | June | 29 | 14 | 2 | Week 2 | June 29 Week 2 | JUNE 29 | PLANNED | JUNE 29 PLANNED
1 | 2029-06-15 | June | 29 | 15 | 3 | Week 3 | June 29 Week 3 | JUNE 29 | PLANNED | JUNE 29 PLANNED
2 | 2029-06-16 | June | 29 | 16 | 3 | Week 3 | June 29 Week 3 | JUNE 29 | PLANNED | JUNE 29 PLANNED
3 | 2029-06-17 | June | 29 | 17 | 3 | Week 3 | June 29 Week 3 | JUNE 29 | PLANNED | JUNE 29 PLANNED
4 | 2029-06-18 | June | 29 | 18 | 3 | Week 3 | June 29 Week 3 | JUNE 29 | PLANNED | JUNE 29 PLANNED
5 | 2029-06-19 | June | 29 | 19 | 3 | Week 3 | June 29 Week 3 | JUNE 29 | PLANNED | JUNE 29 PLANNED
6 | 2029-06-20 | June | 29 | 20 | 3 | Week 3 | June 29 Week 3 | JUNE 29 | PLANNED | JUNE 29 PLANNED
7 | 2029-06-21 | June | 29 | 21 | 3 | Week 3 | June 29 Week 3 | JUNE 29 | PLANNED | JUNE 29 PLANNED
1 | 2029-06-22 | June | 29 | 22 | 4 | Week 4 | June 29 Week 4 | JUNE 29 | PLANNED | JUNE 29 PLANNED
2 | 2029-06-23 | June | 29 | 23 | 4 | Week 4 | June 29 Week 4 | JUNE 29 | PLANNED | JUNE 29 PLANNED
3 | 2029-06-24 | June | 29 | 24 | 4 | Week 4 | June 29 Week 4 | JUNE 29 | PLANNED | JUNE 29 PLANNED
4 | 2029-06-25 | June | 29 | 25 | 4 | Week 4 | June 29 Week 4 | JUNE 29 | PLANNED | JUNE 29 PLANNED
5 | 2029-06-26 | June | 29 | 26 | 4 | Week 4 | June 29 Week 4 | JUNE 29 | PLANNED | JUNE 29 PLANNED
6 | 2029-06-27 | June | 29 | 27 | 4 | Week 4 | June 29 Week 4 | JUNE 29 | PLANNED | JUNE 29 PLANNED
7 | 2029-06-28 | June | 29 | 28 | 4 | Week 4 | June 29 Week 4 | JUNE 29 | PLANNED | JUNE 29 PLANNED
1 | 2029-06-29 | June | 29 | 29 | 5 | Week 5 | June 29 Week 5 | JUNE 29 | PLANNED | JUNE 29 PLANNED
2 | 2029-06-30 | June | 29 | 30 | 5 | Week 5 | June 29 Week 5 | JUNE 29 | PLANNED | JUNE 29 PLANNED
1 | 2029-07-01 | July | 29 | 1 | 1 | Week 1 | July 29 Week 1 | JULY 29 | PLANNED | JULY 29 PLANNED
2 | 2029-07-02 | July | 29 | 2 | 1 | Week 1 | July 29 Week 1 | JULY 29 | PLANNED | JULY 29 PLANNED
3 | 2029-07-03 | July | 29 | 3 | 1 | Week 1 | July 29 Week 1 | JULY 29 | PLANNED | JULY 29 PLANNED
4 | 2029-07-04 | July | 29 | 4 | 1 | Week 1 | July 29 Week 1 | JULY 29 | PLANNED | JULY 29 PLANNED
5 | 2029-07-05 | July | 29 | 5 | 1 | Week 1 | July 29 Week 1 | JULY 29 | PLANNED | JULY 29 PLANNED
6 | 2029-07-06 | July | 29 | 6 | 1 | Week 1 | July 29 Week 1 | JULY 29 | PLANNED | JULY 29 PLANNED
7 | 2029-07-07 | July | 29 | 7 | 1 | Week 1 | July 29 Week 1 | JULY 29 | PLANNED | JULY 29 PLANNED
1 | 2029-07-08 | July | 29 | 8 | 2 | Week 2 | July 29 Week 2 | JULY 29 | PLANNED | JULY 29 PLANNED
2 | 2029-07-09 | July | 29 | 9 | 2 | Week 2 | July 29 Week 2 | JULY 29 | PLANNED | JULY 29 PLANNED
3 | 2029-07-10 | July | 29 | 10 | 2 | Week 2 | July 29 Week 2 | JULY 29 | PLANNED | JULY 29 PLANNED
4 | 2029-07-11 | July | 29 | 11 | 2 | Week 2 | July 29 Week 2 | JULY 29 | PLANNED | JULY 29 PLANNED
5 | 2029-07-12 | July | 29 | 12 | 2 | Week 2 | July 29 Week 2 | JULY 29 | PLANNED | JULY 29 PLANNED
6 | 2029-07-13 | July | 29 | 13 | 2 | Week 2 | July 29 Week 2 | JULY 29 | PLANNED | JULY 29 PLANNED
7 | 2029-07-14 | July | 29 | 14 | 2 | Week 2 | July 29 Week 2 | JULY 29 | PLANNED | JULY 29 PLANNED
1 | 2029-07-15 | July | 29 | 15 | 3 | Week 3 | July 29 Week 3 | JULY 29 | PLANNED | JULY 29 PLANNED
2 | 2029-07-16 | July | 29 | 16 | 3 | Week 3 | July 29 Week 3 | JULY 29 | PLANNED | JULY 29 PLANNED
3 | 2029-07-17 | July | 29 | 17 | 3 | Week 3 | July 29 Week 3 | JULY 29 | PLANNED | JULY 29 PLANNED
4 | 2029-07-18 | July | 29 | 18 | 3 | Week 3 | July 29 Week 3 | JULY 29 | PLANNED | JULY 29 PLANNED
5 | 2029-07-19 | July | 29 | 19 | 3 | Week 3 | July 29 Week 3 | JULY 29 | PLANNED | JULY 29 PLANNED
6 | 2029-07-20 | July | 29 | 20 | 3 | Week 3 | July 29 Week 3 | JULY 29 | PLANNED | JULY 29 PLANNED
7 | 2029-07-21 | July | 29 | 21 | 3 | Week 3 | July 29 Week 3 | JULY 29 | PLANNED | JULY 29 PLANNED
1 | 2029-07-22 | July | 29 | 22 | 4 | Week 4 | July 29 Week 4 | JULY 29 | PLANNED | JULY 29 PLANNED
2 | 2029-07-23 | July | 29 | 23 | 4 | Week 4 | July 29 Week 4 | JULY 29 | PLANNED | JULY 29 PLANNED
3 | 2029-07-24 | July | 29 | 24 | 4 | Week 4 | July 29 Week 4 | JULY 29 | PLANNED | JULY 29 PLANNED
4 | 2029-07-25 | July | 29 | 25 | 4 | Week 4 | July 29 Week 4 | JULY 29 | PLANNED | JULY 29 PLANNED
5 | 2029-07-26 | July | 29 | 26 | 4 | Week 4 | July 29 Week 4 | JULY 29 | PLANNED | JULY 29 PLANNED
6 | 2029-07-27 | July | 29 | 27 | 4 | Week 4 | July 29 Week 4 | JULY 29 | PLANNED | JULY 29 PLANNED
7 | 2029-07-28 | July | 29 | 28 | 4 | Week 4 | July 29 Week 4 | JULY 29 | PLANNED | JULY 29 PLANNED
1 | 2029-07-29 | July | 29 | 29 | 5 | Week 5 | July 29 Week 5 | JULY 29 | PLANNED | JULY 29 PLANNED
2 | 2029-07-30 | July | 29 | 30 | 5 | Week 5 | July 29 Week 5 | JULY 29 | PLANNED | JULY 29 PLANNED
3 | 2029-07-31 | July | 29 | 31 | 5 | Week 5 | July 29 Week 5 | JULY 29 | PLANNED | JULY 29 PLANNED
1 | 2029-08-01 | August | 29 | 1 | 1 | Week 1 | August 29 Week 1 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
2 | 2029-08-02 | August | 29 | 2 | 1 | Week 1 | August 29 Week 1 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
3 | 2029-08-03 | August | 29 | 3 | 1 | Week 1 | August 29 Week 1 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
4 | 2029-08-04 | August | 29 | 4 | 1 | Week 1 | August 29 Week 1 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
5 | 2029-08-05 | August | 29 | 5 | 1 | Week 1 | August 29 Week 1 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
6 | 2029-08-06 | August | 29 | 6 | 1 | Week 1 | August 29 Week 1 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
7 | 2029-08-07 | August | 29 | 7 | 1 | Week 1 | August 29 Week 1 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
1 | 2029-08-08 | August | 29 | 8 | 2 | Week 2 | August 29 Week 2 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
2 | 2029-08-09 | August | 29 | 9 | 2 | Week 2 | August 29 Week 2 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
3 | 2029-08-10 | August | 29 | 10 | 2 | Week 2 | August 29 Week 2 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
4 | 2029-08-11 | August | 29 | 11 | 2 | Week 2 | August 29 Week 2 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
5 | 2029-08-12 | August | 29 | 12 | 2 | Week 2 | August 29 Week 2 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
6 | 2029-08-13 | August | 29 | 13 | 2 | Week 2 | August 29 Week 2 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
7 | 2029-08-14 | August | 29 | 14 | 2 | Week 2 | August 29 Week 2 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
1 | 2029-08-15 | August | 29 | 15 | 3 | Week 3 | August 29 Week 3 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
2 | 2029-08-16 | August | 29 | 16 | 3 | Week 3 | August 29 Week 3 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
3 | 2029-08-17 | August | 29 | 17 | 3 | Week 3 | August 29 Week 3 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
4 | 2029-08-18 | August | 29 | 18 | 3 | Week 3 | August 29 Week 3 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
5 | 2029-08-19 | August | 29 | 19 | 3 | Week 3 | August 29 Week 3 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
6 | 2029-08-20 | August | 29 | 20 | 3 | Week 3 | August 29 Week 3 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
7 | 2029-08-21 | August | 29 | 21 | 3 | Week 3 | August 29 Week 3 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
1 | 2029-08-22 | August | 29 | 22 | 4 | Week 4 | August 29 Week 4 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
2 | 2029-08-23 | August | 29 | 23 | 4 | Week 4 | August 29 Week 4 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
3 | 2029-08-24 | August | 29 | 24 | 4 | Week 4 | August 29 Week 4 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
4 | 2029-08-25 | August | 29 | 25 | 4 | Week 4 | August 29 Week 4 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
5 | 2029-08-26 | August | 29 | 26 | 4 | Week 4 | August 29 Week 4 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
6 | 2029-08-27 | August | 29 | 27 | 4 | Week 4 | August 29 Week 4 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
7 | 2029-08-28 | August | 29 | 28 | 4 | Week 4 | August 29 Week 4 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
1 | 2029-08-29 | August | 29 | 29 | 5 | Week 5 | August 29 Week 5 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
2 | 2029-08-30 | August | 29 | 30 | 5 | Week 5 | August 29 Week 5 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
3 | 2029-08-31 | August | 29 | 31 | 5 | Week 5 | August 29 Week 5 | AUGUST 29 | PLANNED | AUGUST 29 PLANNED
1 | 2029-09-01 | September | 29 | 1 | 1 | Week 1 | September 29 Week 1 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
2 | 2029-09-02 | September | 29 | 2 | 1 | Week 1 | September 29 Week 1 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
3 | 2029-09-03 | September | 29 | 3 | 1 | Week 1 | September 29 Week 1 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
4 | 2029-09-04 | September | 29 | 4 | 1 | Week 1 | September 29 Week 1 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
5 | 2029-09-05 | September | 29 | 5 | 1 | Week 1 | September 29 Week 1 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
6 | 2029-09-06 | September | 29 | 6 | 1 | Week 1 | September 29 Week 1 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
7 | 2029-09-07 | September | 29 | 7 | 1 | Week 1 | September 29 Week 1 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
1 | 2029-09-08 | September | 29 | 8 | 2 | Week 2 | September 29 Week 2 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
2 | 2029-09-09 | September | 29 | 9 | 2 | Week 2 | September 29 Week 2 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
3 | 2029-09-10 | September | 29 | 10 | 2 | Week 2 | September 29 Week 2 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
4 | 2029-09-11 | September | 29 | 11 | 2 | Week 2 | September 29 Week 2 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
5 | 2029-09-12 | September | 29 | 12 | 2 | Week 2 | September 29 Week 2 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
6 | 2029-09-13 | September | 29 | 13 | 2 | Week 2 | September 29 Week 2 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
7 | 2029-09-14 | September | 29 | 14 | 2 | Week 2 | September 29 Week 2 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
1 | 2029-09-15 | September | 29 | 15 | 3 | Week 3 | September 29 Week 3 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
2 | 2029-09-16 | September | 29 | 16 | 3 | Week 3 | September 29 Week 3 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
3 | 2029-09-17 | September | 29 | 17 | 3 | Week 3 | September 29 Week 3 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
4 | 2029-09-18 | September | 29 | 18 | 3 | Week 3 | September 29 Week 3 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
5 | 2029-09-19 | September | 29 | 19 | 3 | Week 3 | September 29 Week 3 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
6 | 2029-09-20 | September | 29 | 20 | 3 | Week 3 | September 29 Week 3 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
7 | 2029-09-21 | September | 29 | 21 | 3 | Week 3 | September 29 Week 3 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
1 | 2029-09-22 | September | 29 | 22 | 4 | Week 4 | September 29 Week 4 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
2 | 2029-09-23 | September | 29 | 23 | 4 | Week 4 | September 29 Week 4 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
3 | 2029-09-24 | September | 29 | 24 | 4 | Week 4 | September 29 Week 4 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
4 | 2029-09-25 | September | 29 | 25 | 4 | Week 4 | September 29 Week 4 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
5 | 2029-09-26 | September | 29 | 26 | 4 | Week 4 | September 29 Week 4 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
6 | 2029-09-27 | September | 29 | 27 | 4 | Week 4 | September 29 Week 4 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
7 | 2029-09-28 | September | 29 | 28 | 4 | Week 4 | September 29 Week 4 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
1 | 2029-09-29 | September | 29 | 29 | 5 | Week 5 | September 29 Week 5 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
2 | 2029-09-30 | September | 29 | 30 | 5 | Week 5 | September 29 Week 5 | SEPTEMBER 29 | PLANNED | SEPTEMBER 29 PLANNED
1 | 2029-10-01 | October | 29 | 1 | 1 | Week 1 | October 29 Week 1 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
2 | 2029-10-02 | October | 29 | 2 | 1 | Week 1 | October 29 Week 1 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
3 | 2029-10-03 | October | 29 | 3 | 1 | Week 1 | October 29 Week 1 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
4 | 2029-10-04 | October | 29 | 4 | 1 | Week 1 | October 29 Week 1 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
5 | 2029-10-05 | October | 29 | 5 | 1 | Week 1 | October 29 Week 1 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
6 | 2029-10-06 | October | 29 | 6 | 1 | Week 1 | October 29 Week 1 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
7 | 2029-10-07 | October | 29 | 7 | 1 | Week 1 | October 29 Week 1 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
1 | 2029-10-08 | October | 29 | 8 | 2 | Week 2 | October 29 Week 2 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
2 | 2029-10-09 | October | 29 | 9 | 2 | Week 2 | October 29 Week 2 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
3 | 2029-10-10 | October | 29 | 10 | 2 | Week 2 | October 29 Week 2 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
4 | 2029-10-11 | October | 29 | 11 | 2 | Week 2 | October 29 Week 2 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
5 | 2029-10-12 | October | 29 | 12 | 2 | Week 2 | October 29 Week 2 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
6 | 2029-10-13 | October | 29 | 13 | 2 | Week 2 | October 29 Week 2 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
7 | 2029-10-14 | October | 29 | 14 | 2 | Week 2 | October 29 Week 2 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
1 | 2029-10-15 | October | 29 | 15 | 3 | Week 3 | October 29 Week 3 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
2 | 2029-10-16 | October | 29 | 16 | 3 | Week 3 | October 29 Week 3 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
3 | 2029-10-17 | October | 29 | 17 | 3 | Week 3 | October 29 Week 3 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
4 | 2029-10-18 | October | 29 | 18 | 3 | Week 3 | October 29 Week 3 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
5 | 2029-10-19 | October | 29 | 19 | 3 | Week 3 | October 29 Week 3 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
6 | 2029-10-20 | October | 29 | 20 | 3 | Week 3 | October 29 Week 3 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
7 | 2029-10-21 | October | 29 | 21 | 3 | Week 3 | October 29 Week 3 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
1 | 2029-10-22 | October | 29 | 22 | 4 | Week 4 | October 29 Week 4 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
2 | 2029-10-23 | October | 29 | 23 | 4 | Week 4 | October 29 Week 4 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
3 | 2029-10-24 | October | 29 | 24 | 4 | Week 4 | October 29 Week 4 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
4 | 2029-10-25 | October | 29 | 25 | 4 | Week 4 | October 29 Week 4 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
5 | 2029-10-26 | October | 29 | 26 | 4 | Week 4 | October 29 Week 4 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
6 | 2029-10-27 | October | 29 | 27 | 4 | Week 4 | October 29 Week 4 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
7 | 2029-10-28 | October | 29 | 28 | 4 | Week 4 | October 29 Week 4 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
1 | 2029-10-29 | October | 29 | 29 | 5 | Week 5 | October 29 Week 5 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
2 | 2029-10-30 | October | 29 | 30 | 5 | Week 5 | October 29 Week 5 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
3 | 2029-10-31 | October | 29 | 31 | 5 | Week 5 | October 29 Week 5 | OCTOBER 29 | PLANNED | OCTOBER 29 PLANNED
1 | 2029-11-01 | November | 29 | 1 | 1 | Week 1 | November 29 Week 1 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
2 | 2029-11-02 | November | 29 | 2 | 1 | Week 1 | November 29 Week 1 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
3 | 2029-11-03 | November | 29 | 3 | 1 | Week 1 | November 29 Week 1 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
4 | 2029-11-04 | November | 29 | 4 | 1 | Week 1 | November 29 Week 1 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
5 | 2029-11-05 | November | 29 | 5 | 1 | Week 1 | November 29 Week 1 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
6 | 2029-11-06 | November | 29 | 6 | 1 | Week 1 | November 29 Week 1 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
7 | 2029-11-07 | November | 29 | 7 | 1 | Week 1 | November 29 Week 1 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
1 | 2029-11-08 | November | 29 | 8 | 2 | Week 2 | November 29 Week 2 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
2 | 2029-11-09 | November | 29 | 9 | 2 | Week 2 | November 29 Week 2 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
3 | 2029-11-10 | November | 29 | 10 | 2 | Week 2 | November 29 Week 2 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
4 | 2029-11-11 | November | 29 | 11 | 2 | Week 2 | November 29 Week 2 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
5 | 2029-11-12 | November | 29 | 12 | 2 | Week 2 | November 29 Week 2 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
6 | 2029-11-13 | November | 29 | 13 | 2 | Week 2 | November 29 Week 2 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
7 | 2029-11-14 | November | 29 | 14 | 2 | Week 2 | November 29 Week 2 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
1 | 2029-11-15 | November | 29 | 15 | 3 | Week 3 | November 29 Week 3 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
2 | 2029-11-16 | November | 29 | 16 | 3 | Week 3 | November 29 Week 3 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
3 | 2029-11-17 | November | 29 | 17 | 3 | Week 3 | November 29 Week 3 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
4 | 2029-11-18 | November | 29 | 18 | 3 | Week 3 | November 29 Week 3 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
5 | 2029-11-19 | November | 29 | 19 | 3 | Week 3 | November 29 Week 3 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
6 | 2029-11-20 | November | 29 | 20 | 3 | Week 3 | November 29 Week 3 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
7 | 2029-11-21 | November | 29 | 21 | 3 | Week 3 | November 29 Week 3 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
1 | 2029-11-22 | November | 29 | 22 | 4 | Week 4 | November 29 Week 4 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
2 | 2029-11-23 | November | 29 | 23 | 4 | Week 4 | November 29 Week 4 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
3 | 2029-11-24 | November | 29 | 24 | 4 | Week 4 | November 29 Week 4 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
4 | 2029-11-25 | November | 29 | 25 | 4 | Week 4 | November 29 Week 4 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
5 | 2029-11-26 | November | 29 | 26 | 4 | Week 4 | November 29 Week 4 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
6 | 2029-11-27 | November | 29 | 27 | 4 | Week 4 | November 29 Week 4 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
7 | 2029-11-28 | November | 29 | 28 | 4 | Week 4 | November 29 Week 4 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
1 | 2029-11-29 | November | 29 | 29 | 5 | Week 5 | November 29 Week 5 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
2 | 2029-11-30 | November | 29 | 30 | 5 | Week 5 | November 29 Week 5 | NOVEMBER 29 | PLANNED | NOVEMBER 29 PLANNED
1 | 2029-12-01 | December | 29 | 1 | 1 | Week 1 | December 29 Week 1 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
2 | 2029-12-02 | December | 29 | 2 | 1 | Week 1 | December 29 Week 1 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
3 | 2029-12-03 | December | 29 | 3 | 1 | Week 1 | December 29 Week 1 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
4 | 2029-12-04 | December | 29 | 4 | 1 | Week 1 | December 29 Week 1 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
5 | 2029-12-05 | December | 29 | 5 | 1 | Week 1 | December 29 Week 1 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
6 | 2029-12-06 | December | 29 | 6 | 1 | Week 1 | December 29 Week 1 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
7 | 2029-12-07 | December | 29 | 7 | 1 | Week 1 | December 29 Week 1 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
1 | 2029-12-08 | December | 29 | 8 | 2 | Week 2 | December 29 Week 2 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
2 | 2029-12-09 | December | 29 | 9 | 2 | Week 2 | December 29 Week 2 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
3 | 2029-12-10 | December | 29 | 10 | 2 | Week 2 | December 29 Week 2 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
4 | 2029-12-11 | December | 29 | 11 | 2 | Week 2 | December 29 Week 2 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
5 | 2029-12-12 | December | 29 | 12 | 2 | Week 2 | December 29 Week 2 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
6 | 2029-12-13 | December | 29 | 13 | 2 | Week 2 | December 29 Week 2 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
7 | 2029-12-14 | December | 29 | 14 | 2 | Week 2 | December 29 Week 2 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
1 | 2029-12-15 | December | 29 | 15 | 3 | Week 3 | December 29 Week 3 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
2 | 2029-12-16 | December | 29 | 16 | 3 | Week 3 | December 29 Week 3 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
3 | 2029-12-17 | December | 29 | 17 | 3 | Week 3 | December 29 Week 3 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
4 | 2029-12-18 | December | 29 | 18 | 3 | Week 3 | December 29 Week 3 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
5 | 2029-12-19 | December | 29 | 19 | 3 | Week 3 | December 29 Week 3 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
6 | 2029-12-20 | December | 29 | 20 | 3 | Week 3 | December 29 Week 3 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
7 | 2029-12-21 | December | 29 | 21 | 3 | Week 3 | December 29 Week 3 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
1 | 2029-12-22 | December | 29 | 22 | 4 | Week 4 | December 29 Week 4 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
2 | 2029-12-23 | December | 29 | 23 | 4 | Week 4 | December 29 Week 4 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
3 | 2029-12-24 | December | 29 | 24 | 4 | Week 4 | December 29 Week 4 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
4 | 2029-12-25 | December | 29 | 25 | 4 | Week 4 | December 29 Week 4 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
5 | 2029-12-26 | December | 29 | 26 | 4 | Week 4 | December 29 Week 4 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
6 | 2029-12-27 | December | 29 | 27 | 4 | Week 4 | December 29 Week 4 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
7 | 2029-12-28 | December | 29 | 28 | 4 | Week 4 | December 29 Week 4 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
1 | 2029-12-29 | December | 29 | 29 | 5 | Week 5 | December 29 Week 5 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
2 | 2029-12-30 | December | 29 | 30 | 5 | Week 5 | December 29 Week 5 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
3 | 2029-12-31 | December | 29 | 31 | 5 | Week 5 | December 29 Week 5 | DECEMBER 29 | PLANNED | DECEMBER 29 PLANNED
1 | 2030-01-01 | January | 30 | 1 | 1 | Week 1 | January 30 Week 1 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
2 | 2030-01-02 | January | 30 | 2 | 1 | Week 1 | January 30 Week 1 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
3 | 2030-01-03 | January | 30 | 3 | 1 | Week 1 | January 30 Week 1 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
4 | 2030-01-04 | January | 30 | 4 | 1 | Week 1 | January 30 Week 1 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
5 | 2030-01-05 | January | 30 | 5 | 1 | Week 1 | January 30 Week 1 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
6 | 2030-01-06 | January | 30 | 6 | 1 | Week 1 | January 30 Week 1 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
7 | 2030-01-07 | January | 30 | 7 | 1 | Week 1 | January 30 Week 1 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
1 | 2030-01-08 | January | 30 | 8 | 2 | Week 2 | January 30 Week 2 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
2 | 2030-01-09 | January | 30 | 9 | 2 | Week 2 | January 30 Week 2 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
3 | 2030-01-10 | January | 30 | 10 | 2 | Week 2 | January 30 Week 2 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
4 | 2030-01-11 | January | 30 | 11 | 2 | Week 2 | January 30 Week 2 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
5 | 2030-01-12 | January | 30 | 12 | 2 | Week 2 | January 30 Week 2 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
6 | 2030-01-13 | January | 30 | 13 | 2 | Week 2 | January 30 Week 2 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
7 | 2030-01-14 | January | 30 | 14 | 2 | Week 2 | January 30 Week 2 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
1 | 2030-01-15 | January | 30 | 15 | 3 | Week 3 | January 30 Week 3 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
2 | 2030-01-16 | January | 30 | 16 | 3 | Week 3 | January 30 Week 3 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
3 | 2030-01-17 | January | 30 | 17 | 3 | Week 3 | January 30 Week 3 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
4 | 2030-01-18 | January | 30 | 18 | 3 | Week 3 | January 30 Week 3 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
5 | 2030-01-19 | January | 30 | 19 | 3 | Week 3 | January 30 Week 3 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
6 | 2030-01-20 | January | 30 | 20 | 3 | Week 3 | January 30 Week 3 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
7 | 2030-01-21 | January | 30 | 21 | 3 | Week 3 | January 30 Week 3 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
1 | 2030-01-22 | January | 30 | 22 | 4 | Week 4 | January 30 Week 4 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
2 | 2030-01-23 | January | 30 | 23 | 4 | Week 4 | January 30 Week 4 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
3 | 2030-01-24 | January | 30 | 24 | 4 | Week 4 | January 30 Week 4 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
4 | 2030-01-25 | January | 30 | 25 | 4 | Week 4 | January 30 Week 4 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
5 | 2030-01-26 | January | 30 | 26 | 4 | Week 4 | January 30 Week 4 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
6 | 2030-01-27 | January | 30 | 27 | 4 | Week 4 | January 30 Week 4 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
7 | 2030-01-28 | January | 30 | 28 | 4 | Week 4 | January 30 Week 4 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
1 | 2030-01-29 | January | 30 | 29 | 5 | Week 5 | January 30 Week 5 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
2 | 2030-01-30 | January | 30 | 30 | 5 | Week 5 | January 30 Week 5 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
3 | 2030-01-31 | January | 30 | 31 | 5 | Week 5 | January 30 Week 5 | JANUARY 30 | PLANNED | JANUARY 30 PLANNED
1 | 2030-02-01 | February | 30 | 1 | 1 | Week 1 | February 30 Week 1 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
2 | 2030-02-02 | February | 30 | 2 | 1 | Week 1 | February 30 Week 1 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
3 | 2030-02-03 | February | 30 | 3 | 1 | Week 1 | February 30 Week 1 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
4 | 2030-02-04 | February | 30 | 4 | 1 | Week 1 | February 30 Week 1 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
5 | 2030-02-05 | February | 30 | 5 | 1 | Week 1 | February 30 Week 1 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
6 | 2030-02-06 | February | 30 | 6 | 1 | Week 1 | February 30 Week 1 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
7 | 2030-02-07 | February | 30 | 7 | 1 | Week 1 | February 30 Week 1 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
1 | 2030-02-08 | February | 30 | 8 | 2 | Week 2 | February 30 Week 2 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
2 | 2030-02-09 | February | 30 | 9 | 2 | Week 2 | February 30 Week 2 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
3 | 2030-02-10 | February | 30 | 10 | 2 | Week 2 | February 30 Week 2 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
4 | 2030-02-11 | February | 30 | 11 | 2 | Week 2 | February 30 Week 2 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
5 | 2030-02-12 | February | 30 | 12 | 2 | Week 2 | February 30 Week 2 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
6 | 2030-02-13 | February | 30 | 13 | 2 | Week 2 | February 30 Week 2 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
7 | 2030-02-14 | February | 30 | 14 | 2 | Week 2 | February 30 Week 2 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
1 | 2030-02-15 | February | 30 | 15 | 3 | Week 3 | February 30 Week 3 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
2 | 2030-02-16 | February | 30 | 16 | 3 | Week 3 | February 30 Week 3 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
3 | 2030-02-17 | February | 30 | 17 | 3 | Week 3 | February 30 Week 3 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
4 | 2030-02-18 | February | 30 | 18 | 3 | Week 3 | February 30 Week 3 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
5 | 2030-02-19 | February | 30 | 19 | 3 | Week 3 | February 30 Week 3 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
6 | 2030-02-20 | February | 30 | 20 | 3 | Week 3 | February 30 Week 3 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
7 | 2030-02-21 | February | 30 | 21 | 3 | Week 3 | February 30 Week 3 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
1 | 2030-02-22 | February | 30 | 22 | 4 | Week 4 | February 30 Week 4 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
2 | 2030-02-23 | February | 30 | 23 | 4 | Week 4 | February 30 Week 4 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
3 | 2030-02-24 | February | 30 | 24 | 4 | Week 4 | February 30 Week 4 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
4 | 2030-02-25 | February | 30 | 25 | 4 | Week 4 | February 30 Week 4 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
5 | 2030-02-26 | February | 30 | 26 | 4 | Week 4 | February 30 Week 4 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
6 | 2030-02-27 | February | 30 | 27 | 4 | Week 4 | February 30 Week 4 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
7 | 2030-02-28 | February | 30 | 28 | 4 | Week 4 | February 30 Week 4 | FEBRUARY 30 | PLANNED | FEBRUARY 30 PLANNED
1 | 2030-03-01 | March | 30 | 1 | 1 | Week 1 | March 30 Week 1 | MARCH 30 | PLANNED | MARCH 30 PLANNED
2 | 2030-03-02 | March | 30 | 2 | 1 | Week 1 | March 30 Week 1 | MARCH 30 | PLANNED | MARCH 30 PLANNED
3 | 2030-03-03 | March | 30 | 3 | 1 | Week 1 | March 30 Week 1 | MARCH 30 | PLANNED | MARCH 30 PLANNED
4 | 2030-03-04 | March | 30 | 4 | 1 | Week 1 | March 30 Week 1 | MARCH 30 | PLANNED | MARCH 30 PLANNED
5 | 2030-03-05 | March | 30 | 5 | 1 | Week 1 | March 30 Week 1 | MARCH 30 | PLANNED | MARCH 30 PLANNED
6 | 2030-03-06 | March | 30 | 6 | 1 | Week 1 | March 30 Week 1 | MARCH 30 | PLANNED | MARCH 30 PLANNED
7 | 2030-03-07 | March | 30 | 7 | 1 | Week 1 | March 30 Week 1 | MARCH 30 | PLANNED | MARCH 30 PLANNED
1 | 2030-03-08 | March | 30 | 8 | 2 | Week 2 | March 30 Week 2 | MARCH 30 | PLANNED | MARCH 30 PLANNED
2 | 2030-03-09 | March | 30 | 9 | 2 | Week 2 | March 30 Week 2 | MARCH 30 | PLANNED | MARCH 30 PLANNED
3 | 2030-03-10 | March | 30 | 10 | 2 | Week 2 | March 30 Week 2 | MARCH 30 | PLANNED | MARCH 30 PLANNED
4 | 2030-03-11 | March | 30 | 11 | 2 | Week 2 | March 30 Week 2 | MARCH 30 | PLANNED | MARCH 30 PLANNED
5 | 2030-03-12 | March | 30 | 12 | 2 | Week 2 | March 30 Week 2 | MARCH 30 | PLANNED | MARCH 30 PLANNED
6 | 2030-03-13 | March | 30 | 13 | 2 | Week 2 | March 30 Week 2 | MARCH 30 | PLANNED | MARCH 30 PLANNED
7 | 2030-03-14 | March | 30 | 14 | 2 | Week 2 | March 30 Week 2 | MARCH 30 | PLANNED | MARCH 30 PLANNED
1 | 2030-03-15 | March | 30 | 15 | 3 | Week 3 | March 30 Week 3 | MARCH 30 | PLANNED | MARCH 30 PLANNED
2 | 2030-03-16 | March | 30 | 16 | 3 | Week 3 | March 30 Week 3 | MARCH 30 | PLANNED | MARCH 30 PLANNED
3 | 2030-03-17 | March | 30 | 17 | 3 | Week 3 | March 30 Week 3 | MARCH 30 | PLANNED | MARCH 30 PLANNED
4 | 2030-03-18 | March | 30 | 18 | 3 | Week 3 | March 30 Week 3 | MARCH 30 | PLANNED | MARCH 30 PLANNED
5 | 2030-03-19 | March | 30 | 19 | 3 | Week 3 | March 30 Week 3 | MARCH 30 | PLANNED | MARCH 30 PLANNED
6 | 2030-03-20 | March | 30 | 20 | 3 | Week 3 | March 30 Week 3 | MARCH 30 | PLANNED | MARCH 30 PLANNED
7 | 2030-03-21 | March | 30 | 21 | 3 | Week 3 | March 30 Week 3 | MARCH 30 | PLANNED | MARCH 30 PLANNED
1 | 2030-03-22 | March | 30 | 22 | 4 | Week 4 | March 30 Week 4 | MARCH 30 | PLANNED | MARCH 30 PLANNED
2 | 2030-03-23 | March | 30 | 23 | 4 | Week 4 | March 30 Week 4 | MARCH 30 | PLANNED | MARCH 30 PLANNED
3 | 2030-03-24 | March | 30 | 24 | 4 | Week 4 | March 30 Week 4 | MARCH 30 | PLANNED | MARCH 30 PLANNED
4 | 2030-03-25 | March | 30 | 25 | 4 | Week 4 | March 30 Week 4 | MARCH 30 | PLANNED | MARCH 30 PLANNED
5 | 2030-03-26 | March | 30 | 26 | 4 | Week 4 | March 30 Week 4 | MARCH 30 | PLANNED | MARCH 30 PLANNED
6 | 2030-03-27 | March | 30 | 27 | 4 | Week 4 | March 30 Week 4 | MARCH 30 | PLANNED | MARCH 30 PLANNED
7 | 2030-03-28 | March | 30 | 28 | 4 | Week 4 | March 30 Week 4 | MARCH 30 | PLANNED | MARCH 30 PLANNED
1 | 2030-03-29 | March | 30 | 29 | 5 | Week 5 | March 30 Week 5 | MARCH 30 | PLANNED | MARCH 30 PLANNED
2 | 2030-03-30 | March | 30 | 30 | 5 | Week 5 | March 30 Week 5 | MARCH 30 | PLANNED | MARCH 30 PLANNED
3 | 2030-03-31 | March | 30 | 31 | 5 | Week 5 | March 30 Week 5 | MARCH 30 | PLANNED | MARCH 30 PLANNED